## IEEE_Cover
October 2010 |  | P802-15-Comment_Entry_Form.xls
IEEE P802.15
Wireless Personal Area Networks
Project | IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Title | 802.15 Letter Ballot Comment Submission
Date Submitted | 2011-04-22
Source | Pat Kinney | Voice: +1.847.960.3715
Kinney Consulting
| 251 Clair View Ct, Lake Zurich, IL, USA | E-mail: pat.kinney@ieee.org
Re:
Abstract | 802.15 Comments for Letter Ballot
Purpose | [This document is used to submit comments on IEEE 802.15 Working Group Letter Ballots.]
Notice | This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Comments
CID | Name | Affiliation | Email | Clause | Sub-clause | Page | Line # | Comment | Proposed Change | Must Be Satisfied? (if so enter Yes) | Technical Editors Proposed Change
C1 | Huan-Bang Li | NICT | lee@nict.go.jp | 3 | 3.2 | 8 | 7 | Do we need to define 'appropriate' ? For example, does the 'appropriate' in line 2 of the same page obey this definition? | delete this definition. | No. | Reject. Please resubmit at Sponsor Ballot (currently targeted for between July and September meeting 2011). The draft will be professionally edited before publication.
C2 | Huan-Bang Li | NICT | lee@nict.go.jp | 4 |  | 11 | 19 | PN should be acronym for pseudo noise | change 'pseudo-random' to 'pseudo noise'. | Yes. | Reject. Please resubmit at Sponsor Ballot (currently targeted for between July and September meeting 2011). The draft will be professionally edited before publication.
C3 | Huan-Bang Li | NICT | lee@nict.go.jp | 5 | 5.4 | 14 | 25 | In Figure 3, there is a letter 't' companied by an arrow. Howewer, this is no description what it stands for. | please clarify. | No. | Reject. Please resubmit at Sponsor Ballot (currently targeted for between July and September meeting 2011). The draft will be professionally edited before publication.
C4 | Huan-Bang Li | NICT | lee@nict.go.jp | 6 | 6.3.1.9 | 33 | 25 | wrongly cited subclause | change 6.6.1.16 to 6.6.2. | Yes. | Reject. Please resubmit at Sponsor Ballot (currently targeted for between July and September meeting 2011). The draft will be professionally edited before publication.
C5 | Huan-Bang Li | NICT | lee@nict.go.jp | 6 | 6.3.6.4 | 45 | 2 | wrongly cited subclause. | change 6.6.1.16 to 6.6.2. | Yes. | Reject. Please resubmit at Sponsor Ballot (currently targeted for between July and September meeting 2011). The draft will be professionally edited before publication.
C6 | Huan-Bang Li | NICT | lee@nict.go.jp | 6 | 6.3.7.9 | 51 | 4 | wrongly cited subclause | change 6.6.1.16 to 6.6.2. | Yes. | Reject. Please resubmit at Sponsor Ballot (currently targeted for between July and September meeting 2011). The draft will be professionally edited before publication.
C7 | Huan-Bang Li | NICT | lee@nict.go.jp | 6 | 6.6.2 | 69 | 13 | There are two periods following word 'bits'. | delete one period. | Yes. | Reject. Please resubmit at Sponsor Ballot (currently targeted for between July and September meeting 2011). The draft will be professionally edited before publication.
C8 | Huan-Bang Li | NICT | lee@nict.go.jp | 6 | 6.7.2.7 | 75 | 22 | The meaning of 'the most overall length' is not clear. | Change to 'the most desired (or wanted, or popular) overall length'. | No. | Reject. Please resubmit at Sponsor Ballot (currently targeted for between July and September meeting 2011). The draft will be professionally edited before publication.
C9 | Huan-Bang Li | NICT | lee@nict.go.jp | 7 | 7.2.9.4 | 93 | 11 | wrongly cited subclause. | change '0' to '6.4.2'. | Yes. | Reject. Please resubmit at Sponsor Ballot (currently targeted for between July and September meeting 2011). The draft will be professionally edited before publication.
C10 | Huan-Bang Li | NICT | lee@nict.go.jp | 7 | 7.6.1.2.3 | 110 | 18-22 | It seems that different fonts or sizes are applied in Figure 81, especially, '=' in (a) looks different from that in (b) | Unify the fonts or sizes. | No. | Reject. Please resubmit at Sponsor Ballot (currently targeted for between July and September meeting 2011). The draft will be professionally edited before publication.
C11 | Huan-Bang Li | NICT | lee@nict.go.jp | 10 |  | 207-208, 213-216, 218, 221-223, 226-229, 242-243 |  | There are arbitrary spaces befor the title of some subclauses, such as 10.2.1, 10.3.1, 10.6.2, 10.6.2.2, 10.7.1, 10.7.1.3, 10.7.1.4, 10.7.1.5, 10.7.2, 10.8.1, 10.9.1, 10.9.2, 10.10.1, 10.10.1.1, 10.10.1.2, 10.10.1.3, 10.10.1.4, 10.10.2.4, 10.11.1, 10.11.2, etc. Can we delete all those spaces so that there is no space before the title of all subclauses as in the other clauses. | Delete spaces before the title of all subclauses. | No. | Reject. Please resubmit at Sponsor Ballot (currently targeted for between July and September meeting 2011). The draft will be professionally edited before publication.
C12 | Kaoru Yokoo | Fujitsu | kaoru_yokoo@jp.fujitsu.com | 5 | 5.5.1.3 | 16 | 29 | It is found that a state with "Secured" and having no Connected_NID is problematic. In the Secured state, a node can send the Disassociation or the Connection Request frame with encryption. In that case, the node send these frames with Sender ID = Unconnected_NID to a hub. When the hub received the frames (encrypted and Sender ID = Unconnected_NID), it can not choose appropriate key to decrypt its payload since there is no information to identify sender other than the Sender ID. My proposal is that the node and the node goes to the Orphan state if it loose the Connected_NID. | The node and the node goes to the Associated state if it loose the Connected_NID. Add sentence, "If their PTK is missing or invalid or the node’s Connected_NID is lost, they are required to move back to Associated state. To repeal the security association and hence the current MK, either the node or the hub is allowed to send a Security Disassociation frame to the other, thus moving back to Orphan state." after Line 29 and 36. | No | Reject. Please resubmit at Sponsor Ballot (currently targeted for between July and September meeting 2011). The draft will be professionally edited before publication.
C13 | Kaoru Yokoo | Fujitsu | kaoru_yokoo@jp.fujitsu.com | 5 | 5.5.1.2 | 16 | 17 | Although "Master key missing/invalid" is only considered when a node in the Associated state, the event may also happen in PTK recreation process in the Connected state. In the case, I believe that the node goes back to the Orphan state directly from the Connected state without sending security disassociation frame which should include KMAC. | It is recommend to define such case and add appropriate path from the Connected state to the Orphan state in Figure 4. Add sentence "If their MK is missing or invalid during their PTK creation, they are required to move back to Orphan state. " after line 17. | No | Reject. Please resubmit at Sponsor Ballot (currently targeted for between July and September meeting 2011). The draft will be professionally edited before publication.
C14 | Clint Chaplin | Samsung Electronics | clint.chaplin@gmail.com | 6 | 6.3.10.2 | 54 | 3 | List bullets are not being reset between lists | Reset list bullets between lists | No | Reject. Please resubmit at Sponsor Ballot (currently targeted for between July and September meeting 2011). The draft will be professionally edited before publication.
C15 | Clint Chaplin | Samsung Electronics | clint.chaplin@gmail.com | 7 | 7.2.9.4 | 93 | 11 | "as defined in 0" reference is not vaild | Update reference to valid place | No | Reject. Please resubmit at Sponsor Ballot (currently targeted for between July and September meeting 2011). The draft will be professionally edited before publication.
C16 | Clint Chaplin | Samsung Electronics | clint.chaplin@gmail.com | 7 | 7.3.1 | 96 | 30 | Is "improvise" the right word here? "Improvise" to me says to develop in an ad-hoc fashion; to make up on the spot. Is that correct? |  | No | Reject. Please resubmit at Sponsor Ballot (currently targeted for between July and September meeting 2011). The draft will be professionally edited before publication.
C17 | Seung-Hoon Park | Samsung Electronics | shannon.park@samsung.com | 11 | 5.2 | 256 | 8 to 11 | Always Active field is not relavant to Rate Indicator function of HBC. | Please describe alternative method to inform RI mode. | Yes | Reject. Please resubmit at Sponsor Ballot (currently targeted for between July and September meeting 2011). The draft will be professionally edited before publication.
C18 | O Omeni | Toumaz UK Ltd. | ocomeni@gmail.com | 3 | 3.1 | 4 | 4 | spelling mistake "binlink" | replace "binlink" with "bilink" | No | Reject. Please resubmit at Sponsor Ballot (currently targeted for between July and September meeting 2011). The draft will be professionally edited before publication.
C19 | O Omeni | Toumaz UK Ltd. | ocomeni@gmail.com | 6 | 6.3.10 | 53 | 14 | subclause should be "6.3.9.1" instead of "6.3.10" | change subclause from "6.3.10" to "6.3.9.1" | No | Reject. Please resubmit at Sponsor Ballot (currently targeted for between July and September meeting 2011). The draft will be professionally edited before publication.
C20 | O Omeni | Toumaz UK Ltd. | ocomeni@gmail.com | 6 | 6.3.10.1 | 53 | 14 | subclause should be "6.3.9.2" instead of "6.3.10.1" | change subclause from "6.3.10.1" to "6.3.9.2" | No | Reject. Please resubmit at Sponsor Ballot (currently targeted for between July and September meeting 2011). The draft will be professionally edited before publication.
C21 | O Omeni | Toumaz UK Ltd. | ocomeni@gmail.com | 6 | 6.3.10.2 | 54 | 14 | subclause should be "6.3.9.3" instead of "6.3.10.2" | change subclause from "6.3.10.2" to "6.3.9.3" | No | Reject. Please resubmit at Sponsor Ballot (currently targeted for between July and September meeting 2011). The draft will be professionally edited before publication.
C22 | O Omeni | Toumaz UK Ltd. | ocomeni@gmail.com | 6 | 6.3.11 | 54 | 10 | 6.3.11 should be 6.3.10 | change subclause numbering from here onwards accordingly up till page 62 (6.3.11.10). | No | Reject. Please resubmit at Sponsor Ballot (currently targeted for between July and September meeting 2011). The draft will be professionally edited before publication.
C23 | O Omeni | Toumaz UK Ltd. | ocomeni@gmail.com | 6 | 6.2.3 | 31 | 14 | To clarify the preset condition and post processing of the division. | : After line 14, add a new line as follows: The initial remainder of the division is set to zero, and the final remainder is not inverted as is the case in some other standards. | No | Reject. Please resubmit at Sponsor Ballot (currently targeted for between July and September meeting 2011). The draft will be professionally edited before publication.
C24 | O Omeni | Toumaz UK Ltd. | ocomeni@gmail.com | 9 | 9.4 | 191 | 10 | List begins at g) not a) | Restart list numbering from a) | No | Reject. Please resubmit at Sponsor Ballot (currently targeted for between July and September meeting 2011). The draft will be professionally edited before publication.
C25 | O Omeni | Toumaz UK Ltd. | ocomeni@gmail.com | 9 | 9.4.1.1 | 192 | 13 | List begins at m) not a) | Restart list numbering from a) | No | Reject. Please resubmit at Sponsor Ballot (currently targeted for between July and September meeting 2011). The draft will be professionally edited before publication.
C26 | O Omeni | Toumaz UK Ltd. | ocomeni@gmail.com | 9 | 9.6.1 | 197 | 13 | List begins at q) not a) | Restart list numbering from a) | No | Reject. Please resubmit at Sponsor Ballot (currently targeted for between July and September meeting 2011). The draft will be professionally edited before publication.
C27 | O Omeni | Toumaz UK Ltd. | ocomeni@gmail.com | 9 | 9.9.4 | 206 | 4 | List begins at x) not a) | Restart list numbering from a) | No | Reject. Please resubmit at Sponsor Ballot (currently targeted for between July and September meeting 2011). The draft will be professionally edited before publication.
C28 | O Omeni | Toumaz UK Ltd. | ocomeni@gmail.com | 9 | 9.9.4 | 206 | 16 | List begins at aa) not a) | Restart list numbering from a) | No | Reject. Please resubmit at Sponsor Ballot (currently targeted for between July and September meeting 2011). The draft will be professionally edited before publication.
C29 | Anuj Batra | Texas Instruments | batra@ti.com | 9 | 9.4 | 191-192 | 10-22, 1-2 | The numbering for the list is incorrect, it starts with (g), but should actually start with (a) | Restart the number for the list with (a) | Yes | Reject. Please resubmit at Sponsor Ballot (currently targeted for between July and September meeting 2011). The draft will be professionally edited before publication.
C30 | Anuj Batra | Texas Instruments | batra@ti.com | 9 | 9.4.1.1 | 192 | 13-26 | The numbering for the list is incorrect, it starts with (m), but should actually start with (a) | Restart the number for the list with (a) | Yes | Reject. Please resubmit at Sponsor Ballot (currently targeted for between July and September meeting 2011). The draft will be professionally edited before publication.
C31 | Anuj Batra | Texas Instruments | batra@ti.com | 9 | 9.5.1 | 196 | 2 | There is an extra space between the "," and "N-1" | Remove the extra space between the "," and "N-1" | Yes | Reject. Please resubmit at Sponsor Ballot (currently targeted for between July and September meeting 2011). The draft will be professionally edited before publication.
C32 | Anuj Batra | Texas Instruments | batra@ti.com | 9 | 9.5.2 | 196 | 7 | There is an extra space between the "," and "N-1" | Remove the extra space between the "," and "N-1" | Yes | Reject. Please resubmit at Sponsor Ballot (currently targeted for between July and September meeting 2011). The draft will be professionally edited before publication.
C33 | Anuj Batra | Texas Instruments | batra@ti.com | 9 | 9.6.1 | 197-198 | 13-18, 1 | The numbering for the list is incorrect, it starts with (q), but should actually start with (a) | Restart the number for the list with (a) | Yes | Reject. Please resubmit at Sponsor Ballot (currently targeted for between July and September meeting 2011). The draft will be professionally edited before publication.
C34 | Anuj Batra | Texas Instruments | batra@ti.com | 9 | 9.9.4 | 206 | 4-13 | The numbering for the list is incorrect, it starts with (x), but should actually start with (a) | Restart the number for the list with (a) | Yes | Reject. Please resubmit at Sponsor Ballot (currently targeted for between July and September meeting 2011). The draft will be professionally edited before publication.
C35 | Anuj Batra | Texas Instruments | batra@ti.com | 9 | 9.9.4 | 206 | 16-18 | The numbering for the list is incorrect, it starts with (aa), but should actually start with (a) | Restart the number for the list with (a) | Yes | Reject. Please resubmit at Sponsor Ballot (currently targeted for between July and September meeting 2011). The draft will be professionally edited before publication.
C36 | Anuj Batra | Texas Instruments | batra@ti.com | 11 | 11.2 | 250 | 11 | Figure 158 does not print correctly | Redraw Figure 158 using standard microsoft drawing tools and ensure that they print correctly | Yes | Reject. Please resubmit at Sponsor Ballot (currently targeted for between July and September meeting 2011). The draft will be professionally edited before publication.
C37 | Anuj Batra | Texas Instruments | batra@ti.com | 11 | 11.3 | 251 | 6 | Figure 159 does not print correctly | Redraw Figure 159 using standard microsoft drawing tools and ensure that they print correctly | Yes | Reject. Please resubmit at Sponsor Ballot (currently targeted for between July and September meeting 2011). The draft will be professionally edited before publication.
C38 | Anuj Batra | Texas Instruments | batra@ti.com | 11 | 11.4 | 252 | 2 | Figure 161 does not print correctly | Redraw Figure 161 using standard microsoft drawing tools and ensure that they print correctly | Yes | Reject. Please resubmit at Sponsor Ballot (currently targeted for between July and September meeting 2011). The draft will be professionally edited before publication.
C39 | Anuj Batra | Texas Instruments | batra@ti.com | 11 | 11.6 | 257 | 7 | Figure 165 does not print correctly | Redraw Figure 165 using standard microsoft drawing tools and ensure that they print correctly | Yes | Reject. Please resubmit at Sponsor Ballot (currently targeted for between July and September meeting 2011). The draft will be professionally edited before publication.
C40 | Anuj Batra | Texas Instruments | batra@ti.com | 11 | 11.7.1 | 259 | 9 | Figure 167 does not print correctly | Redraw Figure 167 using standard microsoft drawing tools and ensure that they print correctly | Yes | Reject. Please resubmit at Sponsor Ballot (currently targeted for between July and September meeting 2011). The draft will be professionally edited before publication.
C41 | Anuj Batra | Texas Instruments | batra@ti.com | 11 | 11.7.2 | 260 | 1 | Figure 168 does not print correctly | Redraw Figure 168 using standard microsoft drawing tools and ensure that they print correctly | Yes | Reject. Please resubmit at Sponsor Ballot (currently targeted for between July and September meeting 2011). The draft will be professionally edited before publication.
C42 | Anuj Batra | Texas Instruments | batra@ti.com | Annex C | C.1 | 270 | 8 | Figure C.1 does not print correctly | Redraw Figure C.1 using standard microsoft drawing tools and ensure that they print correctly | Yes | Reject. Please resubmit at Sponsor Ballot (currently targeted for between July and September meeting 2011). The draft will be professionally edited before publication.
C43 | Kiran Bynam | Samsung Electronics | kiran.bynam@samsung.com | 10 | 10.9.4 | 220 | 4 to 6 | It looks as if time hopping is mandatory | "If Enabled" should be added to these lines | Yes | Reject. Please resubmit at Sponsor Ballot (currently targeted for between July and September meeting 2011). The draft will be professionally edited before publication.
C44 | Kiran Bynam | Samsung Electronics | kiran.bynam@samsung.com | 10 | 10.15 | 236 | 10 | Block length of 126 puts lot of memory constraints | Can we reduce the block length ? | Yes | Reject. Please resubmit at Sponsor Ballot (currently targeted for between July and September meeting 2011). The draft will be professionally edited before publication.
C45 | Charles Farlow | Medtronic | charles.s.farlow@medtronic.com | 2 | N/A | 2 | 17 | [Technical] The current ETSI MICS standard (EN 301 839-1) is not a draft. The standard should not be proceeded by the term "Draft". | Eliminate the term "Draft" | Yes | Reject. Editorial. Please resubmit at Sponsor Ballot (currently targeted for between July and September meeting 2011). The draft will be professionally edited before publication.
C46 | Charles Farlow | Medtronic | charles.s.farlow@medtronic.com | 2 | N/A | 2 | 20 | [Technical] The referenced ETSI standard was published in October 2009. | Replace "January 2009" with "October 2009"; this is also consistent with the "Document history" contained within EN 301 839-1. | Yes | Reject. Editorial. Please resubmit at Sponsor Ballot (currently targeted for between July and September meeting 2011). The draft will be professionally edited before publication.
C47 | Charles Farlow | Medtronic | charles.s.farlow@medtronic.com | 7 | 7.9 | 123 | 4-7 | [Technical] The revised standard does not match the comment resolution spreadsheet. The implant must also select the appropriate channel in compliance with clause 10. The term "clause" rather than "subclause" is used in ETSI standards. The proposed change matches the comment resolution spreadsheet with the addition of clause 8.6 for low power low duty cycle operation as discussed in the last session (May 2011). | Change "The hub may choose a new channel only when required by, and in compliance with, applicable considerations and regulations including clause 10 or subclause 8.6 of ETSI EN 301 839-1. An implant shall communicate as a node with a hub, taking into account applicable considerations and regulations including subclause 8.6 of ETSI EN 301 839-1." to "The hub may choose a new channel only when required by, and in compliance with, applicable regulations including clause 8.6 or clause 10 of ETSI EN 301 839-1. An implant shall communicate as a node with a hub, in compliance with applicable regulations including clause 8.6 or clause 10 of ETSI EN 301 839-1." | Yes | The comment requests change FROM: clause 10 or subclause 8.6 TO: clause 8.6 or clause 10. Change FROM: subclause 8.6 TO: clause 8.6 or clause 10. This is editorial. Reject. Please resubmit at Sponsor Ballot (currently targeted for between July and September meeting 2011). The draft will be professionally edited before publication.
C48 | Charles Farlow | Medtronic | charles.s.farlow@medtronic.com | 7 | 7.9.4 | 128 | 19 | [Editorial] The phrase "low power low duty cycle" is used throughout the document (and associated abbreviations). | Include a definition of "low power low duty cycle" in sub-clause 3.2. | No | Reject. Please resubmit at Sponsor Ballot (currently targeted for between July and September meeting 2011). The draft will be professionally edited before publication.
C49 | Charles Farlow | Medtronic | charles.s.farlow@medtronic.com | 7 | 7.9.4 | 128 | 21,22 | [Editorial] The term "clause" rather than "subclause" is used in ETSI standards. | Change both instances of "subclause" to "clause" | No | Reject. Please resubmit at Sponsor Ballot (currently targeted for between July and September meeting 2011). The draft will be professionally edited before publication.
C50 | Charles Farlow | Medtronic | charles.s.farlow@medtronic.com | 7 | 7.9.4 | 128 | 22-23 | [Technical] Duty cycle isn't the only limitation defined in the ETSI standard for Low Power Low Duty Cycle communication. There is also a limit on the number of transmissions and operating frequency. | Change "A node may initiate a frame transaction with a hub at any time in a channel, and with a duty cycle, as specified in applicable regulations including subclause 8.6 of ETSI EN 301 839-1." to "A node may initiate a frame transaction with a hub at any time in a channel specified from 403.5 MHz to 403.8 MHz, in compliance with the limits for duty cycle and maximum number of transmissions specified in clause 8.6 of ETSI EN 301 839-1." | Yes | Reject. The original sentence in the dratf covers thethe proposed change, We do not need to copy the current clause 8.6 in ETSI EN 301839-1, we just need to comply with it.
C51 | Charles Farlow | Medtronic | charles.s.farlow@medtronic.com | 9 | 9.8.2 | 201 | 4 | [Technical] The listed ETSI clause is not correct. | Change "clause 8.6" to "clause 8.3"; Clause 8.3 is "Effective radiated power of the fundamental emission" | Yes | Reject. Editorial. Please resubmit at Sponsor Ballot (currently targeted for between July and September meeting 2011). The draft will be professionally edited before publication.
C52 | Charles Farlow | Medtronic | charles.s.farlow@medtronic.com | 11 | 262-263 | 11.8.1 | 3-13, 1-4 | [Technical] The resolution of comment S11-001 in Letter Ballot 76 is rejected. The technical portion of comment S11-001 submitted for Letter Ballot 71 is: [The low-frequency spectral mask may not be sufficient to prevent suspension of therapy in the large population of patients with implanted medical devices. Additionally, the spectral mask may not be sufficient to prevent interference with signals from MICS implants emitted at relatively low levels of EIRP (generally less than 200 nW).] The group's rebuttal is not sufficient since the masks may not be sufficient (this is pending understanding of the transmit power limit) to prevent potential degradation of medical device operation. | While low frequency masks (below the HBC frequency of operation) are defined in D04, the discussion with AdvaMed to establish maximum output power levels and an appropriate spectral mask is not yet complete (three conference calls held to date). The minutes from the last conference call are documented in IEEE P802.15-11-0441-00-0006. The proposed resolution is to remove clause 11 and any text referencing this clause from the draft standard, with the HBC mode potentially being further considered in a new Study Group or Task Group. This action would provide AdvaMed members and HBC proponents additional time to analyze potential degradation of medical device operation (due to EMI produced by HBC), without delaying approval of IEEE 802.15.6 and its other modes. | Yes | Reject. This comment has been submitted previouly and was rejected. We have made a correction in draft 04 changing the clause 11.8.2 FROM: Transmit power The radiation power to the human body shall be less than -36dBm as total power in the operating band. Devices shall limit their transmit power to mitigate against interference to other devices and systems, and to meet the regulatory policies. TO: Transmit power The radiation power to the human body shall be less than -36dBm as total power in the operating band. Devices shall limit their transmit power to mitigate against interference to other devices and systems, to protect the safety for the human body and to meet the regulatory policies. This added the phrase: to protect the safety for the human body, required by the legal review.
C53 | Charles Farlow | Medtronic | charles.s.farlow@medtronic.com | 11 | 263 | 11.8.2 | 6 | [Technical] The resolution of comment S11-002 in Letter Ballot 76 is rejected. The technical portion of comment S11-002 submitted for Letter Ballot 71 is: [The group's rebuttal is not sufficient since the phrase "The radiation power to the human body .." is ambiguous. This phrase (including measurement methodology) must be fully explained and understood so members of the medical device industry can make the appropriate conversions as required to evaluate compliance to ANSI/AAMI PC69 Annex M (Correlation between levels of test voltages used in the standard and radiated field strengths).] | The related discussion with AdvaMed to establish maximum output power levels and an appropriate spectral mask is not yet complete (three conference calls held to date). The minutes from the last conference call are documented in IEEE P802.15-11-0441-00-0006. The proposed resolution is to remove clause 11 and any text referencing this clause from the draft standard, with the HBC mode potentially being further considered in a new Study Group or Task Group. This action would provide AdvaMed members and HBC proponents additional time to analyze potential degradation of medical device operation (due to EMI produced by HBC), without delaying approval of IEEE 802.15.6 and its other modes. | Yes | Reject. This comment has been submitted previouly and was rejected. We have made a correction in draft 04 changing the clause 11.8.2 FROM: Transmit power The radiation power to the human body shall be less than -36dBm as total power in the operating band. Devices shall limit their transmit power to mitigate against interference to other devices and systems, and to meet the regulatory policies. TO: Transmit power The radiation power to the human body shall be less than -36dBm as total power in the operating band. Devices shall limit their transmit power to mitigate against interference to other devices and systems, to protect the safety for the human body and to meet the regulatory policies. This added the phrase: to protect the safety for the human body, required by the legal review.