## IEEE_Cover
July 2011 |  | DCN 15-11-0539-00-0006
IEEE P802.15
Wireless Personal Area Networks
Project | IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Title | 802.15.6 NO Voter Must Be Satisfied Comments from LB79,LB76,LB71,LB6, LB55
Date Submitted | July 21 2011
Source | Arthur Astrin | Voice: +1 650 704 2517
Astrin Radio
| 1051 Greenwood, Palo Alto, CA 94301, USA | E-mail: astrin@ieee.org
| Daniel Lewis | Voice: +61 2 6267 6252
NICTA
| 7 London Circuit, Canberra, ACT 2600, Australia | E-mail: daniel.lewis@nicta.com.au
Re: | EC Closing Meeting Actions for 802.15.6
Abstract | 802.15.6 NO Voter Must Be Satisfied Comments from LB79,LB76,LB71,LB66&LB55
Purpose | [This document is used to submit comments for TG6 Letter Ballot.]
Notice | This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Totals
Letter Balott Number | "NO Voter Comments that were makred "Must Be Satisfied"
LB55 | 178
LB66 | 44
LB71 | 26
LB76, LB79 | 2
TOTAL | 250

## LB76, LB79 -Active
CID | Name | Affiliation | Clause | Page | subclause | Line | Comment | Proposed Change | Must Be Satisfied | Resolution
8 | Charles Farlow | Medtronic | 11 | 262-263 | 11.8.1 | 3-13, 1-4 | The technical portion of comment C52 submitted for LB76 was: [The low-frequency spectral mask may not be sufficient to prevent suspension of therapy in the large population of patients with implanted medical devices. Additionally, the spectral mask may not be sufficient to prevent interference with signals from MICS implants emitted at relatively low levels of EIRP (generally less than 200 nW).] The group's rebuttal is not sufficient since the masks may not be sufficient (this is pending understanding of the transmit power limit) to prevent potential degradation of medical device operation. The addition of the qualitative phrase "to protect the safety for the human body" in sub-clause 11.8.2 is not sufficient to ensure patient safety. The IEEE legal guidance states "... If this is a matter of concern, its should be discussed further with members of the implantable medical device industry to determine an appropriate spectral mask." HBC proponents have not worked in good faith to resolve concerns voiced by members of the implantable medical device industry. | While low frequency masks (below the HBC frequency of operation) are defined in D04, the discussion with AdvaMed to establish maximum output power levels and an appropriate spectral mask is not yet complete (three conference calls held to date). The minutes from the last conference call are documented in IEEE P802.15-11-0441-00-0006. The proposed resolution is to remove clause 11 and any text referencing this clause from the draft standard, with the HBC mode potentially being further considered in a new Study Group or Task Group. This action would provide AdvaMed members and HBC proponents additional time to analyze potential degradation of medical device operation (due to EMI produced by HBC), without delaying approval of IEEE 802.15.6 and its other modes. | Yes | Rejected Previously Submitted and Rejected
9 | Charles Farlow | Medtronic | 11 | 263 | 11.8.2 | 6-8 | The technical portion of comment C53 submitted for LB76 was: [The group's rebuttal is not sufficient since the phrase "The radiation power to the human body .." is ambiguous. This phrase (including measurement methodology) must be fully explained and understood so members of the medical device industry can make the appropriate conversions as required to evaluate compliance to ANSI/AAMI PC69 Annex M (Correlation between levels of test voltages used in the standard and radiated field strengths).] The addition of the qualitative phrase "to protect the safety for the human body" in sub-clause 11.8.2 is not sufficient to ensure patient safety. The IEEE legal guidance states "... Further, if the proper transmit power is a matter of concern, it should be discussed further with members of the implantable medical device industry to determine an appropriate transmit power level." HBC proponents have not worked in good faith to resolve concerns voiced by members of the implantable medical device industry. | The related discussion with AdvaMed to establish maximum output power levels and an appropriate spectral mask is not yet complete (three conference calls held to date). The minutes from the last conference call are documented in IEEE P802.15-11-0441-00-0006. The proposed resolution is to remove clause 11 and any text referencing this clause from the draft standard, with the HBC mode potentially being further considered in a new Study Group or Task Group. This action would provide AdvaMed members and HBC proponents additional time to analyze potential degradation of medical device operation (due to EMI produced by HBC), without delaying approval of IEEE 802.15.6 and its other modes. | Yes | Rejected Previously Submitted and Rejected
2 | TOTAL

## LB71 - 2 Months Lost
CID | Name | Affiliation | Category | Page | Sub-clause | Line # | Comment | Proposed Change | Must Be Satisfied? (enter Yes or No) | Resolution | Comments
S6-050 | Didier Sagan | Zarlink Semiconductor | Technical | 29 | 6.2.2.1 | 24 | This implies using one Security Sequence Number series for both uplink and downlink data/management frames. A device which fails to receive multiple frames, including retries, will not know how many times the Security Sequence Number has incremented. When this device then needs to transmit a Management/data frame, it will not know the next Security Sequence Number, and may send a number that is not greater than the last, resulting in an authentication failure. It is necessary to have a different series for each direction, uplink and downlink. | Modify as follows b) i ) In frames from the hub to a node, secured with a used PTK, whether they are transmitted from the hub to a node, for the first time or they are retries, it is incremented by one from its value in the last transmitted frame the hub to a node secured with the same PTK. ii ) In frames from the node to a hub, secured with a used PTK, whether they are transmitted from the node to a hub, for the first time or they are retries, it is incremented by one from its value in the last transmitted frame from the node to a hub secured with the same PTK. | Yes | Reject. This comment is addressed by acceptance of comment S6-012. | Missing many frames is a likely occurrence with some of the coexistence mechanisms. [from Rick Powell]
S6-051 | Didier Sagan | Zarlink Semiconductor | Technical | 29 | 6.2.2.1 | 27 | This implies using one Security Sequence Number series for multiple nodes, and for both uplink and downlink data/management frames. A node which is not participating in an allocation interval will not know how many times the Security Sequence Number has incremented. When this node then needs to transmit a Management/data frame, it will not know the next Security Sequence Number, and may send a number that is not greater than the last, resulting in an authentication failure. It is necessary to have a different series for each participating node. | Modify as follows c) i) In frames from the hub to a specific node, secured with a used GTK, whether they are transmitted for the first time or they are retries, it is incremented by one from its value in the last transmitted frame from the hub to the same node secured with the same GTK. ii) In frames from a specific node to the hub, secured with a used GTK, whether they are transmitted for the first time or they are retries, it is incremented by one from its value in the last transmitted frame from the same node to the hub secured with the same GTK. | Yes | Reject. This comment is addressed by acceptance of comment S6-012. | Comment from Rick Powell
S6-053 | Didier Sagan | Zarlink Semiconductor | Technical | 62 | 6.4.2.3 | 10 | This field should be not present if and only if only one new frame is allowed and all previous frames have been received. If all previous frames have been received, then its value, when present, should be the next sequence number from that of the previous frame. | Modify as follows: The Oldest Frame Expected field is not present if, and only if, only one new frame is expected and allowed following the B-Ack frame. Otherwise, it is present and set to the sequence number of the oldest frame that is of the same frame subtype as the frame preceding the current B-Ack frame and that is still expected to be, but not yet, received, or to the next expected sequence number if there are no frames older than the preceding frame received. | Yes | Accept in principle. Modify as follows: The Oldest Frame Expected field is not present if only one new frame is expected and allowed following the B-Ack frame. Otherwise, it is present and set to the sequence number of the oldest frame that is of the same frame subtype as the frame preceding the current B-Ack frame and that is still expected to be, but not yet, received, or to the next expected sequence number if there are no frames older than the preceding frame received. | Comment from Rick Powell
S7-060 | Didier Sagan | Zarlink Semiconductor | Technical | 89 | 7.2.8 | 31 | In the case of a Poll type frame sent by the hub, the hub may exit receive prior to the end of the expected frame if at the start of the MAC header of the expected frame, if it has not received any portion (such as a physical layer preamble) of a frame. This also applies to the hub reclaiming an allocation after waiting for retransmission of a management/data frame after sending an Ack type frame when More Data = 0 and Last Frame = 0 in the transmitted management/data frame. It also applies to other timeout cases where a device may exit receive at the beginning of the MAC header. | Change as follows: If a recipient – a node or a hub – is to receive a frame pSIFS or pMIFS after (the end of) the previous frame, it shall be ready to receive a frame no later than pSIFS or pMIFS, respectively, after the end of the previous frame, and shall not exit receive state earlier than the start of the MAC header of the expected frame, if it has not received any portion (such as a physical layer preamble) of a frame, with the assumption that the time interval between the end of the previous frame and the start of the expected frame is pSIFS+pExtraIFS or pMIFS+pExtraIFS, respectively. | Yes | Accept in principle. Change as follows: "If a recipient – a node or a hub – is to receive a frame pSIFS or pMIFS after (the end of) the previous frame, it shall be ready to receive a frame no later than pSIFS or pMIFS, respectively, after the end of the previous frame, and shall not exit receive state earlier than the start of the MAC header of the expected frame." | Comment from Rick Powell
S7-066 | Didier Sagan | Zarlink Semiconductor | Technical | 108 | 7.6.1.2.3 | 20 | A hub may only replace a future Post/Poll within the same allocation interval in which is was originally assigned. Consider the case: A node has 3 uplink allocation intervals, one for each of 3 sub-types. If the 1st allocation interval needs more time and receives a future post/poll, is should not be canceled by the 2nd allocation interval for a different sub-type. | Modify the sentence as follows: A hub may replace a future poll or post announced earlier for a node with another future poll or post for the node by subsequently sending to the node a Poll, T-Poll, I-Ack+Poll, or B-Ack+Poll frame or an I-Ack or B-Ack frame within the same allocation interval (further specified in 7.8.1), | Yes | Accept in principle. Define Non-Final Fragment / Poll Timing / Inactive field for Poll, T-Poll, I-Ack and B-Ack and I-Ack+Poll and B-Ack+Poll frames sent by hub to node, such that when set to 1, all poll or post allocations previously assigned by the hub to the node are cancelled. (page 28). Clarify that the current encoding is still valid with respect to poll/post allocations. Update text of 7.6.1.2.3 to reference the field when replacing a future poll or post announced earlier (lines 20-31). Data or management frames will not cancel future post/poll allocations. Update Figure 79(a), changing "replaces" with "cancel" in two instances. Update FIgure 79(b) such that data or management frames do not cancel future poll/post allocations. | Comment from Rick Powell
S7-067 | Didier Sagan | Zarlink Semiconductor | Technical | 108 | 7.6.1.2.3 | 24 | A hub may only cancel a future Post/Poll within the same allocation interval in which is was originally assigned, and only with a Poll, T-Poll, I-Ack+Poll, or B-Ack+Poll frame or an I-Ack or B-Ack frame. Consider the case: A node has 2 uplink allocation intervals and one bilink allocation interval, one for each of 3 sub-types. If the 1st allocation interval needs more time and receives a future post/poll, it should not be canceled by a post in the bilink allocation interval. The hub may use the bilink allocation interval to send a new connection assignment before sending a poll for the 3rd sub-type. | Modify the sentence as follows: A hub may cancel a future poll or post announced earlier for a node with another future poll or post for the node by subsequently sending to the node an I-Ack or B-Ack frame within the same allocation interval (further specified in 7.8.1), with the More Data field of the MAC header set to zero, as illustrated in Figure 79(b). | Yes | See S7-066. | Comment from Rick Powell
S7-068 | Didier Sagan | Zarlink Semiconductor | Technical | 109 | 7.6.1.2.3 | 1 | In Figure 79a, in the first transaction, a future post/poll may only be replaced or canceled within the allocation interval in which is was originally assigned. Consider the case: A node has 3 uplink allocation intervals, one for each of 3 sub-types. If the 1st allocation interval needs more time and receives a future post/poll, is should not be canceled by the 2nd allocation interval for a different sub-type. | Correct Figure 79a | Yes | See S7-066. | Comment from Rick Powell
S7-069 | Didier Sagan | Zarlink Semiconductor | Technical | 109 | 7.6.1.2.3 | 3 | In Figure 79b, in the first transaction, a future post/poll may only be replaced or canceled within the allocation interval in which is was originally assigned. It may also not be canceled with a posted M/D frame. In the 2nd set of transactions, the future post/poll assignment of the Downlink allocation is independent of the following future post/poll of the Ack+Poll. The final Ack only cancels the future Post/Poll of the Ack+Poll, but not of the preceding Poll. | Correct Figure 79b | Yes | See S7-066. | Comment from Rick Powell
S7-070 | Didier Sagan | Zarlink Semiconductor | Technical | 109 | 7.6.1.2.3 | 24 | Same as above | Modify the sentence as follows: A node shall treat a future poll or post announced earlier for it as cancelled upon receiving an I-Ack or B-Ack frame within the same allocation interval (further specified in 7.8.1), with the More Data field of the MAC header set to zero, as illustrated in Figure 79(b). | Yes | See S7-066. | Comment from Rick Powell
S7-071 | Didier Sagan | Zarlink Semiconductor | Technical | 109 | 7.6.1.2.3 | 32 | Same as above | Modify the sentence as follows: A node shall update the start time of a future poll or post announced earlier for it upon receiving a Poll, T-Poll, I-Ack+Poll, or B-Ack+Poll frame or an I-Ack or B-Ack frame within the same allocation interval (further specified in 7.8.1), with the More Data field of the MAC header set to one, as illustrated in Figure 79(a). | Yes | See S7-066. | Comment from Rick Powell
S9-017 | Didier Sagan | Zarlink Semiconductor | Technical | 196 | 9.8.1 | 8 | Definition is not clear enough regarding what sample is refered to | Replace "first sample" with "first valid sample of the TX filter" and "last sample" with "last valid sample of the TX filter" | Yes | Accept in principle: See resolution for S9-015
S9-018 | Didier Sagan | Zarlink Semiconductor | Technical | 196 | 9.8.2 | 13 | Definition is not clear enough regarding what sample is refered to | Replace "first sample" with "first valid sample of the TX filter" and "last sample" with "last valid sample of the TX filter" | Yes | Accept in principle: See resolution for S9-015
S9-019 | Didier Sagan | Zarlink Semiconductor | Technical | 196 | 9.8.3 | 18 | Definition is not clear enough regarding what sample is refered to | Replace "first sample" with "first valid sample of the TX filter" and "last sample" with "last valid sample of the TX filter" | Yes | Accept in principle: See resolution for S9-015
S9-020 | Didier Sagan | Zarlink Semiconductor | Technical | 196 | 9.8.4 | 23 | Definition is not clear enough regarding what sample is refered to | Replace "first sample" with "first valid sample of the TX filter" and "last sample" with "last valid sample of the TX filter" | Yes | Accept in principle: See resolution for S9-015
S8-009 | Rene Struik | independent | T | 157 | 8.1 |  | (TR) Clause 8.1, p. 157: For constrained platforms, prime curves are much less efficient than binary curves, esp. in hardware-assisted implementations. This is the more so, since binary field arithmetic can be implemented using shift registers, for which support is already required to implement the error detecting code CRC-16 and the channel hopping (via the use of LFSR); with prime curves, one would need routines for large integer arithmetic and modular reduction. Main concern here is not only efficiency, but also complexity of providing side channel resistance, and energy consumption (if low enough, this would thwart DoS attacks [which can be expected if the standard really takes off and would seem highly undesirable, esp. for monitoring of noncritical and critical medical data.). Current state of the art suggests that binary curves allow hardware-assisted implementation where energy cost of public-key key agreement is less than cost of sending a single frame, whereas I do not know of any prime curve implementation that has a really low energy implementation cost. Suggested remedy: Replace the elliptic curve P-256 by the K-283 curve throughout (this is a binary Koblitz curve specified in NIST Pub 186-3, which seems the most efficient in this context (also used by ZigBee SE v1.x and ISA SP100.11a). Adapt the test on received public key points (p. Clause 8.1, p. 157, l. 36-38) accordingly, viz. check that received point is not the point at infinity (i.e., satisfies the defining equation (16)) and is in the prime order subgroup of K-283. For more details, cf. 11-15/358. | Suggested remedy: Replace the elliptic curve P-256 by the K-283 curve throughout (this is a binary Koblitz curve specified in NIST Pub 186-3, which seems the most efficient in this context (also used by ZigBee SE v1.x and ISA SP100.11a). Adapt the test on received public key points (p. Clause 8.1, p. 157, l. 36-38) accordingly, viz. check that received point is not the point at infinity (i.e., satisfies the defining equation (16)) and is in the prime order subgroup of K-283. For more details, cf. 11-15/358. | Yes | Reject. This is a repeat comment which has been recirculated (see D02/S8-007). No new information provided since previous rejection in D01, D02. Cited document is Pending and not available on mentor document server. | Not actionable, no 11-15/358
S8-010 | Rene Struik | independent | T | 157 | 8.1 |  | (TR) Clause 8.1, p. 157ff: The current draft does define password-based public-key key agreement and unauthenticated public-key key agreement, but does *not* define certificate-based public-key key agreement. It is unclear how a password-based authentication scheme alone furthers “security and ease of use”, since it (1) seems to assume a user interface that allows provisioning of a password string; (2) seems to require set-up of passwords for each pair of devices that wish to communicate (thereby, not tackling the main n2 key distribution problem). Why not use certificate-based key agreement with device certificates, so as to allow reduction of key management and trust management to the management of device identities and which allows network admittance to be based on device identities (intrinsically non-secret information), rather than on passwords (intrinsically secret information, no matter how low the entropy in password-based protocols may be). While password-based approaches can be made to work on some devices, despite disadvantages stated above, I would have expected some consideration of certificate-based public-key key agreement as well, esp. since this can be made to work with a simple Yes/No button user interface and would be more scalable due to avoidance of n2 key distribution problem. Moreover, it facilitates authorized access to patients in emergency settings [one of the deployment use cases] (via the use of certificates issued by an accredited organization), which does not seem to be provided by a password-based scheme or an unauthenticated public-key key agreement scheme. How else is one supposed to check the credentials of emergency crew personnel (and knows if some emergency personnel is checking a victim's pulse or some ex-girl/boy friend is trying to kill, without leaving a forensic trace?) As to password-based key agreement, is there a way to “shoot in” a password into a device using a standardized interface? Suggested remedy: Introduce certificate-based public-key key agreement scheme as well, so as to reap scalability and simplicity of user interface benefits pointed out above. For more details, cf. 11-15/358. | Suggested remedy: Introduce certificate-based public-key key agreement scheme as well, so as to reap scalability and simplicity of user interface benefits pointed out above. For more details, cf. 11-15/358. | Yes | Reject. Comment proposed change is not actionable and represents a new proposal which is out of scope. | Not actionable, no 11-15/358
S8-011 | Rene Struik | independent | T | 158 | 8.1 | 2 | (TR) Clause 8.1, p. 158, l. 2-6: It is unclear why there would be a need to specify the CMAC mode of operation, since one a keyed hash function arises by invoking the combined encryption and authentication mode of operation CCM in a particular way. Having more than one construct only drives up implementation cost and adds to key management cost, without any security benefit. More generally, the protocol design could be designed more efficiently, by considering the objective of lowering overall implementation cost, rather than piece-meal implementation cost. Suggested remedy: Replace the CMAC mode by a particular instantiation of the CCM mode of operation, so as to realize a keyed hash function. In the notation of Clause 8.1, p. 158, l. 5 and NIST Pub 800-38C {or Clause 8.3 of Draft D03}, one could use CCM(A,P, t, q), where the Associated Data (A) is the message M, the Plaintext (P) is the empty string, the length t of the authentication tag is L, and where q=2. For more details, cf. 11-15/358. | Suggested remedy: Replace the CMAC mode by a particular instantiation of the CCM mode of operation, so as to realize a keyed hash function. In the notation of Clause 8.1, p. 158, l. 5 and NIST Pub 800-38C {or Clause 8.3 of Draft D03}, one could use CCM(A,P, t, q), where the Associated Data (A) is the message M, the Plaintext (P) is the empty string, the length t of the authentication tag is L, and where q=2. For more details, cf. 11-15/358. | Yes | Reject. This is a repeat comment which has been recirculated (See D02/S8-008). Comment proposed change is not actionable and represents a new proposal which is out of scope. | Not actionable, no 11-15/358
S8-008 | O Omeni | Toumaz UK Ltd. | Editorial | 158 | 8.1 | 9 | the reference IEEE Std 1363-2000 is inconsistent with the next mention of this concatenation. FIPS Pub 186-3 is the other reference used and should be the correct one. | change "IEEE Std 1363-2000" to "FIPS Pub 186-3" | No | Accept in principle. Change other reference to FIPS in similar context to IEEE standard.
S8-002 | Jin-Meng Ho | Texas Instruments | Editorial | 171 | 8.3 | 14 | Inconsistent format. | Italize "Secured" and "Connected". | N | Accept. Editorial.
S8-012 | Rene Struik | independent | T | 158 | 8.1.1 |  | (TR) Clause 8.1.1, p. 158: (also with all public-key based schemes in Clause 8.1 described further on). The specification suggests that if both parties have different security suite recommendations, then the initiating device should abort operation and try again, potentially with reconciled security suite. This seems to be unnecessarily restrictive, since (a) this necessitates generation of a new random number by either party (esp. computationally intensive if public-key based schemes are used and a new ephemeral key needs to be generated); (b) this could be prevented if one would communicate a set of acceptable security suites instead (and just proceed with one in the intersection, if not the empty set). Suggested remedy: Clearly stipulate that ephemeral keys *shall* be generated afresh at each invocation of the protocol (Note RS: thus opting for conservative approach here). Use set of security suites instead. For more details, cf. 11-15/358. | Suggested remedy: Clearly stipulate that ephemeral keys *shall* be generated afresh at each invocation of the protocol (Note RS: thus opting for conservative approach here). Use set of security suites instead. For more details, cf. 11-15/358. | Yes | Reject. This is a repeat comment which has been recirculated (See D02/S8-032). Comment proposed change is not actionable and represents a new proposal which is out of scope. The proposed change does not address the comment. The keys cited in the proposed change do not have to be regenerated. Current draft defines regeneration of nonces. | Not actionable, no 11-15/358
S8-013 | Rene Struik | independent | T | 159 | 8.1.2 | 4 | (TR) Clause 8.1.2, p. 159, l. 4-6: This scheme seems to come down to a variant of the so-called ephemeral Diffie-Hellman scheme. However, it seems to discard that cryptographic protocols may provide some security assurances, but can never yield a verdict on the question as to whether one really wishes to admit the other device to the network (except when encoded in attributes of certificates in pre-arranged fashion). Thus, the claim that no human interaction is required results in each pair of devices that executes this protocol to indeed establish a secure (non-authenticated) channel. This could lead to serious Denial of Service attacks on the system and lots of non-desired links, with associated impact on storage cost, computational burden, etc. It is unclear that this protocol can only be launched after a human authorization step (e.g., how would this work with an implanted pacemaker device?). With 11-15/030r08, it was suggested that this protocol is not used with implants, since requiring a human authorization step. However, how is one to enforce this and does one now have different chip sets, depending on whether a medical device is on the skin, just below it, an implant, or something worn around the waist (only external devices can be expected to have a user interface). Suggested remedy: This protocol should be accompanied by an authorization step, during which a verdict is reached on whether one indeed wishes to have a secure channel with the other communicating party. For more details, cf. 11-15/358. | Suggested remedy: This protocol should be accompanied by an authorization step, during which a verdict is reached on whether one indeed wishes to have a secure channel with the other communicating party. For more details, cf. 11-15/358. | Yes | Reject. This is a repeat comment which has been recirculated (See D02/S8-011). No new information provided since previous rejection in D01, D02. Cited document is Pending and not available on mentor document server. | Not actionable, no 11-15/358
S8-014 | Rene Struik | independent | T | 160 | 8.1.2 | 4 | (TR) Clause 8.1.2, p. 160, l. 4 (also l. 6): It is unclear why the key confirmation messages are truncated to be 64-bit long. The additional cost of making this a full 128-bit crypto strength protocol (by using 128-bit key confirmation messages) is negligible, since no computational cost and only 8 octets of additional over-the-air communication cost for each of the two key confirmation flows. Suggested remedy: Change accordingly (i.e., replace the numeral 64 by 128). For more details, cf. 11-15/358. | Suggested remedy: Change accordingly (i.e., replace the numeral 64 by 128). For more details, cf. 11-15/358. | Yes | Reject. This is a repeat comment which has been recirculated (See D02/S8-037). No new information provided since previous rejection in D01, D02. Cited document is Pending and not available on mentor document server. | Not actionable, no 11-15/358
S8-015 | Rene Struik | independent | T | 160 | 8.1.2 | 9 | (TR) Clause 8.1.2, p. 160, l. 9: The identifiers of the communicating parties are not included with the MK computation, but only included with the keyed hash function computations. It is not a priori clear whether this precludes certain subtle attacks here, as have been known for other public-key key agreement schemes that initially did not include this information (e.g., unknown key-share attack, etc.). Suggested remedy: Please include the identifiers of the communicating parties in the master key (MK). | Suggested remedy: Please include the identifiers of the communicating parties in the master key (MK). | Yes | Reject. This is a repeat comment which has been recirculated (See D02/S8-038). | Not actionable, no 11-15/358
S8-016 | Rene Struik | independent | T | 161 | 8.1.3 | 4 | (TR) Clause 8.1.3, p. 161, l. 4-5: It is entirely unclear how the “out of band” transfer of public keys is supposed to happen, nor why this is supposed to be “secret” transfer (after all, it concerns public keys (intrinsically public information). If key initialization is left as out-of-band exercise, this may most likely render the scheme less useful and would create a plethora of mutually non-interoperable vendor solutions to solve this bootstrapping problem (thereby, assuring orders of magnitude less use than potential). As an aside, 10/676r0 suggests that the scheme is optional. I would presume that the scheme specified is mandatory, if public key hidden association is used. Suggested remedy: Please remove this scheme, since there is no hope to have a standardized multi-vendor interface that would realize the stipulated behavior. Moreover, remove the adjective “secret” in l. 4. For more details, cf. 11-15/358. | Suggested remedy: Please remove this scheme, since there is no hope to have a standardized multi-vendor interface that would realize the stipulated behavior. Moreover, remove the adjective “secret” in l. 4. For more details, cf. 11-15/358. | Yes | Reject. This is a repeat comment (D02/S8-039) which has been recirculated. | Not actionable, no 11-15/358
S8-017 | Rene Struik | independent | T | 163 | 8.1.4 | 35 | (TR) Clause 8.1.4, p. 163, l. 35, Eqn. (28): My previous comment that the scalar M_X+1 should be removed was rejected in 11-15/030r08, but adopted nevertheless. However, not clear what the factor 232 is doing in Eqn. (29) now. Suggested remedy: Please explain. For more details, cf. also 11-15/358. | Suggested remedy: Please explain. For more details, cf. also 11-15/358. | Yes | Reject. Proposed change is not actionable. The scalar M_X+1 was included to ensure no two password values would be matched to the same point on the elliptic curve. It was replaced with this new factor to achieve the same objective, but simplify the implementation. | Not actionable, no 11-15/358
26 | TOTAL

## LB66 - 6 Months Lost
CID | Name | Affiliation | Revised category | Category | Page | Sub-clause | Line # | Comment | Proposed Change | Must Be Satisfied? (enter Yes or No) | D02 Action |  |  | TG Response | Voters Response to TGs Response | D01 CID
S7-183 | Taehan Bae | Samsung Electronics | Technical | S7-002 |  | 111 | 7 | 19 | The sentence "An implant shall communicate as a node with a hub" does not capture the implant node behavior in MICS. For example an implant node cannot initiate communication with a hub except in case of a medical implant event report. | Change it to "An implant shall communicate as a node with a hub following the applicable regulations and cosniderations" | same as S7-002 | Yes | 0
S7-184 | Taehan Bae | Samsung Electronics | Technical | S7-003 |  | 111 | 7 | 20 | Mutual discovery and frame exchanges between a node and hub may not occur immediately | Remove immediately from the sentence "The hub and the node may perform a mutual discovery procedure described in 7.8.1 and 7.8.2 20 immediately before their frame exchanges" | reject "may" is used, hence it isnt mandatory | Yes | 0
S7-185 | Taehan Bae | Samsung Electronics | Technical | S7-005 |  | 111 | 7.8.1 | 24-26 | The explanation for waking a unconnected node with a known EUI-48 is not sufficient.It is written as illustarted in figure 79, however it is required to complement with the related text. | Explain how the poll-post window (figure 79) is used by the node and explain the node behavior | same as S7-032 | Yes | 0
S7-186 | Taehan Bae | Samsung Electronics | Technical | S7-007 |  | 111 | 7.8.1 | 34-35 | A node can discover hub by an unconnected T-Poll frame or a Wakeup frame. | Change the sentence to "The unconnected node should cyclically tune to each MICS band channel for pMICSUnconnectedPollRxTime, until it receives an unconnected T-Poll frame or a Wakeup frame and hence discovers a hub" | same as S7-007 | Yes | 0
S7-187 | Taehan Bae | Samsung Electronics | Technical | S7-010 |  | 112 | 7 | 15-19 | How the ordered list of channels used by node for unconnected mutual discovery? | "The hub should provide….based on other consideration" has no usefulness for unconnected mutual discovery. However it has meaning for medical emergency event report. It can be removed and placed in the subclause 7.8.3 | same as 010 | Yes | 0
S7-188 | Taehan Bae | Samsung Electronics | Technical | S7-011 |  | 114 | 7 | 18-20 | The sentence "A node connected with a hub…prcoedure as specified in 7.8.2" can be improved for better readability and understanding. | No need to mention "using the mutual discovery prcoedure as specified in 7.8.2". This may confuse reader and it may lead to thinking " whether mutual discovery is required before medical implant event data transfer" | same as 011 | Yes | 0
S7-189 | Taehan Bae | Samsung Electronics | Technical | S7-015 |  | 115 | 7 | 12 and 13 | The sentence 12-14 is not easy to understand. | Change the sentence to "To prevent prolonged collision between emergency frames and transmission by the hub", after retrying a frame……..allow for transmission and reception of possible Emergency frames" | same as 091 | Yes | 0
S7-190 | Taehan Bae | Samsung Electronics | Technical | S7-112 |  | 127 | 7.12.3 | 26 | There is no indication of how priority should be handled for active superframe interleaving. | Add a recommendation for priority handling. "Hub 1 SHOULD accept co-existence requests from hub 2, if hub 2 is indicating a higher priority service" | Accept in principle see resolution in S7-112 | Yes | 0
S7-191 | Taehan Bae | Samsung Electronics | Technical | S7-113 |  | 127 | 7.12.3 | 26 | There is no option available for hubs that are co-existing to inform termination of networks and releasing bandwidth. | Add a bit to the message field of the request frame to indicate termination of current hub's network. When a request frame is sent to a hub 2 which is already sharing with this bit set, it will understand that the hub 1 is going to terminate its piconet and release its bandwidth and so, hub 2 can now have more bandwidth available for communication | Reject see S7-113 | Yes | 0
S7-193 | Taehan Bae | Samsung Electronics | Editorial | S7-110 |  | 132 | 7.12 | 6 | There is no overview of the co-existence mechanisms and the text dives directly into the different options | Add a small summary of the different mechanisms in 7.12.x before starting 7.12.1. Suggestion for summary is as follows. "Multiple co-existence mechanism options are available in IEEE 802.15.6. Some interference mitigation options such as beacon shifting and channel hopping do not require any co-ordination between hubs. Other options such as active superframe interleaving may provide non-interference modes for co-existence but require co-ordination between hubs. Thus, there is a tradeoff available in the standard to implementers between complexity and interference mitigation" | See S7-110. | Yes | 0
S7-194 | Taehan Bae | Samsung Electronics | Technical |  |  | 140 | 7.12.6 | 1 | It is not clear why active superframe interleaving cannot be applied for MICS band in Table 22. | Please add active superframe interleaving as an option for MICS band. | Reject see S7-194 | Yes | 0
S10-073 | Taehan Bae | Samsung Electronics |  | Technical | 192 | 10.3.1 | 4 | Each mode should have only one mandatory modulation | For the default mode, IR-UWB and FM-UWB should be indicated into mandatory and optional, respectively. | Yes | S10-080
S10-074 | Taehan Bae | Samsung Electronics |  | Technical | 197 | 10.8.1 |  | The bit for symbol mapper is missed | In IR-UWB, Table 60 is mandatory and Table 61 is optional. Therefore, for the PHY header, symbol mapper of Table 60 should be always utilized and one reserved bit of PHY header must be allocated for the selection of symbol mapper. (i.e. 0->Table 60, 1->Table 61 for the payload) | Yes | Accept. Intoduce 1 bits in the PHR to indicate Table 60 or Table 61.
S10-075 | Taehan Bae | Samsung Electronics |  | Editorial | 205 | 10.11.1 | footnote | There is no desciption about GPPM until this page. | Change the GPPM into Group Pulse Position Modulation (GPPM) | Yes | Accept in principle. Add GPPM in list of acronyms.
S10-014 | Ciaran Connell | DecaWave Limited |  |  | 164 | 10 | 1 | The IR-UWB PHY defined in this section is unnecessary. It has very similar bit-rates to 802.15.4a with similar complexity, but it has inferior performance to 802.15.4a. There is absolutely no reason to define another UWB PHY with these qualities when 802.15 already has an IR_UWB PHY that fulfils all the 802.15.6 requirements. | Replace the IR-UWB PHY section (section 10), with a statement saying something like: , "Use the PHY defined in 802.15.4a." | Yes | Reject | Out of scope. Commenter failed to submit an UWB PHY proposal (4a or else) to TG6 when applicable. |  | UWB-PHY optimized for BAN and not for location and tracking | This is not true. In the first place the 4a UWB PHY is optimised for both low power communications as well as location. How can retaining the complexity and bit rates but reducing the performance make the proposed 15.6 PHY more optimised for BAN. There is nothing about this proposed PHY that is better for BAN than 15.4a. | S10-31
S10-015 | Michael McLaughlin | DecaWave Limited |  |  | 164 | 10 | 1 | The IR-UWB PHY defined in this section is unnecessary. It has very similar bit-rates to 802.15.4a with similar complexity, but it has inferior performance to 802.15.4a. There is absolutely no reason to define another UWB PHY with these qualities when 802.15 already has an IR_UWB PHY that fulfils all the 802.15.6 requirements. | Replace the IR-UWB PHY section (section 10), with a statement saying something like: , "Use the PHY defined in 802.15.4a." | Yes | S10-014 |  |  | UWB-PHY optimized for BAN and not for location and tracking | This is not true. In the first place the 4a UWB PHY is optimised for both low power communications as well as location. How can retaining the complexity and bit rates but reducing the performance make the proposed 15.6 PHY more optimised for BAN. There is nothing about this proposed PHY that is better for BAN than 15.4a. | S10-32
SG-001 | Steve Shellhammer | Qulacomm | T |  |  |  |  | A coexistence assurance (CA) document was not distributed with the draft. | Please distribute a CA document on the next letter ballot | Yes | Accepted
S10-016 | Billy Verso | DecaWave Limited |  |  | 164 | 10 | 1 | The IR-UWB PHY defined in this section is unnecessary. It has very similar bit-rates to 802.15.4a with similar complexity, but it has inferior performance to 802.15.4a. There is absolutely no reason to define another UWB PHY with these qualities when 802.15 already has an IR_UWB PHY that fulfils all the 802.15.6 requirements. | Replace the IR-UWB PHY section (section 10), with a statement saying something like: , "Use the PHY defined in 802.15.4a." | Yes | S10-014 |  |  | UWB-PHY optimized for BAN and not for location and tracking | This is not true. In the first place the 4a UWB PHY is optimised for both low power communications as well as location. How can retaining the complexity and bit rates but reducing the performance make the proposed 15.6 PHY more optimised for BAN. There is nothing about this proposed PHY that is better for BAN than 15.4a. | S10-43
S10-028 | Ouvry Laurent | CEA-Leti |  | Technical | 191 | 10.1 | 22 | "In a BAN, the coordinator shall implement either an IR-UWB transceiver only or shall implement IR-UWB and FM-UWB transceivers in the same coordinator". First, the term "coordinator" is not used in the other section. Second, it is simpler to state that a hub shall implement IR-UWB. | Rephrase as : In a BAN using the UWB frequency bands, the hub shall implement the IR-UWB mandatory modulation and demodulation. | Yes | Change coodinator by hub and devices by nodes.
S10-029 | Ouvry Laurent | CEA-Leti |  | Technical | 191 | 10.2 | 25 | The default mode shall be used in medical and non-medical applications. The high QoS mode shall be used for critical medical applications. | There is no definition of "critical medical applications" in the standard. See the usr priority of table 17 and adjust the definition accordingly. | Yes | Change crtical by high priority medical data
S10-030 | Ouvry Laurent | CEA-Leti |  | Technical | 191 | 10.2 | 29 | It is unclear wether this is a definition of high QoS mode, or a definition of "critical medical applications". It is also unclear if it implies that the traffic priority level 6 is RESERVED to high QoS | Clarify the statement. Explain if normal mode can use the user priority 6 or not. | Yes | Change critical by high priority medical data
S10-031 | Ouvry Laurent | CEA-Leti |  | Technical | 192 | 10.3.1 | 7 and 9 | One mandatory modulation/data rate for FM-UWB. | Add : "if FM-UWB is implemented (optional)" | Yes | S10-080
S10-032 | Ouvry Laurent | CEA-Leti |  | Editorial | 193 | 10.5 | 2 | Priority of access to resources is based on the fact that if the intended application is medical or non -medical. | Rephrase (remove "if" ?) | Yes | Accept
S10-033 | Ouvry Laurent | CEA-Leti |  | Technical | 193 | 10.5 | 9 | reduce EIRP | State a value. | Yes | Delete 10.5
S10-034 | Ouvry Laurent | CEA-Leti |  | Technical | 193 | 10.5 | 9 | (non) medical devices | This is not the device which is medical or non medical, but the service (see MAC section). Harmonise. | Yes | S10-033
S10-035 | Ouvry Laurent | CEA-Leti |  | Editorial | 193 | 10.5 | 8 | coordinator | replace by "hub" | Yes | S10-028
S10-036 | Ouvry Laurent | CEA-Leti |  | Technical | 193 | 10.5 | 9 | shall enforce | how ? There are no control frames defined in the MAC for that | Yes | S10-033
S10-037 | Ouvry Laurent | CEA-Leti |  | Technical | 193 | 10.5 | 5 | medical applications shall be given a higher priority | Is it not the case that medical services are already given a higher priority than non medical services ? Refer to the MAC shemes and possibilities | Yes | S10-033
S10-047 | Ouvry Laurent | CEA-Leti | editorial | Technical | 193 | 10.6 | 15 | Figure 122: SF1 to SFQ | What are these "SF" whihc defines de SFD ? Update. | Yes | Change figure for SF1 to SFq
S10-038 | Ouvry Laurent | CEA-Leti |  | Editorial | 193 | 10.7 | 22 | In case of HARQ operation, the PSDU contains either the MPDU or BCH parity bits. | rephrase: "In the high QoS mode, the PSDU contains either the MPDU or the BCH parity bits" | Yes | Accept. Harmonize the use of high QoS and HARQ operation.
S10-039 | Ouvry Laurent | CEA-Leti |  | Editorial | 193 | 10.7 | 21 | MPDU | The MPDU is neither defined in the sections 4 (abbreviations) nor the MAC section, nor the NB PHY section ! Harmonise by adding its definition in section 4 and the MAC section 6.2. | Yes | Accept. Define MPDU as MAC frame format of figure 8 and list of acronyms.
S10-040 | Ouvry Laurent | CEA-Leti |  | Technical | 196 | 10.7.4 | 15 | Bit Interleaving | there is no need for bit interleaving, which adds unnessary complexity, memory handling and latency. Remove bit interleaving | Yes | Reject | Bit interleaving improves performance in fading channels. Impact on complexity is minor as it is not block interleaver, but random interleaver.
S10-042 | Ouvry Laurent | CEA-Leti |  | Technical | 197 | 10.8 | 4 | From MAC via SAP in figure 126 | The PHR does not come from the MAC. Remove | Yes | Accept
S10-041 | Ouvry Laurent | CEA-Leti |  | Technical | 197 | 10.8.1.3 | 23 | Burst mode | Explain which IFS shall apply between consecutive frames of a burst (eg : "in burst mode, the inter-frame spacing shall be equal to a pMIFS") | Yes | Accept
S10-043 | Ouvry Laurent | CEA-Leti |  | Editorial | 199 | 10.9.1 | 18 | The set of sequences shall be divided into two pools, where each pool has a set of 4 preambles. | replace by "The set of sequences shall be divided into two pools, where each pool has a set of 4 sequences" | Yes | Accept
S10-044 | Ouvry Laurent | CEA-Leti | Editorial | Technical | 199 | 10.9.1 | 21 | The coordinator might scan all the logical channels | replace by : "The hub may scan all the logical channels …" since this is not mandatory | Yes | Accept
S10-045 | Ouvry Laurent | CEA-Leti |  | Technical | 199 | 10.9.1 | 16 | Sequence length of 63 | Shorter sequences (eg 31) would simplify the receiver implementation, especially in presence of large time drifts | Yes | Reject | No sufficient data supports this comment.
S10-046 | Ouvry Laurent | CEA-Leti |  | Technical | 199 | 10.9.1 | 1 | The preamble shall consist of sync N =4 repetitions | More sequences of smaller length would benefit the performance and the receiver implementation | Yes | S10-045
S10-048 | Ouvry Laurent | CEA-Leti | Editorial | Technical | 208 | 10.11.2.3 | 14 | 10.11.2.3 Differentially encoded PSK modulation with spreading | State in the paragraph right after that this is not for all data rate modes (thus this is optional and only applicable to two of the data rate modes) | Yes | Accept
S10-049 | Ouvry Laurent | CEA-Leti |  | Editorial | 210 | 10.12.1 | 2 | Table 65. Last row, uncoded bit rate | divide by 10 | Yes | Accept
S10-050 | Ouvry Laurent | CEA-Leti |  | Technical | 218 | 10.16.3 | 10 | Chaotic pulse waveform | Nt is not defined, except for the example of Nw=64ns. Therefore the chaotic pulse waveform definition is neither stringent enough for compliance checking, nor precise enough for an implementer. Either remove chaotic pulse waveform from the standard, or provide definitions for all Tw values | Yes | Chaotic pulses are truncated versions of Tw=64nsec.
S10-051 | Ouvry Laurent | CEA-Leti |  | Technical | 224 | 10.18.1 | 20 | The mandatory data rate shall be 250 kbps (uncoded), corresponding to (R0,R1,R2)=(1,1,0) in Table 68. | For the IR-UWB PHYs, the mandatory mode as the lowest data rate and is 0,0,0. Explain how it is possible to lower the rate from the mandatory mode in network operation, and at which rates are transmitted the SHR and PHR. | Yes | Accept in principle. Sub-carriers frequency band plan and corresponding data rates are introduced.
S10-052 | Ouvry Laurent | CEA-Leti | Editorial | Technical | 225 | 10.18.2 | 1 | Table 69. | remove rows about 3dB bandwidth (redundant with the spectral mask) and output power (or add a definition for it) | Yes | Accept
S10-053 | Ouvry Laurent | CEA-Leti |  | Technical | 226 | 10.18.3.3 | 18 | SHR transmission | Explain which SFD is used | Yes | Add figure for PPDU without SFD.
44 | TOTAL

## LB55 - 12 Months Lost
ID Number | Name | Affiliation | Category | Page | Sub-clause | Line # | Comment | Proposed Change | Must Be Satisfied? (enter Yes or No) | Resolution | Comments |  |  | Resolution assigment
S14-8 | David Cypher | NIST | Technical | 3 | 2 | 13 | Note 3 incorrectly defines NIST | Change for to of |  | Accept comment | Done
S14-9 | David Cypher | NIST | General | 5 | 3 |  | The entire clause 3 defines multiple terms for the same thing, which violates the 802.15 OM (LB54) clause 11 (15-10-0324-00-0000 1.1, bullet 5) | Use one term only (e.g. active state (not awake) and inactive state (not hibernation state) |  | Accept comment. Delete page 5, line 21 and page 6, line 40 | Done
S5-5 | David Cypher | NIST | Editorial | 16 | 5.5.1.1 | 9 | Use of first occurrence of an acronym (MK) must be spelled out | Insert Master Key | Yes | E. | Done
S5-21 | David Cypher | NIST | Technical | 13 | 5.2 | 12 | There is no mMaxBANSizes in Table 23 | Correct term by deleting the final "s" to agree with the name in Table 23 | Yes | Accept. Editorial comment. | Done
S5-22 | David Cypher | NIST | Technical | 15 | 5.5 | 11 | There are two items in the subject verb agreement is not correct | Change is to are | Yes | Accept. Editorial comment. | Done
S6-050 | David Cypher | NIST | Editorial | 22 | 6.2.1.1.6 | 3 | exclusieve is misspelled | correct | Yes | Same as S6-47 | Done
S6-051 | David Cypher | NIST | Editorial | 22 | 6.2.1.1.6 | 4 | curren is misspelled | correct | Yes | Same as S6-48 | Done
S6-053 | David Cypher | NIST | Technical | 24 | 6.2.1.1.11 | 40 | What is the 6. Doing on this line? | Delete | Yes | Same as S6-8 | Done
S6-054 | David Cypher | NIST | Technical | 30 | 6.3.1.10.2 | 16 | Table 4 third column is named Beacon Shifting Sequence pattern, while the text states Beacon Shifting Sequence Phase terms do not agree. | Select one term | Yes | Accepted in principle: (1) In the table's heading, change "sequences" to "Sequence field encoding". (2) In the left column, after "index" add "m in" (with "m" in italic). (3) in the middle column, change "valeus" to "as function of Beacon Shifting Sequence Phase n = 0, 1, 2, …, 15 " (with n in italic), and delete all instances of ", n = 0, 1, ...". except the header entry italic. (4) In lines 2 and 41, page 24, after "incremented by one", add ", modulo 256, ". See updated text/table in DCN 0677-00. | Done
S6-055 | David Cypher | NIST | Technical | 30 | 6.3.1.11 | 19 | The text states that this field is present only if the channel hopping is currently enabled as encoded according to Figure 14. This is a self reference because there is no other field stating if channel hopping is enabled. | Insert another field in Figure 14, which indicates whether the Channel Hopping State will be included. | Yes | Accepted in principle: See S6-277. | Done
S6-056 | David Cypher | NIST | Technical | 31 | 6.3.2 | 15 | The length of the Security Association Date field in Figure 17 is marked greater than or equal to 0, however in Figure 19 page 19 the field is fixed with a size of 72. | Correct inconsistency by changing greater than or equal to 0 to 72 | Yes | Reject. Figure 17 is correct showing greater than or equal to zero as general case. | Done
S6-057 | David Cypher | NIST | Technical | 32 | 6.3.2.3.4 | 15 | Header is not consistent with name in Figure 18 | Delete Protocol | Yes | Same as S6-187 | Done
S6-058 | David Cypher | NIST | Editorial | 34 | 6.3.2.6.2 | 28 | Use subscript for the Y | Beacon Shifting Sequence | Yes | Reject. The proposed change includes a typographical error, citing irrelevant "beacon shifting sequence". See S6-379. | Done
S6-059 | David Cypher | NIST | Technical | 36 | 6.3.3.2.1 | 15 | Wrong level of indent | Change level of indent to same as the other four fields from figure 20 | Yes | E. Accept. | Done
S6-060 | David Cypher | NIST | Technical | 36 | 6.3.3.2.2 | 19 | Wrong level of indent | Change level of indent to same as the other four fields from figure 20 | Yes | E. Accept. | Done
S6-061 | David Cypher | NIST | Technical | 37 | 6.3.4.4 | 18 | Is this index a single bit or multiple bits? Line 18 indicates that one can subtract 1 for the value, while line 22 indicates that it has a value of zero or one only. | Fix inconsistency | Yes | Accept in principle. Change text on line 18-19 to "…is set to the modulo-2 sum of one plus its value used…" Changes implemented in DCN 0678-00. | Done
S6-062 | David Cypher | NIST | Technical | 38 | 6.3.5.4 | 26 | Is this index a single bit or multiple bits? Line 18 indicates that one can subtract 1 for the value, while line 22 indicates that it has a value of zero or one only. | Fix inconsistency | Yes | See S6-280. | Done
S6-063 | David Cypher | NIST | Technical | 41 | 6.3.6.8 | 12 | Why is there a need to code 256 as zero, when this is a 2 byte field allowing for the coding of 256 naturally? | Delete entire sentence | Yes | See S6-282. | Done
S6-064 | David Cypher | NIST | Technical | 43 | 6.3.7.10 | 18 | Cross reference is wrong. It points to a 1-bit Wakeip Phase field, not a 2-octet Wakeup Phase field as in 6.3.6.7 | Correct cross reference and guarantee that there is uniqueness in field naming. | Yes | We should Accept, This is an editorial comment. DCN 0679-00 already addresses this comment. | Done
S6-065 | David Cypher | NIST | Technical | 44 | 6.3.7.11 | 2 | Cross reference is wrong. It points to a 1-bit Wakeip Period field, not a 2-octet Wakeup Period field as in 6.3.6.8 | Correct cross reference and guarantee that there is uniqueness in field naming. | Yes | We should Accept, This is an editorial comment. DCN 0679-00 already addresses this comment. | Done
S6-066 | David Cypher | NIST | Technical | 44 | 6.3.7.18 | 18 | Cross reference is wrong. | Change 6.7.11 to 6.7.12 | Yes | We should Accept, This is an editorial comment. DCN 0679-00 already addresses this comment. | Done
S6-067 | David Cypher | NIST | Technical | 45 | 6.3.8 | 1 | Figure 26 contains two fields that are not defined in 6.3.7 | Properly define the missing fields (B+EAP1 Length, EAP2 Length) | Yes | See S6-385. | Done
S6-068 | David Cypher | NIST | Technical | 47 | 6.3.11.4.2 | 8 | Wrong level of indent | Indent level should be one lower than the Command it is part of 6.3.11.4.1.1 | Yes | TG discussed and agreed to accept in principle. New text of DCN 0755-00 addresses this comment. | Done
S6-069 | David Cypher | NIST | Technical | 47 | 6.3.11.4.3 | 14 | Wrong level of indent | Indent level should be one lower than the Command it is part of 6.3.11.4.1.1 | Yes | TG discussed and agreed to accept in principle. New text of DCN 0755-00 addresses this comment. | Done
S6-070 | David Cypher | NIST | Technical | 47 | 6.3.11.4.3 | 14 | Header is title wrong | Change to Coexistent Mode | Yes | TG discussed and agreed to accept in principle. New text of DCN 0755-00 addresses this comment. | Done
S6-071 | David Cypher | NIST | Technical | 47 | 6.3.11.4.4. | 22 | Inconsistency with name of field | Change data rate to duty cycle to agree with the field name in Figure 29 | Yes | Same as S6-72 | Done
S6-072 | David Cypher | NIST | Technical | 48 | 6.3.11.4.4 | 1 | Table 12 column three is inconsistent with Figure 29 and clause heading | Change data rate to duty cycle to agree with the field name in Figure 29 | Yes | Accept. Change to "duty cycle" in Table 12 heading. | Done
S6-073 | David Cypher | NIST | Editorial | 48 | 6.3.11.5(b) | 3 | Wrong level of indent and lettering | Indent level should be five (I.e. 6.3.11.4.2) | Yes | TG discussed and agreed to accept in principle. New text of DCN 0755-00 addresses this comment. | Done
S6-074 | David Cypher | NIST | Editorial | 48 | 6.3.11.5.1 | 10 | Wrong level of indent | Indent level should be one more than the frame that it belongs to | Yes | TG discussed and agreed to accept in principle. New text of DCN 0755-00 addresses this comment. | Done
S6-075 | David Cypher | NIST | Technical | 48 | 6.3.11.5.1 | 11 | Lacks indication for setting the 1-bit field for accepted or rejected | Add missing setting | Yes | Same as S6-293 | Done
S6-076 | David Cypher | NIST | Editorial | 48 | 6.3.11.5.2 | 12 | Wrong level of indent | Indent level should be one more than the frame that it belongs to | Yes | TG discussed and agreed to accept in principle. New text of DCN 0755-00 addresses this comment. | Done
S6-077 | David Cypher | NIST | Technical | 48 | 6.3.11.5.2 | 13 | This is a 2-bit filed not a 1-bit field | Insert 2-, to make a 2-bit field to agree with figure 30 | Yes | TG discussed and agreed to accept in principle. New text of DCN 0755-00 addresses this comment. | Done
S6-078 | David Cypher | NIST | Editorial | 48 | 6.3.11.5.3 | 15 | Wrong level of indent | Indent level should be one more than the frame that it belongs to | Yes | TG discussed and agreed to accept in principle. New text of DCN 0755-00 addresses this comment. | Done
S6-079 | David Cypher | NIST | Technical | 48 | 6.3.11.5.3 | 19 | Table 13 header row in not consistent with field name in figure 30 | Change data rate to duty cycle to agree with the field name in Figure 30 | Yes | Accept. Same as S6-463 | Done
S6-080 | David Cypher | NIST | Editorial | 49 | 6.3.11.5.4 | 1 | Wrong level of indent | Level should be at the same level as the other command frames (I.e., 6.3.11.4.3 | Yes | TG discussed and agreed to accept in principle. New text of DCN 0755-00 addresses this comment. | Done
S6-081 | David Cypher | NIST | Editorial | 49 | 6.3.11.5.5 | 9 | Wrong level of indent | Level should be one more than the command frame that this field is part of (I.e., 6.3.11.4.3.1) | Yes | TG discussed and agreed to accept in principle. New text of DCN 0755-00 addresses this comment. | Done
S6-082 | David Cypher | NIST | Editorial | 49 | 6.3.11.5.6 | 12 | Wrong level of indent | Level should be one more than the command frame that this field is part of (I.e., 6.3.11.4.3.2) | Yes | E. | Done
S6-083 | David Cypher | NIST | Editorial | 49 | 6.3.11.5.4 | 2 | Add space between 31 and in | Add space between 31 and in | Yes | TG discussed and agreed to accept in principle. New text of DCN 0755-00 addresses this comment. | Done
S6-084 | David Cypher | NIST | Editorial | 49 | 6.3.11.5.7 | 17 | Wrong level of indent | Level should be at the same level as the other command frames (I.e., 6.3.11.4.4 | Yes | E. | Done
S6-085 | David Cypher | NIST | Technical | 50 | 6.4.2 | 5 | Figure 32 the frame status bitmap uses 0, 1, … instead of L-R | Replace 0, 1, .. With L-R | Yes | MAC subgroup discussed and agreed to proposed resolution in DCN 0677-00. | Done
S6-086 | David Cypher | NIST | Technical | 53 | 6.4.8 | 1 | Figure 35 has Piconet priority as a 1-bit, while text of 6.4.8.6 states that it is a 2-bit field | Fix inconsistency | Yes | TG discussed and agreed to accept. New text of DCN 0755-00 addresses this comment. | Done
S6-087 | David Cypher | NIST | Technical | 53 | 6.4.8 | 1 | Figure 35 has a beacon period length as a 1-bit, but the text of 6.4.8.1 indicates more than one bit, especially if it is a length field | Fix inconsistency | Yes | TG discussed and agreed to accept. New text of DCN 0755-00 addresses this comment. | Done
S6-088 | David Cypher | NIST | Technical | 53 | 6.4.8.3 | 11 | There is no minCAP in Table 23, 24, or 25 | Define minCAP | Yes | See S6-299 | Done
S6-089 | David Cypher | NIST | Technical | 54 | 6.4.8.7 | 7 | What is a coordinator? There is no such term in this document | Replace coordinator with hub | Yes | TG discussed and agreed to accept. New text of DCN 0755-00 addresses this comment in subclause 6.4.8 | Done
S6-090 | David Cypher | NIST | Technical | 54 | 6.4.8.8 | 9 | What is a coordinator? There is no such term in this document | Replace coordinator with hub | Yes | Same as S6-89 | Done
S6-091 | David Cypher | NIST | Technical | 54 | 6.4.8.8 | 9 | What are coordinators? There is no such term in this document | Replace coordinators with hubs | Yes | TG discussed and agreed to accept. New text of DCN 0755-00 addresses this comment in subclause 6.4.8 | Done
S6-092 | David Cypher | NIST | Technical | 54 | 6.4.8.8A | 10 | There is no description of the NID 1-bit fields | Insert the missing description of the 1-bit NIDs | Yes | TG discussed and agreed to accept in principle. New text of DCN 0755-00 addresses this comment in subclause 6.4.8 | Done
S6-093 | David Cypher | NIST | Technical | 56 | 6.6.1.12 | 14 | Test is not consistent with header | Insert hub, to make Relayed Hub/Node | Yes | Accept. Editorial. | Done
S6-094 | David Cypher | NIST | Technical | 64 | 6.7.8 | 14 | Header does not agree with the text | Change Uplink to Downlink | Yes | Accept. E. | Done
S6-095 | David Cypher | NIST | Technical | 64 | 6.7.10 | 21 | Header does not agree with the text | Change Uplink to Bilink | Yes | Accept. Editorial | Done
S6-096 | David Cypher | NIST | Technical | 66 | 6.7.11 | 5 | Text states that the fields are defined in 6.3.6, which is a false statement. 6.3.6 does not contain Node address, NID, Uplink, Downlink, Bilink Assignment IEs Delayed Bilink Assignment IE, Channel order IE or Channel Hopping IE | Properly describe the missing IE here | Yes | MAC subgroup discussed and agreed to proposed resolution in DCN 0677-00. | Done
S6-097 | David Cypher | NIST | Technical | 67 | 6.7.15.1 | 26 | What is an OUI-24l? | Delete l | Yes | Accept. E. | Done
S6-098 | David Cypher | NIST | Technical | 59 | 6.7.2.1 | 18 | Only the Frame Subtype is shown below | Change below to in the following sub clauses | Yes | Accept. E. | Done
S6-099 | David Cypher | NIST | Editorial | 59 | 6.7.2.2 | 19 | Should be one level more than the Allocation ID level, since this item is part of it | Change 6.7.2.2 to 6.7.2.1.1 | Yes | Same as S6-100. | Done
S6-100 | David Cypher | NIST | Editorial | 60 | 6.7.2.3 | 19 | Should be one level more than the Allocation ID level, since this item is part of it | Change 6.7.2.2 to 6.7.2.1.2 | Yes | E. | Done
S6-421 | David Cypher | NIST | Technical | 58 | 6.7 | 2 | Table 15, row 14, the IE name does not agree with the Description. IN one Bilink and in the other uplink | Fix inconsistency | Yes | Accepted in principle: In the Description entry for Element ID of 14, change "uplink" to "bilink". | Done
S6-422 | David Cypher | NIST | Technical | 57 | 6.7 | 21 | This is the last line on the page, nothing is defined below. | Change below to in the following sub clauses | Yes | Accepted in principle: Change "as defined below" to "in the rest of this subclause". | Done
S7-410 | David Cypher | NIST | Technical | 69 | 7.1 | 15 | Insert a period after 7.13 and before MAC, so that the words can be made sense of. | Insert a period after 7.13 and before MAC, so that the words can be made sense of. | Yes | Accept. E. |  | Done
S7-059 | David Cypher | NIST | Technical | 71 | 7.2.3 | 1 | Table 17 lists user priority requiring a minimum of 3 bit to represent 8 values. There is a piconet priority which is 2-bits. There is a user priority of 4-bits in the Request IEs. Neither can be the priority to which this is referring since the first does not have enough bit and the second has too many that the table has not marked as reserved. | Fix inconsistency | Yes | Accept in principle. See DCN 0677-00 for text addressing this comment. |  | Done
S7-060 | David Cypher | NIST | Technical | 72 | 7.2.6 | 9 | What is the "Not acknowledge??" doing here? | Delete it | Yes | Accept. E. |  | Done
S7-061 | David Cypher | NIST | Technical | 72 | 7.2.7 | 11 | What does Table 17 have to do with the Frame Acknowledgement? | Delete cross reference to Table 17 | Yes | MAC subgroup discussed and agreed to proposed resolution in 0666-01. |  | Done
S7-076 | David Cypher | NIST | Technical | 72 | 7.2.7 | 14 | Change below to in the following sub clauses | Change below to in the following sub clauses | Yes | MAC group discussed and agreed to accept this comment. |  | Done
S7-062 | David Cypher | NIST | Technical | 73 | 7.2.7.2 | 5 | There is no mG-AckDataSubtype in table 3. mG-AckDataSubtype is a MAC sublayer parameter, not a subframe type. Its value of 15 is a user defined subtype in table 3. | Fix inconsistency | Yes | MAC subgroup discussed and agreed to proposed resolution in DCN 0663-00. |  | Done
S7-063 | David Cypher | NIST | Technical | 73 | 7.2.7.2 | 6 | What is latter? Only a hub is ever mentioned, there is no latter. | Replace latter with identifying entity | Yes | Accept. E. |  | Done
S7-064 | David Cypher | NIST | Technical | 73 | 7.2.7.2 | 8 | If mG-AckDataSubtype is a valid subtype, then add it to table 3 | Fix inconsistency | Yes | Same proposed resolution as S7-062. |  | Done
S7-065 | David Cypher | NIST | Technical | 75 | 7.2.9 | 11 | The N-Ack and G-Ack are the same, not different | Put () around G-Ack | Yes | MAC subgroup discussed and agreed to reject as context in draft document is correct. Refer to Table 1. |  | Done
S7-066 | David Cypher | NIST | Technical | 76 | 7.3.1 | 15 | header not using consistent name | Insert superframe before boundaries | Yes | Accept. E. |  | Done
S7-077 | David Cypher | NIST | Technical | 76 | 7.3.1 | 29 | Delete "as described below" and insert a comma | Resulting in "… access phase, but not both." | Yes | MAC subgroup discussed and agreed to proposed resolution of DCN 0666-01. |  | Done
S7-067 | David Cypher | NIST | Editorial | 77 | 7.3.2 | 22 | Insert a space after 7.3.1and before in. | Insert a space after 7.3.1and before in. | Yes | E. |  | Done
S7-411 | David Cypher | NIST | Editorial | 78 | 7.4 | 32 | Remove the italics on the n inside the word function | Remove the italics on the n inside the word function | Yes | E. |  | Done
S7-412 | David Cypher | NIST | Technical | 79 | 7.4 | 19 | There is no Multinode Assignment frame | Insert Connection to use a defined frame | Yes | MAC subgroup discussed and agreed to proposed resolution in DCN 0663-00. |  | Done
S7-078 | David Cypher | NIST | Technical | 80 | 7.5.1 | 15 | Where is it described below? Both 7.5.1.1 and 7.5.2.1 have the exact same heading of "Starting a contended allocation." | Replace "as described below" with actual cross reference to 7.5.2.1 | Yes | Accept. E. |  | Done
S7-079 | David Cypher | NIST | Technical | 81 | 7.5.1.1 | 26 | Where and what is "as further described below." to which this is referring? | Replace with cross reference or delete text | Yes | Accept. E. |  | Done
S7-068 | David Cypher | NIST | Technical | 82 | 7.5.2 | 26 | The use of below is not descriptive. | Insert cross reference | Yes | Accept. E. |  | Done
S7-080 | David Cypher | NIST | Technical | 84 | 7.6.2 | 30 | Where and what is "as described below." to which this is referring? | Replace with cross reference or delete text | Yes | Accept. E. |  | Done
S7-417 | David Cypher | NIST | Technical | 92 | 7.8 | 32 | Delete "described below" | Delete "described below" | Yes | MAC subgroup discussed and agreed to proposed resolution of DCN 0666-01. |  | Done
S7-069 | David Cypher | NIST | Technical | 94 | 7.8.2.1.1 | 20 | What is this doing here? Why is it redefining the one from clause 6 | Remove entire clause | Yes | Agree in principle. See doc 915-02 for text to replace this subclause |  | Done
S7-081 | David Cypher | NIST | Technical | 94 | 7.8.2.1.2 | 25 | Delete "as described below" | Delete "as described below" | Yes | MAC subgroup discussed and agreed to proposed resolution of DCN 0666-01. |  | Done
S7-070 | David Cypher | NIST | Technical | 95 | 7.8.2.1.2 | 18 | Figure 75 Terms coordinator and device need to be replaced by hub and node (four occurrences) | Terms coordinator and device need to be replaced by hub and node | Yes | MAC subgroup discussed and agreed to proposed resolution in DCN 0666-01. |  | Done
S7-082 | David Cypher | NIST | Technical | 96 | 7.8.2.1.4 | 10 | Replace "as described below" with "described in this sub clause" | Replace "as described below" with "described in this sub clause" | Yes | Accept. E. |  | Done
S7-071 | David Cypher | NIST | Technical | 97 | 7.8.2.1.4 | 3 | Figure 77 Terms coordinator and device need to be replaced by hub and node (four occurrences) | Terms coordinator and device need to be replaced by hub and node | Yes | MAC subgroup discussed and agreed to proposed resolution in DCN 0666-01. |  | Done
S7-413 | David Cypher | NIST | Technical | 98 | 7.9 | 9 | The use of below is not descriptive. | Insert cross reference | Yes | Resolution proposed by DCN 0652-00 and 0544-02 was discussed and agreed upon by MAC subgroup 09Sep10. |  | Done
S7-083 | David Cypher | NIST | Technical | 102 | 7.10 | 15 | Replace "as specified below" with "specified in this sub clause" | Replace "as specified below" with "specified in this sub clause" | Yes | Accept. E. |  | Done
S7-414 | David Cypher | NIST | Technical | 105 | 7.11 | 8 | The use of below is not descriptive. | Insert cross reference | Yes | Same as S7-68 |  | Done
S7-415 | David Cypher | NIST | Editorial | 107 | 7.12 | 24 | Insert a space between 7.12.1 and for | Insert a space between 7.12.1 and for | Yes | E. |  | Done
S7-416 | David Cypher | NIST | Technical | 107 | 7.12 | 26 | Replace below with actual cross reference | Replace below with actual cross reference | Yes | MAC subteam discussed and agreed to proposed resolution of DCN 0677-00. |  | Done
S7-072 | David Cypher | NIST | Technical | 107 | 7.11.2 | 7 | There is no Figure 86 (a) | Correct cross reference | Yes | Accept. E. |  | Done
S7-073 | David Cypher | NIST | Technical | 107 | 7.11.2 | 10 | There is no Figure 86 (a) | Correct cross reference | Yes | Same as S7-72 |  | Done
S7-074 | David Cypher | NIST | Technical | 107 | 7.11.2 | 14 | There is no Figure 86 (b) | Correct cross reference | Yes | Accept. E. |  | Done
S7-075 | David Cypher | NIST | Technical | 111 | 7.12.3 | 16 | Entire 7.12.3 and subclauses and 7.12.4: What is a coordinator? There is no such term in this document | Replace coordinator with hub | Yes | MAC subgroup discussed and agreed to proposed resolution in DCN 0666-01. |  | Done
S8-8 | David Cypher | NIST | Technical | 121 | 8.1.2 | 9 | Replace below with equation 21 | Replace below with equation 21 | Yes | E. Change implemented in DCN 0678-00. | Done
S8-9 | David Cypher | NIST | Technical | 121 | 8.1.2 | 18 | Replace below with equation 21 | Replace below with equation 21 | Yes | E. Change implemented in DCN 0678-00. | Done
S8-10 | David Cypher | NIST | Technical | 121 | 8.1.2 | 31 | Are P2 and P3 the same as P_2 and P_3 on line 29 and line 30? | If so, use consistent terms because P2 <> P_2 | Yes | E. Change implemented in DCN 0678-00. | Done
S8-11 | David Cypher | NIST | Technical | 121 | 8.1.2 | 22 | Where below? Equation 22? | Replace below with equation 22 | Yes | E. Change implemented in DCN 0678-00. | Done
S8-12 | David Cypher | NIST | Technical | 121 | 8.1.2 | 24 | Where below? Equation 22? | Replace below with equation 22 | Yes | E. Change implemented in DCN 0678-00. | Done
S8-13 | David Cypher | NIST | Technical | 123 | 8.1.3 | 12 | Where below? Equation 26? | Replace below with equation 26 | Yes | E. Change implemented in DCN 0678-00. | Done
S8-14 | David Cypher | NIST | Technical | 124 | 8.1.3 | 7 | Replace below with equation 26 | Replace below with equation 26 | Yes | E. Change implemented in DCN 0678-00. | Done
S8-15 | David Cypher | NIST | Technical | 124 | 8.1.3 | 11 | Replace below with equation 27 | Replace below with equation 27 | Yes | E. Change implemented in DCN 0678-00. | Done
S8-16 | David Cypher | NIST | Technical | 124 | 8.1.3 | 20 | Are P2 and P3 the same as P_2 and P_3 on line 18 and line 19? | If so, use consistent terms because P2 <> P_2 | Yes | E. Change implemented in DCN 0678-00. | Done
S8-17 | David Cypher | NIST | Technical | 124 | 8.1.3 | 13 | Where below? Equation 27? | Replace below with equation 27 | Yes | E. Change implemented in DCN 0678-00. | Done
S8-18 | David Cypher | NIST | Technical | 125 | 8.1.3 | 15 | Where below? Equation 28? | Replace below with equation 28 | Yes | E. Change implemented in DCN 0678-00. | Done
S8-19 | David Cypher | NIST | Technical | 125 | 8.1.4 | 18 | Where below? Equation 34? | Replace below with equation 34 | Yes | E. Change implemented in DCN 0678-00. | Done
S8-20 | David Cypher | NIST | Technical | 125 | 8.1.4 | 29 | Where below? Equation 34? | Replace below with equation 34 | Yes | E. Change implemented in DCN 0678-00. | Done
S8-21 | David Cypher | NIST | Technical | 125 | 8.1.4 | 33 | Where below? Equation 35? | Replace below with equation 35 | Yes | E. Change implemented in DCN 0678-00. | Done
S8-22 | David Cypher | NIST | Technical | 125 | 8.1.4 | 35 | Where below? Equation 35? | Replace below with equation 35 | Yes | E. Change implemented in DCN 0678-00. | Done
S8-23 | David Cypher | NIST | Technical | 126 | 8.1.4 | 4 | Replace "are defined below" with "are as follows" | Replace "are defined below" with "are as follows" | Yes | E. Change implemented in DCN 0678-00. | Done
S8-24 | David Cypher | NIST | Technical | 126 | 8.1.4 | 19 | Are P2 and P3 the same as P_2 and P_3 on line 17 and line 18? | If so, use consistent terms because P2 <> P_2 | Yes | E. Change implemented in DCN 0678-00. | Done
S8-25 | David Cypher | NIST | Technical | 128 | 8.1.5 | 8 | Where below? Equation 37? | Replace below with by equation 37 | Yes | E. Change implemented in DCN 0678-00. | Done
S8-26 | David Cypher | NIST | Technical | 128 | 8.1.5 | 19 | Where below? Equation 37? | Replace below with by equation 37 | Yes | E. Change implemented in DCN 0678-00. | Done
S8-27 | David Cypher | NIST | Technical | 128 | 8.1.5 | 27 | Where below? Equation 41? | Replace below with by equation 41 | Yes | E. Change implemented in DCN 0678-00. | Done
S8-28 | David Cypher | NIST | Technical | 132 | 8.2.1 | 1 | Where below? Equation 46? | Replace below with by equation 46 | Yes | E. Change implemented in DCN 0678-00. | Done
S8-29 | David Cypher | NIST | Technical | 132 | 8.2.1 | 5 | Where below? Equation 46? | Replace below with by equation 46 | Yes | E. Change implemented in DCN 0678-00. | Done
S8-30 | David Cypher | NIST | Technical | 132 | 8.2.1 | 7 | Where below? Equation 46? | Replace below with by equation 46 | Yes | E. Change implemented in DCN 0678-00. | Done
S8-31 | David Cypher | NIST | Editorial | 134 | 8.3.1 | 29 | Missing a period to indicate that the statement is complete. | Insert a period. | Yes | E. | Done
S8-32 | David Cypher | NIST | Editorial | 134 | 8.3.1 | 30 | Delete period at the start of this sentence | Delete the period | Yes | E. | Done
S8-52 | David Cypher | NIST | Editorial | 119 | 8 | 2 | Move period before Figure 5 to after | Move period before Figure 5 to after | Yes | E. | Done
S9-16 | David Cypher | NIST | Technical | 160 | 9.7.7 | 1 | Remove below and replace with Equation 68 (as per the IEEE Standards Style Manual 2009 ((See its example on page 50)) | Remove below and replace with Equation 68 (as per the IEEE Standards Style Manual 2009 ((See its example on page 50)) | Accept | Yes | 0
S9-83 | David Cypher | NIST | Technical | 141 | 9 | 2 | Why is this document defining optional physical layer for 802.15.6, when this is to be 802.15.6? | Rewrite "This clause specifies an optional narrowband physical layer." | Accept | Yes | 0
S11-29 | David Cypher | NIST | Technical | 201 | 11.6.1 | 8 | As below what? | Do not understand what is to be expected | Accepted. P201 L9: 10 in front of (frame sync). P202 L1: 11 in front of (superframe sync). P201 L8: "as below" will be replaced by "as follows" | The corresponding section for sync is removed. | 0
SG-5 | David Cypher | NIST | Editorial | 209 | Annex A | 5 | Annex A; B3 has no entry | Delete B3 | Yes | Accepted in principle
S14-28 | James Gilb | SiBEAM | Editorial | 1 | 1 | 20 | This is not a document, it is a standard. | Change "document" to "standard" | Reject. Subclause 1 is taken from the TG6 PAR. Per IEEE document guidelines of 2009, scope purpose and need are to be included exactly as in the PAR. In addition, the existing text is correct as written as "this standard defines a standard" would not be appropriate. | Done
S14-29 | James Gilb | SiBEAM | Editorial | 1 | 1 | 24 | There is no 802.15 MAC. | Delete "802.15" | Reject. Subclause 1 is taken from the TG6 PAR. Per IEEE document guidelines of 2009, scope purpose and need are to be included exactly as in the PAR. | Done
S14-30 | James Gilb | SiBEAM | Editorial | 3 | 2 | 6 | It appears that there is a mistake, you should only have one introduction paragraph to the references. These two paragraphs appear to conflict. | Verify that the correct paragraph(s) are being used here by checking the 2009 style guide. | E. | Ok, but check | JMH: Removed 2nd paragraph | DONE Default text from template
S14-31 | James Gilb | SiBEAM | Editorial | 5 | 3 | 1 | The format for the definitions does not follow the style guide. | Refer to 10.5.2 in the 2009 style guide. | E. | Ok, but check | DONE
S14-32 | James Gilb | SiBEAM | Technical | 6 | 3 | 5 | A definition needs to be general, not specific to the standard. | Delete "Connected_NID" and review all definitions to make sure that they apply to all standards and not just to this standard. For things that apply to this standard, define the terms in the Clauses. Review all the definitions, probably at least half should be removed from Clause 3. | Accept in principle. Create new glossary subclause, add definitions to this new glossary subclause. | TODO | DONE Created section 3.2, definitons specific to this standard
S14-33 | James Gilb | SiBEAM | Technical | 6 | 3 | 40 | "All terms defined in IEEE standards are incorporated into the IEEE-SA Standards Definitions Database. For this reason, it is important that terms and definitions have as general an application as possible." 2009 Style Guide | This definition is an example of one that should be deleted because it has scope only in this standard. Also, it is wrong to have two terms that mean the same thing. Delete this definition and change all occurrences of "hibernation" to "inactive" | Accept in principle. Create new glossary subclause, add definitions to this new glossary subclause. | TODO | DONE Created section 3.2, definitons specific to this standard
S14-34 | James Gilb | SiBEAM | Technical | 10 | 4 | 4 | This is not an acronym expansion. Plus AES and CCM are expanded elsewhere. | Delete "AES-128 CCM" and the acroread. | Accept. | Done
S5-28 | James Gilb | SiBEAM | Technical | 15 | 5 | 15 | Clause 5 should be an informative introduction. Don't put detailed figures in Clause 5 that will appear elsewhere. This repeats normative information that will lead errors in the draft. | Delete Figure 4. | Yes | See S5-1. These figures do not appear anywhere else. They are placed in clause 5 which serves as an introduction to both MAC and security, as they concern both MAC and security, which are separately specified in subsequent clauses. | Done
S6-316 | James Gilb | SiBEAM | Editorial | 20 | 6.2.1.1.1 | 16 | The subclause heading is indented too far. | Fix the indentation for 5th level subclause headings throughout the draft. | Yes | E | Done
S6-317 | James Gilb | SiBEAM | Editorial | 24 | 6.2.1.1.11 | 40 | Extra "6." | Delete "6." | Yes | Same as S6-8 | Done
S6-318 | James Gilb | SiBEAM | Editorial | 27 | 6.2.2 | 12 | A number without a unit is spelled out. | Change "1" to "one" here and throughout the document when it is used without a unit. Also look for other occurrences, e.g., "0", "2", and spell them out as well. | Yes | E | Done
S6-319 | James Gilb | SiBEAM | Editorial | 37 | 6.3.4.3 | 9 | This is an example of a number without a unit that should be spelled out. | Change "2" to "two" and "3" to "three" and check the rest of the draft. | Yes | E | Done
S6-320 | James Gilb | SiBEAM | Editorial | 42 | 6.3.7.3 | 1 | The cell borders are not correct (i.e., the cell body borders are two thick for the first two rows.) | Fix the cell borders | Yes | Same as S6-188 | Done
S6-321 | James Gilb | SiBEAM | Editorial | 46 | 6.3.10.2 | 3 | "ith" should be "i^th" with the i italicized (variables are italics). Also, the spacing between the previous items and this paragraph needs to be increased. | Change as indicated. | Yes | E | Done
S6-322 | James Gilb | SiBEAM | Editorial | 47 | 6.3.11.4.2 | 8 | The depth for this heading should probably be 6, but you are not allowed a depth of 6. | Delete the subclause heading or reorganize the subclauses so a dept of 6 is not required. This affects a few subclauses in this area. | Yes | TG discussed and agreed to accept in principle. New text of DCN 0755-00 addresses this comment. | Done
S6-323 | James Gilb | SiBEAM | Editorial | 48 | 6.3.11.5 | 3 | Subclause numbering is wrong "6.3.11.5 (b)" | Delete the "(b)". | Yes | TG discussed and agreed to accept in principle. New text of DCN 0755-00 addresses this comment. | Done
S6-324 | James Gilb | SiBEAM | Editorial | 47 | 6.3.11.4.1 | 1 | "6.3.11.4.1 Command – Coexistence Request", titles are lower case except for the first word, proper nouns and acronyms. | Lower case the title to match the 2009 Style Guide here and throughout the draft. | Yes | Reject. The whole cited term is the name of a frame and has the first letter of every word capitalized. It is a proper noun. | Done
S6-325 | James Gilb | SiBEAM | Technical | 49 | 6.3.11.5.5 | 10 | "The Battery Power Remaining field is set to" doesn't make a requirement. | Change to "The Battery Power Remaining field shall be set to". This applies to all the field descriptions. | Yes | E. | Done
S6-326 | James Gilb | SiBEAM | Editorial | 52 | 6.4.8 | 1 | Extra "[" | Delete "[" | Yes | TG discussed and agreed to accept. New text of DCN 0755-00 addresses this comment. | Done
S6-327 | James Gilb | SiBEAM | Editorial | 53 | 6.4.8.6 | 4 | An IEEE standard cannot make claims of safety. "Life critical Medical" may cross that line. | Refer this name to the IEEE editors for review. They may specify a better name. I understand the idea behind it, but different wording may be required. | Yes | TG discussed and agreed to accept. New text of DCN 0755-00 addresses this comment. | Done
S6-328 | James Gilb | SiBEAM | Editorial | 59 | 6.7.2 | 8 | Don't put the length of this field in the figure. "(= 6N)". The length is defined in another figure. Keeping these numbers up to date as the standard changes will only lead to errors. | Delete "(= 6N)" from the figure and similar lengths from the other IE figures. | Yes | Reject. Current figure is correct as written. | Done
S6-434 | James Gilb | SiBEAM | Technical | 20 | 6.2 | 4 | The ordering of octets and bits has already been defined (nicely) in the opening of this Clause. Repeating the octet and bit ordering in each figure can only lead to mistakes and misunderstanding.s | Delete the bit and octet ordering from Figure 8 going forward. Only include the ordering in the figure if the convention is not being followed. If the convention is not being followed, then you probably want to follow it anyway (CRCs and some security fields are exceptions). | Yes | Rejected. There are figures which show the bit order instead of the octet order. In those figures, keeping the bit order is essential since it shows which bits are used for which fields. | Done
S7-459 | James Gilb | SiBEAM | Editorial | 69 | 7.1 | 2 | It is a mistake to have an introductory paragraph that describes the following clause. It is difficult to keep up to date and makes amendments more difficult. | Delete subclause 7.1, it doesn't add any value. | Yes | Reject. This subclause provides value to the reader of subclause 7. |  | Done
S7-311 | James Gilb | SiBEAM | Editorial | 72 | 7.2.6 | 9 | Delete "Not acknowledged??" | Change as indicated. | Yes | E. |  | Done
S7-312 | James Gilb | SiBEAM | Editorial | 74 | 7.2.7.4 | 2 | "A source—a node or a hub—may" | Change to "A source node or a hub may" | Yes | E. |  | Done
S7-460 | James Gilb | SiBEAM | Technical | 75 | 7.3 | 26 | Clause 5 isn't supposed to define normative requirements. "To provide or support time referenced allocations in its body area network (BAN), a hub shall establish a time base as specified in 5.4" | Move the normative descripton from Clause 5 to Clause 7. | Yes | Accept. E. MAC editor's note (11/29/2010): Clause 5 does not use shalls anymore. |  | Done
S7-313 | James Gilb | SiBEAM | Editorial | 82 | 7.5.2 | 24 | You can't use "as defined below" because there is nothing below that subclause. | Change to "as defined in 7.5.2.1." or delete the sentence or replace with "Slotted aloha access rules are defined in this subclause." | Yes | E. |  | Done
S7-314 | James Gilb | SiBEAM | Editorial | 85 | 7.6.2 | 1 | "Type-I polled allocation (Poll Type = 0)" should not be underlined. In amendments, underlining means added text, so you shouldn't use it here as there may be future MAC amendements. | Delete the underlining. You may want to split the cell to clarify this. The table has too much text. Alternately, you could write this in text instead of a table using the format that was used for the frame formats, e.g., 1) case 1, set to x, 2) case 2, a) set this, b) set that. | Yes | E. |  | Done
S7-315 | James Gilb | SiBEAM | Editorial | 86 | 7.6.2.1.1 | 1 | In Figure 66, the boxes for Future and Immediate overlap, making the figure hard to read. | I would suggest changing this to a standard message sequence format (ask the WG TE for help with this) or fix the figure so the boxes don't overlap | Yes | Accept in principle. Edit text boxes of Figure 66. |  | Done
S7-316 | James Gilb | SiBEAM | Editorial | 94 | 7.8.2.1.1 | 20 | Frame formats belong in Clause 6, not here. | Move this subclause to Clause 6. | Yes | Agree in principle. Wakeup frame will be extracted and new subclause created for Wakeup frame usage in non-beacon non-superframe mode of operation. Subclause 7.8 will be re-written as well. Wakeup frame format will be moved to subclause 6. |  | Done
S7-317 | James Gilb | SiBEAM | Editorial | 96 | 7.8.2.1.3 | 4 | The figure title exceeds the margins. | Correct the figure title, most likely you need to split it into two lines. | Yes | E. |  | Done
S7-318 | James Gilb | SiBEAM | Editorial | 106 | 7.11.1 | 2 | "To hibernate—without receiving or transmitting any traffic—in" The use of dashes doesn't make sense here. | Delete the dashed set offs for hibernate and wakeup. Add instead a short paragraph that defines the two terms. | Yes | E. |  | Done
S7-319 | James Gilb | SiBEAM | Editorial | 107 | 7.11.2 | 7 | Change "Figure 86(a)" to "Figure 86" on line 7 and line 10, change "Figure 86(b)" to "Figure 86" | Change as indicated. | Yes | E. |  | Done
S7-461 | James Gilb | SiBEAM | Technical | 108 | 7.12 | 1 | "10-50 MHz HBC/EFC[a]" is undefined at this time, so you cannot put it in the table. | Delete the column for "10-50 MHz HBC/EFC[a]" | Yes | MAC subteam discussed and agreed to proposed resolution of DCN 0677-00. |  | Done
S7-462 | James Gilb | SiBEAM | Technical | 108 | 7.12 | 1 | "2.36 GHz MBANS Band" is pending, hence it must be deleted. | Delete the column for "2.36 GHz MBANS Band" | Yes | MAC subteam discussed and agreed to proposed resolution of DCN 0677-00. |  | Done
S7-452 | Jaehwan Kim | ETRI | Technical | 92 | 7.8 |  | The source allocation for MICS devices are not clear. There seems to be some sort of resource alloctaion under discovery. Why resource allocation has been put under unconnected/conencted discovery, it is confusing. | Resource allocation and discovery mechanism should be separated. | Yes | Reject. Wakeup mechanisms are presented in this subclause. Polls are the fundmental allocation mechanism. The resource allocations are defined in other subclauses and available to MICS devices via Connection Request/Assignment mechanism. |  | Done
S7-453 | Jaehwan Kim | ETRI | Technical | 92 | 7.8 |  | How resource allocation happens in a network scenraio of one controller device and multiple implant device? Mechanism is missing from the draft. | Add the mechanism. | Yes | Reject. Mechanism is defined and based on connection request and assignment process. |  | Done
S7-507 | Jaehwan Kim | ETRI | Technical | 93 | 7x | 6 | Is the T-Poll transmitted for discovery or for resource allocation? Why discovery mechanism and channel access are combined? These are two different mechanisms. It is creating lot of confusion in the next. | Separate the discovery operation to the channel access operation. | Yes | Reject. Wakeup mechanisms are presented in this subclause. Polls are the fundmental allocation mechanism. The resource allocations are defined in other subclauses and available to MICS devices via Connection Request/Assignment mechanism. |  | Done
S7-508 | Jaehwan Kim | ETRI | Technical | 94 | 7x |  | "As illustrated in Figure 73, prior to more frame exchanges with a connected node, the hub shall transmit a 2 group of up to pMICSPolls Poll frames separated by pMICSPollSeparation, each addressed to the node and 3 providing an immediate polled allocation" The above paragraph describes poll allocation and it does not suit with the title of the section | Rewrite the pargraph. | Yes | Reject. No actionable change proposed by commenter. |  | Done
S7-268 | Jaehwan Kim | ETRI | Technical | 95 | 7.8.2.1.3 |  | Multicast lockup aided discovery. The concept desciribed in the paragraph is not multiple node discovery. It is more like multipler node wakeup mechanism. |  | Yes | Agree in principle. See doc 915-02 for text to replace this subclause |  | Done
S7-269 | Jaehwan Kim | ETRI | Technical | 96 | 7.8.2.1.4 |  | Multicast wakeup mechanism. This section clearly describes the multi-node wakeup mechanism. The section naming is appropriate as well. The Multicast lockup aided discovery section is confusing and not required. | Remove the Multicast lockup aided discovery section. | Yes | Agree in principle. See doc 915-02 for text to replace this subclause |  | Done
S7-506 | Jaehwan Kim | ETRI | Technical | 98 | 7x | 6 | Ambiguity on line 5 and 6. Line 5 and 6 are not well does not fit in the flow of Medical event report section and not well connected to the rest of the section. | Rewrite line 5 and 6 | Yes | Accept in principle. Add sentence "In some cases, when hub is operational, multiple retries of Emergency frame from a node might collide with the frames transmitted from the hub." prior to the sentence of lines 5-6 of subclause 7.8.3. |  | Done
S9-52 | Jaehwan Kim | ETRI | Technical | 143,148, 155, 157 | 9.1.4, 9.3.1.1, 9.5.2, 9.7.1 |  | Channel plan of 902-928MHz frequency bands is not appropriate for the frequency regulation of Korea | It is proposed to alter the current modulation parameters for bands of 902 MHz to 928 MHz into the same parameters of the 863-870 and 950-963 MHz bands and re-designate the channels as folllowing expression. fc=903.20+0.40*n (MHz), where n = 0,...,59. These alterations will increase the utillization of WBAN industry in Korea. Furthermore, adopting the same modulation parameters at the multiple bands would be more advantageous to implement multiple frequency systems. | Accept proposed resolution in doc 15-10-0556-04 slide 18 | Yes: but note we also changed table 14 row 5 in section 6.6.2.3 as per last bullet in slide 17 of 15-10-0556-04, ie we have made a change in the MAC section, which you may need to re-do after you merge documents | 0 | DONE
S10-414 | Jaehwan Kim | ETRI | Technical | 168 | 10.5.4 | 16 | Npad is not always positive number | The floor function should be changed into ceil function | Accept |  | 0 |  | Editorial-Marco | Done
S10-415 | Jaehwan Kim | ETRI | Technical | 168 | 10.5.4 | 19 | Npad is not always positive number | The floor function should be changed into ceil function | Accept |  | 0 |  | Editorial-Marco | Done
S10-417 | Jaehwan Kim | ETRI | Technical | 169 | 10.5.5 |  | The length 64 for bit interleaving is not sufficient to overcome the burst error | Enlarge the length of interleaving | Deferred |  | 1 |  | Marco | Done | TG6_UWB_Comment_S10-417__Proposed_Resolution.ppt & UWB subgroup discussion
S10-416 | Jaehwan Kim | ETRI | Technical | 173 | 10.10 | 11 | The value of PRF for 101 mode(differential coherent) is wrong | The PRF for 101 mode should be changed into 7.8125 | Accept |  | 0 |  | S10-131
S10-418 | Jaehwan Kim | ETRI | Editorial | 178 | 10.11.3 | 4 | The sentence, "This represents the concept of the proposal Group PPM (GPPM)", is declared in draft version 6(15-10-0245-06-0006), but this sentence was eliminated in IEEE802.15.6/D01 for letter ballot. | This sentence should be included in the chapter 10.11.3 and the detail explanation are required to insert in the appendix. | Deferred |  | 1 | added in Appendix | Jaehwan Kim | Done
SG-3 | Jaehwan Kim | ETRI | Technical |  | Global |  | It is not easy to know whcih channel access should be used in what condition. | motivation of each channel access should be described. | Yes | Rejected. Not actionable change
S9-126 | Dino Miniutti | NICTA | Technical | 149 | 9x | 9 | Document does not specify the generator polynomial for FCS generation | Specify a polynomial | Reject comment -- FCS is generated in MAC (see section 6.2.3), not PHY | Yes | 0
S9-127 | Dino Miniutti | NICTA | Technical |  | 9x |  | Figures 105 and 108 have burst mode and scrambler seeds interchanged | Specify a consistent position for these bits | Accept in principle - "Update Figure 105 to follow bit order defined in Figure 108" | Yes | 0
S6-103 | Emmanuel Monnerie | Landis+Gyr | Technical | 52 | 6.4.6.4 | 4-8 | The use of a signal strength to define the link quality is questionable. This field cannot be used in a reliable way in presence of noise or interference | Remove the "Relay Link Quality" field or find another way to measure the link quality. | Yes | See S6-201. | Done
S7-084 | Emmanuel Monnerie | Landis+Gyr | Technical | 94 | 7.8.2.1.1 | 20-22 | This clause is missing some text and need further explanation. | Remove it or add some text. | Yes | Same as S7-58 |  | Done
S10-239 | Emmanuel Monnerie | Landis+Gyr | Technical | 172 | 10.7.1 | 10-13 | The SFD is not defined | Define the SFD structure | Yes | Deferred |  | 1 |  | S10-13
S6-329 | Hartman Van Wyk | Itron Inc | Technical | 52 | 6.4.6.4 | 4-8 | The "received signal strength of signals" does not truly reflect the quality of the link in presence of noise and interference. | Keep history of retries and calculate average packet success rate and use this for quality of link | Yes | See S6-201. | Done
S6-104 | David Olson | Landis+Gyr | Technical | 52 | 6.4.6.4 | 4-8 | The use of a signal strength to define the link quality is questionable. This field cannot be used in a reliable way in presence of noise or interference | Remove the "Relay Link Quality" field or find another way to measure the link quality. | Yes | Same as S6-103 | Done
S7-085 | David Olson | Landis+Gyr | Technical | 94 | 7.8.2.1.1 | 20-22 | This clause is missing some text and need further explanation. | Remove it or add some text. | Yes | Same as S7-58 |  | Done
S10-240 | David Olson | Landis+Gyr | Technical | 172 | 10.7.1 | 10-13 | The SFD is not defined | Define the SFD structure | Yes | Deferred |  | 1 |  | S10-13
178 | TOTAL