## IEEE_Cover
November 2011
IEEE P802.15
Wireless Personal Area Networks
Project | IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Title | 802.15.6 Sponsor Ballot 2 Comments Proposed Resolutions Jin Meng Ho
Date Submitted | 2011-11-03
Source | Clint Chaplin | Voice: +1-408-768-0827
Samsung Electronics
| 3000 Orchard Parkway, San Jose, CA 95134 | E-mail: firstname dot lastname at gmail dot com
Re:
Abstract | 802.15.6 Comments for Sponsor Ballot 2
Purpose
Notice | This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## comments
Comment # | Name | Vote | Affiliation | Category | Page | Subclause | Line | Comment | Must Be Satisfied | Proposed Change | Resolution Status | Resolution Detail | Other1 | Other2 | Other3
r01-34 | Ho, Jin-Meng | Approve | Texas Instruments Incorporated | Technical | 43 | 6.3.6.5.1 | 5 | To ensure that the recipient processes a field referenced in the Connection Change Indicator, the sender needs to set the corresponding Change bit to 1 if that field is newly defined or changed. | No | Throughout 6.3.6.5.1 - 6.3.6.5.7, add "newly provided or" before "changed" (7 instances). Also make the same change in the last paragraph of page 42. | Accepted
r01-38 | Ho, Jin-Meng | Approve | Texas Instruments Incorporated | Editorial | 112 | 7.8.2 | 1 | Typo. | No | Change "(uplink)" polled allocation interval" to "immediate polled allocation interval". | Accepted
r01-55 | Davenport, David | Approve | GE Global Research | Technical | 131 | 7.11.1.2 | 31 | This sentence does not clearly define the conditions under which the node may commence its reception. | No | Delete "up to GTn - Gto earlier or" from this line as this condition is unnecessary and already the default condition defined by the previous sentence with "shall". | Revised | Delete "earlier of". Make similar changes throughout 7.11.1.
r01-56 | Davenport, David | Approve | GE Global Research | Technical | 135 | 7.11.2.2 | 27 | This sentence does not clearly define the conditions under which the node may commence its reception. | No | Delete "up to GTn - Gto earlier or" from this line as this condition is unnecessary and already the default condition defined by the previous sentence with "shall". | Revised | Delete "earlier of". Make similar changes throughout 7.11.2.
r01-59 | Davenport, David | Approve | GE Global Research | Technical | 133 | 7.11.1.4 | 9 | Lines 9 and 12 state that the guard times must be "accounted for" but do not clearly say how such accounting occurs. The text is ambiguous. | No | Change lines 9 and 12 to read "accounted for in the allocation per 7.11.1.3. | Accepted
r01-60 | Davenport, David | Approve | GE Global Research | Technical | 136 | 7.11.2.3 | 5 | Apparent contradiction between this line: "The node and the hub shall not include guard times in the scheduled allocation intervals they request or assign..." and previous page 7.11.2.2 line 27: "The node may commence its reception ...if the request and assignment of the interval accordingly accounted for a relative clok drift up to GTc-GTo." | No | Change this line to "The node may include guard times as part of its request for scheduled allocation intervals. A node requesting centralized guard time allocation shall indicate its PPM number and maximum synchronization interval. A hub shall not add guard time in the scheduled allocation interval assigned to a node." | Revised | Change lines 5-6 to the following: The node and the hub shall not include guard times other than GTc as given in Equation (13) in the scheduled alllocation intervals they request or assign, respectively. Make a similar change to lines 14-15, page 133.
r01-62 | Ida, Ichirou | Approve | FUJITSU | Technical | 135 | 7.11.2.2 | 9 | A node can not consider other nodes but only hub, then the node should only take care of clock drift between itself and the node for reception. Therefore the equation (13) is only valid for node's reception among these three equation. | No | Add following sentense for clarity, "the node shall refer to Equation (13) for GTc calculation for its reception." | Revised | "… as follows (with the node using Equation (13) for GTc in its reception):"