## IEEE_Cover
November 2011
IEEE P802.15
Wireless Personal Area Networks
Project | IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Title | 802.15.6 Sponsor Ballot 2 Comments Proposed Resolutions Jin Meng Ho
Date Submitted | 2011-11-03
Source | Clint Chaplin | Voice: +1-408-768-0827
Samsung Electronics
| 3000 Orchard Parkway, San Jose, CA 95134 | E-mail: firstname dot lastname at gmail dot com
Re:
Abstract | 802.15.6 Comments for Sponsor Ballot 2
Purpose
Notice | This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## comments
Comment # | Name | Vote | Affiliation | Category | Page | Subclause | Line | Comment | Must Be Satisfied | Proposed Change | Resolution Status | Resolution Detail | Other1 | Other2 | Other3
r01-34 | Ho, Jin-Meng | Approve | Texas Instruments Incorporated | Technical | 43 | 6.3.6.5.1 | 5 | To ensure that the recipient processes a field referenced in the Connection Change Indicator, the sender needs to set the corresponding Change bit to 1 if that field is newly defined or changed. | No | Throughout 6.3.6.5.1 - 6.3.6.5.7, add "newly provided or" before "changed" (7 instances). Also make the same change in the last paragraph of page 42. | Accepted
r01-38 | Ho, Jin-Meng | Approve | Texas Instruments Incorporated | Editorial | 112 | 7.8.2 | 1 | Typo. | No | Change "(uplink)" polled allocation interval" to "immediate polled allocation interval". | Accepted
r01-55 | Davenport, David | Approve | GE Global Research | Technical | 131 | 7.11.1.2 | 31 | This sentence does not clearly define the conditions under which the node may commence its reception. | No | Delete "up to GTn - Gto earlier or" from this line as this condition is unnecessary and already the default condition defined by the previous sentence with "shall". | Revised | Delete "earlier or". Make similar changes throughout 7.11.1.
r01-56 | Davenport, David | Approve | GE Global Research | Technical | 135 | 7.11.2.2 | 27 | This sentence does not clearly define the conditions under which the node may commence its reception. | No | Delete "up to GTn - Gto earlier or" from this line as this condition is unnecessary and already the default condition defined by the previous sentence with "shall". | Revised | Delete "earlier or". Make similar changes throughout 7.11.2.
r01-59 | Davenport, David | Approve | GE Global Research | Technical | 133 | 7.11.1.4 | 9 | Lines 9 and 12 state that the guard times must be "accounted for" but do not clearly say how such accounting occurs. The text is ambiguous. | No | Change lines 9 and 12 to read "accounted for in the allocation per 7.11.1.3. | Accepted