## Timeline
DCN: |  | 15-11-0XXX-00-004N
|  |  |  | 2012 |  |  |  | 2013 | [5 empty] | 2014 | [5 empty] | 2015 | [5 empty] | 2016
| # | Task | Comments | May | July | Sept | Nov | Jan | Mar | May | July | Sept | Nov | Jan | Mar | May | July | Sept | Nov | Jan | Mar | May | July | Sept | Nov | Jan | Feb | Mar
| 1 | Draft call for Applications | bar: 2012 May
| 2 | Issue Call for Applications | bar: 2012 May
| 3 | Application Submission Period | bar: 2012 May to 2012 July
| 4 | Draft call for Tech Requirement | bar: 2012 July
| 5 | Issue Call for Tech Requirement | bar: 2012 Sept
| 6 | Tech Requirement Submittion Period | bar: 2012 Sept to 2012 Nov
| 7 | Draft call for Proposals | bar: 2013 Jan
| 8 | Issue Call for Proposals | bar: 2013 Mar
| 9 | Proposals Submission Period | bar: 2013 Mar
| 7 | Evaluate Proposals | bar: 2013 Mar to 2013 May
| 8 | Begin Amendment Editing | bar: 2013 July to 2013 Sept
| 9 | Create First Draft Specification | bar: 2013 Sept
| 10 | Discuss First Draft Specification | Resolve issues and revise | bar: 2013 Nov to 2014 Jan
| 11 | Issue Letter ballot | bar: 2014 Jan to 2014 Mar
| 12 | Letter Ballot Period | bar: 2014 May
| 13 | Comment Resolution | bar: 2014 May to 2014 July
| 14 | Coexistence Document | bar: 2014 July
| 15 | Issue Recirculation Ballot | bar: 2014 Sept to 2014 Nov
| 16 | Recirculation Ballot | bar: 2015 Jan to 2015 Mar
| 17 | Comment Resolution | bar: 2015 Mar
| 18 | Issue Sponsor Ballot | bar: 2015 May
| 19 | Sponsor Ballot | bar: 2015 May
| 20 | Comment Resolution | bar: 2015 July
| 21 | Issue Recirculation Ballot | bar: 2015 July
| 22 | Recirculation Ballot | bar: 2015 Sept
| 23 | Comment Resolution | bar: 2015 Sept
| 24 | Accepted Amendment
Plenary and Interim Meeting Months

## Legend
Plenary and Interim Meeting Months
Completed Tasks
In Progress tasks