## IEEE_Cover
June 2012 |  | P802-15-4k_Comment_Entry_Form.xls
IEEE P802.15
Wireless Personal Area Networks
Project | IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Title | 802.15.4k Review Comment Resolution Database
Date Submitted | 2012-06-20
Source | Pat Kinney | Voice: +1.847.960.3715
Kinney Consulting
| 251 Clair View Ct, Lake Zurich, IL, USA | E-mail: pat.kinney@ieee.org
Re: | 15-12-0089-06 Review
Abstract | 802.15 TG4k Comments
Purpose | [This document is used to submit comments on TG4e draft amendment, Letter Ballot 77.]
Notice | This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Comments
CID | Name | Affiliation | Sub-clause | Page | Line # | Comment | Proposed Change | Grp | A AiP R OoS W | Resolution
248 | Yang Yang | WSNIRI | 3.1 | 3 | 8 | the coordinator in a star network will not be a repeater. | change the definition of reperter to "A coordinator in a relayed slot-link network…" |  | A
141 | Monique Brown | On Ramp Wireless | 4.2 | 5 | 9 | There is redundancy between 4.2 and 4.3.1. | Consider combining the text from both places and putting only in 4.3.1. Consider as the first paragraph in 4.3.1: "Low energy critical infrastructure monitoring (LECIM) networks primarily operate in a star topology. LECIM networks are typically asymmetric in energy consumption and capability, having a coordinator that is mains powered (or otherwise provided a substantial power source) and energy constrained endpoints. This asymmetry is a characteristic feature of the LECIM network." |  | A
78 | Schwoerer | France Telecom | 4.2 | 5 | 21-24 | In addition to energy, cost is or may also be a key differentiator between endpoint and concentrator | Add "cost" as a possible limitation |  | A | change to "energy or cost constrained endpoints
79 | Schwoerer | France Telecom | 4.3 | 5 | 27-29 | It seems there is no limit to the number of "relay" that can be used. | Add a limit of a reasonnable number of hop (2 ?) |  | R | the limit is not appropriate to the general overview of clause 4
1 | Pat Kinney | Kinney Consulting | 4.3.1 | 5 | 23 | "endpoints" should be singular | change to "endpoint" |  | A
249 | Yang Yang | WSNIRI | 4.3.1 | 5 | 28 | what is the definition of "virtual star network"? | please give more clear definition. |  | AiP | change to "operating as a virtual in a star network topology
142 | Monique Brown | On Ramp Wireless | 4.5.1.1 | 5 | 42 | Review cross-references in the two bulleted items. | Consider changing all cross-references to Clause 5 references where the bulk of the information is contained (remove references to Clause 4). |  | A
2 | Pat Kinney | Kinney Consulting | 4.5.1.1 | 5 | 45 | RSLN appears as an acronym w/o being spelled out | spell out first time it is used |  | A
209 | Monique Brown | On Ramp Wireless | 4.5.1.1 | 5 | 46 | Define RSLN the first time it is used. | Note that it is defined twice in Clause 5. I think it may be OK to define it again later in the main section in which it is used. Check on this. |  | A
143 | Monique Brown | On Ramp Wireless | 4.5.1.5 | 5 | 53 | Don't reference any of the PIB attributes in Clause 4. The idea of a PIB attribute hasn't even been introduced. | Remove "(i.e., macRSLNenabled is TRUE)" from the sentence. |  | A
3 | Pat Kinney | Kinney Consulting | 4.5.1.5 | 6 | 10 | color in Figure 4ba is not necessary | change to gray scale drawing |  | A
157 | Monique Brown | On Ramp Wireless | 4.5.1.5 | 6 | 13 | Is Figure 4ba just an example of a cyclic-superframe? Or does every cyclic-superframe look exactly like the figure? | Change the figure title to "Example RSLN cyclic-superframe structure" if appropriate. |  | R | delete Figure 4ba inaccordance with CID 158
158 | Monique Brown | On Ramp Wireless | 4.5.1.5 | 6 | 13 | Figure 4ba has a lot of overlap with Figure 11i. | In Figure 4ba, remove the prioritized slot, coordinator slot, etc. Save those details for Clause 5. |  | AiP | change to "as shown in Figure 4ba 11i"
219 | Monique Brown | On Ramp Wireless | 4.5.2.1 | 6 | 35 | Reword from "relayed inward for transferring data" to "relayed inward as a means of transferring data." Make same change to 4.5.2.2. | See comment. |  | A
250 | Yang Yang | WSNIRI | 4.5.2.1 | 6 | 35, 43 | "In an RSLN repeater" | change to "For an RSLN repeater" |  | A
220 | Monique Brown | On Ramp Wireless | 4.5.4.1a | 6 | 53 | Change to "mechanism described in 5.1.1.4.5." | See comment. |  | A
144 | Monique Brown | On Ramp Wireless | 4.5.4.1a | 7 | 1 | Don't reference any of the constants in Clause 4. Constants have not been introduced yet. | Remove reference to aBackoffSlotBoundary. This is too much detail for Clause 4 anyway. |  | A | change to "every aBackoffSlot boundary at regular intervals, even if the channel is assessed..."
251 | Yang Yang | WSNIRI | 4.5.4.1a | 7 | 1 | "… every aBackoffSlot boundary", can't find any definition about aBackoffSlot in this draft or 15.4-2006, or 15.4-2011. | is the "aBaxkoffSlot" here is "aUnitBackoffPeriod" defined in 15.4? |  | AiP | constant was deleted as per CID 144
262 | Jie Shen | WSNIRI | 4.5.4.1a | 7 | 1 | "… conducts a CCA every aBackoffSlot boundary", if the interval of CCA operations is too small? As the aUnitBackoffPeriod defined in 15.4 is just 20 symbols. | and this description is not the same with 5.1.1.4.5, please give clear definition here. |  | AiP | constant was deleted as per CID 145
221 | Monique Brown | On Ramp Wireless | 4.5.4.2 | 7 | 8 | Add cross-reference to 5.1.1.4.6. | See comment. |  | R | not necessary
252 | Yang Yang | WSNIRI | 4.5.4.2a | 7 | 30~31 | definitions of "fragment", "fragmentation sequence"….can be listed in 3.1. | move the part of definitions about fragmentation. |  | A | move the following to defintions: In this standard, the term “fragment” refers to an individual MPDU fragment, the term “fragment sequence”refers to the collection of fragments transmitted that together comprise the original MPDU, “fragment "number” is the position in the sequence of an individual fragment, and the “fragment sequence ID” identifies the fragment sequence.
145 | Monique Brown | On Ramp Wireless | 4.5.4.2a | 8 | 1 | The term "fragment sequence ID" does not occur anywhere else in the document. | Replace with a more appropriate term. |  | AiP | replace fragment sequence ID with transaction ID
4 | Pat Kinney | Kinney Consulting | 4.5.4.2a | 8 | 8 | color in Figure 6a is not necessary | change to gray scale drawing |  | A
205 | Monique Brown | On Ramp Wireless | 4.5.4.3 | 8 | 38 | The acronym I-ACK is already spelled out in the title. Don't spell it out again in line 38. | See comment. |  | A
5 | Pat Kinney | Kinney Consulting | 4.5.4.3.2 | 8 | 52 | missing xref | replace editor note with xref to IE definiton |  | AiP | delete editor note and hence xref
126 | Monique Brown | On Ramp Wireless | 4.5.4.3.2 | 8 | 52 | Either remove red text or replace it with a useful cross-reference. | See comment. |  | A | see CID 5
222 | Monique Brown | On Ramp Wireless | 4.5.4.4 | 9 | 5 | Make "acknowledgment" plural. | See comment. |  | A
253 | Yang Yang | WSNIRI | 4.5.4.69 | 9 | 17~19 | "grade 0 for transmitting delay sensitive data, grade 1 for the reliable transmission of data, and grade 2 for the best effort data transmission" use the same style may be better | change to "grade 0 for transmission of delay sensitive data, grade 1 for reliable transmission of data, and grade 2 for the best effort transmission of data" |  | A
146 | Monique Brown | On Ramp Wireless | 4.5.5.3 | 9 | 27 | Change from "will be limited" to "is limited." | See comment. |  | A
6 | Pat Kinney | Kinney Consulting | 4.5.5.3 | 9 | 28 | the following sentence is grammatically incorrect "For low powered devices, transmission power may be limited to increasing the life span of the device within the network." | change to "To increase the device's battery life, the transmit power of low energy devices may be limited to a reduced value." |  | AiP | change to "To increase the device's battery life, low energy devices may use low transmit power."
147 | Monique Brown | On Ramp Wireless | 4.5.5.3 | 9 | 29 | Change from "coordinator can have" to "coordinator may have." | See comment. |  | A
254 | Yang Yang | WSNIRI | 4.5.5.3 | 9 | 30~31 | "extend the coverage of the star network with no burden to a device while preserving the topology", if the coordinator acts as a repeater, the whole topology of network is a tree, maybe we can't say "preserving the topology" | please give clear definition of RSLN topology. |  | AiP | Change to "...to extend the coverage of the star network with no burden to a device while preserving the star topology with no burden to the end device"
390 | James Gilb | Tensorcom | 5.1 | 11 | 7 | Don't need to add this to the list in 5.1. | Delete insertion. |  | A
7 | Pat Kinney | Kinney Consulting | 5.1.1.1 | 11 | 15 | spelling out RSLN is not necessary after the first use | delete spelling out |  | A
53 | Pat Kinney | Kinney Consulting | 5.1.1.4.5 | 11 | 22 | PCA has already been spelled out | just use PCA |  | A
223 | Monique Brown | On Ramp Wireless | 5.1.1.4.5 | 11 | 22 | Edit title from "CSMA" to "CSMA-CA." | See comment. |  | A
148 | Monique Brown | On Ramp Wireless | 5.1.1.4.5 | 11 | 23 | This new algorithm would be easier to follow with the aid of a flow chart. | Include a flow chart for this new algorithm similar to Figure 11 in 15.4-2011. |  | R | a flow chart is not necessary
54 | Pat Kinney | Kinney Consulting | 5.1.1.4.5 | 11 | 24 | PCA has already been spelled out | just use PCA |  | A
150 | Monique Brown | On Ramp Wireless | 5.1.1.4.5 | 11 | 24 | Make an opening statement saying that the CSMA algorithm is the same as in 5.1.1.4 with the exception of the backoff mechanism. | How about something like the following: "When implementing PCA, the CSMA-CA algorithm described in 5.1.1.4 shall be used with a modified backoff mechanism. This alternate backoff mechanism shall be used when the CCA indicates a busy channel and macPriorityChannelAccess is TRUE." |  | R | the proposed text is not correct
336 | B. Rolfe | BCA | 5.1.1.4.5 | 11 | 24 | Make it clear that the rest of the subclause only applies when macPriorityChannelAccess is true in a device tha supports PCA. | Change to "This subclause describes the alternate backoff procedure used to for the transmission of a critical event priority message when macPriorityChannelAccess is TRUE in a device that supports PCA. " |  | AiP | Change to "This subclause describes the alternate backoff mechanism procedure used to for the transmission of a critical event priority message when macPriorityChannelAccess is TRUE in a device that supports PCA. "
151 | Monique Brown | On Ramp Wireless | 5.1.1.4.5 | 11 | 25 | Sometimes called "alternate backoff procedure" but usually called "alternate backoff mechanism." Stick to one name. | Always call it "alternate backoff mechanism." |  | A | see CID 336
208 | Monique Brown | On Ramp Wireless | 5.1.1.4.5 | 11 | 25 | The acronym PCA is spelled out in many places. There are other places where the acronym should be used but is not (priority channel access is used in place of PCA). | Spell the acronym out once and make sure that it is used where appropriate. |  | A
337 | B. Rolfe | BCA | 5.1.1.4.5 | 11 | 31 | "the first transmission" should this actually be "prior to the first retransmission attempt"? i.e. only after initial tranmission failes to we ever do a backoff. | see comment |  | AiP | change from " the first transmission" to "prior to the first transmission"
338 | B. Rolfe | BCA | 5.1.1.4.5 | 11 | 33 | Don't need "in addition". | remove |  | A
256 | Yang Yang | WSNIRI | 5.1.1.4.5 | 11 | 34 | "idle for a duration of a backoff slot", the duration here is aUnitBackoffPerod, or just the duration of the last backoff? | please give clear definition. |  | AiP | where a device continues to Change to "monitor the channel and decrements the contention window value of unit backoff periods any time the channel is sensed idle for a duration of a backoff slot aUnitBackoffPerod, in order to gain access to the channel as soon as possible.
339 | B. Rolfe | BCA | 5.1.1.4.5 | 11 | 34 | "decrements the value of unit backoff periods" ?? | decrements the backoff counter by…??? |  | AiP | see CID 256
340 | B. Rolfe | BCA | 5.1.1.4.5 | 11 | 41 | "macPCAAllocationSuperRate shall be FALSE" sounds like prescribing requirements on the higher layer as this is a RW attribute as descibed in table 52. | clarify
8 | Pat Kinney | Kinney Consulting | 5.1.1.4.5 | 11 | 45 | equation 1 is not where the index is, rather it is on the following page | move equation to the index
149 | Monique Brown | On Ramp Wireless | 5.1.1.4.5 | 11 | 46 | Equation 1 is in the wrong place. | Fix it.
224 | Monique Brown | On Ramp Wireless | 5.1.1.4.5 | 11 | 53 | PIB attributes in this paragraph are not entirely in italics. | Fix it.
391 | James Gilb | Tensorcom | 5.1.1.4.5 | 11 | 53 | "macPCAAllocationRate shall have the value of the function." - what function? | Clarify
255 | Yang Yang | WSNIRI | 5.1.1.4.5 | 11 | 25~26 | "This backoff procedure shall be used when the CCA indicates a busy channel and macPriorityChannelAccess is TRUE" maybe is not very suitable, as macPriorityChannelAccess can't indicate there is a delay sensitive frame waiting to be transmitted. | change to "This backoff procedure shall be used when there is a delay sensitive data waiting for transmission, and the CCA indicates a busy channel.“
263 | Jie Shen | WSNIRI | 5.1.1.4.5 | 11 | 25~26 | the usage of backoff procedure definited here "This backoff procedure shall be used when the CCA indicates a busy channel and macPriorityChannelAccess is TRUE" maybe is not very suitable, as the result of CCA is variable always, MAC can't make the decision of whether backoff all the time. | change to "When macPriorityChannelAccess is TRUE, this backoff procedure shall be used in nonbeacon-enabled network or CAP of beacon-enabled network.“
257 | Yang Yang | WSNIRI | 5.1.1.4.5 | 11 | 33~34 | "decrements the value of unit backoff periods...", description about the decrement is not very clear. | please give clear definition about the value of decrement
57 | Pat Kinney | Kinney Consulting | 5.1.1.4.5 | 12 | 18 | Sentence: "The remaining priority channel allocations shall be evenly distributed throughout the superframe. If such an allocation should occur outside the CAP, the allocation shall be omitted" is inappropriately restrictive. | Change to: " The remaining PCAs should be distributed throughout the superframe, however no PCA shall occur outside a CAP"
264 | Jie Shen | WSNIRI | 5.1.1.4.5 | 12 | 27 | "…the multi-superframe duration is greater than …" | change to "…the multi-superframe duration is longer than …"
392 | James Gilb | Tensorcom | 5.1.1.4.5 | 12 | 30 | In the last sentence is prescribing requirements on the higher layer, which determines the CAP length by specifying the size of the CFP. | "If macPriorityChannelAccess is set to TRUE when the CAP duration is less than aMinCAPLength plus the time required for a single priority channel allocation, PCA shall not be enabled"
258 | Yang Yang | WSNIRI | 5.1.1.4.5 | 12 | 18~19 | "The remaining priority channel allocations shall be evenly distributed throughout the superframe", what is the period between the evenly distribution? | please give more description about the evenly PCA distribution mechanism.
154 | Monique Brown | On Ramp Wireless | 5.1.1.4.6 | 12 | 33 | The heading 5.1.1.4.6 is called "CSMA-CA algorithm." I don't think "LECIM ALOHA PCA" belongs beneath this heading. I know that 5.1.1.4.5 is part of PCA, but it is also part of CSMA. | Maybe elevate it one heading level making it 5.1.1.x - occurring somewhere after 5.1.1.4. Then it will be beneath 5.1.1 Channel access.
341 | B. Rolfe | BCA | 5.1.1.4.6 | 12 | 37 | "...duration is a both a PHY and implementation-dependent parameter" has an extra "a" | "...duration is implementation-dependent and depends on the PHY in use." does it?
9 | Pat Kinney | Kinney Consulting | 5.1.1.4.6 | 12 | 38 | The following does not make sense: "A macLECIMAlohaBackoffSlot duration is a both a PHY and implementation-dependent parameter. It shall be sufficiently long, in order to accommodate the transmission of a single MPDU fragment with associated interframe spacing (IFS) periods and any ACK frames." | Change to "A macLECIMAlohaBackoffSlot duration, dependent upon the PHY and implementation, needs to be be sufficiently long to accommodate the transmission of a single MPDU fragment with associated interframe spacing (IFS) periods and any ACK frames."
343 | B. Rolfe | BCA | 5.1.1.4.6 | 12 | 43 | "priority channel allocation shall be at least four" implies a requirement on the higher layer if the number of slots is assigned by th higher layer. | "should" and/or reword?
225 | Monique Brown | On Ramp Wireless | 5.1.1.4.6 | 12 | 46 | Make "allocation" plural. | See comment.
344 | B. Rolfe | BCA | 5.1.1.4.6 | 12 | 46 | "Priority frames may be transmitted in the entire CAP portion of the superframe." do we mean in ANY part of the CAP? | clarify
345 | B. Rolfe | BCA | 5.1.1.4.6 | 12 | 49 | Antoher "shall" on the higher layer? | review
259 | Yang Yang | WSNIRI | 5.1.4.5 | 12 | 5 | in Alloc(1), there shall be no "1". | Alloc(1) = once every… "1," before "every" shall be delete.
265 | Jie Shen | WSNIRI | 5.1.4.5 | 12 | 1~10 | according to the definition of macPCAAllocationRate and macCritMsgDelayTol, can't understand why the difference of value of macPACAllocationRate is decided by "macCritMsgDelayTol / 3". | I supposed the interval shall be "SD < macCritMsgDelayTol", "SD = macCritMsgDelayTol" and "SD > macCritMsgDelayTol", maybe I'm wrong, but please give more decription or explaination.
204 | Monique Brown | On Ramp Wireless | 5.1.1.7.1 | 13 | 16 | Spell out the acronym HWSL the first time it is used. It is already spelled out in 5.1.11.3.3. | Spell out for first use. I think it may be OK to spell it out again in the main section in which it is described, but I'm not sure (this is 5.1.11.3.3). Check this. In any case, it should not be spelled out again on p. 25, line 17.
346 | B. Rolfe | BCA | 5.1.1.7.1 | 13 | 16 | whre we add ", and" it would read better to make it two sentences instead. | see comment
393 | James Gilb | Tensorcom | 5.1.1.8 | 13 | 33 | Throughout this section the terms "slot-link", "time slot", "slot", "device slot" and "link" are used to mean the same thing (so it appears). | Pick a term and use it consistently. I rather like "time slot" as it is defined already in the standard.
156 | Monique Brown | On Ramp Wireless | 5.1.1.8 | 13 | 41 | What is the difference between a multi-superframe and a cyclic-superframe? Also slotted-superframe appears to be new. | Start out the paragraph by defining a slotted superframe and a cyclic-superframe. Explain how the definition of multi-superframe fits into all this. Then explain what the term slot-link means. Or maybe it would be more helpful to the reader to include the definitions in Clause 4 when it is first discussed.
394 | James Gilb | Tensorcom | 5.1.1.8.1 | 13 | 37 | "Time slots in a slotted superframe may be a 1-to-1 link (i.e., a link between the PAN coordinator and a single device)" can a slot-link be assigned and/or used for communication directly between two devices that are not the PAN coordinator? If not why not? | Not sure.
395 | James Gilb | Tensorcom | 5.1.1.8.1 | 13 | 39 | Is the multi-superframe described here the same as the multi-superframe defined in 802.15.4e? It appears very similar but not sure it is identical. | Clarify.
396 | James Gilb | Tensorcom | 5.1.1.8.1 | 13 | 39 | IT seems like the main difference between an RSLN superframe and the base superframe is that all slots can be allocated to the CFP. Multi-superframes extend the number of slots available. What does the cyclic superframe offer beyond that? Could the existing mult-superframe be used with the added 'relay' function instead? | Clarify
397 | James Gilb | Tensorcom | 5.1.1.8.1 | 14 | 1 | "specified by the owner of the slot" says the owner of the slot specifies the characteristics of the slot link which I don't think is what you really mean. | "The slot link specification includes the owner of the slot, …."
10 | Pat Kinney | Kinney Consulting | 5.1.1.8.1 | 14 | 11 | color in Figure 11ia is not necessary | change to gray scale drawing
398 | James Gilb | Tensorcom | 5.1.1.8.2 | 14 | 23 | Title should be "Beacon slots" since several kinds of beacon slots are defined. | Change title
399 | James Gilb | Tensorcom | 5.1.1.8.2 | 14 | 25 | "a link for transmitting" is wrong. The beacon slot is the slot where the beacon is transmitted. That's why you called it the "Beacon slot" presumably. | "The PAN coordinator transmits a beacon frame in the beacon slot."
400 | James Gilb | Tensorcom | 5.1.1.8.2 | 14 | 27 | Specifies that the beacon generated by the PAN coordinator is relayed by the repeater, apparently in two different slots, the cyclic-superframe slot and the multi-superframe slot. The first conflicts with the prior sentence which says the PAN coordinator transmits a beacon in the cyclic-superframe slot. | Clarify what beacons to in which slots and reconcile with the Figure.
160 | Monique Brown | On Ramp Wireless | 5.1.1.8.3 | 14 | 37 | "for transmitting delay sensitive data or command frames" Make it clear that the term "delay sensitive" also applies to the command frames. | Change to "for transmitting delay sensitive data or delay sensitive command frames."
162 | Monique Brown | On Ramp Wireless | 5.1.1.8.3 | 14 | 37 | The flow of information might be easier to understand if some kind of diagram is included. I have the same comment for the other types of slots in a cyclic-superframe. | Add diagrams for clarity.
226 | Monique Brown | On Ramp Wireless | 5.1.1.8.3 | 14 | 40 | Change to "slotted-superframe within a cyclic-superframe." Similar changes also needed elsewhere. | See comment.
401 | James Gilb | Tensorcom | 5.1.1.8.3 | 14 | 42 | If a frame received by a repeater is repeated in the next priority slot, this seems likely to produce a collision, since the device that sent that frame to the repeater is likely in the SoI of the repeater, and likely to transmit in the next priority slot too. Without ALOHA, and the synchronized timing achieved by time-slotting.... | Not sure, it seems really broken.
229 | Monique Brown | On Ramp Wireless | 5.1.1.8.3 | 14 | 44 | Add a reference to where the grades are explained. | Add a reference to 5.1.6.7.
402 | James Gilb | Tensorcom | 5.1.1.8.4 | 14 | 51 | Is "coordinator slot" the same as "coordinator down-link slot" in figure 11i? The figure doesn't show coordinator slots in each multi-superframe. | Correct figure, text, or both.
403 | James Gilb | Tensorcom | 5.1.1.8.4 | 14 | 52 | What is the "inner coordinator" and "inner coordinator slot-link" ? The term "inner coordinator"is also used in 5.1.6.7.2 but not defined first. | Clarify
161 | Monique Brown | On Ramp Wireless | 5.1.1.8.4 | 14 | 53 | New terms need to be defined. | Define "inner coordinator" or think of another way to say what you mean.
11 | Pat Kinney | Kinney Consulting | 5.1.1.8.5 | 15 | 8 | The slots aren't allocated as stated in the following "One primary bidirectional device slot and multiple supplementary bidirectional device slots are allocated to each device in an RSLN-enabled PAN. | Change to "One primary bidirectional device slot and multiple supplementary bidirectional device slots may be allocated to each device in an RSLN-enabled PAN.
404 | James Gilb | Tensorcom | 5.1.1.8.5 | 15 | 8 | What does "multiple" mean here? Would help if macNumBidirDeviceSlot were referenced here, the definition of which suggests there can be zero to 6 suplimenta slots. This raises another question - who assigns these slots? How does one device know what value the macNumBidirDeviceSlot attribute of another device is set to? | "One primary bidirectional device slot and zero or more supplementary bidirectional device slots are allocated to each device in an RSLN-enabled PAN" or "One primary bidirectional device slot and (macNumBidirDeviceSlot - 1) supplementary bidirectional device slots are allocated to each device in an RSLN-enabled PAN" and specify who assigns what and how.
405 | James Gilb | Tensorcom | 5.1.1.8.5 | 15 | 9 | First part of the sentence seems to restate the obvious (more slots is more slots); Then we talk about retransmissions - is it meant that retransmissions only occur in these slots, or that theses slots are only for retransmission, or what? | Clarify
406 | James Gilb | Tensorcom | 5.1.1.8.5 | 15 | 9 | "If the number o fbidirectional device slots in a cyclic-superframe is larger than the number of devices in the RSLN-enabled PAN, each device has a preemptive, primary bidirectional device slot-link." Not really sure what this means. | Clarify
407 | James Gilb | Tensorcom | 5.1.1.8.5 | 15 | 15 | is "the bidirectional slot" mean any bidirectional slot? | see comment
351 | B. Rolfe | BCA | 5.1.2.7.1 | 15 | 35 | "an FFD" is redundant as only an FFD can act as a PAN coordinator. | "A device"
352 | B. Rolfe | BCA | 5.1.2.7.1 | 15 | 37 | I think we're missing something. Need to say how MLME-START for a RSLN is different from starting a non-RSLN PAN. | Need to add more to MLME-START and add something about having a RLSNSpecification parameter in the START and what we do with it.
408 | James Gilb | Tensorcom | 5.1.2.7.2 | 15 | 52 | Awkward first sentence; The MAC does a scan when an MLME-SCAN.request is issued by the higher layer; "wishes" exist above the MAC, the MAC only responds to specific stimuli. | The higher layer initiates joining an RLSN PAN by issuing an MLME-SCAN.request to initiate an active or passive scan, and selects a RLSN PAN coordinator or a repeater from the information contained in the received beacons.". Similarly fix the language for association, etc.
12 | Pat Kinney | Kinney Consulting | 5.1.2.7.2 | 15 | 54 | incorrect use of i.e., rather e.g is appropriate | replace i.e. with e.g.
349 | B. Rolfe | BCA | 5.1.6.7.2 | 15 | 19 | What does "The command frame to a certain device" - does this mean any directed frame or only those addressed to a specific device (and if so how is that determined?). | clarify
350 | B. Rolfe | BCA | 5.1.6.7.2 | 15 | 21 | "The link access mechanism of a bidirectional slot-link depends upon the direction of transmission and the bidirectional device slot type." But then we say ALOHA is used in the primary slot and CSMA is used in suplimentary slots? | clarify
353 | B. Rolfe | BCA | 5.1.2.7.1 | 16 | 29 | The "The Beacon Bitmap field of the enhanced beacon" I think means the Beacon Bitmap Field of the Extended DSME PAN Descriptor IE (figue 48ab). | Clarify
409 | James Gilb | Tensorcom | 5.1.2.7.2 | 16 | 2 | The next higher layer would use MLME-SET.request to set PIB attribute values. | refer to primitive MLME-SET to set attribute values.
410 | James Gilb | Tensorcom | 5.1.2.7.2 | 16 | 32 | At the start of this clause it says "The device selects the PAN coordinator or a suitable inward repeater" but then only discusses association with an inward repeater. | Something is missing.
269 | Matt Johnson | Independent | 5.1.2.7.1 | 17 |  | While figure 16b is clear in color, it is very difficult to distinguish between devices when the draft is printed in grey-scale. | Modify color keying to include a better differentiation between devices, such as including some texture or cross hatchingalong with the colors.
13 | Pat Kinney | Kinney Consulting | 5.1.2.7.2 | 17 | 20 | color in Figure 16b is not necessary | change to gray scale drawing
163 | Monique Brown | On Ramp Wireless | 5.1.2.7.2 | 17 | 31 | Using color to convey information in figures is not allowed. | Remove the color from Figure 16b, 29a and 29b.
411 | James Gilb | Tensorcom | 5.1.2.7.3 | 17 | 36 | Missing a lot of information. What does "suitable" mean and how is it determined? What in the scan results identifies the network as RSLN capable (specific fields). What part of this is done by the MAC? How are slots assigned to the device - is there an association request, a request/grant step, etc? | Complete specification
412 | James Gilb | Tensorcom | 5.1.2.7.4 | 17 | 52 | This clause describes some methods that may be used to collect various infomration but does not indicate when this is initiated and how. | Complete specification
164 | Monique Brown | On Ramp Wireless | 5.1.2.7.4 | 18 | 19 | Modify text for clarity. | Change from "the PAN coordinator uses the HELLO type of MLME-RSLN- MANAGEMENT primitives" to "the PAN coordinator issues the MLME-RSLN-MANAGEMENT primitives with the ManagementType attribute set to HELLO."
165 | Monique Brown | On Ramp Wireless | 5.1.2.7.4 | 18 | 20 | Modify text for clarity. | Change from "The HELLO type of RSLN management command is relayed to the destination device" to "The RSLN management request command with the Management Type field set to indicate Hello is relayed to the destination device." Then the device sends the RSLN management response command in reply. Make similar changes to the remaining paragraphs in this subclause.
227 | Monique Brown | On Ramp Wireless | 5.1.6 | 18 | 43 | Change from "the MPDU fragmentation" to "MPDU fragmentation." | See comment.
413 | James Gilb | Tensorcom | 5.1.6.7.1 | 18 | 54 | Receipt of the MCPS-DATA.request primitive INITIATES transmission of a data frame, not "data frames." | change "frames" to "frame".
354 | B. Rolfe | BCA | 5.1.6.7.1 | 19 | 1 | "searches the earliest" should be "searches for the earliest" ? Similar chagne on line 5. | see comment
355 | B. Rolfe | BCA | 5.1.6.7.1 | 19 | 7 | device using grade 2 link …and transmits the data without requiring an acknowledgement". Does this mean that for Grade 0 and 1 an acknowledgement is always expected? | Add that Grade 0 and 1 are acknowledged as descibed in 5.1.6.7.3
348 | B. Rolfe | BCA | 5.1.6.7.2 | 19 | 17 | This is awkward. What we really need to do is amend 5.1.6.2 to describe receive filtering done when relaying. | See comment
414 | James Gilb | Tensorcom | 5.1.6.7.2 | 19 | 17 | This clause implies that a relaying device is never the destination of a frame, and always retransmits anything that it receives, without address filtering. How do we know the intended destination of the frame didn't hear it the first time? Seems like a good way to cause congestion. | Not sure, it seems really broken.
347 | B. Rolfe | BCA | 5.1.6.7.2 | 19 | 23 | Title and first paragraph suggest this is describing the relaying slot link, | Move to appropriate subclasue.
166 | Monique Brown | On Ramp Wireless |  | 19 | 36 | New terms need to be defined. | Define "outer coordinator" or think of another way to say what you mean.
14 | Pat Kinney | Kinney Consulting | 5.1.6.7.2 | 20 |  | color in Figure 29a and 29b is not necessary | change to gray scale drawing
270 | Matt Johnson | Independent | 5.1.6.7.2 | 20 |  | While figure 29b is clear in color, it is very difficult to distinguish between devices when the draft is printed in grey-scale. | Modify color keying to include a better differentiation between devices, such as including some texture or cross hatchingalong with the colors.
382 | Seong-Soon Joo | ETRI | 5.1.6.7.2 | 20 |  | "layer" used in figure 29a & 29b is not defined in the draft. | Change "layer" to "tier" in figure 29a & 29b.
228 | Monique Brown | On Ramp Wireless | 5.1.6.7.3 | 21 | 6 | Revise text for clarity. | Change from "relayed by the repeaters on the RSLN path along to the end device or vice versa" to "relayed by the repeaters along the RSLN path to the end device or vice versa"
356 | B. Rolfe | BCA | 5.1.6.7.3 | 21 | 31 | The slot-link ACK and Acknowledge from the final destination seem redundant, as either indicates it received the message. Also for the grade 0 case, what is the timeout for the originating device to wait for the Acknowledgement? It seems like it must depend on the number of relays, number of relay retransmissions, and other things. | Not sure.
357 | B. Rolfe | BCA | 5.1.6.7.3 | 21 | 47 | I may be confused but it seems like the timeout should depend not on where in the "tier" the source device is located, but how many tiers (hops) are between the source and final destination. I may not understand what a "tier" is of course. | Need to clarify.
358 | B. Rolfe | BCA | 5.1.10.1 | 23 | 32 | We probably need to also add some text at the start of the subclause that qualifies the existing text based on macExtendedDSMEenabled set to FALSE. | see comment
167 | Monique Brown | On Ramp Wireless | 5.1.10.1 | 23 | 36 | Define a term when used for the first time in the document. | Define MD as multi-superframe duration.
415 | James Gilb | Tensorcom | 5.1.10.5.3 | 24 | 13 | "AO" should be "macAllocationOrder" (AO hasn't been introduced yet) | Change "AO" to "macAllocationOrder".
168 | Monique Brown | On Ramp Wireless | 5.1.11.3.1 | 24 | 25 | Start off by defining this new mode. Then say how to activate it. | See comment.
15 | Pat Kinney | Kinney Consulting | 5.1.11.3.1 | 24 | 40 | Figure 34sa should be shown as a MSC format | Change to a MSC format
359 | B. Rolfe | BCA | 5.1.11.3.2 | 24 | 52 | This probably belongs in the "General" clause above or perhaps in clause 4. | relocate
416 | James Gilb | Tensorcom | 5.1.11.3.2 | 24 | 52 | The first paragraph belongs in clause 4. The first sentence is probably true true for some LECIM networks but not necessarily true for all LECIM networks such as a monitoring device that reports to the concentrator.
169 | Monique Brown | On Ramp Wireless | 5.1.11.3.2 | 25 | 1 | What is the definition of "normal time?" | Rewrite text to avoid introducing a new term.
360 | B. Rolfe | BCA | 5.1.11.3.2 | 25 | 4 | Is macLowEnergySuperframeSupported set in the PAN coordinator or the endpoint? It seems from the description it controls behaivor of the PAN coordinator but I may be confused. | clarify
361 | B. Rolfe | BCA | 5.1.11.3.2 | 25 | 10 | "The Frame Pending field of the Frame Control field in the received data frame shall determine whether the receiver is to be kept on or turned off following the reception of the data frame." doesn't need to be said since this is the already defined meaning of frame pending in a recieved data frame (5.2.1.1.3). | delete sentence.
16 | Pat Kinney | Kinney Consulting | 5.1.11.3.3 | 25 | 30 | Figure 34sb should be shown as a MSC format | Change to a MSC format
159 | Monique Brown | On Ramp Wireless | 5.1.1.8.2 | 26 | 14 | This text is confusing. "The cyclic-superframe beacon slot is reserved for the RSLN-enabled PAN coordinator. The beacon from the PAN coordinator is relayed by the repeater in its cyclic-superframe beacon slot." The first sentence says only the RSLN PAN Coord can use the slot, but the second sentence says the repeater can use it, too. | Please clarify.
17 | Pat Kinney | Kinney Consulting | 5.1.11.3.3 | 27 | 10 | Figure 34sc should be shown as a MSC format | Change to a MSC format
213 | Monique Brown | On Ramp Wireless | 5.1.11.4 | 27 | 39 | Add I-RIT to Clause 3. Don't define twice - remove from line 44. | See comment.
170 | Monique Brown | On Ramp Wireless | 5.1.11.4.1 | 27 | 44 | Change "alternative low energy MAC" to "alternative low energy mode." | See comment.
171 | Monique Brown | On Ramp Wireless | 5.1.11.4.1 | 27 | 47 | Add reference to where definition of "conventional RIT" occurs. | See comment.
172 | Monique Brown | On Ramp Wireless | 5.1.11.4.1 | 28 | 15 | Replace "concentrator" with "coordinator." | See comment.
203 | Monique Brown | On Ramp Wireless | 5.2.1.9 | 28 | 53 | Spell out the acronym FCH the first time it is used. | Spell out FCH. Then, use only the acronym in 5.4.1.2 and places that follow.
173 | Monique Brown | On Ramp Wireless | 5.2.1.9 | 28 |  | Need to restructure how and where the CRC is defined, in order to accommodate the addition of the CVS field. | Work with WG TE to devise a solution.
210 | Monique Brown | On Ramp Wireless | 5.2.2.1.1a | 29 | 8 | Make sure the subclause title for this one and 5.2.4 matches what's in 15.4e. | Update subclause titles.
18 | Pat Kinney | Kinney Consulting | 5.2.2.1.1a | 29 | 22 | TBD in Table 3b | replace TBD with attribute request identifier for macRSLNenabled
364 | B. Rolfe | BCA | 5.2.4 | 29 | 27 | General editorial: I would like a ruling from the WG TE for a consistent language when refering to a figure that specifies the (normative) format of an IE or frame. Should we have "The format is shown in…" and "the format shall be as shown in"… and "shall bef formated as shown in ...". Really a roll-up issue but might as well start now. | Consult WG TE. Apply fermented beverages as needed.
19 | Pat Kinney | Kinney Consulting | 5.2.4.2 | 29 | 38 | 4 TBDs in Table 4b | replace TBDs with Element IDs
362 | B. Rolfe | BCA | 5.2.4.9a | 30 | 39 | For the last three fields we state that the field is "only valid" conditinoallhy. When the condition is not met, is the field present, but should be ignored, or is the field not transmitted? | Clarify. My preference would be to not include fields in the transmitted frame that are nto valid but I am not sure if that is what was meant.
363 | B. Rolfe | BCA | 5.2.4.23 | 31 | 1 | "the IE" should be "Context Descriptoin". | see comment
20 | Pat Kinney | Kinney Consulting | 5.2.4.23 | 31 | 9 | There are only 14 bits allocated in the first 2 octets | put the other two bits into reserve
217 | Monique Brown | On Ramp Wireless | 5.2.4.23 | 31 | 9 | Define TID the first time it is used only. Also add it to Clause 3. | See comment.
365 | B. Rolfe | BCA | 5.2.4.23.1 | 31 | 19 | "that is locally unique in the PAN and" is not necessary (or necessarily true). | Delete.
21 | Pat Kinney | Kinney Consulting | 5.2.4.23.1 | 31 | 34 | Table 4s refers to a "fragement cell" that is not defined | either define "fragment cell" or change its name to something that is known
366 | B. Rolfe | BCA | 5.2.4.23.2 | 31 | 25 | Repeating the obvious: "The I-ACK Policy field indicates the I-ACK policy to be employed". | delete
196 | Monique Brown | On Ramp Wireless | 5.2.4.23.2 | 31 | 38 | What is the transaction setup frame? Is this the fragment context frame? | Please clarify.
22 | Pat Kinney | Kinney Consulting | 5.2.4.23.4 | 32 | 7 | MPDU Size/Success threshold field only describes the length of the MPDU being fragmented, there is no "success" defined | either eliminate the "succeess threshold" or define it
367 | B. Rolfe | BCA | 5.2.4.23.4 | 32 | 9 | Need to describe what the field contains when it is used as "success threshold". | "When I-ACK policy field contains 1,2 or 3 …[existing text]. When I-ACK policy field conains 4, the number of valid fragents before acnkowledgement"
197 | Monique Brown | On Ramp Wireless | 5.2.4.23.5 | 32 | 15 | Text says "The fragment sequence description may contain any combination of..." | Should fragment sequence description be replaced by fragment context frame?
240 | Monique Brown | On Ramp Wireless | 5.2.4.23.5 | 32 | 35 | Last paragraph should be moved closer to beginning of subclause. | Make either first or second paragraph.
371 | B. Rolfe | BCA | 5.2.4.23.6 | 32 | 10 | "a an" only need one; "Fragmentation Context MPDU Fragment Sequence Context Description IE." has more Fragment Context than we need. | see comment
368 | B. Rolfe | BCA | 5.4.2.23.3 | 32 | 3 | First sentence is redundant. | Delete
370 | B. Rolfe | BCA | 5.4.2.23.5 | 32 | 15 | First sentence "context" s/b "content". | see comment
215 | Monique Brown | On Ramp Wireless | 5.2.4.23.6 | 33 | 10 | "alternate CRC remainder initialization value" Should be "CVS RIV." | Make terminology consistent. Also, change "a an" to "an."
214 | Monique Brown | On Ramp Wireless | 5.2.4.23.6 | 33 | 11 | Add CVS RIV to Clause 3. | See comment.
198 | Monique Brown | On Ramp Wireless | 5.2.4.23.6 | 33 | 16 | Text says "Fragmentation Context MPDU Fragment Sequence Context Description IE." | Change to "MPDU Fragment Sequence Context Description IE."
199 | Monique Brown | On Ramp Wireless | 5.2.4.23.8 | 33 | 43 | Change title of figure to "PHY-dependent fragment _sequence_ context parameters for LECIM FSK PHY" for consistency. | See comment.
372 | B. Rolfe | BCA | 5.2.4.24.1 | 34 | 31 | We need a cross reference to where inward and outward transmission are defiend. | see comment
373 | B. Rolfe | BCA | 5.2.4.24.2 | 34 | 39 | There is a "Time synchronizaton specification" in 5.2.4.9.2 (DSME) which includes beacon timestamp and an offset value..might be confusing. This looks identical to the beacon timestamp. Can we call it "beacon timstamp" then? | rename field "Beacon timestamp".
377 | B. Rolfe | BCA | 5.2.4.24.3 | 34 | 52 | Reference to 5.2.4.25 doesn't quite make sense, as that defines an IE which is 4 octets (including 2 octet IE descriptor). I *think* we mean this has the same format as the content of that IE, as shown in figure 48nx. The confusion arises because the convention is that the IE figures don't show the IIE descriptor [it says in 5.2.4 that all IEs contain one]. | Verify intent and clarify text. We have the same issue multipel places - we reference the entire IE where I think the intent is to refer only to a field within the IE. It might be fixed by using the figure reference instead of clause #.
374 | B. Rolfe | BCA | 5.2.4.24.3 | 35 | 1 | I'm confused as to how the bitmap maps. In figure 11i and accompaning text I see one beacon slot per slotted superframe. Do we mean each bit is for the becaon slot of a slotted superframe in the mult-superframe/cyclic superframe? In which case what happens when there are more than 9 slotted superframes in a cyclic superframe? It appears a LOT mroe than 9 can be defined, but that may be where I am confused! | clarify
375 | B. Rolfe | BCA | 5.2.4.24.4 | 35 | 10 | What is a pending slot? We have a way to identify it, but we don't use the term anywhere eles? Not sure what "pending the frame" means. | see comment
376 | B. Rolfe | BCA | 5.2.4.25 | 36 | 1 | "Generates" should be "generated" or "is generating"?. Change "The relaying tier of the PAN coordinator shall be set to zero." to "A value of zero shall indicate the PAN coordinator"; Referring to Table 46 doesn't work as this does not define a value encodable over the air. Better to show the bit values and corresponding grade; What is "this slotted superframe" referring to? Is this the same as having the Slotted superframe Index set to 0? | see comment
127 | Monique Brown | On Ramp Wireless | 5.2.4.27 | 37 | 7 | Confusing terminology. Don't use "SF" to mean "superframe." Superframe is never called SF in the base standard, and anyway SF already means "spreading factor" (spreading factor is defined in 15.4g and this draft). | Replace all instances of SF meaning superframe by the word "superframe."
211 | Monique Brown | On Ramp Wireless | 5.2.4.27 | 37 | 29 | Define the acronym CFP only once. | See comment.
276 | Cristina Seibert | Silver Spring Networks | 5.2.4.29.1 | 38 | 17 | It sounds like the presence of this IE with a unique ID is used to signal the DSSS PHY is supported. Is this a good use of what is a limited ID space? Where is the actual ID specified? | Clarify
278 | Cristina Seibert | Silver Spring Networks | 5.2.4.29.1 | 38 | 26 | Typo in Figure heading: should state "LECIM DSSS Capability IE". Also, this is only the "content" field of the IE, not the entire IE (latter comment applies also to Figure 48naf).. | fix as suggested
271 | Matt Johnson | Independent | 5.2.4.29.1 | 38 | 17-19 | The text refers to the DSSS PHY and Figure 48nad. But figure 48nad is captioned LECIM FSK | Text should agree with caption
272 | Matt Johnson | Independent | 5.2.4.29.1 | 38 | 29-54 | Table 4v seems to indicate that these are the bands for the DSSS PHY. Yet when compared to table 66, the 169 MHz and 433 MHz bands do not as being supported by the DSSS PHY | Remove unsupported bands to be consistent with Table 66
277 | Cristina Seibert | Silver Spring Networks | 5.2.4.29.2 | 39 | 47 | It sounds like the presence of this IE with a unique ID is used to signal the FSK PHY is supported. Is this a good use of what is a limited ID space? Where is the actual ID specified? | Clarify
279 | Cristina Seibert | Silver Spring Networks | 5.2.4.29.2 | 39 | 49 | Wrong reference, should be Figure 48naf | fix as suggested
280 | Cristina Seibert | Silver Spring Networks | 5.2.4.32 | 42 | 14 | Typos, should be 1 = 25 kbps, 2 = 12.5 kbps | fix as suggested
23 | Pat Kinney | Kinney Consulting | 5.3 | 43 | 20 | 6 TBDs in command frame identifier column of Table 5 | replace TBDs with correct identifiers
24 | Pat Kinney | Kinney Consulting | 5.3.11.2.2 | 44 | 25 | IEEE editing doesn't allow a replacement of subclause text with a block of other text. | Strike the text that is changed and insert text appropiately
378 | B. Rolfe | BCA | 5.3.11.2.5 | 44 | 47 | "The Extended DSME GTS Allocation field shall be present if macExtendedDSMEenabled is TRUE. This field shall be formatted as illustrated in Figure 59gb." How does the device receiving the command know the field is present? | Clarify
379 | B. Rolfe | BCA | 5.3.11.3.7 | 45 | 45 | "The BI Index field shall be present if macExtendedDSMEenabled is TRUE." how does the receiver of the command know if the field is present? Same question for Superframe ID field, Slot ID field, Channel Index field. | Clarify
380 | B. Rolfe | BCA | 5.3.12.2 | 46 | 28 | "all coordinators" don't need "all". | Delete "all".
212 | Monique Brown | On Ramp Wireless | 5.3.14 | 47 | 20 | Incomplete editing instruction. | Complete the editing instruction.
25 | Pat Kinney | Kinney Consulting | 5.3.14 | 47 | 24 | statement mandates that all FFDs must be RSLN capable for a PAN to use RSLN, i.e. a mixed collection of FFDs such as RSLN capable and not RSLN capable cannot be an RSLN PAN | a RSLN PAN could exist with some FFDs that aren't RSLN capable, change the statement to only require RSLN-capable FFDs as appropriate.
381 | B. Rolfe | BCA | 5.3.14 | 47 | 24 | Awkward wording makes it hard to validate the requirement. | Change to: "A RSLN capable devices shall be capable of transmitting and receiving all command frame types defined in 5.3.14.1 and 5.3.14.2."
383 | Seong-Soon Joo | ETRI | 5.3.14.1 | 47 | 28 | RSLN-Association request command does not carry the RelayingSync information of MLME-ASSOCIATE.request primitive. | insert the 2 octet long Relaying Sync information on RSLN-Association request command.
384 | Seong-Soon Joo | ETRI | 5.3.14.2 | 47 | 44 | RSLN-Association response command does not carry the RelayingSync information for MLME-ASSOCIATE.response primitive. | insert the 2 octet long Relaying Sync information on RSLN-Association response command.
26 | Pat Kinney | Kinney Consulting | 5.4 | 51 | 25 | Statement "support for MPDU fragmentation is optional" is not true for LECIM DSSS PANs | either state that the DSSS LECIM PAN requires support of fragmentation or refer to the PHY clause that states this
62 | Pat Kinney | Kinney Consulting | 5.4 | 51 | 25 | Fragmentation is not optional for DSSS PHYs | change to: "Support for MPDU fragmentation is mandatory for LECIM DSSS PHYs and optional for all other PHYs.
174 | Monique Brown | On Ramp Wireless | 5.4 | 51 | 28 | Revise text for clarity. | Change text to "...processed into a sequence of fragment cells known as a fragment sequence."
175 | Monique Brown | On Ramp Wireless | 5.4 | 51 | 29 | The first sentence uses the term "fragment cell," and the third sentence talks about "each fragment." | Make terminology consistent. Choose either "fragment cell" or "fragment" and use it consistently throughout the text.
230 | Monique Brown | On Ramp Wireless | 5.4 | 51 | 29 | Change "an CVS" to "a CVS." | See comment.
231 | Monique Brown | On Ramp Wireless | 5.4 | 51 | 29 | Cross-ref is not necessary here. | Remove 5.4.1.1.
232 | Monique Brown | On Ramp Wireless | 5.4.1.1 | 51 | 39 | Change from "a frame shall contain" to "such a frame shall contain." | See comment.
177 | Monique Brown | On Ramp Wireless | 5.4.1.1 | 51 | 48 | Change "the value of the transaction ID information" to "the value of the transaction ID." Also change "that ID information" to "that transaction ID." | See comment.
176 | Monique Brown | On Ramp Wireless | 5.4.1.1 | 51 | 50 | Text says, "If a fragment cell is not received within aMPDUFragTimeout, the fragmentation transaction shall be terminated." So fragments cannot be retransmitted? | Please explain.
27 | Pat Kinney | Kinney Consulting | 5.4.1.1 | 51 | 52 | concept of a zero in Transaction ID field makes no sense. How does a PHY "know" how to send a unit message? I see no advantage either, since the ID field is still there. | delete the last paragraph in 5.4.1.1 and the sentence of line 19 on page 52
233 | Monique Brown | On Ramp Wireless | 5.4.1.1 | 51 | 53 | Change from "The Transaction ID field value of zero" to "A Transaction ID field value of zero." | See comment.
178 | Monique Brown | On Ramp Wireless | 5.4.1.1 | 51 | 54 | "value of zero in the context description." | Replace "context description" with "MPDU Fragment Sequence Context Description IE."
179 | Monique Brown | On Ramp Wireless | 5.4.1.1 | 52 | 1 | "point-to-point unique context" | Why not use the same terminology that was used at the start of the paragraph?
234 | Monique Brown | On Ramp Wireless | 5.4.1.2 | 52 | 4 | Change heading to "Fragment cell format." Change line 6 to "The fragment cell format is..." Change the figure heading to "Fragment cell format." | See comment.
180 | Monique Brown | On Ramp Wireless | 5.4.1.2 | 52 | 24 | "which fragment in the sequence the data part contains" | Replace with "the fragment contained in the Fragment Data field."
181 | Monique Brown | On Ramp Wireless | 5.4.1.2 | 52 | 28 | It is strange to name a field and then say that it is "reserved for future use." Same comment for Figure 59ddo I-ACK format. | Follow convention and just call it "reserved." Or change text to "...field indicates an extended cell descriptor. A value of zero indicates that an extended cell descriptor is not used; a value of one indicates that an extended cell descriptor is used. The Extension field shall be set to zero for this version of the standard."
201 | Monique Brown | On Ramp Wireless | 5.4.1.2 | 52 | 34 | Use only the acronym here and in Figure 59ddl. | Change to "The CVS field is used..." in the text and to "CVS" in the figure.
182 | Monique Brown | On Ramp Wireless | 5.4.1.3 | 52 | 42 | Use terminology consistently. | Change to "Determine the fragment sequence context using the MHR fields of the MPDU..."
183 | Monique Brown | On Ramp Wireless | 5.4.1.3 | 52 | 45 | "Construct the fragment context frame, as described in 5.4.1.1." | I don't see enough info in 5.4.1.1 to construct it. More explanation is needed and how about a figure showing the format?
184 | Monique Brown | On Ramp Wireless | 5.4.1.3 | 52 | 47 | "Elide/compress the MHR fields that are effectively transmitted in the fragment context frame." | What is meant by "effectively transmitted?" Maybe it should be "included as part of the fragment context frame."
185 | Monique Brown | On Ramp Wireless | 5.4.1.3 | 52 | 49 | "contain the maximum number of data octets." | Should this be "shall contain?"
186 | Monique Brown | On Ramp Wireless | 5.4.1.3 | 52 | 51 | I think the Fragment Validation field is the CVS, right? | Update field name.
187 | Monique Brown | On Ramp Wireless | 5.4.1.3 | 53 | 3 | Text says, "according to the I-ACK policy value specified in the fragment context frame." | There is no figure showing a fragment format frame. So either replace the name of the frame here with the name of the IE (at least this is something the reader can find in a figure) or include a figure showing the fragment format frame.
235 | Monique Brown | On Ramp Wireless | 5.4.1.3 | 53 | 4 | Should be "not received within the I-ACK timeout period." | See comment.
28 | Pat Kinney | Kinney Consulting | 5.4.1.3 | 53 | 14 | color in Figure 59ddm is not necessary | change to gray scale drawing
188 | Monique Brown | On Ramp Wireless | 5.4.1.3 | 53 | 33 | The figure uses the notation "FP." | Either define FP or use another notation.
206 | Monique Brown | On Ramp Wireless | 5.4.2 | 53 | 54 | Replace "incremental acknowledgment" with "I-ACK." | See comment.
189 | Monique Brown | On Ramp Wireless | 5.4.2 | 54 | 2 | Replace "can" with "shall." | "shall retransmit only those fragments."
124 | Monique Brown | On Ramp Wireless | 5.4.2.1 | 54 | 4 | Inconsistent terminology. Is it "incremental fragment acknowledgment" or "fragment incremental acknowledgment?" | Decide which one to use. Don't spell it out so many times.
190 | Monique Brown | On Ramp Wireless | 5.4.2.1 | 54 | 7 | Text says "according to the I-ACK policy provided in the context setup." | It would be more consistent to say it is according to the I-ACK Policy field in the MPDU Fragment Sequence Context Description IE or in the fragment format frame.
122 | Monique Brown | On Ramp Wireless | 5.4.2.1.1 | 54 | 17 | Inconsistent terminology. Figure 59ddn shows the Fragment Status field, while Figure 59ddo calls it the I-ACK Fragment Status field. | Make the terminology between Figure 59ddn and Figure 59ddo consistent.
123 | Monique Brown | On Ramp Wireless | 5.4.2.1.1 | 54 | 17 | Figure 59ddn shows the last field as I-ACK Validation. Figure 59ddo, which is part of the I-ACK shown in Figure 59ddn, shows the last field as Cell Validation. Should there be two validation fields? | Correct Figure 59 ddo if necessary. Align the cell validation field names with 5.2.1.9. Make sure that every field shown in the figures have accompanying descriptions.
202 | Monique Brown | On Ramp Wireless | 5.4.2.1.1 | 54 | 19 | FCF was already defined. | Use only the acronym here.
369 | B. Rolfe | BCA | 5.4.2.1.1 | 54 | 38 | We have "I-ACK" and "IACK". | Pick one.
236 | Monique Brown | On Ramp Wireless | 5.4.2.1.1 | 54 | 41 | Change figure title to "Fragment Status field" for consistency. | See comment.
237 | Monique Brown | On Ramp Wireless | 5.4.2.1.1 | 54 | 44 | Change to "...status flags are included in the Fragment Status Flags field." | See comment.
191 | Monique Brown | On Ramp Wireless | 5.4.2.1.1 | 54 | 51 | I don't think you can use "shall" when talking about an implementation-dependent feature. | Change "shall" to "should." Also change "but" to "and."
238 | Monique Brown | On Ramp Wireless | 5.4.2.1.1 | 55 | 17 | Change "correspond" to "corresponding." | See comment.
192 | Monique Brown | On Ramp Wireless | 5.4.2.1.2 | 55 | 27 | Text says "in the fragment sequence context, as defined in 5.4.1.1." | It would be better to say "via the fragment context frame" or "via the MLME Fragment Sequence Context Description IE, as defined in 5.2.4.23."
239 | Monique Brown | On Ramp Wireless | 5.4.2.1.2 | 55 | 27 | Change from "Upon completion of the fragment cell" to "Upon completing the transmission of the fragment cell." | See comment.
193 | Monique Brown | On Ramp Wireless | 5.4.2.2 | 55 | 40 | If the Fragment Status IE is new, it should be included in 5.2.4 | Add to 5.2.4.x.
194 | Monique Brown | On Ramp Wireless | 5.4.2.2 | 55 | 50 | The MCPS-DATA.indication passes up the MSDU, according to 6.3.3. The text says MPDU. | Please check. Also missing "." in primitive name. Should be MCPS-DATA.indication.
195 | Monique Brown | On Ramp Wireless | 5.4.2.2 | 55 | 53 | Where is MCPS-EXT-ACK.request defined? | Please clarify.
417 | James Gilb | Tensorcom | 6.2.2 | 57 | 27 | A large number of parameters are added without any description of how they are used by the primitives. It seems like there may be more to the story than told so far. | Provide specifiation of how the parameters are used w/appropriate cross references to functional clauses.
331 | B. Rolfe | BCA | 6.2.2.1 | 58 | 5 | RelayingSync type text isn't really a valid type, it should be part of the description. Also I think the xref may be wrong as it doesn't make sense to me. | Move to description and make Type "Integer" and fix xref or explain parameter value relates to the vields of the Synchronous Relaying Specification field of the Cyclic-superframe specification field. Also in 6.d.d.2 and 6.2.2.3
385 | Seong-Soon Joo | ETRI | 6.2.2.1 | 58 | 5 | type and vald range of RelayingSync in Table 9 are not matched to the description of RelayingSync. | change type to "Integer" cahnge valid range to "0x0000-0xffff"
335 | B. Rolfe | BCA | 6.2.2.1 | 58 | 16 | Parameter HoppingSequence Request is really a Boolean as desribed. | Change type to Boolean and Range, Description accordingly. Also in 6.2.2.2
334 | B. Rolfe | BCA | 6.2.2.1 | 58 | 19 | Table 9: I don't understand why "Direction" parameter is included in the MLME-ASSOCIATE request, confirm and indication. This is related to GTS allocation which happens after association (MLME-DSME-GTS)? | Clarify. Also in 6.2.2.2.
386 | Seong-Soon Joo | ETRI | 6.2.2.2 | 58 | 26 | type and vald range of RelayingSync in Table 10 are not matched to the description of RelayingSync. | change type to "Integer" cahnge valid range to "0x0000-0xffff"
387 | Seong-Soon Joo | ETRI | 6.2.2.3 | 59 | 23 | type and vald range of RelayingSync in Table 11 are not matched to the description of RelayingSync. | change type to "Integer" cahnge valid range to "0x0000-0xffff"
418 | James Gilb | Tensorcom | 6.2.12.1 | 60 | 20 | This needs to specify the parameter content for RSLNSpecification completely and give some idea how it is used by the service. | Complete specification
419 | James Gilb | Tensorcom | 6.2.12.1 | 60 | 20 | Need to describe how the new parameter is used, for example, does the presence of an RSLNSpecifiaiton indicate that the PAN about to be started should be an RSLN PAN? How does this affect the operation of the MLME-Start primitive? | Complete specification
299 | B. Rolfe | BCA | 6.2.22 | 60 | 31 | Title should be “operating mode switch” and line 33 “operating channel” should be “operating mode”. | see comment
300 | B. Rolfe | BCA | 6.2.22 | 60 | 33 | Still has “operating channel” in the sentence. | Change sentence to "These primitives support the coordination of a change in PHY operating parameters amongst peer devices." device.
301 | B. Rolfe | BCA | 6.2.22 | 60 | 39 | “operating channel” again | Change to "The MLME-PHY-OP-SWITCH.request primitive is used to initiate the PHY Parameter Change Notification process."
388 | Seong-Soon Joo | ETRI | 6.2.2.4 | 61 | 21 | type and vald range of RelayingSync in Table 12 are not matched to the description of RelayingSync. | change type to "Integer" cahnge valid range to "0x0000-0xffff"
304 | B. Rolfe | BCA | 6.2.21 | 61 | 19 | Table 12: We have a new status enumeration value "UNAVAILABLE_RESOURCE" that does not appear to be used anywhere. | Either we delete the change or we figure out where we meant to use it.
302 | B. Rolfe | BCA | 6.2.22.1 | 62 | 44 | Don't need "prior to the switch" in the description | delete "prior to the switch".
306 | B. Rolfe | BCA | 6.2.21 | 63 | 14 | "If the Device is a PAN coordinator of a beacon-enabled PAN that is not using enhanced beacons, and the SignalMethod parameter is USE_BEACON, then the MLME-PHY-OP-SWITCH.request shall not commence the transmission of switch notifications, but shall return the MLME-PHY-OP-SWITCH.confirm with a status of UNSUPPORTED_OPERATION." should this be in 6.2.22.2 (confirm primitive)? | See comment
308 | B. Rolfe | BCA | 6.2.22.1 | 63 | 11 | "or until the value in the TargetTime parameter has passed." s/b "The the TargetTime has elapsed". | see comment
303 | B. Rolfe | BCA | 6.2.22.1 | 63 | 28 | "In the case that an MP frame is used" is redundant per context of the paragraph. | Change second sentence to: "The MP frame shall repeatthe frame after a delay equal to the value of the RepeatInterval parameter, until the RepeatCount number of repetitions is exhaused or the TargetTime is reached. The Notification Time field shall be updated with each transmission."
305 | B. Rolfe | BCA | 6.2.22.2 | 64 | 13 | Table 44bb: We define a new enumeration value "UNSUPPORTED_OPERATION". We already have one for "UNSUPPORTED_FEATURE" (15.4e-2012). Let's use that instead. | Change "UNSUPPORTED_OPERATION" to "UNSUPPORTED_FEATURE" where it occurs.
307 | B. Rolfe | BCA | 6.2.22.2 | 64 | 20 | We need to describe what can go wrong. | Add: "If the device does not support enhanced beacons, the PHY Parameter Change IE, and/or the PHY Operation Switch features, then the status shall be set to UNSUPPORTED_FEATURE. If the AR field of the MHR was set in notification generated by the request, and no Acknowledgemetn is received according to <xref>, the status shall be set to NO_ACK. ". May also need XREF for where the base standard defines conditions that would generate the other status values?
309 | B. Rolfe | BCA | 6.2.22.3 | 64 | 21 | Add xref to MCPS data for other parameters. Or maybe this would be redundant with Table 44cc which references the MCPS-DATA.indication parameters table? | Add "the value of the remaining parameters is set according to the received frame as described in 6.3.3"
310 | B. Rolfe | BCA | 6.2.23.1 | 64 | 54 | Missing "peer" | Change to "This primitive allows an RSLN-enabled device to request the device status, clock time, slot-link information, relaying path information, and control of the transmission power of a peer device.
311 | B. Rolfe | BCA | 6.2.23.1 | 65 | 47 | Intro paragrpah can be more concise (crib rom 802.15.4-2011 style) | "The MLME-RSLN-MANAGEMENT.request primitive is used to..."
312 | B. Rolfe | BCA | 6.2.23.1 | 65 | 52 | "the MLME of the device" we don't need "of the device" unless there is some further qualifing (example "of a cordinator" or "of an unassociated device" from 802.15.4-201 1). Occurs multiple times. | Just "The MLME" will do where no further qualification is required.
313 | B. Rolfe | BCA | 6.2.23.1 | 65 | 54 | "The ManagementType shall be contained in the corresponding field of the command frame." we should reword so as to say that the field value is set according to the parameter. | "The Management Type field of the RLSN Managemetn Request command shall be set to the value of the ManagementType parameter"
314 | B. Rolfe | BCA | 6.2.23.2 | 66 | 24 | The first sentence is wrong. Combine this with the next paragraph and we have it. And then the last sentence is redundant. | "The MLME-RSLN-MANAGEMENT.indication is used to indicate the reception of an RSLN Management Request command."
315 | B. Rolfe | BCA | 6.2.23.2 | 66 | 43 | Table 44ee: The parameter descriptions should reference the received command frame (this is cut and paste from the request). | For ManagementType description: "The contents of the Management Type field of the received RSLN Managemetn Request command [5.3.14.3]".
316 | B. Rolfe | BCA | 6.2.23.3 | 68 | 25 | "corresponding fields" again. Probably need to call them out by field name. | see comment
317 | B. Rolfe | BCA | 6.2.23.4 | 68 | 48 | "On receipt of an RSLN Management Response command, the MLME of the device shall notify the higher layer with the result of the RSLN management request." is the description of the indication primitive. | Delete or move?
318 | B. Rolfe | BCA | 6.2.23.4 | 69 | 1 | Table 44gg: Not sure all these parameters make sense for the confirm. I think we need more details on the confirm, such as s it issued after the request is sent, or after the response is received?. This may clarify what the parameter values would be. | See comment
319 | B. Rolfe | BCA | 6.3.1 | 70 | 1 | "When fragmentation of the MPDU is enabled" How do we know fragmentation is enabled? | Change to:"When macMPDUFragmentationEnabled is TRUE)"
320 | B. Rolfe | BCA | 6.3.1 | 70 | 1 | What to do when these features are not supported by the implantation: Choice (1): Ignore the parameters.“When MPDU Fragmentation is not supported by the implementation the parameter is not used” or should we return a status of UNSUPPORTED_FEATURE. | see comment
130 | Monique Brown | On Ramp Wireless | 6.4.1 | 70 | 26 | Change cross-reference from 5.1.1.1 to 5.1.1.4. | See comment.
321 | B. Rolfe | BCA | 6.4.2 | 70 | 46 | Add IE definition(s) to support priority access as noted in the editorial comment | see comment
131 | Monique Brown | On Ramp Wireless | 6.4.2 | 71 | 37 | Some PIB attributes are shown in PIB table but is not actually used. | Either add text explaining macCSNeffectTimeout's usefulness or delete it from the PIB table. Same comment for macCriticalMessageDelayTolerance (mCMDT). Also, what is mCMDT?
261 | Yang Yang | WSNIRI | 6.4.3.2 | 71 | 17 | "The number of symbol periods required…" | "The number of symbols for backoff…"
342 | B. Rolfe | BCA | 6.4.3.2 | 71 | 17 | macLECIMAlohaBackoffSlot should be read only based on how it is described in 5.1.1.4.6 | Mark read only or clarify usage in 5.1.1.4.6.
29 | Pat Kinney | Kinney Consulting | 6.4.3.2 | 71 | 26 | Table 52 - macMPDUFragPadValue has TBDs for Type, Range, and Description | Replace TBDs with proper values such as integer for Type, 0 - 2047 for Range, etc
322 | B. Rolfe | BCA | 6.4.3.2 | 71 | 26 | TBDs in macMPDUFragPadValue | Type is "Octet", Range is "-", Change last sentence of description to "Implementation Dependent value".
30 | Pat Kinney | Kinney Consulting | 6.4.3.2 | 71 | 36 | Table 52 - macCSNeffectTimeout has TBDs for Range, and Default | Replace TBDs with proper values
323 | B. Rolfe | BCA | 6.4.3.2 | 71 | 36 | "macCSNeffectTimeout" isn't used anymore. | Remove here and in P.2.6
31 | Pat Kinney | Kinney Consulting | 6.4.3.2 | 71 | 39 | Table 52 - macCVSRIV has TBD for Range | Replace TBD with proper value
324 | B. Rolfe | BCA | 6.4.3.2 | 71 | 40 | Resolve TBD for macIACKtimeout range. This may depend on the PHY or it might be OK to use a fixed number of symbol periods. | TBD
268 | Jie Shen | WSNIRI | 6.4.3.2 | 71 | 17~21 | according to the definition of macLECIMAlohaBackoffSlot is very like the definition of "aUnitBackoffPeriod", both defined the number of symbols for backoff, but the naming of macLECIMAlohaBackoffSlot is strange. | can we use the name of macLECIMAlohaUnitBackoffPeriod? Or something else like that, just please keep the naming unified.
325 | B. Rolfe | BCA | 6.4.3.2 | 72 | 15 | macCVSRIV range should be "-" or "any 16 or 32 bit pattern". Default s/b "see 5.2.1.9" (it's different for CRC-16 and CRC-32). | see comment
32 | Pat Kinney | Kinney Consulting | 6.4.3.2 | 72 | 16 | Table 52 - macIACKTimeout has TBDs for Range, and Default | Replace TBDs with proper values
55 | Pat Kinney | Kinney Consulting | 6.4.3.2 | 72 | 25 | PCA has already been spelled out | just use PCA
266 | Jie Shen | WSNIRI | 6.4.3.2 | 72 | 25 | macPCAAllocationSuperRate actually indicate whether there is more than one allocation per superframe, is a Boolean attribute, can we use another more suitable name of this PIB? "rate" may make people confusing. | give another name of this PIB
326 | B. Rolfe | BCA | 6.4.3.2 | 72 | 25 | The achronym PCA is first used in 4.5 (corretly) so we can displance with "priority channel access" and use the achronym PCA here. | see comment
56 | Pat Kinney | Kinney Consulting | 6.4.3.2 | 72 | 32 | PCA has already been spelled out | just use PCA
260 | Yang Yang | WSNIRI | 6.4.3.2 | 72 | 40 | please give unified definition of PIB, in all the other parts of this draft, the name used is macCritMsgDelayTol. | change "macCriticalMessageDelayTolerance" here to "macCritMsgDelayTol", or change all the "macCritMsgDelayTol"s in this draft to "macCriticalMessageDelayTolerance".
267 | Jie Shen | WSNIRI | 6.4.3.2 | 72 | 43 | what is the means of "60.0/float"? | please give more clear definition.
327 | B. Rolfe | BCA | 6.4.3.2 | 72 | 43 | Need to replace "14-bit float giving resolution 60.0/float" with something that describes the minimum resolution required (if any). | see comment
216 | Monique Brown | On Ramp Wireless | Table 52 | 72 | 16 | Acronym RIV was already defined. | Don't re-define here.
133 | Monique Brown | On Ramp Wireless | 6.4.3.2 | 73 | 5 | Some PIB attributes are shown in PIB table but is not actually used. | Either add text explaining macRSLNcapable's usefulness or delete it from the PIB table. Same comment for macExtendedDSMEcapable.
328 | B. Rolfe | BCA | 6.4.3.2 | 73 | 5 | macRSLNcapable s/b read only | see comment
329 | B. Rolfe | BCA | 6.4.3.2 | 73 | 9 | macExtendedDSME should be read only. capable should be FALSE. | see comment
420 | James Gilb | Tensorcom | 6.4.3.2 | 73 | 9 | Default for macExtendedDSME enabled should be FALSE. | Change default to FALSE.
421 | James Gilb | Tensorcom | 6.4.3.2 | 73 | 9 | Default for macRSLNenabled should be FALSE. | Change default to FALSE.
135 | Monique Brown | On Ramp Wireless | 6.4.3.6 | 73 | 41 | Attribute macMultisuperframeOrder has been modified but is not used anywhere in the draft. | Either explain its usefulness or remove it from Table 52h.
330 | B. Rolfe | BCA | 6.4.3.6 | 73 | 42 | TBD for default value of macMultisuperframeOrder | Provide default value
136 | Monique Brown | On Ramp Wireless | 6.4.3.6 | 73 | 46 | macAllocationOrder is shown in two tables: Table 52h and Table 52i. | Change macAllocationOrder to AllocationOrder in Table 52i (assuming it really belongs in the neighbor information).
137 | Monique Brown | On Ramp Wireless | 6.4.3.6 | 73 | 48 | I see macBeaconIntervalIndex in Table 52h and Table 1a. I don't see it anywhere else in the draft. | Add text to the appropriate place showing its use.
332 | B. Rolfe | BCA | 6.4.3.7 | 74 | 31 | Symbols s/b "symbol periods" or "symbol durations". Also in next two attributes where using symbols to define a time period. (i.e. "symbol duration" is a time, "symbol" is a thing that is timeless ;0). | replace with "symbol duratino" where "symbol" is used as a unit of time.
33 | Pat Kinney | Kinney Consulting | 6.4.3.7 | 74 | 37 | Table 52j - macHWSLFramePendingWaitTime has TBD for default | Replace TBDs with proper values
128 | Monique Brown | On Ramp Wireless | 6.4.3.7 | 74 | 37 | What is macMinLIFSPeriod? | Replace with macSIFSPeriod (assuming that's what is meant).
333 | B. Rolfe | BCA | 6.4.3.7 | 74 | 38 | Don’t'really like "keep the receiver on". What we are describing is a period of time where following transmissions may be expected. "receiver on" sounds like an implementation. | reword
422 | James Gilb | Tensorcom | 6.4.3.7 | 74 | 38 | TBD in default (macHWSLFramePendingWaitTime) | Complete specification
423 | James Gilb | Tensorcom | 6.4.3.7 | 74 | 38 | TBDs (macHWSLWakeupInterval) | Complete specification
34 | Pat Kinney | Kinney Consulting | 6.4.3.7 | 74 | 43 | Table 52j - macHWSLWakeupInterval has TBD for Type, Range, and default | Replace TBD with proper value
424 | James Gilb | Tensorcom | 6.4.3.12 | 75 | 40 | Repeats normative information given in 5.2.4.24.3. It also repeats it wrong, as the where is not correct since the difference (macBeaconOrder - macSuperframeOrder) can in fact be greater than 9. | Change to "See 5.2.4.24.3" where it is all explained.
65 | Steve Jillings | Semtech | 8.1.1 | 77 | 20 | Table 66 references 19.1.2,1 for details of the LECIM Parameters. This is nor actually referenced in 19.1.2.1 | Update Table 66 to include LECIM DSSS parameters
281 | Cristina Seibert | Silver Spring Networks | 8.1.1 | 77 | 48 | Missing 37.5 kbps FSK/GFSK/P-FSK/P-GFSK mode | add
113 | Jeritt Kent | Analog Devices, Inc. | 8.1.1 | 77 | 21-50 | If all of the "Symbols" values in Table 66 are "Binary", then why have that column? | Simply add text or a footnote stating that all of the symbols for FSK/GFSK/P-FSK/P-GFSK are binary and remove that column.
112 | Jeritt Kent | Analog Devices, Inc. | 8.1.1 | 77 | 27-28 | While documents exist showing only 75kHz of BW for the 169MHz band, there have been discussions around extension into the ERMES band (169.4 to 169.8125MHz). This would be a much more usable option; especially given the 100kHz and 200kHz channel spacings. 4k has more generality than 4g as regards some of these European bands that specifically break out metering as a unique application. | Ensure that IEEE has the latest communiqué from ETSI regarding the 169MHz band - specifically Decision 2005/928/EC and the latest draft from SE24 post-Kolberg tests
120 | Jeritt Kent | Analog Devices, Inc. | 8.1.1 | 78 | 42-47 | It was contentious whether the low datarates of 4g made sense for FSK at 2450MHz. 4k datarates are even lower. Does this really make technical sense? | Remove 2450MHz
114 | Jeritt Kent | Analog Devices, Inc. | 8.1.2.11.1 | 79 | 51 | Sentence: "phyCurrentChannel…" states channel identifier number from 0 to N. This is incorrect per Table 68l. | Change "0 to N" to "1 to N"
241 | Xiang Wang | WSNIRI | 8.1.2.11.1 | 80 | 15 | Table 68I, 470-510 Band can align with IEEE802.15.4g | change text to Frequency Band(MHz): 470-510 FreqBandEdge(MHz): 470 FreqOffset(MHz): 0.4 ChanSpacing(MHz): 0.4 phyCurrentChannel range:1-99
242 | Xiang Wang | WSNIRI | 8.1.2.11.1 | 80 | 15 | Table 68I, 779-787MHz Band, the parameters are not correct. | change text to Frequency Band(MHz): 779-787 FreqBandEdge(MHz): 779 FreqOffset(MHz): 2 ChanSpacing(MHz): 2 phyCurrentChannel range:1-4
66 | Steve Jillings | Semtech | 8.1.2.11.1 | 80 | 16 | Table 68l incorrectly applied to DSSS PHYs | Refer to 15-12-0089-05-004k Section 19.1.2.1 and Table 190
67 | Steve Jillings | Semtech | 8.1.2.11.1 | 80 | 25 | Text: The 863 MHz LECIM FSK PHY frequency offset is not based upon a multiple of 100 kHz. The channel plan for the 863 MHz band is as follows: — Channel 0: 868.300 MHz — Channel 1: 868.950 MHz — Channel 2: 869.525 MHz Applies to legacy 868 - 870 MHz DSSS PHY | Insert following text: The channel plan for the 868MHz band is as follows: — Channel 0: 868.300 MHz — Channel 1: 868.950 MHz — Channel 2: 869.525 MHz
115 | Jeritt Kent | Analog Devices, Inc. | 8.1.2.11.1 | 80 | 25 | Sentence: "The 863 MHz…of 100 kHz" is confusing and appears to be in the wrong location discussing FSK in a DSSS subsection. Tables 68m and 68n do note an 863 band, but their ChanCenterFreq0 numbers are inconsistent with the line items from line 27-30 on page 80. | Review and clarify.
116 | Jeritt Kent | Analog Devices, Inc. | 8.1.2.11.1 | 80 | 1-54 | DSSS channels start with Channel 1 while FSK channels start with Channel 0… any value to being consistent? | Consider a consistent baseline.
80 | Schwoerer | France Telecom | 8.1.2.11.1 | 80 | 25-30 | This mention of 863 MHZ Lecim FSK PHY seems to be a typo. Isn't it LECIM DSSS PHY instead | Replace FSK PHY by DSSS PHY appropriate
81 | Schwoerer | France Telecom | 8.1.2.11.1 | 80 | 25-30 | Channel numbering start at 868,300 MHz. From what is presented in table 68i, channel numbering for the same band start a 863,075 MHz, It seems unconsistant | Correct sentence or table is one of them is erronus or clarify in wich case which clause apply.
282 | Cristina Seibert | Silver Spring Networks | 8.1.2.11.2 | 80 | 38 | Missing "see" next to sub-clause reference? | Change to "(see 9.3)"
283 | Cristina Seibert | Silver Spring Networks | 8.1.2.11.2 | 80 | 41 | No need to mention "modulation schemes", also ChanSpacing not actually specified in the tables themselves. | Change to "Parameters TotalNumChan and ChanCenterFreq0 for different frequency bands and channel spacings are specified in Table 68m and Table 68n." Change Table 68m heading to "TotalNumChan and ChanCenterFreq0 when ChanSpacing = 200 kHz." Similarly in Table 68n for ChanSpacing = 100 kHz.
117 | Jeritt Kent | Analog Devices, Inc. | 8.1.2.11.2 | 80 | 51 | Why include the 169MHz band in a table with 200kHz channel spacing - it does not show up in Table 68n with 100kHz spacing??? | Let the footnote or text explain the uniqueness of the 169MHz band describing the only center frequency and remove that row from the table.
284 | Cristina Seibert | Silver Spring Networks | 8.1.2.11.2 | 80 | 51 | Remove entry for Band ID 169 from Table 68m and state textually that "For Band identifier 169, ChanCenterFreq0 shall be 169.4375 MHz and TotalNumChan shall be 1". | fix as suggested
118 | Jeritt Kent | Analog Devices, Inc. | 8.1.2.11.2 | 81 | 1-2 | Since we reference ChanSpacing as a parameter in equation (2) on page 80, there needs to be a reference to this value. | Change the headings in Tables 68m and 68n from "...200kHz channel spacing" and "…100kHz channel spacing" to "ChanSpacing = 200kHz" and "ChanSpacing = 100kHz"
119 | Jeritt Kent | Analog Devices, Inc. | 8.1.2.11.2 | 81 | 22-38 | Is it intended that there are no 100kHz channel spacing options for the 917, 920, and 2450 bands per table 68n? | Check
291 | Cristina Seibert | Silver Spring Networks | 9.2 | 83 | 2 | Sub-clause 9.2 missing. Changes should be generally consistent with those done for SUN PHYs. | Add "and LECIM" after "SUN PHYs" in the constant descriptions.
129 | Monique Brown | On Ramp Wireless | 9.3 | 83 | 16 | phyLECIMDSSSPPDUModulation. This is too hard to read. We need a new convention for naming PIB attributes in the case of more than one acronym in a row. | How about phyLecimDsssPpduModulation or phyLECIMDsssPPDUModulation. Work with WG TE to come up with a universal naming convention.
243 | Xiang Wang | WSNIRI | 9.3 | 83 | 20 | Table71, phyLECIMDSSSPPDUModulation- Rate means chip rate? | clarify
138 | Monique Brown | On Ramp Wireless | 9.3 | 83 | 25 | I don't see phyLECIMDSSSPPDUTxAt used in the draft. | Either add text explaining its use or delete it from PIB table.
246 | Xiang Wang | WSNIRI | 9.3 | 83 | 25 | Table71, what's the requirement of network timing sync accuracy ? It's hard to measure and maintain network sync within modulation symbol level with low cost. | discussion with radio frequency tolerance
35 | Pat Kinney | Kinney Consulting | 9.3 | 83 | 30 | Table 71, unknown factor in description of phyLECIMDSSSPSDUSpreadingFactor, 2x | define x, or reference defintion in Description
247 | Xiang Wang | WSNIRI | 9.3 | 83 | 38 | If gold code generator resets each SHR and PSDU symbol, the device can not sense the frame if waked after the start point of frame(SHR), and can not using CCA mechiasm | discussion
36 | Pat Kinney | Kinney Consulting | 9.3 | 83 | 47 | Table 71, unknown factor in description of phyLECIMDSSSSHRSpreadingFactor, 2x | define x, or reference defintion in Description
139 | Monique Brown | On Ramp Wireless | 9.3 | 84 | 26 | I don't see phyLECIMDSSSPSDUOVSFSpreadingFactor or phyLECIMDSSSPSDUOVSFCodeIndex used anywhere outside of this table. | Add text showing its usefulness.
140 | Monique Brown | On Ramp Wireless | 9.3 | 85 | 28 | I don't see phyLECIMCurrentBand, phyLECIMFSKSymbolRate, phyCurrentLECIMPHYType or phyChannelSpacing used anywhere outside of this table. | Either add text or remove from table.
285 | Cristina Seibert | Silver Spring Networks | 9.3 | 85 | 28 | Incomplete list of bands, missing 921, 922. | Add
37 | Pat Kinney | Kinney Consulting | 9.3 | 85 | 40 | Table 71, editor note denotes something is missing | respond to note and delete it
292 | Cristina Seibert | Silver Spring Networks | 9.4 | 85 | 44 | Sub-clause 9.4 missing. | Add sub-clause with definition of phyMaxFrameDuration and any other depending attributes.
218 | Monique Brown | On Ramp Wireless | 19 | 87 | 34 | Define SHR the first time it is used only. Also make sure PHR, FSK, MPDU, PSDU are properly introduced. | See comment.
38 | Pat Kinney | Kinney Consulting | 19.1 | 87 | 12 | DSSS has already been used and spelled out | delete spelling out
39 | Pat Kinney | Kinney Consulting | 19.1.1 | 87 | 17 | if all multiple octet fields shall be transmitted least significant octet first then it will be received first | delete "or received"
294 | Cristina Seibert | Silver Spring Networks | 19.1.1 | 87 | 29 | How is the PSDU length known in the absence of a PHR signaling the length field? Is that also a provisioned parameter?? How does the receiver identify the end of the packet, where the tail bits would be, etc? | Clarify
40 | Pat Kinney | Kinney Consulting | 19.1.1 | 87 | 34 | SHR and SFD have already been used in Table 4z, they should be spelled out there | delete spelling out
244 | Xiang Wang | WSNIRI | 19.1.1 | 87 | 41 | What's the benefit of using preamble16 and preamble 32 instead of all zeros bits | clarify
245 | Xiang Wang | WSNIRI | 19.1.1 | 87 | 48 | SFD[10101011] ise equal to the last 8 bits of preamble 32, how to distinguish them | change SFD pattern
125 | Monique Brown | On Ramp Wireless | 19.1.2.4 | 88 | 37 | The acronym PBRI is only used once within the text. It is not necessary to include it. | Remove the acronym from here and also from Clause 3.
295 | Cristina Seibert | Silver Spring Networks | 19.1.2.4 | 88 |  | References to "fragment size" throughout. What if fragmentation is not used? What about the tail bits from the convolutional encoder? | generalize
41 | Pat Kinney | Kinney Consulting | 19.1.2.6 | 96 | 35 | figure 156 uses color that is not necessary | change Figure 156 to greyscale
42 | Pat Kinney | Kinney Consulting | 19.1.2.6.1 | 97 | 27 | 3rd Generation Partnership Project (3GPP) Technical Specification 25.213 is used as an indespensible reference | add it to clause 2
207 | Monique Brown | On Ramp Wireless | 19.1.2.6.2 | 97 | 39 | Spell out OVSF in the title and not in line 42. | See comment.
43 | Pat Kinney | Kinney Consulting | 19.1.3.1 | 100 | 22 | RF tolerance is a TBD | replace TBD with a proper value
82 | Schwoerer | France Telecom | 19.1.3.1 | 100 |  | There is still a TBD
68 | Steve Jillings | Semtech | 19.1.3.4 | 100 | 33 | Receiver sensitivity should ensure that a LECIM device can meet the 120 dB propagation loss requirement of the PAR | -
44 | Pat Kinney | Kinney Consulting | 19.1.3.4 | 100 | 35 | RX sensitvity is cited as a TBD | replace TBD with a proper value
83 | Schwoerer | France Telecom | 19.1.3.5 | 100 |  | Is an interferer another lecim device using a different ovsf code ? or just any signal ? | Explain what kind of interferer is considered.
110 | Jeritt Kent | Analog Devices, Inc. | 19.2 | 101 | 25 | Font Size for FSK PHY Specification seems incorrect. | Suggest a different font/boldface to set these main section headers X.X apart from Y.Y.Y
45 | Pat Kinney | Kinney Consulting | 19.1.3.6 | 101 | 10 | Tx-Rx should be all caps | replace with TX-RX
46 | Pat Kinney | Kinney Consulting | 19.1.3.6 | 101 | 13 | time is TBD | replace with a proper value
84 | Schwoerer | France Telecom | 19.1.3.6 | 101 |  | There is still a TBD
47 | Pat Kinney | Kinney Consulting | 19.1.3.7 | 101 | 15 | Tx-Rx should be all caps | replace with TX-RX
48 | Pat Kinney | Kinney Consulting | 19.1.3.7 | 101 | 18 | time is TBD | replace with a proper value
85 | Schwoerer | France Telecom | 19.1.3.7 | 101 |  | There is still a TBD
69 | Steve Jillings | Semtech | 19.1.3.8 | 101 | 21 | Given usage scenario, isn't the minimum TX power requirement superfluous? | Delete 19.1.3.8
111 | Jeritt Kent | Analog Devices, Inc. | 19.2.1 | 101 | 37 | The word "ignored" is vague. Does ignored mean that a receiver does not even need to clock in the bits… as there are temporal implications there? Can one save die area by not allocating memory elements for those bits in the receiver section - treat them as if they never existed? Perhaps there is a better technical word than ignored? | Consider another word for "ignored"
70 | Steve Jillings | Semtech | 19.2.1.3 | 102 | 18 | Support for 2047 octet packets. For a LOW-ENERGY MAC and PHY amendment that will be expected to implement spreading (and subsequent fragmentation) to achieve 120 dB propagation loss? 2047 octets is too large a number | Restrict maximum packet length to 127 octets
109 | Jeritt Kent | Analog Devices, Inc. | 19.2.1.3 | 102 | 21 | Sentence: "The Frame Length… respectively." is better placed as the first sentence of subsection 19.2.1.3 to make the reading clearer. | Move the sentence to first sentence in subsection 19.2.1.3
290 | Cristina Seibert | Silver Spring Networks | 19.2.1.3 | 102 | 41 | The 1-octet PHR lacks robustness (e.g. no Parity bit) and adds unnecessary receiver complexity for little gain (1 saved octet). The SHR field itself is a minumum of 7 octets, so the 1-octet saving essentially gets washed out. | Remove 1-octet PHR option. Remove the text pertaining to short PHR in FEC/interleaver sections.
287 | Cristina Seibert | Silver Spring Networks | 19.2.1.3 | 102 | 50 | How do we signal the type of FCS (2-octet or 4-octet)? In 4g we use a bit in the PHR, however since FCS is a MAC operation, it seems cleaner to signal it in the MAC portion of the frame rather than the PHY. However there may not be bits left in the MHR for that, also this approach would not allow for backwards compatibility with already defined MAC frames. Another possibility appropriate for LECIM is to resort to provisioning and not plan to signal the FCS type at all. Finally, we can state it is expected that short frames (i.e. those for which PHRL = 0) use the 2-octet FCS and long frames (i.e. those for which PHRL = 1) use the 4-octet FCS. | Pick one of the options listed.
86 | Schwoerer | France Telecom | 19.2.1.3 | 102 | 31-36 | It is unclear if commissioning is the only possible solution to defines PHY parameter | State that commissioning is the only way to configure PHY parameter not present in the PHT
105 | Jeritt Kent | Analog Devices, Inc. | 19.2.2 | 103 | 8 | What is intended by the "/" as is FSK/Gaussian FSK (GFSK)? Does this mean "AND" or "OR" or something else? | Is there a better way to nomenclate this?
286 | Cristina Seibert | Silver Spring Networks | 19.2.2 | 103 | 28 | Shouldn't symbol timing simply be 1/phyLECIMFSKSymbolRate (in ms)? | consider changing as suggested
106 | Jeritt Kent | Analog Devices, Inc. | 19.2.2 | 103 | 19-23 | What is the technical reason for increasing modulation index with a decrease in datarate? | To maintain bandwidth efficiency, restrict modulation index to 0.5 and with rare exception 1.0 - not 2.0…
107 | Jeritt Kent | Analog Devices, Inc. | 19.2.2 | 103 | 25-26 | Sentence: "Channel spacing…one channel" is superfluous. The sentence is duplicated as a footnote to Table 68m on page 81. | Select one of the sentences where is has most value and delete the other.
87 | Schwoerer | France Telecom | 19.2.2 | 103 | 28-29 | Only one symbol duration is given when several data rates are presented (same clause as well as table 66). No explanation is given on the way to meet those several data rate with a single symbol duration | Explain how the lower data rate can be obtained
274 | Cristina Seibert | Silver Spring Networks | 19.2.2.1 | 103 | 48 | First sentence of paragraph is incorrect. PHR and PSDU are not processed as a single coding block but two separate ones. | Change to "When FEC is enabled, the PHR and PSDU shall be processed for coding as described in 19.2.2.4.". At the same time, the paragraph is redundant so can be taken out entirely.
108 | Jeritt Kent | Analog Devices, Inc. | 19.2.2.1 | 103 | 43-54 | Phrase: "…unless otherwise specified elsewhere in this standard." Is this valid syntax? | Check with editors on syntax
49 | Pat Kinney | Kinney Consulting | 19.2.2.1 | 104 | 6 | Figure 164 doesn't need color | change figure to greyscale
101 | Jeritt Kent | Analog Devices, Inc. | 19.2.2.1 | 104 | 1-36 | Figure 164 is inaccurate if correspondent text regarding interleaving and FEC is accurate. | Change shaded Interleaver Block to two blocks. The block in the PHR path should be unshaded, and the one in the PSDU block should be shaded and merged with the shaded FEC block, since use of interleaving mandates FEC per lines 53-54 on page 106.
102 | Jeritt Kent | Analog Devices, Inc. | 19.2.2.1 | 104 | 29-32 | FSK modulation block is a series block that is shaded implying that FSK modulation "can be selected"… What is the alternative? Should there be a P-FSK block, too? | Reevaluate FSK modulation block versus objective.
103 | Jeritt Kent | Analog Devices, Inc. | 19.2.2.2 | 104 | 40-41 | Sentence: "The nominal…shall be" can be clearer. | Change sentence to: "The nominal single-sided frequency deviation…" or "full scale" (modify equation) if preferred.
104 | Jeritt Kent | Analog Devices, Inc. | 19.2.2.2 | 104 | 40-49 | Is there a place in this document where (delta)f is not equal to fdev? If not, then why have two variables for the same thing? | Consider one variable.
71 | Steve Jillings | Semtech | 19.2.2.3.1 | 105 | 21 | Frequency Deviation Tolerance: Do we really plan on specifing the fdev tolerance of 15.4g for 15.4k? | -
72 | Steve Jillings | Semtech | 19.2.2.3.2 | 105 | 27 | Zero Crosssing Tolerance: Do we really plan to specify the 15.4g tolerances? | -
99 | Jeritt Kent | Analog Devices, Inc. | 19.2.2.4 | 105 | 53 | Termination sequence not sequences | Remove the "s"
98 | Jeritt Kent | Analog Devices, Inc. | 19.2.2.4 | 106 | 28-32 | There are two sets of "000000". There are additional annotations that can be added to Figure 166 to make it clearer. | Annotate Figure 166 to specifically label the PHR and PSDU "termination sequences". Show the pad bits as zeroes and label the length as NPAD.
100 | Jeritt Kent | Analog Devices, Inc. | 19.2.2.4 | 106 | 42-43 | Sentence: "The value of…Table 196." is superfluous. The sentence is duplicated at lines 6-7 on page 107, and it is much clearer there. | Remove entire sentence
293 | Cristina Seibert | Silver Spring Networks | 19.2.2.5 | 106 | 45 | Typo in sub-clause heading, it should be "bit" not "symbol" | Change to "Code-bit interleaving"
96 | Jeritt Kent | Analog Devices, Inc. | 19.2.2.5 | 107 | 23 | We define ceiling and floor but not mod… Is mod considered a function like sin and cos or more like ceiling and floor? Do we need to define "mod"? | Define "mod" with "… where mod is the modulus of…" or, perhaps, even higher detail defining what a modulus is…
97 | Jeritt Kent | Analog Devices, Inc. | 19.2.2.5 | 107 | 40-42 | We describe the process of interleaving. Is one to assume, then, that deinterleaving order is Z^NB first and Z^0 last per "inverse relation"? | Leave nothing to guesswork regarding deinterleaving - explain it better.
275 | Cristina Seibert | Silver Spring Networks | 19.2.2.6 | 108 | 40 | Spreading sequences based on (0101) and (1010) repetitions seem less than optimal. | Consider reusing sequences from the MR-OQPSK PHY, e.g. replace with set of 0/1 orthogonal patterns for SF = 8 and SF = 16.
95 | Jeritt Kent | Analog Devices, Inc. | 19.2.2.6 | 108 | 1-15 | Figure 167 shows how interleaving is done, but the only description of de-interleaving is in lines 44-48 on page 107 which states, "The deinterleaver, which performs the inverse relation…". One may guess that the Fill In and Read Out figures merely swap for the deinterleaver, but, perhaps, the starts become ends. Both have validity if the only explanation one has is "inverse relation". Deinterleaving needs more detail. | Modify Figure 167 to a dual purpose showing interleaving and deinterleaving or add a figure to show deinterleaving or add text that makes the deinterleaving process very clear.
298 | Cristina Seibert | Silver Spring Networks | 19.2.3 | 108 | 49 | The reference to 18.1.3 may not be appropriate because parts of that sub-clause do not apply to this PHY. | Suggest incorporating the sub-clause explicitly instead of by reference, and removing the text about the Data Whitening field of the PHR being set to 1.
289 | Cristina Seibert | Silver Spring Networks | 19.2.3 | 108 | 50 | Shouldn't data whitening be required for an FSK-based PHY? | Replace "may optionally" with "shall". Update the reference modulator diagram and text in 19.2.2.1 accordingly.
90 | Jeritt Kent | Analog Devices, Inc. | 19.2.4.1 | 109 | 5 | Reference is incorrect | Change 19.2.2 to 8.1.1
88 | Jeritt Kent | Analog Devices, Inc. | 19.2.4.2 | 109 | 9 | Insert commas around T | Change text to: "…frequency tolerance, T, at the transmitter…"
288 | Cristina Seibert | Silver Spring Networks | 19.2.4.3 | 109 | 16 | imprecise language | Change to: "The channel switch time is defined as the time elapsed at the antenna between the trailing edge of the last symbol of one PPDU to the leading edge of the first symbol of a consecutive PPDU sent on a different channel." Apply the same change to 19.1.3.2.
91 | Jeritt Kent | Analog Devices, Inc. | 19.2.4.3 | 109 | 16-17 | Text can be clearer | Change text to: "The channel switch time is defined as the time elapsed upon departure from a current channel to arrival in a new channel within a function (transmit or receive), including any required setup or settling time."
89 | Jeritt Kent | Analog Devices, Inc. | 19.2.4.4 | 109 | 20 | Sentence contains catachresis. | Change "assure" to "ensure".
73 | Steve Jillings | Semtech | 19.2.4.5 | 109 | 22 | Receiver sensitivity should ensure that a LECIM device can meet the 120 dB propagation loss requirement of the PAR | -
93 | Jeritt Kent | Analog Devices, Inc. | 19.2.4.5 | 109 | 25-26 | Wording could be stronger | Change text to: "…a compliant device shall exhibit sensitivity better than or equal to -95dBm."
74 | Steve Jillings | Semtech | 19.2.4.6 | 109 | 28 | Interference rejection specification does not meet requirements for CRITICAL infrastructure monitoring. For license-exempt frequency space no provision made for blocking immunity or CCR given that spreading will be required to meet 120 dB propagation loss in some bands of operation | Amend receiver interference rejection and scope as per 15-12-0151-02-004k
92 | Jeritt Kent | Analog Devices, Inc. | 19.2.4.6 | 109 | 45-51 | Text does not accurately describe the objective tests. | Change text to: "The desired signal is input to the receiver at a level of -92dBm. In each of that signal's two alternate and two adjacent channels, one interfering signal at a time shall be input at the level specified in Table 198 relative to the desired signal, for a total of four tests. The receiver shall meet the error rate criteria defined in 8.1.7 under these conditions."
50 | Pat Kinney | Kinney Consulting | 19.2.4.7 | 109 | 52 | Tx-Rx should be all caps | replace with TX-RX
75 | Steve Jillings | Semtech | 19.2.4.7 | 109 | 52 | TX-RX turnaround time references baseline (12 symbols). Minimum BR is 12.5 kb/s or 640 us! Note 15.4g references 1 ms for aTurnaroundTime for CSM (50 kb/s) | Select aTurnaroundTime more appropriate for PHY mode
76 | Steve Jillings | Semtech | 19.2.4.8 | 110 | 1 | TX-RX turnaround time references baseline (12 symbols). Minimum BR is 12.5 kb/s or 640 us! Note 15.4g references 1 ms for aTurnaroundTime for CSM (50 kb/s) | Select aTurnaroundTime more appropriate for PHY mode
51 | Pat Kinney | Kinney Consulting | 19.2.4.8 | 110 | 2 | Tx-Rx should be all caps | replace with TX-RX
77 | Steve Jillings | Semtech | 19.2.4.9 | 110 | 5 | Given usage scenario, isn't the minimum TX power requirement superfluous? | Delete 19.2.4.9
94 | Jeritt Kent | Analog Devices, Inc. | 19.2.4.9 | 110 | 7-8 | Wording could be stronger | Change text to: "…a compliant device shall exhibit transmit power better than or equal to -3dBm."
297 | Cristina Seibert | Silver Spring Networks | Annex D | 111 | 1 | missing line numbers on pages 111, 112. | add line numbers
296 | Cristina Seibert | Silver Spring Networks | D.7 | 111 | 1 | Along with the PHY features, shouldn't the newly added MAC features be also highlighted in the PICS? | add
63 | Pat Kinney | Kinney Consulting | D7 | 111 |  | There are no PICS listed for MAC behaviors | at the very least add PICS for RSLN, HSWL, Fragmentation, PHY Parameter change to Tables D5 and D6.
389 | Seong-Soon Joo | ETRI | Annex P P.1.1 | 113 | 48 | Star toplogy is a solution to minimize infra and the coverage of a star LECIM network depends on the range of the RF PHY adopted for the network. Star topology is not only possible due to the long range of RF PHY. The sentence, "i.e., no repeaters are ... due long range.", does not support the reason to choose the star topology for the LECIM infra. | Delete the sentence "i.e., no repeaters are ... due long range." |  | AiP | change to "i.e., not a mesh network repeaters are typically needed due long range.
52 | Pat Kinney | Kinney Consulting | P.1 | 113 | 16 | 1016(e) of Public Law is informatively referenced | add this to the bibleography |  | A
273 | Matt Johnson | Independent | P.1.1 | 113 | 48 | Says "no need for repeaters" but P.1.3.3 discusses repeaters | Revise to remove ambiguity about repeaters |  | A | see CID 389
200 | Monique Brown | On Ramp Wireless | P.1.3.1 | 117 | 2 | Write out the meaning of CDMA the first time it is used. Use only the acronym after that. | Change to "...resources, code division multiple access [CDMA])" on p. 117. Then, use only the acronym in P.2.1 |  | A
121 | Jeritt Kent | Analog Devices, Inc. | P.2.1 | 117 | 40-41 | Process gain should be processing gain. | Change |  | A
132 | Monique Brown | On Ramp Wireless | P.2.4 | 118 | 35 | The level of detail given in this paragraph does not belong in an informative annex. | Delete text starting from "To ensure frame priority functionality whenever PCA..." from Annex P. Ensure that this information is included somewhere in the normative text. |  | AiP | Jussi to provide modified text 17 July
155 | Monique Brown | On Ramp Wireless | P.2.4 | 118 | 40 | "Frame priority is established by two means." But PCA and the two alternate backoff mechanisms go hand in hand, don't they? Line 41 says that PCAs are only used in beacon-enabled mode, but this contradicts 5.1.1.4.5 and 5.1.1.4.6. | Please make text between Clause 5 and Annex P agree. |  | AiP | see CID 132
152 | Monique Brown | On Ramp Wireless | P.2.4 | 118 | 42 | Too much detail for an informative annex. Anyway, this info is already given in Clause 5. | Remove " When present, the PCAs are evenly distributed throughout the superframe. The first such PCA is included in the beginning of every CAP of a superframe or multi-superframe. If a scheduling of a PCA would occur outside of the CAP, that PCA is omitted." |  | AiP | see CID 133
153 | Monique Brown | On Ramp Wireless | P.2.4 | 118 | 49 | Too much detail for an informative annex. This info should be in the normative text. | Remove the detail from this paragraph and the one that follows. Make sure it is all covered in Clause 5. |  | AiP | see CID 134
134 | Monique Brown | On Ramp Wireless | P.2.6 | 119 | 36 | Instead of repeating the lists of all the PIB attributes here, replace all lists with the appropriate cross-references. | Add cross-references similar to the one for PHY PIB attributes on p.120, line 23. Same comment for the IEs listed in P.2.7. |  | R | this list will assist the reader of the standard after rollup
64 | Pat Kinney | Kinney Consulting | P2.6 | 119 | 36 | Some LECIM PIBs are missing | add macCVSoffset, macCVSRIV, Priority Channel Access-specific: - macPriorityChannelAccess, - macPCAAllocationSuperRate, - macPCAAllocationRate, - macCriticalMessageDelayTolerance (mCMDT) |  | A
58 | Pat Kinney | Kinney Consulting | P2.6 | 119 | 46 | The General MAC PIB block is not needed. | Move the macRSLNcapable and macRSLNenabled PIBS to RSLN-specific MAC PIB attributes, move macExtendedDSMEcapable and macExtendedDSMEenabled PIBs to DSME-specific MAC PIB attributes, and delete header "General MAC PIB attributes for functional organization. |  | A
59 | Pat Kinney | Kinney Consulting | P2.7 | 120 | 28 | IE listings should include cross references | Change to:LECIM mechanisms and protocols in this standard require the following IEs: — RSLN ACK Descriptor IE (5.2.4.26) — RSLN-enabled PAN Descriptor IE (5.2.4.24) — RSLN Relaying Specification IE (5.2.425) — Extended DSME PAN Descriptor IE (5.2.4.9a) — MPDU Fragment Sequence Context Description IE (5.2.4.23) — PHY Parameter Change IE (5.2.4.32) — DSSS Operating Mode Description IE (5.2.430) — FSK Operating Mode Description IE (5.2.4.31) — LECIM DSSS Capabilities IE (5.2.4.29.1) |  | A
60 | Pat Kinney | Kinney Consulting | P2.8 | 120 | 46 | Sentence: "The PHY Parameter Change Notification is described in 5.2.4.x." is missing a cross-reference | Change to: "The PHY Parameter Change Notification is described in 5.2.4.32." |  | A
61 | Pat Kinney | Kinney Consulting | P2.8 | 120 | 49 | Current sentence "The CSN IE may be included…" is confusing since there is no CSN IE. | Replace with "The PHY Parameter Change IE may be included…" |  | A

## Sheet1
3, 4 | 32
5 | 173
6 | 63
8 | 20
9 | 13
19 | 70
D | 3
P | 15