## IEEE_Cover
Aug 2012 |  | 15-12-0450-01-004j
IEEE P802.15
Wireless Personal Area Networks
Project | IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Title | 802.15.4j Letter Ballot Comment Submission
Date Submitted | Aug 06 2012
Source | Raymond Krasinski | Voice: +1 914 333-9687
Philips Electronics
| 345 Scarborough Road, Briarcliff Manor, NY, USA | E-mail: ray.krasinski@gmail.com
| David Evans | Voice: +44 (0) 1293 886490
Philips Electronics
| Cambridge, CB4 0FY, UK | E-mail: david.evans@philips.com
Re: | d2P802-15-4j_Draft_Standard
Abstract | 802.15 TG4j Comments Register for LB82
Purpose | [This document is used to submit comments for TG4j Letter Ballot.]
Notice | This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## All Comments
Name | Affiliation | Category | Page | Sub-clause | Line # | Comment | Proposed Change | Must Be Satisfied? (enter Yes or No) | Resolution
B.Rolfe | BCA | Editorial | 2 | 4.2d | 16 | "operating channel" should be "operating channel and/or band"; "Channel Switch" needs to be "PHY Parameter Change IE" as in Table 4b. "switch channel" s/b "change operating channel and/or band" (to be consistent) and on the last sentence "another channel and/or band"; | See comment
B.Rolfe | BCA | Editorial | 2 | 4.2d | 19 | "vacate the channel" should be "vacate the channel and/or band" | See comment
B.Rolfe | BCA | Editorial | 3 | 5.2.4.23 | 6 | "The IE" s/b "The IE content" | See comment
B.Rolfe | BCA | Editorial | 10 | P.1 | 16 | "MAC frame" s/b "message" | See comment
B.Rolfe | BCA | Editorial | 10 | P.2 | 20 | "the reception of a MAC command frame from the coordinator to inform them that" is better as "notification from the coordinator that". | See comment
B.Rolfe | BCA | Editorial | 10 | P.2 | 22 | "macExtendedAddress" : should not use the name of the PIB attribute as it exists only locally. What I *think* is meant that the device desiring to associate performas a can, receives a beacon, extracts the PAN coordinators extended address from the beacon, and then can direct association to that address. | Change to "MAC extedned address".
Paul Chilton | NXP Semiconductors | Editorial | 3 | 5.2.4.23 | 4 | Incorrect use of "effect" | Change to "affect" | Yes
Paul Chilton | NXP Semiconductors | Technical | 10 | P.1 | 16-25 | The use of PANID and scanning to find the new Coordinator implies that PANIDs are unique across all channels for this procedure to work correctly | Provide guidance that PANIDs must be unique across channels, or provide signalling (eg in beacon payload) that this particular coordinator with the PANID is the one to use as the target for the coordinator switch | Yes
Raymond Krasinski | Philips | Editorial | vi |  | 30 | Liang Li and Ning Li were major contributors and should be included in the list of major contributors | Add Liang Li and Ning Li to the list of major contributors | No

## Preface, Global
ID Number | Name | Affiliation | Category | Page | Sub-clause | Line # | Comment | Proposed Change | Must Be Satisfied? (enter Yes or No) | Resolution
S0-1 | Raymond Krasinski | Philips | Editorial | vi |  | 30 | Liang Li and Ning Li were major contributors and should be included in the list of major contributors | Add Liang Li and Ning Li to the list of major contributors | No | Accept
[9 empty] | Total | 1
[9 empty] | Resolved: | 1
[9 empty] | Remaining: | 0

## Subclause 1-4
ID Number | Name | Affiliation | Category | Page | Sub-clause | Line # | Comment | Proposed Change | Must Be Satisfied? (enter Yes or No) | Resolution
S14-1 | B.Rolfe | BCA | Editorial | 2 | 4.2d | 16 | "operating channel" should be "operating channel and/or band"; "Channel Switch" needs to be "PHY Parameter Change IE" as in Table 4b. "switch channel" s/b "change operating channel and/or band" (to be consistent) and on the last sentence "another channel and/or band"; | See comment |  | Accept
S14-2 | B.Rolfe | BCA | Editorial | 2 | 4.2d | 19 | "vacate the channel" should be "vacate the channel and/or band" | See comment |  | Accept
[9 empty] | Total | 2
[9 empty] | Resolved: | 2
[9 empty] | Remaining: | 0

## Subclause 5
ID Number | Name | Affiliation | Category | Page | Sub-clause | Line # | Comment | Proposed Change | Must Be Satisfied? (enter Yes or No) | Resolution
s5-1 | B.Rolfe | BCA | Editorial | 3 | 5.2.4.23 | 6 | "The IE" s/b "The IE content" | See comment |  | Accept
s5-2 | Paul Chilton | NXP Semiconductors | Editorial | 3 | 5.2.4.23 | 4 | Incorrect use of "effect" | Change to "affect" | Yes | Accept
[9 empty] | Total | 2
[9 empty] | Resolved: | 2
[9 empty] | Remaining: | 0

## Annex, Unallocated
ID Number | Name | Affiliation | Category | Page | Sub-clause | Line # | Comment | Proposed Change | Must Be Satisfied? (enter Yes or No) | Resolution
AU-1 | B.Rolfe | BCA | Editorial | 10 | P.1 | 16 | "MAC frame" s/b "message" | See comment |  | Accept
AU-2 | B.Rolfe | BCA | Editorial | 10 | P.2 | 20 | "the reception of a MAC command frame from the coordinator to inform them that" is better as "notification from the coordinator that". | See comment |  | Accept
AU-3 | B.Rolfe | BCA | Editorial | 10 | P.2 | 22 | "macExtendedAddress" : should not use the name of the PIB attribute as it exists only locally. What I *think* is meant that the device desiring to associate performas a can, receives a beacon, extracts the PAN coordinators extended address from the beacon, and then can direct association to that address. | Change to "MAC extedned address". |  | Accept in Principle. Change should read "MAC extended address"
AU-4 | Paul Chilton | NXP Semiconductors | Technical | 10 | P.1 | 16-25 | The use of PANID and scanning to find the new Coordinator implies that PANIDs are unique across all channels for this procedure to work correctly | Provide guidance that PANIDs must be unique across channels, or provide signalling (eg in beacon payload) that this particular coordinator with the PANID is the one to use as the target for the coordinator switch | Yes | Accept in principle. See document xxx for details
[9 empty] | Total | 4
[9 empty] | Resolved: | 4
[9 empty] | Remaining: | 0