## IEEE_Cover
Sep 2012 |  | P802-15-4k_Consolidated Comments.xls
IEEE P802.15
Wireless Personal Area Networks
Project | IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Title | 802.15.4k Letter Ballot Comment Resolutions
Date Submitted | Thursday,Sep 20, 2012
Source | Pat Kinney | Voice: 847-960-3715
Kinney Consulting
| Lake Zurich, IL 60047 | E-mail: pat.kinney@ieee.org
Re: | d1P802-15-4k_Draft_Standard
Abstract | 802.15 TG4k Comment Resolutions for Letter Ballot
Purpose | [This document is used to submit comments for TG4k Letter Ballot.]
Notice | This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## LB83
CID | Name | Affiliation | Page | Sub-clause | Line # | Comment | Proposed Change | Must Be Satisfied? | A AiP R W
74 | Monique Brown | On Ramp Wireless | 5 | 3.1 | 6 | Check each definition against what's in the IEEE Dictionary to be sure that there are no already existing definitions that we can use. | See comment. | NO | A
1 | Benjamin A. Rolfe | BCA | 5 | 3.1 | 14 | (ID) should be (TID) | restore missing T |  | A
73 | Monique Brown | On Ramp Wireless | 5 | 3.1 | 14 | Acronym should be "TID." | Change acronym. | NO | A
75 | Monique Brown | On Ramp Wireless | 5 | 3.2 | 18 | Make sure that each acronym appears in the text somewhere. | See comment. | NO | A
76 | Monique Brown | On Ramp Wireless | 7 | 4.3.1 | 11 | There is a difference between the one and only "PAN coordinator" and "coordinators." | Change both occurrences to "PAN coordinator." Also in line 13, change from "the endpoint" to "an endpoint." | NO | A
260 | Yong Li | cqupt | 7 | 4.3.1 | 11 | "..asymmetric in energy consumption and capability.." I think "asymmetric in energy consumption" is not good enough to explain the LECIM network. | "energy consumption"change to "energy supply" | YES | A
77 | Monique Brown | On Ramp Wireless | 7 | 4.5.4.1a | 34 | Change text from "When using the critical event priority access in a nonbeacon-enabled PAN" to "When a critical event occurs in a nonbeacon-enabled PAN." | See comment. | NO | A
79 | Monique Brown | On Ramp Wireless | 7 | 4.5.4.1a | 36 | Define the acronym CCA, since it is being used for the first time. | Change to clear channel assessment (CCA). | NO | A
78 | Monique Brown | On Ramp Wireless | 7 | 4.5.4.1a | 40 | Change text from "Beacon-enabled PANs using a critical event priority access dedicate fixed-size CAP time allocations in a superframe for PCA" to "When a critical event occurs in a beacon-enabled PAN, fixed-size CAP time allocations are dedicated in a superframe for PCA." | See comment. | NO | A
244 | Wun-Cheol Jeong | ETRI | 7 | 4.5.4.2 | 49 | Does the "backoff slot durations" mean "backoff periods" used in 15.4-2011? Then, why don't you use the term "backoff periods" for consistency? | See the comments | YES | R | As stated in 4.5.4.2 “The backoff slot length is PHY dependent and should be able to accommodate, at minimum, the transmission of a single MAC protocol data unit (MPDU) fragment.” 802.15.4, (5.1.1.4a) defines, with CSMA-CA, a backoff period to be equal to aUnitBackoffPeriod. This is too short for the above requirement. In order to avoid overloading backoff period in the context of ALOHA, I would opt to use backoff slot. Therefore I would Reject the comment. Otherwise, AiP with comment “With ALOHA the term backoff slot is used, which is equal to macLECIMAlohaUnitBackoffPeriod .”
245 | Wun-Cheol Jeong | ETRI | 7 | 4.5.4.2 | 49 | "PCA allocations of four consecutive … into the superframe." may imply that PCA can be allocated in any part of the superframe. However, the allocation is only limited to the CAP. | Recommend to change the sentence as followings: "PCA allocations of four consecutive backoff slot durations are introduced in the CAP of the superframe." | YES | A
259 | Yong Li | cqupt | 7 | 4.5.4.2 | 49 | "PCA allocations of four consecutive backoff slot durations are introduced into the superframe " Is the length of PCA consistent ? | "four" to " more than four" | YES | A
177 | Shusaku Shimada | Yokogawa Co. | 8 | 4.5.4.2a | 3 | As MPDU fragmentation operates on the complete MPDU and adapts to the specific PHY and PHY operating mode, it is appropriate to summarize the specific PHY and PHY operating modes here. | Append a table of specific PHY and PHY operating modes for ideal clarification. | YES | AiP | fragmentation has been constructed to be applicable to most if not all 802.15.4 PHYs. To resolve the commenter's issue, an example will be added to the informative annex which will be referenced in this description
80 | Monique Brown | On Ramp Wireless | 8 | 4.5.4.2a | 35 | Change wording of the third sentence. | Change the third sentence to read: "It is also possible to acknowledge both the reception and reconstruction of the entire MPDU." | NO | A
81 | Monique Brown | On Ramp Wireless | 8 | 4.5.4.3.2 | 49 | Consider a new title to make it clear that it is not merely received correctly. | As a suggestion, consider MPDU reconstruction ACK or MPDU reassembled ACK. | NO | A
262 | Yong Li | cqupt | 8 | 4.5.4.3.2 | 51 | " report the status " | "repot the result" | NO | AiP | change to report the result
261 | Yong Li | cqupt | 8 | 4.5.4.3.2 | 53 | "The reassembly and validation process may require processing time in the MAC sublayer or higher layers... " The reassembly and validation shall be processed in the MAC sublayer but not higher layers. | delete "or higher layers" | YES | A
82 | Monique Brown | On Ramp Wireless | 9 | 4.5.4.3.2 | 1 | Would you really want to send the ACK on a different channel? The receiving device would have to listen to more than one channel at a time. | I realize there are no "shalls" in the text but remove it anyway. | NO | A
264 | Yong Li | cqupt | 9 | 4.5.4.4 | 8 | "a cell validation sequence (CVS) is included with each fragment". Does "cell" means fragment ? | change "cell validation sequence (cvs)" to "fragment validation sequence(FVS)" or give the defination of the "cell" | YES | A
178 | Shusaku Shimada | Yokogawa Co. | 9 | 4.5.5.3 | 19 | The title read "Low energy extension of networking coverage by synchronous relaying". And the following description looks reasonable, except for the term "synchronous". How the relaying can be implemented is diverse including synchronous, asynchronous, queued, synmetrical path or asynmetrically routed, uni-directional or not, and so on. | Delete "synchrounous". |  | AiP | delete 4.5.5.3
265 | Yong Li | cqupt | 9 | 4.5.5.3 | 22 | change "may be limited to a reduced value" to"is limited to minimum" | see comment | YES | AiP | delete 4.5.5.3
263 | Yong Li |  | 9 | 4..5.5.3 | 23 | “ abundantly powered" replaced by " main powered" | see comment | YES | AiP | delete 4.5.5.3
83 | Monique Brown | On Ramp Wireless | 9 | 4.5.5.3 | 23 | Make end point devices plural in both occurrences within the paragraph. Also change "coordinator" to "PAN coordinator." | See comment. | NO | AiP | delete 4.5.5.3
84 | Monique Brown | On Ramp Wireless | 9 | 4.5.5.3 | 24 | Replace "responsibility" with "capability." | See comment. | NO | AiP | delete 4.5.5.3
86 | Monique Brown | On Ramp Wireless | 11 | 5.1.1.4.5 | 12 | I still think a flow chart should be added along the lines of Figure 11. It makes the new algorithm easier to follow. | Add a flow chart. | NO | AiP | Insert the following paragraph after the first paragraph of 5.1.1.4.5 CSMA-CA with PCA “Figure xx (flowchart as per CID27) illustrates the steps of the CSMA-CA algorithm when a PCA frame is to be transmitted. If the algorithm ends in “Success,” The MAC has successfully transmitted the frame. Otherwise, the algorithm terminates with a channel access failure due to maximum number of retransmissions exceeded.”
85 | Monique Brown | On Ramp Wireless | 11 | 5.1.1.4.5 | 15 | This subclause needs better organization. | See doc 15-12-0482-00-004k for suggested text. | NO | A
26 | Chang Sub Shin | ETRI | 11 | 5.1.1.4.5 | 21 | The value of macMinBE can be set to 0. In such case, BE would be a negative value. | change "the value of macMinBE-1" to "the value of macMinBE" |  | AiP | see CID27
27 | Chang Sub Shin | ETRI | 11 | 5.1.1.4.5 | 22 | The CSMA-CA algorithm of IEEE802.15.4 is non-persistent CSMA. But The PCA follows a persistent CSMA. This is totally different algorithm. Recommend to add more detatiled description or flow-chart. | add flowchart defined in worksheet CID27 flowchart to the draft |  | AiP | see CID86
28 | Chang Sub Shin | ETRI | 11 | 5.1.1.4.5 | 23 | there is no contention window in unslotted CSMA-CA mechanism in IEEE802.15.4. | delete or change contention window |  | AiP | Change paragraph to: "When operating a LECIM PHY in a nonbeacon-enabled PAN using unslotted CSMA-CA, the critical event priority transmission may be initiated at any time. During transmission of a priority message, when the CCA returns a status of channel busy, the alternate backoff mechanism shall be used: the backoff exponent BE shall be set to the value of macMinBE–1 or 1, whichever is higher, prior to the first transmission attempt, and BE shall remain constant for subsequent retransmissions. The PCA follows a persistent CSMA mechanism, where a device continues to monitor the channel and decrements the contention window randomly drawn number of backoff periods any time the channel is sensed idle for a duration of aUnitBackoffPeriod, in order to gain access to the channel as soon as possible."
266 | Yong Li | cqupt | 11 | 5.1.1.4.5 | 24 | replace "as soon as possible" by "timely" | see comment | YES | AiP | change as soon as possible with in a timely manner
267 | Yong Li | cqupt | 11 | 5.1.1.4.5 | 31 | "the MAC personal area network information base (PIB) attributes" no need to use full word | change to "the MAC PIB attributes." | YES | R | acronyms must be spelled out for the first use
268 | Yong Li | cqupt | 11 | 5.1.1.4.5 | 37 | "the macPCAAllocationRate" delete "the" which is before PIB attributes for being coordinated with the others. | see comment | YES | A
149 | Raymond Krasinski | Philips Electronics | 11 | 5.1.1.4.5 | 43 | The words "should be" are too vague | replace with "are" | YES | AiP | delete "The remaining PCA allocations should be distributed throughout the superframe, but no PCA allocation shall occur outside a CAP."
269 | Yong Li | cqupt | 11 | 5.1.1.4.5 | 44 | "but no PCA allocation shall occur outside a CAP " why can not PCA allocation occur in the CFP ? Sometime when the number of critical event messages is large, the slots in the CFP which are not taken up shall be allocated to PCA .It will help to transmit the critical message timely. | discussion | NO | R | PCA describes an alternate CSMA method, which only applies to the CAP (CSMA not used in the CFP), as is clear in the text.
270 | Yong Li | cqupt | 11 | 5.1.1.4.5 | 47 | "When a critical …....the primary CSMA-CA, as defined in 5.1.1.4, with the previously described alternate backoff mechanism shall be used."?? Dose that mean both primary CSMA-CA and alternate backoff mechanism shall be used at this moment? | not sure, change the "with" to "and/or"? | YES | AiP | use "with"
87 | Monique Brown | On Ramp Wireless | 12 | 5.1.1.4a | 27 | Change "When critical event PCA is in use" to "When PCA is in use." | See comment. | NO | A
89 | Monique Brown | On Ramp Wireless | 12 | 5.1.1.4a | 34 | Change from "slotted ALOHA is applied" to "slotted ALOHA _may be_ applied." | See comment. | NO | AiP | delete first sentence in paragraph
90 | Monique Brown | On Ramp Wireless | 12 | 5.1.1.4a | 37 | Use the word "shall." | Change text to "Priority frames _shall_ be transmitted in the CAP portion of the superframe." | NO | AiP | delete last sentence of paragraph
88 | Monique Brown | On Ramp Wireless | 12 | 5.1.1.4a | 39 | Change from "shall be sufficiently long, in order to accommodate..." to "shall be long enough to accommodate..." | See comment. | NO | A
91 | Monique Brown | On Ramp Wireless | 13 | 5.1.1.7.4 | 18 | "Both cases" sounds like you're talking about when macHWSLPeriod is nonzero and when macHWSLMaxPeriod is nonzero. | "Both features" may be better wording. | NO | AiP | change to "These behaviors…"
272 | Yong Li | cqupt | 13 | 5.1.6.1 | 38 | "Transmissions in the CAP shall follow a successful application of the slotted version of the CSMA-CA algorithm", | change to "Transmissions in the CAP shall follow the slotted version of the CSMA-CA algorithm". | YES | R | See CID271
66 | Hyunduk Kang | ETRI | 13 | 5.1.6.1 | 40 | Without providing detailed information on how to optimize the use of the CAP, it is not clear whether the offset will be applied to every transmission in the CAP or just the start of the CAP will be delayed for phyLECIMDSSSPPDUTxAt from the beacon. | If this sentence means that the CAP will start after phyLECIMDSSSPPDUTxAt from the beacon, propose to change "the phyLECIMDSSSPPDUTxAt attribute enables … network." into "the CAP in a beacon-enabled network starts after phyLECIMDSSSPPDUTxAt from the start of the beacon." If not, provides the usage of the phyLECIMDSSSPPDUTxAt attibute with the information on how to optimize the use of the CAP. | YES | AiP | Replace lines 40 - 42 with the following text: When the LECIM DSSS PHY is in use in a beacon-enabled PAN, transmissions after the beacon shall commence phyLECIMDSSSPPDUTxAt modulation symbols following reception of the last symbol of the beacon frame. The determination of an appropriate offset value is out of scope of this standard.
72 | Minho Cheong | ETRI | 13 | 5.1.6.1 | 40 | Without providing detailed information on how to optimize the use of the CAP, it is not clear whether the offset will be applied to every transmission in the CAP or just the start of the CAP will be delayed for phyLECIMDSSSPPDUTxAt from the beacon. | If this sentence means that the CAP will start after phyLECIMDSSSPPDUTxAt from the beacon, propose to change "the phyLECIMDSSSPPDUTxAt attribute enables … network." into "the CAP in a beacon-enabled network starts after phyLECIMDSSSPPDUTxAt from the start of the beacon." If not, provides the usage of the phyLECIMDSSSPPDUTxAt attibute with the information on how to optimize the use of the CAP. | YES | AiP | see CID66
161 | Seong-Soon Joo | ETRI | 13 | 5.1.6.1 | 40 | Without providing detailed information on how to optimize the use of the CAP, it is not clear whether the offset will be applied to every transmission in the CAP or just the start of the CAP will be delayed for phyLECIMDSSSPPDUTxAt from the beacon. | If this sentence means that the CAP will start after phyLECIMDSSSPPDUTxAt from the beacon, propose to change "the phyLECIMDSSSPPDUTxAt attribute enables … network." into "the CAP in a beacon-enabled network starts after phyLECIMDSSSPPDUTxAt from the start of the beacon." If not, provides the usage of the phyLECIMDSSSPPDUTxAt attibute with the information on how to optimize the use of the CAP. | YES | AiP | see CID 66
92 | Monique Brown | On Ramp Wireless | 13 | 5.1.6.1 | 41 | Wording is awkward. Also remove the word "enables." This makes it sound like the PIB attribute turns the feature on. | Change to "the PIB attribute _phyLECIMDSSSPPDUTxAt provides support for_ a mechanism (_outside the scope_ of this standard) to offset the transmission in the CAP _of_ a beacon-enabled network.." | NO | AiP | When the LECIM DSSS PHY is in use in a beacon-enabled PAN, transmissions after the beacon shall commence phyLECIMDSSSPPDUTxAt modulation symbols following reception of the last symbol of the beacon frame. The determination of an appropriate offset value is out of scope of this standard.
273 | Yong Li | cqupt | 13 | 5.1.8a | 49 | "in order to signal one or more peer devices" and"Signaling using periodic beacons"in page 14 line 5 | change "signal"to "notify" | YES | A
93 | Monique Brown | On Ramp Wireless | 13 | 5.1.8a | 50 | Change "operational" parameter to "operating" parameter to match 6.2.22.1. | Make the change here and throughout draft. Do a global search. | NO | A | assigned to technical editor
94 | Monique Brown | On Ramp Wireless | 13 | 5.1.8a | 54 | Change to "outside the scope of this standard" to match wording in baseline standard. | See comment. | NO | A | assigned to technical editor
271 | Yong Li | cqupt | 13 | 5.1.6.1 | 36-37 | "…. either after a search or due to its being tracked.." It's confusing | Clarification change "If the beacon is not found after this time, the device shall transmit the frame following the successful application of the unslotted version of the CSMA-CA algorithm, as described in 5.1.1.4. Once the beacon has been found, either after a search or due to its being tracked, the frame shall be transmitted in the appropriate portion of the superframe." to be "If the beacon is not found after this time, the device attempts to transmit the frame following the successful application of the unslotted version of the CSMA-CA algorithm, as described in 5.1.1.4. However, if the beacon has been found the device attempts to transmit the frame in the appropriate portion of the superframe." | YES | R | TE doesn't find the excerpt confusing, additionally the proposed change removed 2 shalls
44 | Dave Evans | Philips | 14 | 5.1.8a.1 | 11 | The PHY Parameter Change IE is already described in clause 5.2.4.23 of Draft 802.15.4j. | Change "5.2.4.29" to "5.2.4.23" and renumber clauses 5.2.4.23 to 5.2.4.28. Note that Draft 802.15.4j has also used clause number 5.2.4.24, see next three comments. | YES | A
95 | Monique Brown | On Ramp Wireless | 14 | 5.1.8a.1 | 13 | Awkward wording: "The Notification Time field shall be updated with each transmission." | Change to "prior to each transmission." Make same change in 5.1.8a.2. | NO | AiP | The Notification Time field shall be updated each time it is transmitted with the local time of the device.
96 | Monique Brown | On Ramp Wireless | 14 | 5.1.8a.1 | 18 | Specify where the RepeatCount parameter is found. | Change to "If the value of the RepeatCount parameter of the MLME-PHY-OP-SWITCH.request primitive is nonzero..." | NO | A
2 | Benjamin A. Rolfe | BCA | 14 | 5.1.8a.2 | 37 | "...transmitted according 5.1.6…" is missing "to". | see comment |  | AiP | change "5.1.6" to " to 5.1.6.1" and " delete paranthetical
274 | Yong Li | cqupt | 14 | 5.1.10 | 47 | Context in DSME shall be expanded to support fragment and retransmit machanism .how to allocate enough slots for fragments of every nodes while the number of GTS slots is limited? Dose the retransmission of failed framents occur in next CAP or request GTS again? | clarify | YES | AiP | change text as per doc 15-12-517
67 | Hyunduk Kang | ETRI | 14 | 5.1.10.1 | 54 | Why the maximum value of MO should be less than 23? In macExtendedDSMEenabled mode, the restriction on the interval of periodic GTS allocation, which should be witihn the beacon interval, is removed. It may need longer GTS allocation inveral in a certain service. | Define new MAC PIB attribute to specify the maximum value of MO. For supporting the longer GTS allocation, modify the format of the Extended DSME superframe spcecification field. | YES | AiP | see text in 15-12-507
162 | Seong-Soon Joo | ETRI | 14 | 5.1.10.1 | 54 | Why the maximum value of MO should be less than 23? It may need longer GTS allocation inveral in a certain service. In macExtendedDSMEenabled mode, the restriction on the interval of periodic GTS allocation, which should be witihn the beacon interval, is removed. | Define new MAC PIB attribute to specify the maximum value of MO. For supporting the longer GTS allocation, modify the format of the Extended DSME superframe spcecification field. | YES | AiP | see CID67
97 | Monique Brown | On Ramp Wireless | 15 | 5.1.10.1 | 15 | I'm a little confused by the use of the acronym BI. Is this acronym used in 15.4e in the multi-superframe case? Or is it just used when talking about a regular superframe? Or maybe there's no distinction. | Review and possibly replace with "beacon interval." | NO | AiP | BI is not an acronym, it is a variable
99 | Monique Brown | On Ramp Wireless | 15 | 5.1.8a.2 | 26 | Is it "multi-purpose frame" or "multipurpose frame?" | Decide and make consistent. | NO | A | change multi-purpose frame to multipurpose frame
100 | Monique Brown | On Ramp Wireless | 15 | 5.1.8a.2 | 45 | Use the word "shall." | Change to "PHY Parameter Change Notification _shall_ be sent." | NO | A
98 | Monique Brown | On Ramp Wireless | 15 | 5.1.11.3.1 | 53 | Add macLEenabled to the appropriate PIB table. This would be for informational purposes only, since it is defined in 15.4e. | See comment. | NO | R | proposed change is not as per IEEE style guide
29 | Chang Sub Shin | ETRI | 15 | 5.1.10.5.3 | Table 1a | macAllocatonOrder and macBeaconIntervalIndex is not MAC PIB attributes. Those are the elements of the MAC PIB attrubute macDSMEACT. | change "macAllocationOrder" to "Allocation Order". change "macBeaconIntervalIndex" to "BI Index". |  | A
101 | Monique Brown | On Ramp Wireless | 17 | 5.1.11.3.1 | 1 | Text says, "macCSLPeriod and macRITPeriod shall be ignored." Subclause 5.1.11 says these attributes are set to zero. | It seems unnecessary to say essentially the same thing in two places (since one occurrence is in the intro text). | NO | R | 1. 4e MAC defined two LE mode: CSL and RIT, which mode is enabled is defined by whether the macCSLPeriod or macRITPeriod is set to a non-zero value. 2. 4k MAC defined a new LE mode as described in 5.1.11.3.1, as the same time, 4k MAC will compatible with 4e MAC, so defined here, when LE mode enabled (macLEEnabled = TRUE), but macCSLPeriod and macRITPeriod both set to zero (means CSL and RIT both not enabled), then our new LE mode is enabled. 3. if we want to enhance the timely delivery of data from a coordinator to an endpoint device, we can enable the optional HWSL mode. HWSL mode is optional, means a special mode or like a "super" mode, which is different with 5.1.11.3.1, we can enable this mode by macHWSLEnabled, and if this PIB is set TRUE, we can ignore the value of macCSLPeriod and macRITPeriod.
103 | Monique Brown | On Ramp Wireless | 17 | 5.1.11.3.1 | 21 | I see "the coordinator" here and in other places. So is it "the" PAN coordinator or just any coordinator? | Revise the text if necessary. | NO | AiP | text is correct, refers to all coordinators including PAN coordinator
275 | Yong Li | cqupt | 17 | 5.1.11.3.3 | 28 | "If the coordinator has an emergency data frame to send, the transmission of the payload frame shall be preceded with a sequence of HWSL wakeup frames" What is "payload frame"? | delete "of the payload frame" | YES | AiP | change from "If the coordinator has an emergency data frame to send, the transmission of the payload frame shall be preceded with a sequence of HWSL wakeup frames." to "If the coordinator has an emergency data frame to send, the transmission of that frame shall be preceded with a sequence of HWSL wakeup frames.
102 | Monique Brown | On Ramp Wireless | 17 | 5.1.11.3.1 | 47 | Missing article. | Change to "an incoming." | NO | A
104 | Monique Brown | On Ramp Wireless | 18 | 5.1.11.3.1 | 50 | Text says, "include the remaining time of the broadcast data frame transmission." It sounds like the broadcast is in progress. Shouldn't that be "include the time remaining until" the broadcast data frame transmission? | Please clarify. | NO | AiP | change from "time of the broadcast..." to "time until the broadcast…"
105 | Monique Brown | On Ramp Wireless | 18 | 5.1.11.3.1 | 53 | The "shall" applies to both parts of the sentence. Text says: "The endpoint device shall then send a data request...and return to sleep..." | Do you want to force the device to go to sleep? What if the broadcast is about to start? Is the clock accuracy good enough to mandate this? | NO | AiP | change from "coordinator and return to sleep" to "coordinator, it may then go to sleep…"
246 | Wun-Cheol Jeong | ETRI | 19 | 5.1.11.4.1 | 18 | "… after each transmission, …" , transmission of what? The sentence says that device turns on the reciever after transmission, instead of transmitting a RIT data request. Does it mean that the device turns on the receiver after the RIT data request? | Clarify it. |  | AiP | change line 16 to "Compared to RIT, instead of transmitting…"
106 | Monique Brown | On Ramp Wireless | 19 | 5.1.11.4.1 | 19 | Are both macIRITEnabled and macIRITPeriod needed? The results of macIRITEnabled = FALSE and macIRITPeriod = zero seem the same. Look how the definitions are written in Table 52j. | Are both PIB attributes needed? Or can we delete macIRITEnabled? If they are both needed, then rewrite the definitions in a way that makes this obvious. | NO | AiP | change from "I-RIT mode is turned on when PIB attribute macIRITPeriod is non-zero and is turned off when macIRITPeriod is zero. The values of macCSLPeriod (in coordinated sample listening) and macRITPeriod shall be set to zero when the value of macIRITPeriod is non-zero." to The values of macCSLPeriod (in coordinated sample listening) and macRITPeriod shall be set to zero when macIRITenabled is true."
247 | Wun-Cheol Jeong | ETRI | 19 | 5.1.11.4.1 | Figure 34sd | Recommend to delete the "Data Exchange" in the figure. It seems irrelevant to the illustration of I-RIT transmission. | Modify the figure |  | AiP | delete data exchanges and show end device's RX with I-RITperiod
45 | Dave Evans | Philips | 21 | 5.2.4.9a | 1 | Clause number 5.2.4.23 is already being used in Draft 802.15.4j. | In Table 4b change "As defined in 5.2.4.23" as appropriate | YES | A | change to 5.2.4.25
46 | Dave Evans | Philips | 21 | 5.2.4.9a | 1 | Clause number 5.2.4.24 is already being used in Draft 802.15.4j. | In Table 4b change "As defined in 5.2.4.24" as appropriate | YES | A | change to 5.2.4.26
107 | Monique Brown | On Ramp Wireless | 23 | 5.2.4.21a | 12 | This sentence doesn't make sense. Text says, "In that case, the PCA allocations shall occur at the superframes, which sequence number is integer divisible by the macPCAAllocationRate value." | Let me give it a try: "In that case, the PCA allocations shall _only occur within the superframes having sequence numbers that are_ integer divisible by the macPCAAllocationRate value." Is that what was meant? Actually, most of this paragraph could be moved to 5.1.1.4.5 (the functional description) and replaced here by a cross-reference. That seems like a better place for it than in an IE description. | NO | AiP | agree with commenter to place definition in 5.1.1.4.5
47 | Dave Evans | Philips | 23 | 5.2.4.23 | 19 | Clause number 5.2.4.23 is already being used in Draft 802.15.4j. | Renumber clauses 5.2.4.23 to 5.2.4.28. | YES | A | similar to CID 45 and CID46
193 | Tuncer Baykas | Tohoku U. | 23 | 5.2.4.23.3 | 53 | The value of the bit is missing. | Change sentence "… be set to one to indicate.." | YES | A
108 | Monique Brown | On Ramp Wireless | 24 | 5.2.4.23.3 | 8 | Where are macIACKprogressTimeout and macFragTransactionTimeout defined? | They should be in a PIB table. Also are they both needed? | NO | AiP | macFragTransactionTimeout is not needed but macIACKprogressTimeout is needed. In last row of Table 4e delete text following the word "validated". B Rolfe will submit text to be added to the PIB table for macIACKprogressTimeout.
48 | Dave Evans | Philips | 24 | 5.2.4.23 | 38 | Figure 48nf indicates that the Addressing information field contains 7 bits whereas Figure 48ne shows this as only 6 bits. | Either delete the reserved bit (6) in Figure 48nf or amend Figure 48ne. | YES | A | delete reserved bit in Figure 48nf
58 | Donghun Lee | ETRI | 24 | 5.2.4.23.5 | 38 | There is a contradiction between Figure 48ne and Figure 48nf. In Figure 48ne the length of addressing information is sepcified by 6 bits, but the length of addressing information field format in Figure 48nf is 7 bits. | Take off the bit 6th field in Figure 48nf. | YES | A | see CID 48
163 | Seong-Soon Joo | ETRI | 24 | 5.2.4.23.5 | 38 | There is a contradiction between Figure 48ne and Figure 48nf. In Figure 48ne the length of addressing information is sepcified by 6 bits, but the length of addressing information field format in Figure 48nf is 7 bits. | Take off the bit 6th field in Figure 48nf. | YES | A | see CID 48
61 | Ed Callaway | Sunrise Micro Devices | 25 | 5.2.4.23.6 | 1 | What is the purpose of the TID Extension Parameters field? If the intent is to add some type of security to the fragmentation scheme, please don't bother -- the extension just adds complexity without adding significant security. At present, substantially all CVS implementations work by performing the calculation as the packet is received -- when the CVS is received at the end, it is trivial to do the real-time comparison between the received and just-calculated values. If this TID Extension scheme is published, the CVS check will lose its real-time feature, and require post-processing of the received packet, as well as a programmable CVS engine, to start with arbitrary RIVs. Yuck! Besides, you haven't defined how the security algorithm is supposed to handle these changed positions of the CVS -- does it ignore it? These are supposed to be simple, low-power devices! Even assuming that this field is employed as described, determining the values even by brute force will only require a maximum of 2^39 ≈ 550 billion tries to get a valid CVS, which is nothing considering Mallory has until the end of the fragmentation sequence to insert a valid false fragment and screw things up. | Please delete 5.2.4.23.6 and associated references to the TID Extension Parameters field. | YES | R | TID extension is not for security, rather it is to add additional uniqueness for large networks. Additional text in annex Q will explain the rationale for this parameter
109 | Monique Brown | On Ramp Wireless | 25 | 5.2.4.23.6 | 27 | Awkward wording: "the initial remainder in the CRC calculation is other than the default..." | Change to "the initial remainder in the CRC calculation is _not equal to_ the default..." | NO | A
36 | Clint Chaplin | Samsung | 25 | 5.2.4.23.7 | 53 | "elided" Ooh, fancy word. Took me a while to figure out it wasn't a misspelling of "deleted". Unfortunately, "elided" has two meanings, either of which might be correct here; omitted, or joined together. Which is it? Plus, non-native english speakers may have problems with this. | Disambiguate. "Suppressed" is a good word; how about using that consistently throughout? |  | R | elided has been used in previous amendments to 15.4
110 | Monique Brown | On Ramp Wireless | 26 | 5.2.4.23.8 | 1 | Is anything needed here for the DSSS PHY? | See comment. | NO | AiP | The DSSS PHY has no need for this section
49 | Dave Evans | Philips | 26 | 5.2.4.24 | 16 | Clause number 5.2.4.24 is already being used in Draft 802.15.4j. | Renumber clauses 5.2.4.24 to 5.2.4.28. | YES | A | see CID 48
69 | Jung-Hwan Hwang | ETRI | 26 | 5.2.4.24 | 16 | This IE is not referred in the draft. It cannot be found when and how to use this IE. | Provide the uasge of this IE in the draft. | YES | A | add the following text to the end of P.2.3: "The simplifed superframe IE is intended to reduce the amount of communications between the coordinator and end devices. This allows a beacon with the simplified superframe specification IE to be transmitted in a single PPDU when the LECIM DSSS PHY is in use."
111 | Monique Brown | On Ramp Wireless | 26 | 5.2.4.24 | 16 | What is the initial value of the Timestamp field? | See comment. | NO | AiP | add the following text "the initial value is implementation dependent"
164 | Seong-Soon Joo | ETRI | 26 | 5.2.4.24 | 16 | This IE is not referred in the draft. It cannot be found when and how to use this IE. | Provide the uasge of this IE in the draft. | YES | A | see CID 69
59 | Donghun Lee | ETRI | 26 | 5.2.4.24 | 41 | The length of First CFP slot in superframe field is specified by 5 bit long in Figure 48nj. It would be enough with 4bit long field. | Correct the bit assignment of CFP specification field format. | YES | A | change from 5 bits to 4 bits and add the extra bit to reserved section
165 | Seong-Soon Joo | ETRI | 26 | 5.2.4.24 | 41 | The length of First CFP slot in superframe field is specified by 5 bit long in Figure 48nj. It would be enough with 4bit long field. | Correct the bit assignment of CFP specification field format. | YES | A | see CID 59
112 | Monique Brown | On Ramp Wireless | 26 | 5.2.4.24 | 51 | Does the Number of GTS Slots field represent the number of GTSs or is it the number of superframe slots per GTS? BTW, "GTS Slots" stands for "guaranteed time slot slots." I think we are talking about two different types of slots, and this field name is confusing. | I *think* the text should read: "The portion of the superframe defined by the values of the First CFP Slot in Superframe field and the Last CFP Slot in Superframe field is divided equally _by_ the number of _GTSs_ ; the resulting value is stored in the Number of GTS Slots field." Except with a different field name - maybe "Superframe Slots per GTS field?" | NO | A | change field name to "number of GTSs"
70 | Jung-Hwan Hwang | ETRI | 27 | 5.2.4.25 | 1 | This IE is not referred in the draft. It cannot be found when and how to use this IE. | Provide the uasge of this IE in the draft. | YES | A | see CID 69
166 | Seong-Soon Joo | ETRI | 27 | 5.2.4.25 | 1 | This IE is not referred in the draft. It cannot be found when and how to use this IE. | Provide the uasge of this IE in the draft. | YES | A | see CID 70
113 | Monique Brown | On Ramp Wireless | 27 | 5.2.4.25 | 17 | "GTS slot" stands for "Guaranteed Time Slot slot." | Replace "GTS slot" with "GTS." Do a global search in case it occurs elsewhere. | NO | A | tech editor is charged with this action
114 | Monique Brown | On Ramp Wireless | 27 | 5.2.4.25 | 20 | I believe this should say: "If _an address_ has not been allocated, the address list entry for that _GTS_ shall contain the value 0xffff." Instead of "If a slot has not been allocated." | See comment. | NO | AiP | See CID 113 (change all occurances of "GTS slot" to "GTS") and change "If a GTS has not been allocated, the address list entry for that slot shall contain the value 0xffff"
194 | Tuncer Baykas | Tohoku U. | 27 | 5.2.4.26 | Figure 48nl | Whats is the maximum size for LECIM capabilities IE? | Indicate that LECIM Capabilities IEs maximum size. | NO | AiP | Add the following text to 8.1.2.11: "For all bands except the 2.4 GHz band, if the device supports the band, it shall support all channels within the band. For the 2.4 GHz band, a device shall support all the channels from the lowest to the highest channels (inclusive) indicated in the LECIM Capabilities IE." Change the Channels Supported field in figure 48nl to be two fields, each two octets. The first is Lowest 2.4 GHz Channel field, and the second is HIghest 2.4 GHz Channel field. Add appropriate descriptions.For Figure 48nl, channels supported, add "as defined in figure 48nm", also for all bands except for the 2.4 MHz band, the device shall support all the channels in that band.
195 | Tuncer Baykas | Tohoku U. | 28 | 5.2.4.26 | 1 | Some of the bands are missing in Table 4w. | Add 921, 922 as possible supported bands. | YES | AiP | Add bits for 921 and 922
196 | Tuncer Baykas | Tohoku U. | 28 | 5.2.4.26 | 1 | Remove all "MHz"s from Table 4w. In Table 66 "MHz" is removed and the term "band identifier" is introduced. Same should be done in Table 4w. | As in the comment. | YES | A
197 | Tuncer Baykas | Tohoku U. | 28 | 5.2.4.26 | 25 | In Table 4x, It is stated that bit numbers 2-5 indicate the maximum spreading factor, but no explanation is given. | Clarify how bits indicate the spreading factors. | YES | AiP | add cross reference to where it is described (PIB section), modify in accordance with doc 15-12-506-00
198 | Tuncer Baykas | Tohoku U. | 28 | 5.2.4.26 | 25 | In Table 4x, Why is it stated that 0001 is reserved for PPDU sizes, what about 0000? | Indicate that 0000 is reserved as well. | NO | AiP | change to indicate that this is a bit map
199 | Tuncer Baykas | Tohoku U. | 29 | 5.2.4.26 | 1 | In Table 4y, Indicate that Bits 11-15 are reserved | In Table 4y, Indicate that Bits 11-15 are reserved | NO | AiP | see CID200
200 | Tuncer Baykas | Tohoku U. | 29 | 5.2.4.26 | 1 | In Table 4y,there is no mention of spreading, whereas in Table 4x it is stated | Use 3 bits to indicate the maximum SF, such as 000 no SF 001 SF2 010 SF 4 011 SF8 100 SF 16 | NO | AiP | Use 4 bits to describe SF as a bitmap, assign additional 2 bits to indicate which spreading patterns are supported
115 | Monique Brown | On Ramp Wireless | 29 | 5.2.4.26 | 9 | The reference to subclause 19.2.2 appears in almost every row of Table 4y. | Replace the explicit references with a footnote: "Defined in 19.2.2" or something similar. | NO | A
201 | Tuncer Baykas | Tohoku U. | 29 | 5.2.4.26 | 28 | In Figure 48nm, there are bands 0-8, which are not stated in 8.1.2 | Use band identfiers instead of 0-8, also add band identifiers 921,922 | NO | AiP | change figure to use existing terminology, e.g. Band 0 should be Band 168, etc.
3 | Benjamin A. Rolfe | BCA | 29 | 5.2.4.29 | 50 | Figure 48nn: change length of Effective Time of Change and Notification Time fields to 4 octets each. | see comment |  | A
50 | Dave Evans | Philips | 29 | 5.2.4.29 | 50 | The PHY Parameter Change IE is already described in clause 5.2.4.23 of Draft 802.15.4j. | Delete all text for clause 5.2.4.29 | YES | AiP | copy text from 4j and insert editing instructions as to merging 4j and 4k into a single document
4 | Benjamin A. Rolfe | BCA | 30 | 5.2.4.28 | 16 | Table 4aa, operating band: Some people might be confused as it says zero - invalid and it says in the order in table 4w. We mean 1 = first row of 4w, etc…it might be nice to clarify, or maybe just start at zero? | Clarify |  | AiP | see CID 201
192 | Tero Kivinen | AuthenTec | 30 | 5.2.4.29 | 30 | In the Table 4aa the bit numbers 14-15 (2 bits) the values for those 2 bits can contain 8 different values, which would require 3 bits instead of only 2. | Extend the bit field from 2 bits to 3 bits, and renumber following bit fields accordingly | YES | A
202 | Tuncer Baykas | Tohoku U. | 30 | 5.2.4.27 | 37 | Explanation for bits 16-18 is inadequate. In table 68l there are only 2 Channel Spacing values 0.1 MHz and 0.2 MHz. Why are 3 bits needed to indicate those values? | Reduce the number of bits for channel spacing. | NO | A
30 | Chang Sub Shin | ETRI | 33 | 5.3.11.2 | 3 | The end device and/or the coordinator may reallocate the DSME-GTS after the association procedure. Or, they may request for additional allocation during the PAN operation. They may use the existing DSME-GTS management procedure, but it may be more effienct to define new management type, especially for the star-configuration such as LECIM network. | add the new DSME-GTS management type or new command for slot allocation in extended DSME mode. |  | R | current technique is adequate, enhancements can be added later
248 | Wun-Cheol Jeong | ETRI | 33 | 5.3.11.2.2 | 38 | Association Type of 1 is set for devices which wish to get DSME-GTS during association. All devices that join the PAN as a child don't necessary use this association type. Correct the description. | Change the sentence "The DSME Assocation Type fild shall be set to one … as a child." with the following one "The DSME Assocation Type fild shall be set to one if a device wishes to be assinged DSME-GTS by a coordinator during association." | YES | A
116 | Monique Brown | On Ramp Wireless | 33 | 5.3.11.2.2 | 40 | Don't use the term "child." | Say something like it associated directly with the coordinator. Is this supposed to be the PAN coordinator? | NO | AiP | see CID248
249 | Wun-Cheol Jeong | ETRI | 33 | 5.3.11.2.5 | 46 | Extended DSME-GTS Allocation is used only for the device with DSME Association Type of 1. Correct the sentence. | Change the sentence "The Extended DSME GTS Allocation field shall be present .. TRUE." with the following one "The Extended DSME GTS Allocation field shall be present if macExtendedDSMEenabled is TRUE and the value of DSME Assocation Type is one." | YES | A
250 | Wun-Cheol Jeong | ETRI | 33 | 5.3.11.2.5 |  | The role of Hopping Sequence Request field is redundant. Remove the field in Figure 59gb, and the paragraph in line 7-8 on page 34. | See the comments | YES | AiP | as per text in 15-12-507
117 | Monique Brown | On Ramp Wireless | 34 | 5.3.11.2.5 | 2 | Awkward wording. Text says: "The Direction field indicates whether the DSME-GTSs are being allocated for TX (data transmission) or for RX (data reception) of the requesting device." | Please clarify. | NO | AiP | Change text to "The Direction field specifies the direction of the DSME-GTSs, which is relative to the data flow from the requesting device. The direction is specified as either transmit or receive." In the last two sentences, replace "TX" with "transmission" and "RX" with "reception."
252 | Wun-Cheol Jeong | ETRI | 34 | 5.3.11.3.6 | 31 | The sub-clause describes the relationship between allocation order and allocation interval assuming that MO>BO. Thus, it is not correct in other case. Please correct the description. | See the comments | YES | AiP | see text in 15-12-507
118 | Monique Brown | On Ramp Wireless | 34 | 5.3.11.3.7 | 43 | It seems strange to index the beacon intervals. I think of the BI as a single, constant thing. | Why not index the beacons themselves? | NO | AiP | modify text for clarity, see 15-12-507
31 | Chang Sub Shin | ETRI | 34 | 5.3.11.3.7 | 46 | When a device associates with the PAN, how does it know the value of current BIIndex? Add the description for tracking the current BIIndex. | add : current BI Index = current PANCoordBSN % 2^(MO-BO) |  | AiP | additional text may be found in 15-12-507-00
251 | Wun-Cheol Jeong | ETRI | 34 | 5.3.11.3 | Throughout the sub-clause | The fields (Allocation Order, BI Index, Superframe ID, Slot ID, Channel Index) in the DSME-Association response command are present only if DSME Association Type is one. Add the descriptions in the corresponding sub-clauses. | See the comments | YES | AiP | additional text may be found in 15-12-507-00
119 | Monique Brown | On Ramp Wireless | 35 | 5.3.11.3.9 | 4 | What does this mean? "The slot ID is the sequence number of the DSME-GTS (not including beacon or CAP slots) in a superframe beginning from zero." Does it mean that all of the superframe slots within the CFP are numbered starting from zero? What is a "sequence number" of a GTS? Is this the superframe slot number of the start of the GTS? | Explain what is meant by "sequence number." Also, it is confusing mixing the two meanings of slots: superframe slot and guaranteed time slot. Please reword this paragraph to be more clear. | NO | AiP | delete "(not including beacon or CAP slots)"
62 | Ed Callaway | Sunrise Micro Devices | 35 | 5.3.12.2 | 23 | "Support for this command is optional. When HWSL is supported, coordinators shall be capable of sending this command, and all endpoint devices shall be capable of receiving this command." Um, no: One specifies device behavior, not network behavior. It is up to the standard-writer to specify what happens when, say, a non-HWSL device tries to join a network using HWSL. One must also define what it means to say, "when HWSL is supported." Supported by what? The PAN coordinator? What if it's supported, but not used at the moment? | Start with, "Implementation of this command is optional. When this command is implemented in a coordinator, it shall be capable of sending and receiving this command. When this command is implemented in an endpoint device, it shall be capable of receiving this command." (I think you'll want coordinators to have the ability to sleep, too.) How a coordinator determines that some, all, or none of the devices within range have HWSL implemented is an exercise for the proponent of this feature. | NO | AiP | description in line 23 is not clear, change to: "Implementation of this command is optional. When HWSL is supported, coordinators shall be capable of sending HWSL wakeup command, and endpoint devices shall be capable of receiving HWSL wakeup command."
276 | Yong Li | cqupt | 36 | 5.4 | 21 | Devices that support the LECIM DSSS PHY shall support MPDU fragmentation" | change "shall" to "should" | YES | R | DSSS is written in a manner that requires fragmentation
121 | Monique Brown | On Ramp Wireless | 36 | 5.4.1 | 32 | The title says, "MPDU PHY adaptation, fragmentation and reassembly." What is meant by "MPDU PHY adaptation?" | Review the title. Consider taking out "PHY adaptation." | NO | A
51 | Dave Evans | Philips | 36 | 5.4.1.1 | 35 | Clause number 5.2.4.23 is already being used in Draft 802.15.4j. | See preceeding comments | YES | A
5 | Benjamin A. Rolfe | BCA | 36 | 5.4.4.1 | 37 | The end of the sentence "such a frame shall contain exactly one IE" might mean a fragment context frame can contain only one IE which isn't true. The intent is that a context frame contains exaclty one MPDU Fragment Sequence Context Description IE | A fragment context frame is any directed MAC command or data frame which contains exactly one MPDU Fragment Sequence Context Description IE. |  | A
120 | Monique Brown | On Ramp Wireless | 36 | 5.4.1 | 48 | Text says: "If a fragment is not received when expected, the fragmentation transaction shall be terminated." What is "when expected?" | Be a little more specific about what needs to happen (acks, retransmissions, etc.). | NO | AiP | delete "If a fragment is not received when expected, the fragmentation transaction shall be terminated."
60 | Donghun Lee | ETRI | 36 | 5.4.1.1 | 48 | With just provided text, it is hard to understand how to know that there is a fragment expected to be received. | Provide the details on how to know that there is a fragment expected to be received. | YES | AiP | see CID 120
167 | Seong-Soon Joo | ETRI | 36 | 5.4.1.1 | 48 | With just provided text, it is hard to understand how to know that there is a fragment expected to be received. | Provide the details on how to know that there is a fragment expected to be received. | YES | AiP | see CID 120
71 | Jung-Hwan Hwang | ETRI | 36 | 5.4.1.1 | 52 | The case of TID field value of zero in the context description frame is provided in this subcluase, but it is not specified in 5.2.4.23.1 TID field. | Add the description on the TID field value of zero case. | YES | AiP | add text to cover case of TID field value
168 | Seong-Soon Joo | ETRI | 36 | 5.4.1.1 | 52 | The case of TID field value of zero in the context description frame is provided in this subcluase, but it is not specified in 5.2.4.23.1 TID field. | Add the description on the TID field value of zero case. | YES | AiP | add text to cover case of TID field value
277 | Yong Li |  | 36 | 5.4 | 24-26 | "the completed MPDU is processed into a sequence of fragments. The context of the fragment sequence is established between the initiating device and the recipient device prior to transmission." | How about "the MPDU is processed into a sequence of fragments.The context of the fragment sequence is established by transmitting a fragment context frame between the initiating device and the recipient device prior to transmission." | NO | A
6 | Benjamin A. Rolfe | BCA | 37 | 5.4.1.2 | 6 | With aMaxPHYPacketSize defined as 2047 for LECIM PHYs, then the maximum MSDU size is larger than will fit into 32 fragments for all the PPDU sizes defined. | Either we need 2 more bits or tweak the specification of maximum MSDU size slightly,. |  | AiP | add text to Table 70: "LECIM FSK PHYs. For LECIM DSSS PHYs this is not a constant, refer to phyLECIMDSSSPSDUSize"
55 | David A. Howard | On-Ramp Wireless, Inc. | 37 | 5.4.1.2 | 8 | Fragment number field is 5bits, when we had agreed to have 6 bits | Change fragment number field to 6 bits, and reserve one of the values (perhaps 0) to indicate 'extention', and remove extention field | YES | A
63 | Ed Callaway | Sunrise Micro Devices | 37 | 5.4.1.3 | 35 | With the possible exception of 5.2.4.23.6 (which I discount in another comment, since it is so easily cracked), did I miss any consideration for the simple denial-of-service attack that this fragmentation scheme enables? Since any MIC for the transaction is sent only with the last fragment, the receiving device can only determine the authenticity of the received fragments after all fragments have been received and the frame is reassembled. There are no means for authenticating individual fragments. This means that Malodorous, Malevolent Mallory could easily generate one or more false fragments and, due to the nature of the CSMA-CA algorithm, send them to the receiving device. When the MIC test fails, the receiving device would not be able to determine which of the fragments he received was the malevolent one (or even that the security problem wasn't a key mismatch or some other, more mundane, issue), and so would have no choice but to ask the sending device to restart the entire transaction. This "amplification" of a single malevolent frame to corrupt a long series of frames in a transaction would be almost irresistable for Mallory -- especially since none of the usual high-power jamming techniques would be required. His signal, in fact, could be weaker than the authentic sending device, as long as he started transmission of his faux-frame before the authentic sending device did, and captured the channel. | I think there is no alternative but to perform a full security protocol on each fragment, just as if they were individual frames. To do otherwise would make all of the existing security worthless. | YES | R | the additional complexity is not justified since denial of service attacks are possible for frames as well.
278 | Yong Li | cqupt | 37 | 5.4.1.3 | 35 | It need at least 8 fragments to transform a MPDU successfully when fragment size is 16 octets and the MPDU size is 127 octets , Is it too much? give a limitation to the number ( 5?) of fragments . | see comments | YES | AiP | see CID55
7 | Benjamin A. Rolfe | BCA | 37 | 5.4.1.3 | 52 | Cross reference would be more helpful if it pointed at 5.2.4.23.2. (where the I-ACK policy values are given) | see comment |  | AiP | use correct, IE numbers have been change via other Comments
122 | Monique Brown | On Ramp Wireless | 38 | 5.4.1.3 | 1 | Text says: "Retransmit the cell preceding the I-ACK if the acknowledge is not received..." Depending on the I-ACK policy in use, it may not be enough to just retransmit that one cell. I'm assuming that "cell" means "fragment." | Please replace the word "cell" in both places in step g) with something more commonly used. Also, rewrite step g) such that it makes sense with all I-ACK policy options. | NO | AiP | see CID254
64 | Ed Callaway | Sunrise Micro Devices | 38 | 5.4.1.3 | 6 | I could see how Figure 59ddb could be misinterpreted by a sufficiently myopic individual. Could the text explicitly state the order in which fragments are to be transmitted? | "Fragments shall be transmitted in the order shown in Figure 59ddb, beginning with the Fragment Context Frame, then Fragment 1 and ending with Fragment n." | NO | AiP | Delete Figure 59ddb and replace "Fragments shall be transmitted in the order shown in Figure 59ddb" with: "Fragments shall be transmitted after the Fragment Context Frame, beginning with Fragment 1 and ending with Fragment n."
123 | Monique Brown | On Ramp Wireless | 38 | 5.4.1.3 | 10 | I don't understand what is being shown at the top of Figure 59ddb. The FCF (fragment footer) appears at the start of it, and the FCS appears at the end. It doesn't appear to be a type of frame. I don't see the MPDU Fragment Sequence Context Description IE as part of the Fragment Context Frame. Also, the FCS length is shown as "text." | Please clarify what is being shown. If it is not meant to be a frame, then change the way it is presented. | NO | AiP | see CID64
203 | Tuncer Baykas | Tohoku U. | 38 | 5.4.1.3 | 10 | Black and white figures are easier to read than grayscale ones. | Convert all grayscale figures to black and white ones. | NO | R | greyscale is allowed as per IEEE style guide
204 | Tuncer Baykas | Tohoku U. | 38 | 5.4.1.3 | 10 | The "ooo" is the Figure is misleading | Change it with thre dots | NO | AiP | see CID64
205 | Tuncer Baykas | Tohoku U. | 38 | 5.4.1.3 | 10 | "Text" is not a valid length indicator | Change "text" to "variable" | YES | AiP | see CID 64
9 | Benjamin A. Rolfe | BCA | 38 | 5.4.1.3 | 35 | "When the fragment context frame is received with the AR field set," but we already said the fragment context frame is always sent with the AR field set so this might be ambiguous? | Conslut WGTE for ruling |  | AiP | Delete: "When the fragment context frame is received with the AR field set, the receiving device shall generate an enhanced acknowledgment, as described in 5.2.2.3, if it is able to receive the fragment sequence. The initiating device shall proceed with the fragment sequence after a positive acknowledgment, and will not proceed if a negative acknowledgement is received. Retransmissions, if enabled, shall be performed according to 5.1.6.4."
124 | Monique Brown | On Ramp Wireless | 38 | 5.4.1.3 | 35 | The information contained in the paragraph beginning with "When the fragment context frame is received with the AR field set..." is related to the information contained in the second paragraph of 5.4.1.1. The text would read better if this information was contained in one place. | Move the information from lines 35-39 to 5.4.1.1. | NO | A
8 | Benjamin A. Rolfe | BCA | 38 | 5.4.1.3 | 38 | We make reference to using the enhancd acknowledgement and a "negative" acknowledgement but do not describe what or when a NACK is generated. | Complete the thought (when/why/how a device negatively acks the context setup) or abondon it completely. |  | AiP | abandon it
125 | Monique Brown | On Ramp Wireless | 38 | 5.4.1.3 | 39 | Make the reference to the retransmission text more specific. | Change from 5.1.6.4 to 5.1.6.4.3. | NO | A
126 | Monique Brown | On Ramp Wireless | 38 | 5.4.1.4 | 47 | Make the reference to the ack text more specific. | Change from 5.1.6 to 5.1.6.4.2. | NO | A
127 | Monique Brown | On Ramp Wireless | 38 | 5.4.2 | 53 | The text says, "In each acknowledgment level, the status of individual fragments is indicated and the initiating device shall retransmit only those fragments that were not received and validated." | Is the status of individual fragments given in the ack of the reassembled MPDU? How is it done? Also, if this information is already sent in the I-ACK(s), then do you need to send it again? Maybe this is for I-ACK policy 2. It looks like an I-ACK may never be sent with policy 2, right? | NO | AiP | delete: "In each acknowledgment level, the status of individual fragments is indicated and the initiating device shall retransmit only those fragments that were not received and validated."
128 | Monique Brown | On Ramp Wireless | 39 | 5.4.2.1.1 | 24 | Will a receive device ACK a fragment if it is received out of order (say for policy 1)? | See comment. | NO | AiP | fragments are always sent in order, so out-of-order shouldn't occur when acking every fragment (Ack policy 1); add text to the end of 5.4.2.1.2 "when ACK policy 1 is in use, reception of an out of order fragment shall result in termination of the transaction."
253 | Wun-Cheol Jeong | ETRI | 39 | 5.4.2.1.1 | 32 | In Figure 59ddd, the name of the subfild "Fragment Status" is the same as its field name. Recommend to use different name. | See the comments |  | AiP | change field name to "fragments received"
129 | Monique Brown | On Ramp Wireless | 39 | 5.4.2.1.1 | 50 | Looking at the Fragment Status field, it appears that we limiting the number of fragments to 32. Is that enough? | See comment. | NO | AiP | see CID55
65 | Ed Callaway | Sunrise Micro Devices | 40 | 5.4.2.1.2 | 23 | You may wish to explicitly state the similarity between the enhanced ACK (5.1.6.4.2) and the I-ACK, including the fact that additional time beyond aTurnaroundTime will likely be needed to start its transmission. | Make it so. Or not. | NO | AiP | we choose "or not"
130 | Monique Brown | On Ramp Wireless | 40 | 5.4.2.1.2 | 23 | It makes more sense to give the overview as the first I-ACK subclause. There is nothing mentioned in the overview from the format subclause. | Move the I-ACK Overview subclause before the I-ACK format clause. | NO | A
131 | Monique Brown | On Ramp Wireless | 40 | 5.4.2.1.2 | 28 | Text says: "If an I-ACK is not received when expected..." | Be a little more specific about what needs to happen. What does "when expected" mean? | NO | AiP | see CID 120 for similar text
10 | Benjamin A. Rolfe | BCA | 40 | 5.4.2.1.2 | 32 | We need a link to Table 4e in the IACK overview, so the reader can find where the IACK policies are devined. Alternately it might be better to move the IACK policy description here and xref from 5.2.4.23.2. Either will do - suggest TE can decide. | see comment |  | AiP | TE to decide
132 | Monique Brown | On Ramp Wireless | 41 | 6.2 | 6 | The editing instruction is not entirely true. The paragraph is unchanged, but the table is not. | Modify editing instruction to be correct. | NO | A
32 | Chang Sub Shin | ETRI | 42 | 6.2.2.3 | 34 | The parameter of "Allocation Order" needs to be added. | add "Allocation Order". Also, modify the Table 11. |  | AiP | text can be found in 15-12-507-00
254 | Wun-Cheol Jeong | ETRI | 42 | 6.2.2.3 | 34 | The parameter "AllocationOrder" is missing in the MLME-ASSOCIATE.response primitive. | Add the parameter in the primitive and the description in Table 11. | YES | AiP | text can be found in 15-12-507-00
33 | Chang Sub Shin | ETRI | 43 | 6.2.2.4 | 21 | The parameter of "Allocation Order" needs to be added. | add "Allocation Order". Also, modify the Table 12. |  | AiP | text can be found in 15-12-507-00
11 | Benjamin A. Rolfe | BCA | 45 | 6.2.22.2 | 17 | Table 44aa: Change range of target time to 0 - 2**32-1 both here and in table 44cc | see comment |  | A
12 | Benjamin A. Rolfe | BCA | 46 | 6.2.22.3 | 23 | "PHY Parameter IE" should be "Operating Mode Description IE" | see comment |  | A
13 | Benjamin A. Rolfe | BCA | 46 | 6.2.22.3 | 25 | There is no "Target Time" field in the referenced IE. | Change "Target Time" to "The Effective Time of Change" |  | A
34 | Chang Sub Shin | ETRI | 47 | 6.3.1 | 41 | It seems that "PCAFrame" works the same as "CriticalEventMessage".Are they different? If not, recommend to merge them. Furthermore, the function of those paremeters seem to be done via TxOption parameter. How about merge them into TxOption bit field? | add additional bit field of TxOption parameter for event message or PCAFrame. |  | AiP | delete PCAframe
14 | Benjamin A. Rolfe | BCA | 48 | 6.3.1 | 5 | Table 46: IACKPolicy is given as an enumeration but the range doesn't match the type. | Either we call it an integer (range 1-4) or we give each policy a name and add the names to table 4e. |  | AiP | call it an integer (range 1-4)
133 | Monique Brown | On Ramp Wireless | 48 | 6.3.1 | 5 | What if the device doesn't use fragmentation/I-ACKs? What would this parameter value be? | See comment. | NO | AiP | add text stating "only used when MPDU fragmentation is enabled
15 | Benjamin A. Rolfe | BCA | 48 | 6.3.2 | 39 | "PCA_PARAMETER_ERROR" isn't really different from "INVALID_PARAMETER" is it? | Use INVALID_PARAMETER. |  | A
206 | Tuncer Baykas | Tohoku U. | 49 | 6.4.2 | 31 | Typo "this description" | Change it to "those descriptions" | NO | AiP | editor instructions are inappropriate for the WG
134 | Monique Brown | On Ramp Wireless | 49 | 6.4.2 | 32 | The NOTE should be underlined, since this is added text. | See comment. | NO | A
16 | Benjamin A. Rolfe | BCA | 50 | 6.4.2 | 13 | Table 52: we have a default for macMPDUFragPadValue of "Dependent oncurrently selected PHY" but haven't specified what it is in the PHY clauses. | Specify what the default is, or specify that it is PHY implementation dependent. |  | AiP | change to PHY implementation dependent
179 | Shusaku Shimada | Yokogawa Co. | 52 | 6.4.32.4 | 5 | Table 52f MAC PIB attributes for Hopping Sequence is changed like as each hopping sequence doesn't have to have an unique ID as long as ID is unique. The relevance of this change with LECIM amendment is not clear and questionable. | Clarify the relevance and/or clear description may be appropriate. |  | R | it is acceptable to modify the standard of which this amendment applies
135 | Monique Brown | On Ramp Wireless | 52 | 6.4.3.6 | 19 | The default value of macChannelDiversityMode is missing. | Add the default value. | NO | AiP | TE to clarify
17 | Benjamin A. Rolfe | BCA | 52 | 6.4.3.6 | 24 | Only the range for macMultisuperframeOrder is changed, the default value is not being changed. | un-underline default. |  | A
35 | Chang Sub Shin | ETRI | 52 | 6.4.3.6 | Table 52h | "macBeaconIntervalIndex" is named as "macBIIndex" in someplaces. For consistency, change "macBeaconIntervalIndex" to "macBIIndex" | See the comment. |  | AiP | see text in 15-12-507
255 | Wun-Cheol Jeong | ETRI | 52 | 6.4.3.6 | Table 52h | The value of macAllocationOrder should be zero when MO is not larger than BO. Correct the description of the attribute macAllocationOrder. | Add the following sentence at the end of the description for macAllocationOrder: "If MO≤BO, the value of macAllocationOrder shall be set to zero." | YES | A
256 | Wun-Cheol Jeong | ETRI | 52 | 6.4.3.6 | Table 52h | PIB attribute macAssociationType is needed. | Add the DSME-specific MAC PIB attribute to the table. | YES | AiP | text as per doc 15-12-507-00
257 | Wun-Cheol Jeong | ETRI | 52 | 6.4.3.6 | Table 52i | The element AssociationType is needed. | Add the element to the table. | YES | AiP | text as per doc 15-12-507-00
18 | Benjamin A. Rolfe | BCA | 53 | 6.4.3.7 | 5 | The name "macLowEnergySuperframeSupported" is a bit misleading given the description, which suggests that the attribute controls if the feature is enabled. | macLowEnergySuperframeEnabled seems more appropriate |  | R | term is used in 4e
150 | Raymond Krasinski | Philips Electronics | 55 | 8.1.1 | 19 | The editing instruction indicates the new rows are to be added at the end of the table. It may make more sense to add into the table in order by band identifier (even though the direction is consistent with what 4g has done) | Change editing direction to add new rows in order by Band identifier, if this is what is intended | NO | AiP | editing notes are left up to the editor
207 | Tuncer Baykas | Tohoku U. | 55 | 8.1.1 | Table 66 | There is no specific rule about how ot select band identifiers. | Use the starting frequency as band identifier | NO | AiP | As there is no group consensus on any change to these identifiers, they will be left as is; however change the 915 band entry to include all DSSS modulation rates as defined in Table 71 i.e. 200, 400, 600, 800, 1000; and then remove DSSS entries from the 917 and 920 band IDs
208 | Tuncer Baykas | Tohoku U. | 56 | 8.1.2.1 | 52 | No need for the editorial note about 802.15.4g | Remove sentence. | NO | R | editorial notes are owned by the Tech Editor
185 | Steve Jillings | Semtech | 57 | 8.1.2.11.1 | 1 | It would be desirable if the tables indicating channel numbering for both DSSS and FSK LECIM PHYs offered commonality | I fear a deja-vu moment from San Diego, but this should be possible | NO | R | there is no consensus on such a change
151 | Raymond Krasinski | Philips Electronics | 57 | 8.1.2.11 | 26 | Clause number 8.1.2.11 is already being used in Draft 802.15.4j. | Change clause number to 8.1.2.12 and update editorial diretion on line 24 accordingly | YES | AiP | Tech editor to change as appropriate
152 | Raymond Krasinski | Philips Electronics | 57 | 8.1.2.11 | 28 | The channel page number should be written out in words in order to be consistent with other, similar clauses | Change "12" to "twelve" | YES | R | current text conforms to syle guide
153 | Raymond Krasinski | Philips Electronics | 57 | 8.1.2.11.1 | 30 | Clause number 8.1.2.11 is already being used in Draft 802.15.4j. | Change clause number to 8.1.2.12.1 | YES | AiP | Tech editor to change as appropriate
209 | Tuncer Baykas | Tohoku U. | 57 | 8.1.2.11.1 | 32 | First sentence needs editorial improvement. | Change it to: "When phyCurrentLECIMPHYType is set to DSSS, the channel plan is described in this sub-clause" | NO | AiP | Tech editor to change as appropriate
184 | Steve Jillings | Semtech | 57 | 8.1.2.11.1 | 36 | Start "For band identifier 169…" as a new paragraph | Make it so | NO | AiP | for page 58, line 36; make sentence new paragraph and change "1" to "one".
211 | Tuncer Baykas | Tohoku U. | 57 | 8.1.2.11.1 | 42 | "N" should be italic. | Change "N" to italic | NO | A
210 | Tuncer Baykas | Tohoku U. | 57 | 8.1.2.11.1 | 45 | No need to indicate "Not all designated channels are available" | Remove sentence or repeat it in 8.1.2.11.2 | NO | AiP | remove sentence
183 | Steve Jillings | Semtech | 57 | 8.1.2.11.1 | 51 | Three exceptions to LECIM DSSS PHY channel numbering in the 868 - 870 MHz band are split by Table 68l | Move line 51 - 54 to after Table 68l in page 58 at line 21 | NO | AiP | TE to ensure that the bullets of this paragraph are kept together
158 | Schwoerer | France Telecom | 57 | 8.1.2.11.1 | 51-54 & fig. 68l | fig 68l specify 69 or 34 channel in the 863-868 MHz band when line 51-54 specify only 3 channels between 868,3 and 869,525 MHz. This is unclear and contradictory. | Remove line 51-54 and let figure 68l define 68 or 34 channels as on the 863-870 MHz band | YES | A
160 | Schwoerer | France Telecom | 57 | 8.1.2.11.1 | 51-54 & fig. 68l | Line 51-54 define only 3 channels (100 kHz each) in the 863-870 MHz when the 863-870 MHz would allow 7 MHz, | Take benefit of the whole 863-870 MHz band, as the FSK PHY do, by defining a band plan that would make use of whole band (69 100 kHz channels) | YES | A | see CID158
159 | Schwoerer | France Telecom | 57 | 8.1.2.11.1 | fig 68l | Fig 68l stand in the middle of the 868 MHz channel list | Move it after the 868 MHz channel list | NO | AiP | see CID183
215 | Tuncer Baykas | Tohoku U. | 58 | 8.1.2.11.2 | 31 | This subcluse uses different editorial style than the previous one. | Change the paragraph after the equation as follows: "where ChanSpacing is the separation between adjacent channels in MHz (phyChannelSpacing), phyCurrentChannel is the current channel number occurring in the range of 0 to TotalNumChan–1, TotalNumChan is the total number of channels for the available frequency band, ChanCenterFreq0 is the first channel center frequency of the band in use (phyLECIMCurrentBand) in MHz. Parameters TotalNumChan and ChanCenterFreq0 for different frequency bands and channel spacings are specified in Table 68m and Table 68n. For band identifier 169, ChanCenterFreq0 shall be 169.4375 MHz and TotalNumChan shall be 1." | NO | AiP | TE to modify text as appropriate
186 | Steve Jillings | Semtech | 58 | 8.1.2.11.2 | 41 | Table 68m. Columns sorted by ChanCenterFreq0 (RH column rather than Band Identifier (LH Column) | Sort by Band Identifier | NO | A
212 | Tuncer Baykas | Tohoku U. | 58 | 8.1.2.11.1 | Table 68l | Use Band indentifiers instead of Frequency bands in the Figure | As stated. | NO | A
213 | Tuncer Baykas | Tohoku U. | 58 | 8.1.2.11.1 | Table 68l | In table 66 it is stated frequency range whereas here frequency band | choose one of those terms | NO | A
214 | Tuncer Baykas | Tohoku U. | 58 | 8.1.2.11.1 | Table 68l | Add 920-928 band | As stated | YES | R | 920-928 is included in the 915 band (902-928)
187 | Steve Jillings | Semtech | 59 | 8.1.2.11.2 | 12 | Table 68n. Columns sorted by ChanCenterFreq0 (RH column rather than Band Identifier (LH Column) | Sort by Band Identifier | NO | A
216 | Tuncer Baykas | Tohoku U. | 61 | 9.2 | 5 | There are rows added by 4g to this table, 4k does not remove does entries. | Add editorial note,Table 70 (the entire table is not shown) as indicated. | NO | A
188 | Steve Jillings | Semtech | 61 | 9.2 | 13 | aMaxPHYPacketSize = 2047 octets for a LOW-ENERGY PHY? | Restrict PSDU length to 127 octets | YES | AiP | Insert the following text at the end of P.1.3.2: The maximum PPDU size that a LECIM PHY shall be able to receive is 2047 octets. To facilitate the multi-year battery life operation expected for envisaged LECIM applications and given the low OTA chip rate provisioned by the PHY in terms of allowable spreading factor (215 chips per symbol for the DSSS PHY and 24 chips per symbol in the case of the FSK PHY) it is recommended that small PPDU frame sizes are used. As an example, the on-air time for an un-fragmented 2047 octet frame at a symbol rate of 12.5 kb/s will require a minimum of 1.3 seconds total air time to be transmitted or received. If the same frame has a spreading factor of 8 applied to each symbol the over the OTA broadcast time will exceed 10 seconds. This increase in transmission and reception time will have a significant impact upon the battery longevity of a LECIM device, even allowing for low duty cycle operation. It should also be noted that the increased transmission time may lead to regulatory duty cycle limitations, especially for the case of network coordinator.
279 | Yong Li | cqupt | 61 | 9.2 | 13 | The rate of LECIM PHYs is lower then 40kbps, that means it will take much long time to transmitting 2047 octets, now that the 4k support the MPDU fragmentation,why does the aMaxPHYPacketSize must be up to 2047 octets? | clearify the condition under which demand so large packet size | YES | AiP | see CID 188
56 | David A. Howard | On-Ramp Wireless, Inc. | 61 | 9.3 | 36 | Missing option for 'tail-biting' convolutional encoder | Add PIB attribute to support 'tail-biting' convolutional encoder. | NO | AiP | delete "The convolutional encoder is the same as specified in 18.3.2.6." and insert text from document 15-12-0526-00-004k
68 | Hyunduk Kang | ETRI | 62 | 9.3 | 5 | The maximum value of phyLECIMDSSSPPDUTxAt attribute will result the offset longer than the longest beacon interval (BO=14). | In order to make the offset witihin the superframe duration, It needs to redescribe the maximum value of phyLECIMDSSSPPDUTxAt attribute with the function of BO, SO, and GTS. | YES | R | even though it is possible to select values that don't work, this value is workable
169 | Seong-Soon Joo | ETRI | 62 | 9.3 | 5 | The maximum value of phyLECIMDSSSPPDUTxAt attribute will result the offset longer than the longest beacon interval (BO=14). | In order to make the offset witihin the superframe duration, It needs to redescribe the maximum value of phyLECIMDSSSPPDUTxAt attribute with the function of BO, SO, and GTS. | YES | R | even though it is possible to select values that don't work, this value is workable
189 | Steve Jillings | Semtech | 62 | 9.3 | 21 | phyLECIMFSKPreambleLength upper limit of 100 octets is excessive | Restrict to 40 octets (which is still probably excessive). Even assuming that RX aTurnaroundTime is 1 ms while TX aTurnaroundTime is "instantaneous", this still allows for 35 octets of preamble to synchronise the RX. How many octets do you need? | YES | AiP | restrict preamble to 64 octets
217 | Tuncer Baykas | Tohoku U. | 63 | 9.3 | Table 71 | Why phyLECIMDSSSPreambleSIZE is integer, whereas phychannelspacigin is Enumeration? | Use one type for similar atrributes | NO | AiP | change the following: 1.phyLECIMDSSSPPDUModulationRate to enum 2.phyLECIMDSSSPSDUSize to enum 3.phyLECIMFSKSpreadingFactor to enum 4.phyLECIMFSKPSDUPositionMod to boolean, True/False
220 | Tuncer Baykas | Tohoku U. | 64 | 9.4 | 42 | Explain the term "(1,0)" in the equation | As indicated | YES | AiP | change eqn to read: phyMaxFrameDuration = [ (phyLECIMDSSSPreambleSize x phyLECIMDSSSPreambleRepetition) + K + (phyLECIMDSSSPSDUSize x 8 x 2phyLECIMDSSSSHRSpreadingFactor ) x (phyLECIMDSSSPPDUModulation x 1000) Where K = 2phyLECIMDSSSSHRSpreadingFactor when phyLECIMDSSSSFDEnable is TRUE, and 0 otherwise
38 | Cristina Seibert | Silver Spring Networks | 64 | 9.4 | 51 | Mistake in equation for phyMaxFrameDuration, needs to reflect 2-octet PHR. | Change to "phyMaxFrameDuration = (phyLECIMFSKPreambleLength + 3 + 2 + aMaxPHYPacketSize) * phySymbolsPerOctet | NO | A
218 | Tuncer Baykas | Tohoku U. | 64 | 9.4 | 51 | typo "two new paragraph" | As indicated | NO | A
219 | Tuncer Baykas | Tohoku U. | 64 | 9.4 | 51 | Explain the term "(0,1)" in the equation | As indicated | YES | AiP | see CID 38
155 | Schwoerer | France Telecom | 64 | 9.4 |  | It would help to give the maximum value that can be reached by this attribute | add the overall maximum value of each attribute | NO | W
19 | Benjamin A. Rolfe | BCA | 65 | 19.1.1 | 14 | Missing description of PSDU field (like give the sizes?). It is mostly obvious, but a sentence about the fixed size selections wouldn't hurt. | "The PSDU field size is set by the value of phyLECIMDSSSPSDUSize, and carries the data of the PPDU" |  | A
37 | Clint Chaplin | Samsung | 65 | 19.1.1 | 17 | "PPDU structure is presented" | "PPDU structure for this PHY is presented" |  | A
221 | Tuncer Baykas | Tohoku U. | 65 | 19.1.1 | 26 | Explain the term "fixed" | If PSDU length is fixed indicate its lenghth | NO | AiP | change "fixed" to "16/24/32"
222 | Tuncer Baykas | Tohoku U. | 65 | 19.1.1 | 40 | This paragraph requires editing. | Indicate that Preamble16 is length of 2 octet preamble and preamble 32 is 4 octect preamble. | NO | AiP | add text "the preamble may be length 0 or one of the preambles that follows:"
20 | Benjamin A. Rolfe | BCA | 65 | 19.1.1 | 44 | Says the preamble can be 0, 16 or 32 bits. Definition of phyLECIMDSSSPreambleSize lists only 16 and 32. Here we talk octets, in the PIB attribute we use bits. We should reference the the attribute phyLECIMDSSSPreambleSize. | Be consistent (bits or octets); Change "may be commissioned" to "may be commissioned via phyLECIMDSSPreambleSize" |  | AiP | in addition to proposed change, add 0 to the range for phyLECIMDSSSPreambleSize
21 | Benjamin A. Rolfe | BCA | 65 | 19.1.2.1 | 54 | Add xref to table 66 | "The data rate is band and/or region specific, as shown in Table 66" |  | A
223 | Tuncer Baykas | Tohoku U. | 65 | 19.1.2.1 | 54 | Indicate at least the data rate range for different bands and regions | As indicated in the comment. | NO | AiP | see CID21
224 | Tuncer Baykas | Tohoku U. | 66 | 19.1.2.2 | 14 | Could S (for chips) be replaced with another notation, like S_{SHR}? | As indicated in the comment. | NO | A
227 | Tuncer Baykas | Tohoku U. | 66 | 19.2.2 | 14 | Improve Figure 155 | N,L,S,M should be italic. Indicate that SF is the spreading factor. Indicate possible values of M. N and M are used in 1.2.4.1 as well. This may create confusion. | NO | AiP | TE to modify the figure, delete dotted-line box, add optional to OVSF, remove variables
57 | David A. Howard | On-Ramp Wireless, Inc. | 66 | 19.1.2.3 | 32 | Missing option for 'tail-biting' convolutional encoder | Add text describing initialization of FEC tail bits with either pad '0' bits added to end of PPDU (as described in the reference), or by using the first 7 bits of the PPDU (tail-biting) | NO | A | see CID 56
226 | Tuncer Baykas | Tohoku U. | 66 | 19.1.2.4 | 37 | Previous section uses the term "convolutional encoder". Here "convolutional coder" is used. | Use the term "convolutional encoder" | NO | A
22 | Benjamin A. Rolfe | BCA | 66 | 19.1.2.4 | 38 | I believe what we mean by "fragment size" is actually "PSDU size". | Change "fragment size" to "PSDU size" to be consistent with the base standard. |  | A
225 | Tuncer Baykas | Tohoku U. | 66 | 19.1.2.2 | Fig. 155 | Clarify if implementing OVSF is mandatory or not. | As stated. | NO | AiP | see CID 227
228 | Tuncer Baykas | Tohoku U. | 67 | 19.1.2.4.1 | 15 | If table 189 and the text explain same operations just keep only one to reduce confusion | Rewrite this section and only use equations to explain the process. Put the table in the informative appendix. | NO | AiP | move table 190 to a new informative annex (introductory text/title: "example of results from 19.1.2.4.2 24 octet 384 bit blocked interleaver"), delete other tables, change referenced text as appropriate( e.g.delete the sequence of N is shown in Table 190)
23 | Benjamin A. Rolfe | BCA | 74 | 19.1.2.6 | 7 | Need a "shall" in this sentence. | Start with "Each input bit shall be mapped to a binary symbol using the mapping…" |  | A
24 | Benjamin A. Rolfe | BCA | 74 | 19.1.2.6 | 14 | Don't need "expllicitly" do we? Also "where" s/b "for" Need to clarify the normative part of this paragraph ("shall be spread…" or something). | Clarify |  | AiP | delete explicitly and change "are then" to "shall be"
229 | Tuncer Baykas | Tohoku U. | 74 | 19.1.2.6 | 21 | Black and white figures are easier to read than grayscale ones. | Convert Figure 156 from grayscale to black and white | NO | AiP | delete CX1 from the figure
230 | Tuncer Baykas | Tohoku U. | 75 | 19.1.2.6 | 6 | SF in Figure 157 is distorted | Redraw Figure 157 | NO | A
25 | Benjamin A. Rolfe | BCA | 75 | 19.1.2.6.1 | 20 | Clarify the normative requirements in this clause. | Clarify. I think use of gold codes as specified in 3GPP, m-sequences equivalent to those given and initial value for LFSR1. (but not 100% sure) |  | W
231 | Tuncer Baykas | Tohoku U. | 75 | 19.1.2.6.1 | 20 | Why is there a reference to 3GPP documents? | Remove the sentence | NO | AiP | do as proposed and eliminate from clause 2
52 | Dave Evans | Philips | 75 | 19.1.2.6.1 | 30 | Incorrect order for the letters in the acronym | Change "LSFR" to "LFSR" | YES | A
232 | Tuncer Baykas | Tohoku U. | 75 | 19.1.2.6.2 | 53 | Reference [1] is missing? | Add reference | NO | AiP | delete [1]
156 | Schwoerer | France Telecom | 75 | 19,1,2,6,1 | 27-28 | The reference to 3GPPP spec seems uncomplete | provide complete reference (revision number, publication date, maybe URL) |  | AiP | see CID231
233 | Tuncer Baykas | Tohoku U. | 76 | 19.1.2.6.2 | 15 | Some of the arrows are missing in Figure 158 | Correct Figure 158 | YES | AiP | add downward arrows to lines without arrows
234 | Tuncer Baykas | Tohoku U. | 76 | 19.1.2.6.2 | 20 | Could the AND and XOR symbols be improved or be made consistent? | Improve the figure 158 | NO | A
157 | Schwoerer | France Telecom | 78 | 19,1,3,1 | 22 | 2,5ppm frequency tolerance seems very challengig | explain if 2,5ppm is really unavoidable or try to relax it | YES | R | Necessary for large spreading factors to maintain timing, additionally, there are many low cost devices with this tolerance
236 | Tuncer Baykas | Tohoku U. | 78 | 19.1.3.1 | 22 | 2.5 ppm radio frequency tolerance is too stringent | Change it to 20 ppm | NO | R | Necessary for large spreading factors to maintain timing, additionally, there are many low cost devices with this tolerance
237 | Tuncer Baykas | Tohoku U. | 78 | 19.1.3.5 | 47 | Sentence needs clarification | Clarify the sentence | NO | AiP | The adjacent channels are those on either side of the desired channel that are closest in frequency to the desired channel. The alternate channel is more than one removed from the desired channel in the operational frequency band. and change to "The adjacent channels are ChanNum  1  phyLECIMDSSSPPDUModulationRate  Spacing." and change to "The alternate channels are ChanNum  2  phyLECIMDSSSPPDUModulationRate  Spacing
238 | Tuncer Baykas | Tohoku U. | 78 | 19.1.3.5 | 54 | Sentence needs clarification | Clarify the sentence | NO | A | see CID237
235 | Tuncer Baykas | Tohoku U. | 78 | 19.1.2.7.2 | Fig. 160 | Could the figure quality be improved? | Improve the figure 160 | NO | A
190 | Steve Jillings | Semtech | 79 | 19.1.3.5 | 38 | Equation describing alternate channel is split from companion text by Tables 192 and 193 | Move equation above tables | NO | AiP | see CID237
239 | Tuncer Baykas | Tohoku U. | 79 | 19.1.3.5 | Table 192 | Receiver sensitivity for SF 16 at 400 Jsym/s should be -112 | As indicated | NO | A
240 | Tuncer Baykas | Tohoku U. | 80 | 19.2.1 | 15 | Octet lengths are variable for all parts in Figure 161 | Remove octet length from all parts | NO | AiP | change N to 2, and spec size to preamble and SFD
41 | Cristina Seibert | Silver Spring Networks | 81 | 19.2.1.3 | 6 | Equation for Parity is incorrect. "PHRL" no longer exists, it's been replaced by FCS. Equation also needs to account for DW bit if added to PHR. | Make Parity bit equation consistent with the PHR. | NO | AiP | change PHRL to FCS and R2 to DW
241 | Tuncer Baykas | Tohoku U. | 81 | 19.2.13 | 7 | Parity calcaulation cannot be done without stating PHRL value. | Clarify parity calucalation | YES | AiP | see CID 41
39 | Cristina Seibert | Silver Spring Networks | 81 | 19.2.1.3 | 16 | Since only the PSDU is whitened, data whitening can be signaled with a bit in the PHR for enhanced interoperability. | Add Data Whitening signaling bit in the PHR. See the PHR format proposed in the subsequent comment. | NO | AiP | see CID 40
40 | Cristina Seibert | Silver Spring Networks | 81 | 19.2.1.3 | 16 | Re-align PHR bits for compatibility with 802.15.4g. | Set the first 2 bits to Reserved. The third bit to Parity. The fourth bit to FCS type, the fifth bit to Data Whitening (DW) and the last 11 bits to Frame Length. | NO | A
42 | Cristina Seibert | Silver Spring Networks | 85 | 19.2.2.5 | 10 | Text "Interleaving of PHR code-bits shall be employed" is inconsistent with paragraph above that states use of interleaving is controlled by PIB attribute. | Change paragraph to: "Since the PHR bits are terminated, PHR code-bits and PSDU code-bits are independent code blocks. Interleaving of PHR code-bits is separate from the interleaving of the PSDU codebits." | NO | A
43 | Cristina Seibert | Silver Spring Networks | 86 | 19.2.2.6 | 52 | Spreading sequences based on (1010) repetitions can be less than optimal. Considerable performance improvements can be achieved in some cases by using spreading sequences with better properties. | Add PIB attribute phyFSKSpreadingPattern to control the type of spreading sequence used in the FSK PHY. Add column the shows the value of phyFSKSpreadingPattern to Table 198. When phyFSKSpreadingPattern = "alternating 1 and 0", use the sequences based on (10) repetitions (currently in Table 198). Otherwise, use the spreading sequences given in Table 172 of the baseline for k=0 when spreading factor = 16, the spreading sequences given in Table 171 of the baseline for k=0 when spreading factor = 8, the spreading sequences given in Table 170 when spreading factor = 4, and the spreading sequences in Table 169 when spreading factor = 2. Remove the row for spreading factor = 1 from Table 198 since no spreading takes place. | NO | A
242 | Tuncer Baykas | Tohoku U. | 86 | 19.2.2.6 | Fig. 166 | Could the figure quality be improved? | Improve the figure 166 | NO | AiP | delete figure 166 and then refer to this figure within 802.15.4g-2012
243 | Tuncer Baykas | Tohoku U. | 88 | 19.1.2.4.2 | 12 | It is unnecessary to introduce new variable if they are not used anywhere else in the amendment | Change the subclase as "The single-sided clock radio frequency tolerance shall be ±20 ppm." | NO | AiP | change to "The clock radio frequency tolerance shall be within + 20 ppm.
191 | Steve Jillings | Semtech | 88 | 19.2.4.5 | 26 | Achieving a sensitivity of -95 dBm does not ensure compliance with the PAR requirements to overcome propagation losses of at least 120 dB, especially for those PHYs / geographic locations that limit output power or electric field strength to a level that even with FEC and SF, the theoretical maximum achievable sensitivity would not meet the 120 dB propagation loss requirement | Either: (1) Define the minimum RX sensitivity level as -101 dBm with NO FEC or SF (Proposed changes to NA 433 MHz band in Part 15.240 would still limit peak output power 0 dBm and theoretically 19 dB of processing gain is available: 12 dB with SF = 16 and 7 dB with FEC enabled) (2) Implement a sensitivity table as per Table 192 in 19.1.3.5 that indicates the minimum receiver sensitivity levels as a function of modulation rate vs. SF. For simplicity, the minimum PHY bit rate of 12.5 kb/s need be documented. State that FEC is disabled | YES | R | changing the minimum RX sensitivity level is not required to comply with the PAR.
154 | Raymond Krasinski | Philips Electronics | 97 | Annex P | 5 | Annex P is already being used in Draft 802.15.4j. | Change to Annex Q | YES | A
136 | Monique Brown | On Ramp Wireless | 98 | P.1.1 | 9 | Change text from "Ten to twenty year life" to "Ten to twenty year _battery_ life." | See | NO | A
137 | Monique Brown | On Ramp Wireless | 98 | P.1.1 | 13 | "Significant difference between coordinator and endpoints." | Did you mean to say "PAN coordinator?" | NO | AiP | add "PAN"
138 | Monique Brown | On Ramp Wireless | 99 | P.1.2.4 | 42 | There appears to be an extra word in the second bulleted item. | Change from "for receiving to queries" to "for receiving queries." | NO | A
139 | Monique Brown | On Ramp Wireless | 100 | P.1.2.5 | 1 | Reword two sentences: "...there is an event, _such as_ an emergency, where the central monitoring system _requires_ readings from all sensors as soon as possible. The central controller _sends_ a request..." | See comment. | NO | A
140 | Monique Brown | On Ramp Wireless | 100 | P.1.3.1 | 50 | If this is a star network, then device A is the "PAN" coordinator. | Change to PAN coordinator. | NO | A | see CID137
141 | Monique Brown | On Ramp Wireless | 100 | P.1.3.1 | 51 | Since we are talking about three possible codes, make this point more clear by changing text to "...beacon transmission and use _two additional,_ unique _codes_/spreading for reception from devices B and C." | See comment. | NO | A
142 | Monique Brown | On Ramp Wireless | 102 | P.2.4 | 47 | The text, "...the CAP duration must be set long enough to accommodate the PCA plus aMinCAPLength," does not belong in the informative annex. | Remove these details from the annex. It should already be in the normative text. | NO | A
143 | Monique Brown | On Ramp Wireless | 102 | P.2.4 | 52 | The text says, "Both mechanisms are used during contention access, but the PCA allocations, however, can only..." | The word "but" is already in the sentence. Remove "however." | NO | A
145 | Monique Brown | On Ramp Wireless | 103 | P.2.4 | 3 | The informative annex seems like the wrong place for a discussion of how these PIB attributes are used (see first two paragraphs on page 103). | Isn't this text already in the normative text? If so, then the information is being repeated. Remove it from the annex. | NO | A
144 | Monique Brown | On Ramp Wireless | 103 | P.2.4 | 5 | There appears to be an extra carriage return between paragraphs. | Remove it. | NO | A
280 | Yong Li | cqupt | 103 | P.2.4 | 9 | ".. in every aUnitBackoffPeriod where…." | change to " ..in each aUnitBackoffPeriod where.." | YES | A
53 | Dave Evans | Philips | 104 | P.2.6 | 7 | The PHY Parameter Change IE that is already described in Draft 802.15.4j and it is clause 5.2.4.23. | Change "5.2.4.29" to "5.2.4.23" | YES | A
54 | Dave Evans | Philips | 104 | P2.7 | 18 | Same as the preceeding comment | Same as the preceeding comment | YES | A | see CID53
146 | Monique Brown | On Ramp Wireless | 104 | P.2.7 | 27 | Text says: "the AR field is set to indicate that an acknowledgment is requested." | Isn't this text already in the normative text? If so, then the information is being repeated. Remove it from the annex. | NO | A
148 | Pat Kinney | Kinney Consulting | 104 | P.3 | 35 | to be sucessful, TRLE must be more detailed, must be compatible with MAC security, and must have consistant parameters with all vendors, therefore it needs to be put into the main body of the standard. | move TRLE into the main body and insert normative statements where required to yield an interoperable behavior | NO | R | cannot be implemented as proposed since the received text to insert the TRLE behavior is not complete
170 | Seong-Soon Joo | ETRI | 104 | P.3.1 | 45 | typo " a PAN coordinator to endpoint,." | Change into " a PAN coordinator to endpoint." | YES | A | delete comma
171 | Seong-Soon Joo | ETRI | 104 | P.3.1 | 50 | typo " to extend the range the network." | Change into " to extend the range of the network." | YES | A
180 | Shusaku Shimada | Yokogawa Co. | 104 | P3.1 | 50 | is to use either routers or repeaters to extend the range the network. | Sentence is not completed. |  | AiP | see CID171
181 | Shusaku Shimada | Yokogawa Co. | 104 | P3.1 | 52 | In a beacon-enabled PAN, the endpoint associates with the PAN coordinator. In a router-enabled network the connection between the PAN coordinator and endpoint that is outside the radio range of the concentrator would associate with the coordinator acting as a router, and the path to the PAN coordinator becomes a routed connection of multiple links. Using a coordinator acting as router to extend the range of an LECIMnetwork may require the installation mains-powered routers. | This annex contains too much functional node type, coordinbator, concentrator, repeator, router, and overlapping of thgese functions. It is questionable that this annex is typical structure of viable implementation or this entire annex might be simplified in a few lines or eliminated at all. | YES | W
182 | Shusaku Shimada | Yokogawa Co. | 104 | P3.1 | 53 | The beacon generated by the PAN coordinator is relayed outward after a unique repeater delay to avoid interfering with other beacons from neighboring repeaters. | This annex contains a bit crude mechnism using a concept of unique repeater delay without proper elaboration of usecase. | YES | W
172 | Seong-Soon Joo | ETRI | 105 | P.3.2 | 25 | The TRLE repeater can extend the range of the LECIM network. It is not provided enough information on how the TRLE repeater works transparently between GTS/DSME PAN coordinator and GTS/DSME PAN device. In clause 5 and 6, it is not found any MAC protocol or MAC service to provide the range extension with the TRLE. | Add the MAC functional description on time-slot relaying to clause 5.1: frame reception at the TRLE repeater and TRLE relaying function. Add the MAC management service to support time-slot relaying to clause 6.2. | YES | R | See CID 148
173 | Seong-Soon Joo | ETRI | 105 | P.3.2 | 25 | It is not provided enough information on how to establish a link between the TRLE-enabled PAN coordinator and a TRLE repeater. In clause 5 and 6, it is not found any MAC protocol or MAC service to establish a link between the TRLE-enabled PAN coordinator and a TRLE repeater. | Add the MAC functional description on link establishment between the TRLE-enabled PAN coordinator and a TRLE repeater to clause 5.1. To support TRLE link establishment, add the MAC frame formats to clause 5.2, add the MAC command to clasue 5.3, and add MAC management service to clause 6.2. | YES | R | see CID148
174 | Seong-Soon Joo | ETRI | 105 | P.3.2 | 25 | It is not provided enough information on how to transmit frames on the TRLE path from the TRLE PAN coordinator to a TRLE enabled device. In clause 5 and 6, it is not found any MAC protocol or MAC service to support transmission on the TRLE path from the TRLE PAN coordinator to a TRLE enabled device. | Add the MAC data service to support transmission on the TRLE path from the TRLE PAN coordinator to a TRLE enabled device to clause 6.3. | YES | R | see CID148
175 | Seong-Soon Joo | ETRI | 109 | P.3.2.2 | 40 | It is not provided enough information on how to accommodate three grades of transmssion for relaying frames. In clause 5 and 6, it is not found any MAC protocol or MAC service to support multiple grades of synchronous access. | Add the MAC data service to support three grades of transmssion to clause 6.3. | YES | R | see CID148
176 | Seong-Soon Joo | ETRI | 110 | P.3.2.3 | 44 | It is not provided enough information on how to manage the TRLE path. In clause 5 and 6, it is not found any MAC protocol or MAC service to support TRLE path management. | To support TRLE path management, add the MAC command to clasue 5.3, and add MAC management service to clause 6.2. | YES | R | see CID148
147 | Monique Brown | On Ramp Wireless | iv |  |  | Add the name of the WG Treasurer. | See comment. | NO | A
258 | Wun-Cheol Jeong | ETRI |  |  |  | Recommend to add functional descriptions of DSME-GTS allocation for extended mode. | See the comments |  | AiP | add text as per doc 15-12-507-00

## CID27 flowchart
CSMA-CA PCA
Slotted?
NB=0, CW=CW0
BE=max(1,macMinBE-1), Total backoffs = random(2BE-1) unit backoff periods
Y
Perform CCA on backoff period boundary
Channel idle?
Total backoffs = Total backoffs-1
Total backoffs = 0?
Y
N
N
Transmit,
NB = NB+1
Success?
Success
NB > macMaxCSMABackoffs?
N
N
Y
Y
Failure
Y
CW = CW-1
CW = 0?
N
Y
CW = CW0
Locate backoff period boundary
NB=0,
BE=max(1,macMinBE-1), Total backoffs = random(2BE-1) unit backoff periods
Perform CCA
Channel idle?
Total backoffs = Total backoffs-1,
wait aUnitBackoffPeriod-CCA assessment time
Total backoffs = 0?
Y
N
N
Transmit,
NB = NB+1
AR =0
Success
NB > macMaxCSMABackoffs?
N
N
Y
Y
Failure
Y
Wait aUnitBackoffPeriod- CCA assessment time
N
Total backoffs = random(2BE-1) unit backoff periods
Total backoffs = random(2BE-1) unit backoff periods
ACK received?