## IEEE_Cover
| doc name: | lb90-comments-resolutions-tg4m
| doc. #: | 15-13-0304-004m
| date: | 2013-05-13
IEEE P802.15
Wireless Personal Area Networks
Project | IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Title | 802.15.4m Letter Ballot 90 Comment Resolution(NB-OFDM)
Source | Alina Liru Lu | E-mail: Liru@nict.com.sg
Re: | d2P802-15-4m_Draft_Standard
Abstract | 802.15 TG4m Letter Ballot Comments
Purpose | [This document is a summary of all comments from the TG4m Letter Ballot.]
Notice | This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Comments
CID | Name | Affiliation | Category | Page | Sub-clause | Line # | Out of Scope | Resolution Assignment | Comment | Proposed Change | Proposed Resolution | A / AP / R / Z / oos / unrsvbl | Resolution Accept Date | Group | Must Be Satisfied? (enter Yes or No) | Resolution sent to commenter (date) | Commenter agreed? Y/N | for Editorial Stats | for Tech/Gen Stats | for closed T/G Grp Stats | for open T/G Grp Stats | for wip T/G Grp Stats | for rdy2vote T/G Grp Stats | for oos T/G Grp Stats | Resolution Due Date | Open Technical Comment Assignments
1 | Alina Liru Lu | NICT | Technical | 95 | 20.3.3.1 | Figure 185 |  | Alina/Mizutani | The description of spreader is not given for Figure 185 | Move line 27 to 34 from page 93 to create a new clause 'spreader' | Accept in principle. See Doc303r0 |  |  | NB-OFDM | Yes |  |  |  | 0 |  | NB-OFDM
2 | Alina Liru Lu | NICT | General | 18 | CAD file | Figure 7 |  | Soo-Young | BER-OFDM and FER-OFDM curves are not seen | Include BER-OFDM and FER-OFDM curves |  |  |  | CAD | Yes |  |  |  | 0 |  | CAD
3 | Kunal Shah | Silver Spring Networks | Editorial | 20 | 5.2 | 38 |  | Clint/Sum | Sub-cluase numbers are not allign with previous 15.4 amendments. | Corret the sub-cluase numbers to be consistent with previous 15.4 amendments. |  |  |  | Editorial | No |  |  | 0
4 | Kunal Shah | Silver Spring Networks | Editorial | 20 | 5.2.4.1 | 44 |  | Clint/Sum | Sub-cluase number is incorrect and should be 5.2.2.1.1a instead of 5.2.2.1.1. | Change the sub-clause number to 5.2.2.1.1a | Accept | A |  | Editorial | No |  |  | A
5 | Kunal Shah | Silver Spring Networks | Editorial | 20 | 5.2.4.1 | 46 |  | Clint/Sum | Sub-cluase number is incorrect and should be 5.2.4.2 instead of 5.2.4.1. | Change the sub-clause number to 5.2.4.2 | Accept | A |  | Editorial | No |  |  | A
6 | Kunal Shah | Silver Spring Networks | Editorial | 20 | 5.2.4.4 | 48 |  | Clint/Sum | Sub-cluase number is incorrect and should be 5.2.4.5 instead of 5.2.4.4. | Change the sub-clause number to 5.2.4.5 | Accept | A |  | Editorial | No |  |  | A
7 | Alina Liru Lu | NICT | Technical | 22 | 20.3.3.1 | Figure 185 |  | Alina/Mizutani | Change 'Pilot and Null tones' to 'Pilot tones' as shown in the title of corresponding clause | apply change | Accept |  |  | NB-OFDM | Yes |  |  |  | 0 |  | NB-OFDM
8 | Kunal Shah | Silver Spring Networks | Editorial | 24 | Table 4ic | 24 |  | Clint/Sum | Part of the table is on another page. | Combine the table into one table. | Accept in principle. | AP |  | Editorial | No |  |  | AP
9 | Steve Jillings | Semtech | Technical | 24 | 5.2.4.33 |  |  | Cristina | Table 4ic shows supported band fields. Rows corresponding to bit number 5 - 16 show support for frequency bands that are not allocated for TVWS operation. The scope of the .4m PHY states "...The amendment enables operation in the VHF/UHF TV broadcast bands between 54 MHz and 862 MHz..." If TVWS is not available in a geographic region, then existing ISM / License-exempt bands should not be allocated. There are existing 15.4 standards which have been developed specifically to support operation in these bands and should be implemented instead | Restrict 15.4m IEs in Table 4ic to those allocated TVWS frequency bands as defined within the scope of the PAR. Delete rows corresponding to bit numbers 5 - 16. |  |  |  | Bands | Yes |  |  |  | 0 |  | Bands
10 | Kunal Shah | Silver Spring Networks | Editorial | 33 | 5.2.4.35.1 | 39 |  | Clint/Sum | Include the description for Request TX Timestamp. Editorial error when implementing CID29 from the LB88 | Include the description as, "Request TX Timestamp shall be set to TX time, when the ranging method is one way ranging" | Accept in principle. Implement the resolution from CID 29 of LB 88. | AP |  | Editorial | No |  |  | AP
11 | Kunal Shah | Silver Spring Networks | Editorial | 43 | 6.2.4.1 | 1 |  | Clint/Sum | Part of the table is on another page. | Combine the table into one table. | Accept in principle. | AP |  | Editorial | No |  |  | AP
12 | Alina Liru Lu | NICT | General | 63 | 20 | 10 |  | Soo-Young | The CAD file can be linked from reference, it is not necessary indicate here | remove the paragraph |  |  |  | CAD | Yes |  |  |  | 0 |  | CAD
13 | Kuor-Hsin Chang | Elster Solutions | Technical | 63 | 20.1.1.2 | 45-46 |  | Cristina/Alina | The purpose of SFD is to assist initial synchronization. A SFD with length of 16 bit is sufficient. Having a 24-bit SFD as an option adds unnecessary complexity with very limited value. | Delete the option of having 24-bit SFD. |  | c |  | FSK | Yes |  |  |  | c
14 | Cristina Seibert | SSN | Technical | 65 | 20.1.2.2 | 36 |  | Cristina/Alina | When implementing various comments on FEC/interleaving, dropped out reference to the interleaving scheme in 19.2.2.5. | At the end of the paragraph, add sentence "The interleaving scheme shall be according to sub-clause 19.2.2.5.". |  | c |  | FSK | No |  |  |  | c
15 | Matt Gillmore | Itron | Technical | 65 | 20.1.2.2 | 34-35 |  | Cristina/Alina | FEC as mentioned in section 18.1.2.4 is less complex than method suggested in section 19.2.2.4. For the following reasons: Constraint length K=4 versus K=7 allows for Lower power consumption, Lower implementation complexity and 18.1.2.4 also proposes a systemic scheme that can be decoded by receivers that do not support FEC. Millions of devices can already support the methods in 18.1.2.4. For more justification if required, please see 15-13-0288-00-004m-comment-on-FEC-methods-for-4m. https://mentor.ieee.org/802.15/dcn/13/15-13-0288-00-004m-fec-proposal-justification-for-4m.ppt | Replace Section 20.1.2.4 line 49 “The FEC scheme shall be according to sub-clause 19.2.2.4” with “The FEC scheme shall be according to sub-clause 18.1.2.4” | Accept in principle. Replace Section 20.1.2.4 line 49 “The FEC scheme shall be according to sub-clause 19.2.2.4” with “The FEC scheme shall be according to sub-clause 18.1.2.4 or 19.2.2.4” |  |  | FSK | Yes |  |  |  | 0 |  | FSK
16 | Alina Liru Lu | NICT | Technical | 66 | 20.1.2.1 | Figure 172 |  | Cristina/Alina | The reference modulator diagram is incomplete. It does not show the scenario when the data is uncoded, or no spreading. | Adopt the figure proposed in Doc. 0286-r0 | Accept |  |  | FSK | Yes |  |  |  | 0 |  | FSK
17 | Cristina Seibert | SSN | Editorial | 67 | 20.1.2.6 | 1 |  | Clint/Sum | Sub-clause title incorrect, it should be "Modulation Quality" | see comment | Accept | A |  | Editorial | No |  |  | A
18 | Cristina Seibert | SSN | Editorial | 67 | 20.1.2.7 | 7 |  | Clint/Sum | Sub-clause title incorrect, it should be "Values for phySymbolsPerOctet" | see comment | Accept | A |  | Editorial | No |  |  | A
19 | Cristina Seibert | SSN | Editorial | 74 | 20.2.2 | 27 |  | Clint/Sum | Suggest editors re-edit paragraph consistent with proposed change in CID 68 of LB 88. | see comment | Accept in principle. Implement the resolution from CID 68 of LB 88. | AP |  | Editorial | No |  |  | AP
20 | Kuor-Hsin Chang | Elster Solutions | Technical | 105 | 20.3.5.1 | 49-50 |  | Cristina | The 4m PAR states: This amendment specifies a physical layer for 802.15.4 meeting TV white space regulatory requirements in as many regulatory domains as practical and also any necessary Media Access Control (MAC) changes needed to support this physical layer. The amendment enables operation in the VHF/UHF TV broadcast bands between 54 MHz and 862 MHz, supporting typical data rates in the 40 kbits per second to 2000 kbits per second range, to realize optimal and power efficient device command and control applications. Why the TVWS-NB-OFDM PHY also operates in the 4g bands? | Remove 4g bands from the bands where TVWS-NB-OFDM PHY operates. |  |  |  | Bands | Yes |  |  |  | 0 |  | Bands
21 | Cristina Seibert | SSN | Editorial | 112 | Annex D | 39 |  | Clint/Sum | in Reference of item RF22.1 "205" should be "Table 205" | see comment | Accept | A |  | Editorial | No |  |  | A
22 | Cristina Seibert | SSN | Editorial | 112 | Annex D | 42 |  | Clint/Sum | in Reference of item RF22.2 "205" should be "Table 205" | see comment | Accept | A |  | Editorial | No |  |  | A
23 | Cristina Seibert | SSN | Editorial | 112 | Annex D | 47 |  | Clint/Sum | in Reference of item RF23.1 "214" should be "Table 214" | see comment | Accept | A |  | Editorial | No |  |  | A
24 | Cristina Seibert | SSN | Technical | 113 | Annex D | 23 |  | Kunal | Status of MLF34 incorrect, "MLF32" should be "MLF32: M" and "MLF33" should be "MLF33: M" | see comment |  |  |  | PICS | No |  |  |  | 0 |  | PICS
25 | Cheolho Shin | ETRI | Technical | After Annex T | Annex | Annex U |  | Soo-Young | show example of encoding a packet for the TVWS-OFDM PHY to avoid ambiguity. | Insert the Annex U for TVWS-OFDM PHY. . Refer to doc. #15-13-0287 |  |  |  | OFDM | Yes |  |  |  | 0 |  | OFDM

## Summary
| Tech/Gen | Editorial | Overall |  |  |  |  | Commentors | # Comments
Comment State | 10 | 13 | 23 | Computed Tally is Incorrect |  |  |  | Kuor-Hsin Chang | 2
Ready2Vote On - rdy2vote | 0 | 0 | 0 |  |  |  |  | Matt Gillmore | 1
Work in Progress - wip | 0 | 0 | 0 |  |  |  |  | Steve Jillings | 1
Open (resolution not assigned) | 10 | 1 | 11 |  |  |  |  | Alina Liru Lu | 5
Accept - A | 0 | 8 | 8 |  |  |  |  | Cristina Seibert | 8
Reject - R | 0 | 0 | 0 |  |  |  |  | Kunal Shah | 7
Accept in Principle - AP | 0 | 4 | 4 |  |  |  |  | Cheolho Shin | 1
Withdrawn - Z | 0 | 0 | 0
Out of Scope - oos | 0 | 0 | 0
Unresolvable - unrsvbl | 0 | 0 | 0
Total processed | 0 | 12 | 12
Percent processed | 0% | 92.31% | 52.17%
Total open | 10 | 1 | 11 |  |  |  |  | 7 | 25
Percent open | 100% | 7.692% | 47.83% | [5 empty] | Computed Tally is Incorrect
T & G Sort by Group | Total | Res Assigned | oos | rdy2vote | wip | No Res Assign | Tally Check
Dev Mode and Cap | 0 | 0 | 0 | 0 | 0 | 0 | OK
Enabling | 0 | 0 | 0 | 0 | 0 | 0 | OK
Power saving | 0 | 0 | 0 | 0 | 0 | 0 | OK
Ranging | 0 | 0 | 0 | 0 | 0 | 0 | OK
TMCTP | 0 | 0 | 0 | 0 | 0 | 0 | OK
FSK | 4 | 0 | 0 | 0 | 0 | 2 | -2
General | 0 | 0 | 0 | 0 | 0 | 0 | OK
OFDM | 1 | 0 | 0 | 0 | 0 | 1 | OK
NB-OFDM | 2 | 0 | 0 | 0 | 0 | 2 | OK
PICS | 1 | 0 | 0 | 0 | 0 | 1 | OK
Misc | 0 | 0 | 0 | 0 | 0 | 0 | OK
Dev-dev | 0 | 0 | 0 | 0 | 0 | 0 | OK
x | 0 | 0 | 0 | 0 | 0 | 0 | OK
x | 0 | 0 | 0 | 0 | 0 | 0 | OK
Total of T & G Groups | 8 | 0 | 0 | 0 | 0 | 6
Are Computed Tallys Correct | NO | YES | YES | YES | YES | NO
Assigned Comments
Alina/Mizutani | 2
Ben | 0
Clint/Sum | 13
Cristina | 2
Cristina/Alina | 4
Kunal | 1
Soo-Young | 3
Sum | 0
Soo-Young/Young-Ae | 0
Mi-Kyung | 0
MingTuo | 0
25
Percent Comments Assigned | 108.7%