## IEEE_Cover
| doc name: | tg10-(l2r)-timeline
| doc. #: | 15-13-0645
| date: | 2014-05-14
IEEE P802.15
Wireless Personal Area Networks
Project | IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Title | 802.15 TG10 Timeline
Source | Clint Powell | E-mail: cpowell@ieee.org
Re: | Timeline for 802.15 TG10
Abstract | 802.15 TG10 Timeline
Purpose | [This document is an estimated timeline for the 802.15 TG10 (L2R) Project.]
Notice | This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## TG10 Timeline
| 2013 | [5 empty] | 2014 | [11 empty] | 2015 | [11 empty] | 2016
| 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
PAR and 5C Approved | x
Task Group Formed | x
Call for Applications (as TG) |  | x | x | x | x
Prep for 1st Joint Session w/802.1 |  |  | x
Review Applications |  |  | x | x | x | x | x
1st Joint Session w/802.1 |  |  |  |  | x
Estab. 802.1 Collab Needed |  |  |  |  | x | x | x
SoW & SRS (802.15/802.1) | [6 empty] | x
Tech. Guid. Doc. & Selection Criteria | [6 empty] | x | x | x
Call for Prelim Proposals Issued | [8 empty] | x | x
Prelim Proposals Heard | [10 empty] | x
Call for Final Proposals issued | [11 empty] | x
Final Proposals Heard | [12 empty] | x | x | x
Baseline Proposal(s) Selected. | [14 empty] | x
Build Baseline | [14 empty] | x | x | x
Adopt Baseline | [16 empty] | x
Develop Draft | [16 empty] | x | x | x
Draft Ready for TG10 Review | [18 empty] | x | x
Comment Resolution / Complete Draft / Approval for Letter Ballot | [19 empty] | x | x
Draft Ready for 1st Letter Ballot | [20 empty] | x
Letter Ballot | [20 empty] | x | x
1st Letter Ballot Complete | [21 empty] | x
Resolve Comments | [22 empty] | x | x | x
1st Recirc | [24 empty] | x
1st Re-circulation Complete | [25 empty] | x
Resolve Comments | [25 empty] | x | x
2nd Recirc | [26 empty] | x | x
2nd Re-circulation Complete | [27 empty] | x
Resolve Comments | [27 empty] | x | x
3rd Recirc | [28 empty] | x
3rd Re-circulation Complete | [28 empty] | x
Resolve Comments | [28 empty] | x
Sponsor Ballot | [29 empty] | x | x
Sponsor Ballot Complete | [30 empty] | x
Resolve Comments | [30 empty] | x | x | x
1st Recirc | [32 empty] | x | x
1st Re-circulation Complete | [33 empty] | x
Resolve Comments | [33 empty] | x
2nd Recirc | [34 empty] | x
2nd Re-circulation Complete | [34 empty] | x
Resolve Comments | [35 empty] | x
3rd Recirc | [35 empty] | x
3rd Re-circulation Complete | [36 empty] | x
Comments Resolved | [36 empty] | x
EC Approval | [36 empty] | x
RevCom Approval | [37 empty] | x