## Sheet1
Index | Things wrong and general idiocy | How can we fix them | Status | Tech/Ed. | Severity
1 | Clause 5 is too big | Split Clause 5 into functional and frame formats | Written | Editorial | Moderate
2 | Can we delete the Industrial applications Annex. | Move to a mentor document? | Written | Editorial | Moderate
3 | Move example packet encodings to a mentor document. | Do for all of them. | Written | Editorial | Moderate
4 | Should we delete ACKs from the MSCs | Yes, do it to simplify the MSCs | Resolved | Editorial | Moderate
5 | Define clearly what causes an ACK to be sent. | Check to see if it stated in one location. |  | Technical | High
6 | What is channel page used for? Can't we get rid of it? | Lets try to remove channel page. Ben to propose. |  | Technical | High
7 | 5.1.6.4.2 – ACKs happen without security processing. | Yes, delete this. |  | Editorial | High
8 | What the hell is the structure of the SUN channel page nonsense? | Perhaps this can be deleted? If not, then it needs to be updated to be correct. |  | Technical | Moderate
9 | Add, candidate for deprecation, deprecated, removed and archived. | Write a short paragraph that says what these mean. Perhaps steal text from 802.11. |  | Technical | Moderate
10 | Should plus/minus be followed with a space? | No space between it and the number. | Resolved | Editorial | Low
11 | Are we really putting the length field in backwards? | We need uniform language do describe this idiocy. |  | Technical | High
12 | Tb for the MSK PHY isn't defined anywhere. |  |  | Technical | High
13 | MSK PHY is simply orthogonal GFSK, why not use that? | Simplify the clause. Perhaps reference the GFSK. |  | Editorial | Moderate
14 | LRP UWB frame format is BS, needs to be re-done | Need better definition of what is wrong. |  | Editorial | Moderate
15 | Remove country and regulations from SUN PHY frequency table. | Yes | Resolved | Editorial | Moderate
16 | Is it really ith and jth? | It is superscript, upright text. | Resolved | Editorial | Low
17 | Is it i.e. or i. e.? | i.e., no space | Resolved | Editorial | Low
18 | Can we deprecate mode switch? | Candidate for deprecation. |  | Technical | Moderate
19 | RIT MSC, is it correct? | Ask Kojima-san |  | Technical | Moderate
20 | Equations in RFID annex need to be fixed. | Clint Powell |  | Editorial | High
21 | Figures in RFID annex need to be fixed. |  |  | Editorial | High
22 | MSCs in Clause 4 need to be deleted or moved. | Pat will work on it. |  | Technical | High
23 | MSCs in Clause 6 need to be deleted or moved. | Pat will work on it. |  | Technical | High
24 | Too much detail on precise behavior in Clause 4. Needs complete re-write. | Make it only a general overview and pointers to correct locations. |  | Editorial | Low
25 | Access methods should not be bound to PHYs in the MAC clause, but rather in the PHY clauses. | Make sure that we are tying access methods to modes, not PHYs |  | Technical | Moderate
26 | In LECIM, it says “The format of the PHR is shown in Figure . All multi-bit fields are unsigned integers and shall be processed MSB first”, but earlier, lsbs are on the left, msbs are on the right. | Check with LECIM people, Rolfe will liaise with Christina? |  | Technical | High
27 | In multi-purpose wakeup frame, the RZ Time IE has size 4/6, yet it is listed as a fixed 2 octets | Ben should check this. |  | Technical | Moderate
28 | There are references to “short address less than 0xfffe” but that simply means a device that has been allocated a short address. | Say instead “shall only be sent by a device that has been assigned a short address.” |  | Editorial | Moderate
29 | Need to combine the PCA alternatives with the general CSMA-CA flow chart. | Pat knows who will work on it. |  | Editorial | Moderate
30 | Merge FastA capabilities field figure with existing capabilities field figure. | Finished. | Resolved | Editorial | Low
31 | Is GTSR in the acronyms? |  |  | Editorial | Low
32 | What where they smoking when they added Enhanced Beacon information to MLME-SET.request? | Delete from here, it is in MLME-START.request. |  | Editorial | High
33 | sduLength is not passed in the MLME, or indeed the length of any multi-octet field. | Delete from this MLME, check to see if msduLength is used by 802.1.
34 | For what possible reason is the MR-FSK symbol timing in the MAC clause? | Move to MR-FSK clause |  | Editorial | Low
35 | Split PHYs into one PHY per clause. | Do it. | Resolved | Editorial | High
36 | Is LE needed as an acronym |  |  | Editorial | Low
37 | There are too many definitions, lets create a glossary |  |  | Editorial | Low
38 | Number figures and tables by Clause | Use Michelle's suggestion |  | Editorial | Moderate
39 | Rename frame control field for other frame. | Do it. |  | Editorial | Low
40 | Rename all PIB attributes for new amendments and move to a single table? | Split PIB table into Generic, PHY specifics |  | Editorial | Low
41 | What is a simple address and shouldn't this be defined along side the other addresses? |  |  | Technical | Moderate
42 | LL Beacon references 2450 MHz PHY, yet none exists | Delete the equation and figure out what the hell this is supposed to mean. |  | Technical | Moderate
43 | GACK is referred to as a GACK frame, yet it is an IE. Can it be sent with other information in a frame? Shall it only be sent alone? |  |  | Technical | Moderate
44 | Is it going to be GACK, group ACK, G-ACK? |  |  | Editorial | Low
45 | Group ACK flags is referenced in the MAC protocol, but it is not a field name in the Group ACK IE. |  |  | Technical | Moderate
46 | Move LL generic to the generic frame format. Move the LL frames to the command section (perhaps?). |  |  | Editorial | Low
47 | Delete MHR and MFR from command figures, i.e., only specify the Payload field? |  |  | Editorial | Low
48 | Is it going to be RZ or Rendezvous? |  |  | Editorial | Low
49 | Serious problems with the Group ACK IE definition |  |  | Technical | High
50 | Why doesn't the numbering for IEs start at zero? Was there some master plan? |  |  | Technical | Moderate
51 | Are all the IEs referenced in the text? If they are defined in the frame formats there needs to be some mention of how they are used. |  |  | Technical | Moderate
52 | MR-FSK Generic PHY IE is defined but not used | Suggest delete. |  | Technical | Moderate
53 | IEID in Beacon frame only includes short IEs, is that correct |  |  | Technical | Moderate
54 | The Enhanced Beacon IE has a field with PIB IDs, but no such things exist | Suggest delete. |  | Technical | High
55 | The “Enhanced Beacon Request command IE per enabled attribute” table can't be in the right place and it is likely incorrectly definedcoexistence specification | Suggest delete. |  | Technical | High
56 | The SUN PHY IE has a length calculation that we likely don't need. | Suggest delete. |  | Technical | Moderate
57 | Can we kill the Generic PHY? | Suggest delete. |  | Technical | High
58 | Should we have subclauses for all the fields in the commands? | Suggest we delete the subclause headings to be consistent with other usage |  | Editorial | Low
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93

## Sheet2
Recommended Deprecation list | For sure we keep.
PSSS PHY | O-QPSK
MPSK PHY | BPSK
LLDN | MR-FSK
ASK | MR-OFDM
MR-OQPSK (DSSS) | UWB
AMCA | GFSK (MSK becomes GFSK with option)
TVWS
RCC
LEICIM DSSS
LEICIM FSK
TSCH
DSME
CSS
Access methods (all, inc. PCA)
Fragmentation
Multi-purpose frame (for TSCH)
Header IEs
Payload IEs
64 bit addressing