## Slide 1
Project: IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Submission Title: Modification of time planning for the task group 3d
Date Submitted: May 13, 2014
Source: Ken Hiraga and Masashi Shimizu
NTT Corporation, Japan
Voice: +81-46-859-3474, FAX: +81-46-855-1497, E-Mail: hiraga.ken@lab.ntt.co.jp
Re: 15-14-0155-00-003d_Time_Planning_for_the_Task_Group
Abstract: This contribution provides an evaluation of the current time planning and a proposal of a realistic time planning for the task group 3d.
Purpose: Modification of time planning for the task group 3d.
Notice: This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Slide 2
Comparison between actual timeline of TG3c and time planning of TG3d
2005
2006
2007
2008
2009
2014
2015
2016
LB
J
M
M
J
S
N
J
M
M
J
S
N
J
M
M
J
S
N
J
M
M
J
S
N
J
M
M
J
S
N
SB
RevCom
CfP
J
M
M
J
S
N
J
M
M
J
S
N
J
M
M
J
S
N
LB
SB
TG3c
actual
timeline
TG3d
time
planning
drafting
technical discussions
Motion -LB
Motion -SB
TG kickoff
TG kickoff
RevCom
CfP
Motion -LB
Motion -SB
drafting
(original@Mar. 2014)

## Slide 3
More realistic time planning would be required for TG3d.
Example:
10 tasks completed between task group formed and CfP in TG3c (IEEE 15-07-0632-00-003c).
Call for Application
Call for intent to propose
System requirements document
Selection criteria document
Channel model creation
Channel model release
Down-selection procedure document
Usage model document
MAC related system attributes
Recommendation of MAC development
Can TG3d finish all discussions required for proposal and draft?

## Slide 4: Proposed Time Planning for TG3d This is still 1.5 years faster than that of TG3c.
 | original@Mar. 2014 |  | current@May 13, 2014 |  | proposal | 
 | start on | finalize | Start on | finalize | Start on | finalize
application requirements document (ARD) | May 2014 | July 2014 | May 2014 | Sep. 2014 | May 2014 | Sep. 2014
technical requirements document (TRD) | May 2014 | Sep. 2014 | May 2014 | July 2015 | May 2014 | Jan. 2015
channel model document (CMD) | May 2014 | Sep. 2014 | May 2014 | July 2015 | May 2014 | Jan. 2015
evaluation criteria document (ECD) | July 2014 | Sep. 2014 | Jan. 2015 | Sep. 2015 | Nov. 2014 | Mar. 2015
call for proposal (CfP) | Sep. 2014 | Sep. 2014 | Sep. 2014 | Nov. 2015 | Sep. 2014 | May 2015
presentation of proposal | Nov. 2014 | Nov. 2014 | Jan. 2016 | Jan. 2016 | July 2015 | July 2015
Reference: 15-14-0155-00-003d_Time_Planning_for_the_Task_Group

## Slide 5: Proposed Time Planning for TG3d This is still 1.5 years faster than that of TG3c.
 | original@Mar. 2014 |  | current@May 13, 2014 |  | proposal | 
 | start on | finalize | Start on | finalize | Start on | finalize
selection of proposals | － | － |  |  | Sep. 2015 | Sep. 2015
drafting 1st draft | － | － | Jan. 2016 | May. 2016 | Sep. 2015 | Jan. 2016
letter ballot (LB) | Jan. 2015 | Nov. 2015 | July 2016 | Jan. 2017 | Jan. 2016 | Nov. 2016
sponsor ballot (SB) | Nov. 2015 | May 2016 | Jan. 2017 | May 2017 | Nov. 2016 | May 2017
submission to RevCom | May 2016 | May 2016 | May 2017 | May 2017 | May 2017 | May 2017
Reference: 15-14-0155-00-003d_Time_Planning_for_the_Task_Group