## IEEE_Cover
| doc name: | ig-dep-tentative-timeline
| doc. #: | 15-14-0340-03
| date: | 2015-05-12
IEEE P802.15
Wireless Personal Area Networks
Project | IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Title | 802.15 IG DEP Tentative Timeline
Source | Jussi Haapola (Centre for Wireless Communications / University of Oulu) | E-mail: jhaapola@ee.oulu.fi
Re: | Tentative Timeline for 802.15 IG Dependability
Abstract | 802.15 IG DEP Tentative Timeline
Purpose | [This document is a tentative timeline for the 802.15 IG DEP and its follow up project.]
Notice | This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## IG Timeline
| 2014 | [7 empty] | 2015 | [11 empty] | 2016 | [11 empty] | 2017 | [11 empty] | 2018
| 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Defining application-dependability matrix | x | x | x | x | x | x
Study Group Formed | [6 empty] | x | [9 empty] | x
Call for Interest |  |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x
Review Call for Interest | [5 empty] | x | x | x | x | x | x | x | x | x | x | x | x
Drafting PAR and 5C | [14 empty] | x | x | x | x | x | x | x
PAR and 5C Approved | [20 empty] | x
Task Group Formed | [20 empty] | x
Call for Applications | [17 empty] | x | x | x | x
Review Applications | [21 empty] | x | x | x
Technical Guidance Framework | [21 empty] | x | x | x
Selection Criteria | [21 empty] | x | x | x
Coexistence Criteria | [23 empty] | x
Call for Proposals Issued | [22 empty] | x | x
Prelim Proposals Heard | [23 empty] | x | x
Call for Final Proposals issued | [25 empty] | x
Present Final Proposals | [26 empty] | x | x | x
Baseline Proposal(s) Selected. | [28 empty] | x
Build Baseline | [28 empty] | x | x | x
Adopt Baseline | [30 empty] | x
Draft Ready for TG Review | [30 empty] | x | x
Comment Resolution / Complete Draft / Approval for Letter Ballot | [31 empty] | x | x
Draft Ready for 1st Letter Ballot | [32 empty] | x
Letter Ballot | [32 empty] | x | x
1st Letter Ballot Complete | [33 empty] | x
Resolve Comments | [34 empty] | x | x | x
1st Recirc | [36 empty] | x
1st Re-circulation Complete | [37 empty] | x
Resolve Comments | [37 empty] | x | x
2nd Recirc | [38 empty] | x | x
2nd Re-circulation Complete | [39 empty] | x
Resolve Comments | [39 empty] | x | x
3rd Recirc | [40 empty] | x
3rd Re-circulation Complete | [40 empty] | x
Resolve Comments / Approval for Sponsor Ballot | [40 empty] | x
Sponsor Ballot | [41 empty] | x | x
Sponsor Ballot Complete | [42 empty] | x
Resolve Comments | [42 empty] | x | x | x
1st Recirc | [44 empty] | x | x
1st Re-circulation Complete | [45 empty] | x
Resolve Comments | [45 empty] | x
2nd Recirc | [46 empty] | x
2nd Re-circulation Complete | [46 empty] | x
Resolve Comments | [47 empty] | x
3rd Recirc | [47 empty] | x
3rd Re-circulation Complete | [48 empty] | x
Comments Resolved | [48 empty] | x
EC Approval | [48 empty] | x
RevCom Approval | [49 empty] | x