## Slide 1
Project: IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Submission Title: [Timeline of TG4s]
Date Submitted: [16 March 2017]
Source: [Shoichi Kitazawa] Company [Koden TI/Muroran IT]
Address [Muroran, Hokkaido JAPAN]
Voice:[], FAX: [], E-Mail:[kitazawa@ieee.org]
Re: []
Abstract: [This document show timeline of the TG4s.]
Purpose: [For discussion.]
Notice: This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Slide 2: Timeline of TG4s

## Slide 3: Time planning
TG Kickoff September 2014
Editing1st Draft May 2015
Motion for Letter Ballot July 2016
Sponsor Ballot July 2017
Submission to RevCom December 2017

## Slide 4: Timeline planning
Year |  | 2014 |  |  |  |  |  | 2015 |  |  |  |  |  | 2016 |  |  |  |  |  | 2017 |  |  |  |  | 
Month |  | 1 | 3 | 5 | 7 | 9 | 11 | 1 | 3 | 5 | 7 | 9 | 11 | 1 | 3 | 5 | 7 | 9 | 11 | 1 | 3 | 5 | 7 | 9 | 11
SG | PAR & CSD development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
TG Work Items | Start TG |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Use Cases & TGD |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Editing Draft |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Letter Ballot |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | LB Comment Resolution |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Initial Sponsor Ballot |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | SB Comment Resolution |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Submission to RevCom |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 5: Reference
IEEE 802.15-14-0457r1