## Slide 1
Project: IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Submission Title: TG4r Sept 2014 next steps
Date Submitted: Sept 2014
Source: SS Benjamin Rolfe (BCA)
Abstract: Plan for next steps for near term activity
Purpose: Overview of activities
Notice: This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Slide 2: Next Steps and Support of TG 4r Sessions
September 2014

## Slide 3: Suggested Next Steps
Update Call for Proposal Time Lines
Extend time line for call for intend to Sept’14
Extended Time Line for Call for Preliminary Proposal –
  Complete TGD and issue CPP prior to November meeting (early responders)
  Extend time to hear preliminary proposals to Jan ’15
Extend Time Line for Call for Final Proposal – Jan ‘15 Meeting (Can begin presentations in January for early responders)
Sept ’14 to Nove’14
Consolidate into formal TGD over 2 conference calls
  Target to issue TGD and CPP 2 weeks prior to November meeting
  Discus schedule on the email reflector
.

## Slide 4: Next Steps
November 2014 Meeting:
Review presentations from “early responders”
Technical discussion to support proposal collaboration and development
.

## Slide 5: Outlook
Year |  | 2014 |  |  |  |  | 2015 |  |  |  |  | 
Month |  | 3 | 5 | 7 | 9 | 11 | 1 | 3 | 5 | 7 | 9 | 11
Approval of PAR and CSD |  |  |  |  |  |  |  |  |  |  |  | 
Technical Guidance Document |  |  |  |  |  |  |  |  |  |  |  | 
Call for Proposal | Call for Interest |  |  |  |  |  |  |  |  |  |  | 
 | Call for Preliminary Proposals |  |  |  |  |  |  |  |  |  |  | 
 | Presentation of Preliminary Propos. |  |  |  |  |  |  |  |  |  |  | 
 | Call for Final Proposals |  |  |  |  |  |  |  |  |  |  | 
Drafting | Presentation of Final Proposals |  |  |  |  |  |  |  |  |  |  | 
 | Alignment of Proposals |  |  |  |  |  |  |  |  |  |  | 
 | Build the first Draft for WG Ballot |  |  |  |  |  |  |  |  |  |  | 
WG Letter Ballot |  |  |  |  |  |  |  |  |  |  |  | 
Sponsor Ballot |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 6: Next Steps to Complete TGD – Chapters to Complete
Review changes made in Athens
Complete Application Requirements Matrix
Frequency Bands and related Regulations
  Clarify additional guidance, if necessary
Coexistence, Interoperability
Benchmarks, Channel Characteristics
  Review suggestions made in Athens
Complexity and Cost considerations

## Slide 7: Chapter: Application Requirements Matrix
Merge content from 15-14-0391-00-004r-technical-guidance-document-input-for-ami.ppt into this chapter
Collect more input from:
  TG4s – SRU – need specific questions to TG4s

## Slide 8: Chapter: Frequency Bands and related Regulations
Suggestion in Athens
  Include in High Level Requirements for proposals that the proposal should indicate the band or bands targeted for operation, if any;
  No further guidance or constraints on bands are needed at this time.

## Slide 9: Chapter: Coexistence, Interoperability
Incorporated coexistence criteria into the High Level Requirements for propsoals
  Proposals to present coexistence characteristics
  Compare and contrast during technical review

## Slide 10: Chapter: Benchmarks, Channel Characteristics
Suggestions from Athens
  Review models developed by past TGs and apply one or more existing models by reference
  It was suggested a particularly good model was done for TG4a (15-04-0662-04).

## Slide 11: Chapter: Complexity and Cost considerations
No new input

## Slide 12: Chapter: Energy and Power Consumption
Added new text from doc #15-14-0556-00 plus input from the task group discussion, incorporated text into TGD.