## Slide 1
Project: IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Submission Title: Closing Report for TG4q (ULP) Task Group, Jan 2015 Meeting
Date Submitted: Jan. 15, 2015
Source: Chiu Ngo, Samsung
75 W. Plumeria Drive, San Jose, CA 95134, USA
Abstract: Meeting Closing Report for TG4q (ULP) Task Group
Purpose: Summary on activities during the Jan meeting.
Notice: This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Slide 2: IEEE 802.15.4q Task Group
Closing Report
14th Meeting of the ULP Task Group
Atlanta, GA, USA
Jan 11-16, 2015

## Slide 3: January 2015 Session
Used 4 time slots
 | Tuesday | Wednesday | Thursday
AM1 | TG4q | TG4q | TG4q
AM2 | TG4q Cancelled |  | TG4q
PM1 |  |  | 
PM2 |  |  | 

## Slide 4: Achievement this week
Went over all 120 comments on the first recirculation letter ballot (#100) and provide preliminary resolutions.
About 60 comments were resolved.

## Slide 5: Plan for March Meeting
Comment resolution on recirculation ballot
Review of James Gilb’s proposal
Conditional approval of sponsored ballot

## Slide 6: Teleconferences
From now to Feb 15, 2015,
  Every Wednesday 7:00AM PST.
From Feb 16, 2015 to July 12, 2015
  Every Wednesday 7:00PM PST/8:00PM PDT

## Slide 7: TG4q Timeline
Preliminary work
  Call for applications Dec 2012
  Applications presentations Jan 2013
  TGD outline Mar 2013
  TGD, applications and channel modeling contribution call Mar 2013
  Review TGD contributions May 2013
  TGD Ongoing & review application contributions Jul 2013
Proposal effort
  Call for intent Jul 2013
  TGD completed Sep 2013
  Call for proposals Sep 2013
  Proposal presentations Nov 2013
Drafting
  First draft May 2014
  Ballotable draft Jul 2014

## Slide 8: TG4q Timeline (cont’)
Balloting
  WG letter ballot (#95) Oct 2014
  First WG LB recirculation (#100) Dec 2014
  Conditional approval of sponsored ballot Mar 2015
  Sponsor ballot Apr 2015
  First SB recirculation May 2015
  Conditional approval to submit to Revcom July 2015

## Slide 9: WG Motion: BRC
Move that the 802.15 WG approves the formation of a Ballot Resolution Committee (BRC) for the WG balloting of the 802.15.4q draft standard with the following membership: Shahriar Emami, Allan Zhu, Hendricus De Ruijter, Chandrashekhar Thejaswi PS, Jinesh Nair, Kiran Bynam, Youngsoo Kim and Chiu Ngo. The 802.15.4q BRC is authorized to approve comment resolutions on behalf of the 802.15 WG. Comment resolution between sessions will be conducted via reflector email and via teleconferences announced to the reflector at least 30 days in advance.
Moved by: Chiu Ngo Seconded by:

## Slide 10
Thank you!