## Slide 1
Project: IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Submission Title: [Proposed project timeline]
Date Submitted: [09 March 2015]
Source: [Andrew Estrada] Company [Sony Electronics, Inc]
Address [San Diego, CA, USA]
Voice:[+1.858.942.5483], E-Mail:[Andrew.Estrada@am.sony.com]
Re: [Proposed project timeline]
Abstract: []
Purpose: []
Notice: This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Slide 2: Schedule Plan Details
PAR/CSD Approval
  EC 2015 March 11
  NesCom 2015 March 27
WG Letter Ballot
  Initial 2016 Jan? (10 months from PAR)
  Recirc1
  Recirc2
Form Sponsor Ballot Pool
MEC/MDR Done
IEEE-SA Sponsor Ballot
  Initial 2017 Jan? (12 months from initial LB)
  Recirc
  Recirc
Final WG and EC approval
Final RevCom approval 2017 May (26 months total)

## Slide 3: How Long Does it Take?
Chart: Recently Published 802.11 standards
| 27.1 | 30 | 33.333333333333336 | 36.666666666666664 | 40 | 43.333333333333336 | 46.666666666666664 | 50 | 53.333333333333336 | 56.666666666666664 | 63.333333333333336
 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 2
Chart: Every 802.11 standard every published
| 15.466666666666667 | 20.638095238095236 | 25.809523809523807 | 30.980952380952381 | 36.152380952380945 | 41.323809523809523 | 46.495238095238093 | 51.666666666666664 | 56.838095238095235 | 62.009523809523806 | 67.180952380952377 | 72.352380952380955 | 77.523809523809533 | 87.86666666666666
 | 1 | 0 | 5 | 0 | 2 | 3 | 0 | 1 | 1 | 0 | 2 | 1 | 4 | 1
802.11ae
802.11 1999
802.11a,b,d,j

## Slide 4: Why So Long?
The Most Time Consuming Activities
Initial Draft
WG Letter Ballot

## Slide 5: Critical Tasks (802.11 history)
802.11j
802.11 2007
Chart: 1st Draft (From PAR to 1st Draft)
| 5.0999999999999996 | 7 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 26 | 28 | 34
 | 1 | 0 | 0 | 3 | 3 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 5
Chart: Letter Ballot (From 1st Draft to Sponsor Ballot)
| 6.5 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 47
 | 0 | 1 | 2 | 2 | 4 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 2
802.11h,z,ae