## Slide 1
Project: IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Submission Title: [Proposed project timeline]
Date Submitted: [09 March 2015]
Source: [Andrew Estrada] Company [Sony Electronics, Inc]
Address [San Diego, CA, USA]
Voice:[+1.858.942.5483], E-Mail:[Andrew.Estrada@am.sony.com]
Re: [Proposed project timeline]
Abstract: []
Purpose: []
Notice: This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Slide 2: Schedule Plan Details
PAR/CSD Approval
  EC 2015 March 11
  NesCom 2015 March 27
WG Letter Ballot
  Initial 2016 Jan? (10 months from PAR)
  Recirc1
  Recirc2
Form Sponsor Ballot Pool
MEC/MDR Done
IEEE-SA Sponsor Ballot
  Initial 2017 Jan? (12 months from initial LB)
  Recirc
  Recirc
Final WG and EC approval
Final RevCom approval 2017 May (26 months total)

## Slide 3: Letter Ballot details
January 2016 Session
  The TG and WG move to submit draft specification to Letter Ballot.
  WG submits to Letter Ballot at the end of the session
  30 days to issue all comments
  TG responds to all comments (as long as it takes)
  Recirculate 2nd draft specification

## Slide 4: Proposed Call for Proposal
May
Vancouver
10-15
July
Waikoloa 12-17
Sep
Bangkok
13-18
Initial
Presentations
Deadline 7 Sept
Issue Call 15 May
Call for Proposals
Full
Presentations
Finalize CMD and TGD
(Hiraga)

## Slide 5: How Long Does it Take?
Chart: Recently Published 802.11 standards
| 27.1 | 30 | 33.333333333333336 | 36.666666666666664 | 40 | 43.333333333333336 | 46.666666666666664 | 50 | 53.333333333333336 | 56.666666666666664 | 63.333333333333336
 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 2
Chart: Every 802.11 standard every published
| 15.466666666666667 | 20.638095238095236 | 25.809523809523807 | 30.980952380952381 | 36.152380952380945 | 41.323809523809523 | 46.495238095238093 | 51.666666666666664 | 56.838095238095235 | 62.009523809523806 | 67.180952380952377 | 72.352380952380955 | 77.523809523809533 | 87.86666666666666
 | 1 | 0 | 5 | 0 | 2 | 3 | 0 | 1 | 1 | 0 | 2 | 1 | 4 | 1
802.11ae
802.11 1999
802.11a,b,d,j

## Slide 6: Why So Long?
The Most Time Consuming Activities
TG Initial Draft
WG Letter Ballot

## Slide 7: Critical Tasks (802.11)
802.11j
802.11 2007
Chart: 1st Draft (From PAR to 1st Draft)
| 5.0999999999999996 | 7 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 26 | 28 | 34
 | 1 | 0 | 0 | 3 | 3 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 5
Chart: Letter Ballot (From 1st Draft to Sponsor Ballot)
| 6.5 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 47
 | 0 | 1 | 2 | 2 | 4 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 2
802.11h,z,ae

## Slide 8: What about 802.15?
26 months is still very aggressive.
Completing the 1st draft is the biggest challenge!
 | Total days from PAR approval to RevCom Final Approval | Total months from PAR approval to RevCom Final Approval | Months from PAR approval to 1st LB | Months from 1st LB approval to 1st SB
IEEE 802.15.3 - 2003 | 1247 | 41.6 | 23.3 | 11.2
IEEE 802.15.3b | 631 | 21.0 | 12.2 | 5.1
IEEE 802.15.3c | 1641 | 54.7 | 39.6 | 9.1