## Slide 1
Project: IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Submission Title: Suggested 15.7r1 Milestones and Schedule
Date Submitted: January 2015
Source: Rick Roberts, Intel Corporation
Voice: 503-712-5012 E-Mail: richard.d.roberts@intel.com
Re:
Abstract: This contribution presents a proposed timeline with milestones. It is offered to the committee which can adopt, modify or ignore the suggested timeline.
Purpose:
Notice: This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Slide 2
2015
2016
2017
2018
CFA Issued
CFA Responses
Finalize TRD and Release CFP
Hear CFP Proposals
Proposal mergers & Draft D0
Draft D1 & LB1
Draft D2 & LB2
Draft D3 & SB1
Draft D4 & SB2
15.7r1 to SA for publication
Timeline Summary
Details on the next four pages.
This contribution presents a proposed timeline with milestones. It is offered to the committee which can adopt, modify or ignore the suggested timeline.

## Slide 3
2015 |  |  | 
Q1 | January (Atlanta) | February | March (Berlin)
 | Affirm officers Update web page Approve schedule & milestone activities Release updated CFA |  | Hear CFA responses Start preparing (ad-hoc) TRD
Q2 | April | May (Vancouver) | June
 |  | (Hear CFA responses) TRD Editing Channel model discussion and finalization (if possible) | 
Q3 | July (Hawaii) | August | September (Bangkok)
 | Finalize channel model (if it is not done in May) Finalize and approve TRD Start preparation CFP (and challenge to release CFP) |  | Finalize and release CFP
Q4 | October | November (Dallas) | December
 |  | Hear CFP responses | 

## Slide 4
2016 |  |  | 
Q1 | January | February | March
 | Hear remaining CFP responses Start proposal mergers |  | Continue proposal mergers Start preparation of revision baseline D0
Q2 | April | May | June
 |  | Finalize revision baseline draft D0 Commence task group review and comment resolution | 
Q3 | July | August | September
 | Continue task group review and comment resolution |  | Finalize first WG letter ballot (LB) draft D1 Submit D1 to WG for LB1
Q4 | October | November | December
 |  | Start LB1 comment resolution | 

## Slide 5
2017 |  |  | 
Q1 | January | February | March
 | Finish LB1 comment resolution Prepare draft D2 Submit D2 to WG for LB2 |  | LB2 comment resolution Prepare D3 for SB1
Q2 | April | May | June
 |  | Commence SA LB3 comment resolution | 
Q3 | July | August | September
 | Finish SB1 comment resolution Prepare D4 for submittal for SA SB2 |  | Do LB4 comment resolution Prepare draft D4 for SA submittal final approval
Q4 | October | November | December
 |  | Resolve final SA editorial comments and prepare final draft D5 for submittal for publication | 

## Slide 6
2018 |  |  | 
Q1 | January | February | March
 | Have publication party! |  | 
Q2 | April | May | June
Q3 | July | August | September
Q4 | October | November | December