## Slide 1
Project: IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Submission Title: Suggested 15.7r1 Milestones and Schedule
Date Submitted: July 2015
Source: Yeong Min Jang [Kookmin University], Rick Roberts [Intel Corporation]
Voice: +82-2-910-5068, 503-712-5012 E-Mail: yjang@kookmin.ac.kr, richard.d.roberts@intel.com,
Re:
Abstract: This contribution presents a proposed timeline with milestones. It is offered to the committee which can adopt, modify or ignore the suggested timeline.
Purpose:
Notice: This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.
doc.: IEEE 802.15-15-0274-04-007a
Submission

## Slide 2
2015
2016
2017
2018
CFA Issued
CFA Responses
Finalize TCD and Release CFP
Hear CFP Proposals
Proposal mergers & Draft D0
Draft D1 & LB1
Draft D2 & LB2
Draft D3 & SB1
Draft D4 & SB2
15.7r1 to SA for publication
Timeline Summary
Details on the next four pages.
This contribution presents a proposed timeline with milestones. It is offered to the committee which can adopt, modify or ignore the suggested timeline.
doc.: IEEE 802.15-15-0274-04-007a
Submission

## Slide 3
2015 |  |  | 
Q1 | January (Atlanta) | February | March (Berlin)
 | Affirm officers Update web page Approve schedule & milestone activities Release updated CFA |  | Hear CFA responses Start preparing (ad-hoc) TRD
Q2 | April | May (Vancouver) | June
 |  | (Hear CFA responses) TCD Editing Channel model discussion | 
Q3 | July (Hawaii) | August | September (Bangkok)
 | Channel model discussion Finalize and approve TCD Start preparation CFP |  | Channel model finalized Finalize and release CFP
Q4 | October | November (Dallas) | December
 |  | Hear Call for Intent Start Proposal discussion | 
doc.: IEEE 802.15-15-0274-04-007a
Submission

## Slide 4
2016 |  |  | 
Q1 | January | February | March
 | Hear CFP responses Continue proposal mergers |  | Present revised proposals Continue proposal mergers Start preparation of revision baseline D0
Q2 | April | May | June
 |  | Finalize revision baseline draft D0 Commence task group review and comment resolution | 
Q3 | July | August | September
 | Continue task group review and comment resolution |  | Continue task group review and comment resolution
Q4 | October | November | December
 | Release draft D1 | Start comment resolution against D1 | 
doc.: IEEE 802.15-15-0274-04-007a
Submission

## Slide 5
2017 |  |  | 
Q1 | January | February | March
 | Continue comment resolution against D1 Prepare draft D2 | Comment resolution to delete against unnecessary parts of D1 | Finish comment resolution against D1 Prepare draft D2
Q2 | April | May | June
 | Release Draft D2 | Request conditional approval for Letter Ballot Prepare D3 | Release D3 Letter Ballot 1
Q3 | July | August | September
 | LB1 comment resolution | Release D4 Letter Ballot 2 | LB2 comment resolution
Q4 | October | November | December
 | Release D5 | SB1 | SB1 comment resolution
doc.: IEEE 802.15-15-0274-04-007a
Submission

## Slide 6
2018 |  |  | 
Q1 | January | February | March
 | SB1 comment resolution | SB2 (??) | SB2(??) SB2 comment resolution
Q2 | April | May | June
 |  | SA review | 
Q3 | July | August | September
 | Publish the standard IEEE802.15.7-2018 Have a party! |  | 
Q4 | October | November | December
doc.: IEEE 802.15-15-0274-04-007a
Submission