## Cover
Project: IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Submission Title: TCD Comments
Date Submitted: May 2015
Source: Rick Roberts Company: Intel
Address
Voice: FAX: E-Mail: richard.d.roberts@intel.com
Re:
Abstract:
Purpose: This document was constructed by the 15.7r1 technical editor to assist the committee in generating the technical guidance document.
Notice: This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Comments
Number | Clause | Comment | Suggestion | Resolution
1 | 2 | reference to VLC | Replace with OWC (Optical Wireless Communications) | accepted
2 | 2 | Typical constraint considerations list | Add coexistence to the list | accepted
3 | 4 | Optical Camera Communications | delete word "short-range" | accepted
4 | 4.1.1 | Offline to Online Marketing | Not familiar with this term - can a link to a definition be provided? | Aoyama-san to provide link
5 | 4.1.1 | Internet of Light (IoL) | Not familiar with this term - can a link to a definition be provided? | Call this classification IoT (M2M, D2D, IOL) … professor Jang to provide link to IOL definition
6 | 4.1.2 | Device Table - Flash Light | Should we add A2? | Add A2
7 | 4.1.2 | Device Table - Indirect Light | Believe A4 should not be included - suggest remove A4 | reject - leave A4 in place, this is of interest to Panasonic
8 | 4.1.2 | Illuminated signage | What does with/without front panel mean? | Rick to edit text for clarification. Front panel means LED backlighting and without front panel means discrete LEDs form sign. Rick to edit text.
9 | 4.1.2 | Illuminated signage | Should we add A2? | Add A2
10 | 4.1.2 | Digital Signage | Should we add A2? | Add … also digital signage is like an LCD monitor display. Rick to provide clarification.
11 | 4.1.2 | Traffic Light | Rename to Traffic Light and Intelligent Traffic System (ITS) | accepted
12 | 4.1.2 | Traffic Light | Should we add A1 and A2? | add a1 and a2
13 | 4.1.2 | Lighthouse | Should we add A1? | add a1
14 | 4.1.2 | Indirect Light | Believe we should remove A4. | reject - see comment 7
15 | 4.1.3 | Reference to sequenctial shutter | Is sequential shutter the same as rolling shutter? If so then suggest that we include reference to rolling shutter since this is a common term. | accepted
16 | 4.1.6 | Last sentence for allowed flicker | Add A3 to allowed flicker? | accepted
17 | 4.1.6 | In regards to "flicker free PHY" … if the light is IR then is flicker a concern for any user cases. | Modify this clause to exclude IR sources from flicker consideration. | accepted in priniciple - if the eye can't see it then we can relax flicker requirement
18 | 4.1.7 | Dimming control | Add A2 to the list. | Accepted
19 | 4.1.8 | Confused by the range of distances. | Ranges are given but how do we interprete this? This needs to be clarified. | Delete reference to distances - delete the first paragraph in 4.1.8.
20 | 4.1.8 | Performance comparison information | Where did "size of 1 meter" and 300 Cd/m2 originate? What does it mean and how is it applied? | Replace 4.1.8 with a clause that indicates performance comparison criteria will be determined by the committee at the time the need arises.
21 | 4.1.11 | Coexistence | Need to add reference to coexistence with existing 15.7 PHYs | accepted
22 | 4.1.12 | MIMO | Need to add MAC protocol to support MIMO so a camera knows how to process the multiple transmitters. | accepted
23 | 4.1.12 | Multiple ingest of uncoordinated transmitters | Does this clause include the case where the camera is ingesting multiple uncordinated transmitters (not MIMO)? This is in reponse to CFA responses that indicated "At least one OCC PHY mode that works with spatially separated LED light sources; that is, it must support simultaneous ingest of data from multiple uncoordinated spatially separated LED light sources. That is, it should be possible to receive multiple simultaneous transmissions, in any stable environment, with easy discovery and reception". | Yes - this clause does support this.
24 | 4.1.12 | Delete some text | Think we should delete the following phrase "because reflected light is not bright enough to employ complicated modulation scheme for mixed signal separation". This added information is not relevant to the TCD. | delete
25 | 4.1.13 | Identification of Transmitter | I don't understand the purpose of this clause. Can this clause be linked to one of the CFA responses so I can understand where this came from? | Intel (Rick) to edit for clarification.
26 | 4.1.14 | Error Detection | This clause is not a requirement but rather is technical implementation detail that would be presented by a proposer. Please delete it. | Delete the FEC clause and replace it with a performance clause to be determined by the committee.
27 | 4.1.15 | Waveform | The proposers will bring in proposals with different modulation formats. IMHO this is not a TCD issue. Please delete. | delete
28 | 4.1 | Add protocol management clause to TCD | Suggested text … "The standard shall address mechanisms that allow the camera enabled receiver MAC to ascertain what is the modulation format being used by a particular transmitter so as to be able to decode the modulation properly". | Table till Thursday
29 | 4.2.3 | PHY mode that allows optimal use of available bandwidth | Please modify to "PHY mode that allows optmal cost trade-off using the available bandwidth". This avoids the situation of including an optimal technical solution that is not cost effective. | Table till Thursday
30 | 4.2.6 | Communication Range | How do we interprete given distance ranges? The text seems to be ambiguious. | delete first paragraph and keep 2nd paragraph
31 | 4.2.7 | Multiple User Support | I don't understand what is meant by "users receiving different data streams from the same light source". So you mean time sequentially (TDMA) or simulataneously (CDMA)? Please clarify. | Clarification provided - no changes
32 | 4.2.8 | Asynchronous Communication | What is meant by asynchronous communication? Does this mean the clocks aren't synchronized like in RS-232? Please clarify. | Meant Asymmetric not asynchronous - change accordingly
33 | 4.2.9 | Handover and interference coordination | Is this in-scope? We are doing a PHY and MAC. How does this relate to the PHY/MAC? | This will be the topic of a session with Mr. Heile
34 | 4.2.11 | Coexistence | Add coexistence with existing 15.7 PHY modes. | accepted
35 | 4.2.13 | Error Detection | This clause is not a requirement but rather is technical implementation detail that would be presented by a proposer. Please delete it. | delete
36 | 4.2.14 | Waveform | The proposers will bring in proposals with different modulation formats. IMHO this is not a TCD issue. Please delete. | Table till Thursday
37 | 4.1.X | Add the following based upon ref 2 | The standard will support at least one OCC PHY mode that works when the LED light source appears as nearly a point source; that is, the LED illuminates only a small number of image pixels. | accepted
38 | 4.1.X | Add the following based upon ref 2 | The standard will support at least one OCC PHY mode that simultaneously allows OCC modulated LED light sources to be identified at a low camera frame rate and then demodulated at a high camera frame rate using region-of-interest sub-sampling. | accepted
39 | 4.1.X | Add the following based upon ref 2 | The standard will support at least one OCC PHY mode that supports OCC transmission, at very short range, in excess of 100 Kchipsper second using camera frames rates equal to or less than 30 frames per second. | Table till Thursday
40 | 4.1.X | Add the following based upon ref 2 | The standard will support at least one OCC MAC mode that supports repetitive informational broadcast at very low data rate; that is, the frame format has very little overhead and is optimized for short payloads sent in a repetitive manner. | accepted
41 | 4.1.X | Add the following based upon ref 2 | Provide at least one OCC MAC mode that supports unidirectional data transmission from one or more coordinated or uncoordinated LED lights. | all ready covered - no edits required
42 | 4.1.X | Add the following based upon ref 7 | The standard will support at least one PHY mode that supports rolling shutter camera communications in line-of-sight scenarios, having the ability to decode even with loss of a large portion of signal samples, due to either: (1) long time gap between exposure periods of consecutive image frames; (2) large TX-RX distance; or (3) unsynchronized TX (light) & RX (camera). | reject
43 | 4.1.X | Add the following based upon ref 7 | The standard will support a PHY mode using rolling shutter sampling that is compatible to a variety of cameras with different rolling shutter sampling rates (read-out time), resolution, and frame rates. | Table till Thursday
44 | 4.1.X | Add the following based upon ref 3 | The standard will support OCC unidirectional, low rate, ID beacon - or simple data transmission - at pulse rates varying from 5Hz – 120Hz, with a short frame format to ensure acceptable low rate response times. | reject