## Tabelle1
IEEE Doc. | 15-15-0757-01-003d
ToDo before the Call for Proposals
| Channel Model Document | Done
Update Table of Contents
Table of definitions has to be filled
Crosscheck if Methodology is consistent with all the chapters
| Chapter 4: Close Proximity P2P Application still requires input | 2015-11-09 | Measurements have been presented
Chapter 5 Intra-Device: Channel Modell Material has to be added
| Chapter 6 Front-/Backhaul: Scenario Definitions have to be defined (Parametersets) | 2015-11-09
| Chapter 7 data center: Check if scenario definitions should be added | 2015-11-09
| Check if all the numbering is consistent (tables, figures, chapters) | 2015-11-11 | Final Check in January
Technical Requirements Document
| Table of definitions has to be filled | 2015-11-10
| TRD summary has to written | 2015-11-10
| Check if all the numbering is consistent (tables, figures, chapters) | 2015-11-10
| References have to be checked (obsolete? Numbering) | 2015-11-10 | Final check in January
Evaluation Criteria Document
All references to the other documents have to be check for the correct revision
| Chapter 4 has to be updated in respect to 3e | 2015-11-11
Chapter 5.4 maybe figures of merit of the RF impairments should be included as reference
Chapter 5.5 Include Values from CMD when it is finished.
Chapter 5.6 Input has to be provided for values regarding power consumption.
Check if all the numbering is consistent (tables, figures, chapters)