## Slide 1
Project: IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Submission Title: Closing Report for TG4q (ULP) Task Group, Nov. 2015 Meeting
Date Submitted: November 12, 2015
Source: Chiu Ngo, Samsung
665 Clyde Ave, Mountain View, CA 94043, USA
Abstract: Meeting Closing Report for TG4q (ULP) Task Group
Purpose: Summary on activities during the Nov’15 meeting.
Notice: This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Slide 2: IEEE 802.15.4q Task Group
Closing Report
19th Meeting of the ULP Task Group
Dallas, TX, USA
Nov. 9~12, 2015

## Slide 3: Nov. 2015 Sessions
Secretary: Chandrashekhar Thejaswi PS
Total of 5 time slots
 | Monday | Tuesday | Wednesday | Thursday
AM1 |  |  |  | 
AM2 |  |  |  | TG4q (Gaston B)
PM1 | TG4q (Gaston B) |  | TG4q (Baker) | 
PM2 |  | TG4q (Baker) |  | TG4q (Gaston B)

## Slide 4: Achievement this week
Reviewed and approved the comment resolution for the second recirculation sponsor ballot on 802.15.4q draft spec. (D7.0).
Reviewed the 5C conditions for 802.15.4q draft spec. (D7.0) and affirmed that the 5C conditions were met.
Prepared an EC conditional approval package for submission 802.15.4q draft spec. (D7.0) to RevCom.
Approved a motion to request 802.15 WG to seek conditional approval from EC to submit the 802.15.4q draft D7.0 to RevCom
Reaffirmed the sponsor BRC

## Slide 5: TG Motion: 5C Conditions
The 802.15.4q TG has reviewed the 5C and moves to affirm that the conditions of 5C (DCN 15-12-0387-06) for IEEE 802.15.4q draft D7.0 have been met.
  Moved by: Hendricus De Ruijter
  Seconded by: Chandrashekhar Thejaswi PS
  Y/N/A: 7/0/0 (PASSED)

## Slide 6: TG Motion: Submission 802.15.4q draft spec. to RevCom
Move the 802.15.4q TG to request 802.15 WG to seek conditional approval by EC for forwarding the 802.15.4q draft D7.0 (with the condition of correct referencing to the latest 802.15.4REV draft ) to RevCom.
  Moved by: Kiran Bynam
  Seconded by: Hendricus De Ruijter
  Y/N/A: 5/0/0 (PASSED)

## Slide 7: TG Motion: Reaffirmation of Sponsor BRC
Move that the 802.15.4q TG requests 802.15 WG to reaffirm the Ballot Resolution Committee (BRC) for the sponsor balloting of the 802.15.4q draft standard with the following membership:
The 802.15.4q BRC is authorized to approve sponsor ballot comment resolutions and the start of recirculation ballots of the 802.15.4q draft on behalf of the 802.15 WG. Comment resolution between sessions will be conducted via reflector email and via teleconferences announced to the reflector at least 30 days in advance.
  Moved by: Hendricus De Ruijter
  Seconded by: Allan Zhu
Y/N/A = 7/0/0 (PASSED)
  Chiu Ngo (Chair)
  Allan Zhu (Huawei)
  Hendricus De Ruijter (Silicon Labs)
  Youngsoo Kim (Samsung)
  Guido Dolmans (IMEC)
  Kiran Bynam (Samsung)
  Chandrashekhar Thejaswi PS (Samsung)

## Slide 8: Teleconferences
From Aug 17, 2015 to Mar. 13, 2016
  Every Monday and Wednesday 7:00PM PST (before US Daylight Saving started, 8:00PM PDT)

## Slide 9: TG4q Timeline
Preliminary work
  Call for applications Dec 2012
  Applications presentations Jan 2013
  TGD outline Mar 2013
  TGD, applications and channel modeling contribution call Mar 2013
  Review TGD contributions May 2013
  TGD Ongoing & review application contributions Jul 2013
Proposal effort
  Call for intent Jul 2013
  TGD completed Sep 2013
  Call for proposals Sep 2013
  Proposal presentations Nov 2013
Drafting
  First draft May 2014
  Ballotable draft Jul 2014

## Slide 10: TG4q Timeline (cont’)
Balloting
  WG letter ballot (#95) Oct 2014
  First WG LB recirculation (#100) Dec 2014
  Second WG LB recirculation (#101) Feb 2015
  Third WG LB recirculation (#105) Apr 2015
  Fourth WG LB recirculation (#107) May 2015
  Approval of sponsor ballot Jun 2015
  Sponsor ballot Jun 2015
  First SB recirculation Sept 2015
  Second SB recirculation Oct 2015
  EC Conditional Approval to submit to RevCom Nov 2015
  Third SB recirculation Dec 2015
  RevCom Approval Mar 2016

## Slide 11: Plan for Jan’16 Meeting
Comment resolution for sponsor ballot recirc.
  Finalize material for RevCom approval

## Slide 12
Thank you!

## Slide 13: WG Motion: Reaffirmation of Sponsor BRC
Move that 802.15 WG to reaffirm the Ballot Resolution Committee (BRC) for the sponsor balloting of the 802.15.4q draft standard with the following membership:
The 802.15.4q BRC is authorized to approve sponsor ballot comment resolutions and the start of recirculation ballots of the 802.15.4q draft on behalf of the 802.15 WG. Comment resolution between sessions will be conducted via reflector email and via teleconferences announced to the reflector at least 30 days in advance.
  Moved by: Chiu Ngo
  Seconded by:
  Chiu Ngo (Chair)
  Allan Zhu (Huawei)
  Hendricus De Ruijter (Silicon Labs)
  Youngsoo Kim (Samsung)
  Guido Dolmans (IMEC)
  Kiran Bynam (Samsung)
  Chandrashekhar Thejaswi PS (Samsung)

## Slide 14: Other 802.15.4q-related WG Motions

## Slide 15
END