## IEEE_Cover
| doc name: | TG4t-HR-Timeline
| doc. #: | 15-16-0xxx
| date: | 2016-01-19
IEEE P802.15
Wireless Personal Area Networks
Project | IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Title | 802.15 TG4t HR Timeline
Source | Clint Powell | E-mail: cpowell@ieee.org
Re: | Timeline for 802.15 TG4t (HR)
Abstract | 802.15 TG10 Timeline
Purpose | [This document is an estimated timeline for the 802.15 TG4t (HR) Project.]
Notice | This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## TG10 Timeline
| 2015 | [5 empty] | 2016 | [11 empty] | 2017
| 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
PAR and 5C Approved |  |  |  |  | x
Task Group Formed |  |  |  |  | x
Call for Intent | [5 empty] | x | x
Technical Guidance Document | [6 empty] | x
Call for Proposals | [6 empty] | x | x | x
Hear Proposals | [8 empty] | x
Baseline Proposal(s) Selected. | [8 empty] | x
Build Baseline Draft | [8 empty] | x | x
Adopt Baseline draft | [9 empty] | x
Draft Ready for TG Review | [9 empty] | x
802.15 Tech Editor Rvw | [9 empty] | x
802.15 Expert Panel Rvw | [9 empty] | x
Comment Resolution / Complete Draft / Approval for Letter Ballot | [10 empty] | x
Draft Ready for 1st Letter Ballot | [10 empty] | x
Letter Ballot | [10 empty] | x | x
1st Letter Ballot Complete | [11 empty] | x
Resolve Comments | [11 empty] | x | x
1st Recirc | [12 empty] | x | x
1st Re-circulation Complete | [13 empty] | x
Resolve Comments | [13 empty] | x
MEC Review | [11 empty] | x | x
Sponsor Ballot Pool Invite | [12 empty] | x | x
WG/EC Sponsor Ballot Approval | [12 empty] | x
Sponsor Ballot | [13 empty] | x | x
Sponsor Ballot Complete | [14 empty] | x
Resolve Comments | [14 empty] | x
1st Recirc | [14 empty] | x | x
1st Re-circulation Complete | [15 empty] | x
Resolve Comments | [15 empty] | x
2nd Recirc | [15 empty] | x
2nd Re-circulation Complete | [15 empty] | x
Resolve Comments | [15 empty] | x | x
EC Approval | [16 empty] | x
RevCom Approval | [17 empty] | x
IEEE Editor Review and Prep | [18 empty] | x | x | x
Editors Cooridnation | [19 empty] | x | x
Publish | [21 empty] | x