## Slide 1
Project: IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Submission Title: [802.15.3e Status Report for May 2016 Session]
Date Submitted: [18 May 2016]
Source: [Andrew Estrada] Company [Sony]
Address [San Diego, CA, USA]
Voice:[+1.858.942.5483], E-Mail:[Andrew.Estrada@am.sony.com]
Re: [802.15.3e Status Report for May 2016 Session.]
Abstract: [Status Report for the May Session]
Purpose: []
Notice: This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Slide 2
IEEE 802.15.3e
High Rate Close Proximity (HRCP)
Status Report
Waikoloa
May 16-19, 2016

## Slide 3: Letter Ballot 119 (Recirc)
Aggregated results:
Return rate was >50% and the abstain rate was <30%, so the ballot is valid. Affirm rate is >75%: Ballot passes
VOTERS | 103 | 103
VOTED | 71 | 72
YES | 65 | 66
ABSTAIN | 2 | 2
NO | 4 | 4
% VOTERS | 68.93% | 69.90%
% YES | 94.20% | 94.29%
% ABSTAIN | 2.82% | 2.78%
Draft Std P802.15.3e | D1.0 | D2.0

## Slide 4: Schedule Plan Details (updated 16 May ‘16)
PAR/CSD Approval
  EC 2015 March 11
  NesCom 2015 March 27
WG Letter Ballot
  Initial 2016 Jan
  Recirc1 (15 days) 2016 May
  Recirc2 (15 days)
  Recirc3 (15 days)
Form Sponsor Ballot Pool
MEC/MDR Done
IEEE-SA Sponsor Ballot
  Conditional EC approval 2016 June 7
  Initial 2016 July
  Recirc1
  Recirc2
Final WG and EC approval
Final RevCom approval 2016 Sep – 2017 May

## Slide 5: Timeline
Jan ‘16
Atlanta
17-22
We are Here!
Mar ‘16
Macau
14-17
May ‘16
Waikoloa
16-19
Jul ‘16
San Diego
25-28
Start Sponsor Ballot
Start Letter Ballot
Recirc 1
Recirc 2
Recirc 3

## Slide 6: Conditions to Start Sponsor Ballot
No new valid no voters
No new valid “must be satisfied” comments supporting valid no votes

## Slide 7: Sponsor Ballot Periods
Initial Ballot is 30 days
Recirc Ballots are at least 10 days

## Slide 8: June 7?
June 7 is the next EC call
TG3e is on the agenda for conditional approval to start sponsor ballot
What do we need by June 7?
  Ballot history
    Aggregated results for each ballot
    Explain remaining comments from No voters

## Slide 9: Conditional Approval
Conditional means that any action taken to resolve No votes gets circulated.
Once these conditions are met, then 802.15 is authorized to start sponsor ballot.

## Slide 10
Thank You!