## IEEE_Cover
September 2016 |  | P802-15-4t_Consolidated_Comments
IEEE P802.15
Wireless Personal Area Networks
Project | IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Title | 802.15.4t Letter Ballot Consolidated Comments
Date Submitted | Monday, September 5, 2016
Source | Clint Powell | Voice: 480-586-8457
PWC, LLC
| Chandler, AZ 85248 US | E-mail: cpowell@ieee.org
Re: | P802.15.4t-D01, D02, D03
Abstract | 802.15 TG4t Comments for Letter Ballot
Purpose | [This document is used to submit comments for TG4t Letter Ballot.]
Notice | This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## LB123 Comments
CID # | Name | Affiliation | Page | Sub-clause | Line # | Comment | Proposed Change | Must Be Satisfied? (enter Yes or No) | Comment Type | Resolution
1001 | Kenichi Mori | Space Time Engineering | ii |  | 1 | Phrase of "IEEE Std 802.15.4 current revision" is ambiguous. It should clarify version or revision number of the baseline document. | Change from "IEEE Std. 802.15.4 current revision" to "IEEE Std. 802.15.4-2015." | Yes | E | Revised. Change to "IEEE Std 802.15.4-2015" (it should be "Std" instead of "Std.").
1002 | Henk de Ruijter | Silicon Labs | 3 | 7.4 | 14 | The PAR mentioned backwards compability with the O-QPSK PHY, However, there is no mechanism for the device to decide what PHY should be used. | Make the RS-GFSK Link Margin IE available for these two PHY's or make the RS-GFSK Link Margin IE available for all 802.15.4 PHYs. This IE is specified in the 15.4q amendment, see clause 7.4.4.32. | Yes | T | Revised. See doc 15-16-0480-00-004t for resolution details.
1003 | Shusaku Shimada | schubiquist Technologies Guild | 4 | 10.1.2.6 | 15 | Cannel number 57 to 72 on channel page 7 should be channel number 11 to 26 on chnnel page 0. Avoid too much chennel number and page complexities. | Text as in comment. Delete Table 10.8a. | Yes | T | Rejected. Following the proposed change would mean having two different modulation schemes using the same channel page/channel number combination. While this is done in other places (e.g., SUN PHY), there is no mechanism to be able to differentiate between the modulation schemes in this case.
1004 | Ed Callaway | ARM, Inc. | 4 | 10.1.2.6 | 21 | "The selection of specific channels is out of the scope of this standard, being performed by higher layers." We cannot specify what is, or is not, to be performed by higher layers. | "The selection of specific channels is out of the scope of this standard." | No | T | Accepted.
1005 | Verotiana Rabarijaona | NICT | 4 | 10.1.2.6 | 25 | The title of Table 10-8 says "for 250 kb/s data rate" whereas the text on l.17 says "data rate other than 2000 kb/s" | Replace with "for 'up to' 250 kb/s data rate" or fix the apparent conflict | No | T | Revised. In line 17, change "operating at a data rate other than 2000 kb/s" to "operating at 250 kb/s." Also change line 14 from "for all data rates except 2000 kb/s" to "for the 250 kb/s data rate" for consistency.
1006 | Kunal Shah | Silver Spring Networks | 7 | 18.1 | 6 | The sentence mentions, "PHR field shall be formatted either as illustrated in Figure 18-0a or Figure 18-0b". As the sentence specifies "Shall" and also provides options for the PHR field, so it is contradicting the purpose. Also Figure 18-0b is extension of Figure 18-0a, so is it require to have two separate figures for PHR format? | One of the option is have Figure 18-0a to be defined as the format for PHR. The explaination can be included for the Extended PHR field to explain the possible options when extended PHR field is set to zero and one. When extended PHR field is set to zero, the figure 18-0b can include only the Frame Length MSB and Reserved fields. Figure 18-0b doesnt need to include the complete PHR format. | Yes | T | Revised. For part one, change "shall be" to "is." For part two, the choice of PHR configurations is most clearly illustrated by the use of two figures.
1007 | Charles Perkins | Futurewei | 7 | 18.1.1 | 12 | Second sentence should be in clause 18.1 |  |  | E | Rejected. Clause 18.1 does not define the individual fields. The purpose of the subclauses 18.1.1-18.1.3 is to define the fields.
1008 | Kunal Shah | Silver Spring Networks | 7 | 18.1.2 | 16 | When exteded PHR field is set to zero, the PHR is 1 octect and when PHR field is set to 1, the PHR is 2 octect. | Clarify and modify the sentence to avoid the confusion. | Yes | E | Rejected. Because we are keeping both Figure 18-0a and Figure 18-0b, no change is necessary. The PHR lengths are given in the Figures.
1009 | Ed Callaway | ARM, Inc. | 7 | 18.1.2 | 18 | "This field also indicates the length of the FCS described in 7.2.10." As written, this means that the Extended PHR field indicates the length of the FCS that is described in 7.2.10, when the Extended PHR field is just one bit in length and can do no such thing. What we mean to say is that the manner in which the FCS indicates the length of the Extended PHR field is described in 7.2.10. We can say this by a slight edit: "This field also indicates the length of the FCS, as described in 7.2.10." | Make it so. | No | E | Accepted.
1010 | Ed Callaway | ARM, Inc. | 7 | 18.1.2 | 18 | "The length of the FCS is selected by the transmitting MAC in an implementation-dependent manner." I think what we mean to say here is, "The value of the Extended PHR field is selected by the transmitting MAC in an implementation-dependent manner, consistent with the requirement that frames having a frame length greater than 127 octets shall have the Extended PHR field set to one." Otherwise, this sentence releases the implementer from any requirements on the Extended PHR field value at all. I would further suggest moving this sentence to the end of the previous paragraph, since with the proposed change it no longer mentions the length of the FCS explicitly and so now seems out of place. | Make it so. | Yes | E | Accepted.
1011 | Liang Li | Vinno | 8 | 18.4.4 | 7 | not explain why and how to choose 2000k/b rate. | Must explain an clear explanation | Yes | T | Withdrawn by commenter.
1012 | Charles Perkins | Futurewei | 8 | 18.2 | 8 | Text says data rate has to be 250 kbs, but table has other entries |  |  | T | Revised. Change sentence to the following: "When operating in the 433 MHz band, the mandatory data rate of the MSK PHY shall be 250 kb/s; all other data rates are optional."
1013 | Verotiana Rabarijaona | NICT | 8 | 18.2 | 8 | Cap "the" before "mandatory" | See comment | No | E | Rejected. The punctuation after "band" is a comma. It's difficult to see because the text is underlined. Therefore, no change is necessary.
1014 | Kenichi Mori | Space Time Engineering | 8 | 18.2 | 9 | Sentence "When operating in the 2450 MHz band, the device shall support at least one of the data rates listed." may mean that not supporting 250kbps mode is allowed. However, PAR mentions backwards-compatibility is necessary. From this point of view, this sentence should be revised to guarantee the backwards-compatibility with already existing O-QPSK PHY. | First, it may be better to give a special PHY name for this standard, e.g. HT-OQPSK (high throughput OQPSK) to distinguish from other IEEE 802.15.4 PHYs. And it may be better to say that "When operating in the 2450MHz band, HT-OQPSK devise shall support two data rates, 250kbps and 2000kbps." | Yes | T | Revised. Part 1: A backwards compatibility mode will be added for devices that have both the 2Mb/s PHY and the 250 kb/s O-QPSK PHY implemented, in which case the receiver shall be capable of receiving an O-QPSK frame or a 2Mb/s frame, whichever comes first (see doc. # 15-16-0523-01 for complete resolution details). Part 2: Regarding the PHY name: We attempted to assign a special PHY name for the standard. However, since we are only adding a new data rate for an existing PHY, we found the resulting text was more confusing. Therefore, we decided not to assign a new name.
1015 | Ed Callaway | ARM, Inc. | 9 | 18.5.2 | 12 | This is a quibble, but in the list "The given range is ±100 kHz for 31.25 kb/s, ±300 kHz for 100 kb/s . . ." I think it would help to insert "the data rate of" in the first pair of numbers, just to make clear where the numbers came from: "The given range is ±100 kHz for the data rate of 31.25 kb/s, ±300 kHz for 100 kb/s . . . ." Just for the first pair, since we are deleting the data rate reference later in the paragraph. | Make it so. | No | E | Accepted.
1016 | Shusaku Shimada | schubiquist Technologies Guild | 9 | 18.5.2 | 14 | ¦f-fc¦>3.5MHz in Table 18-5 could be ¦f-fc¦>3MHz, according to 15.4 MSK convention, however any specific adjacent coexistence assurance analysys is not required due to coherence with O-QPSK convention. | Replace 3.5MHz with 3.0MHz if reasonably correct. | Yes | T | Rejected. The transmit PSD limits are the same as the O-QPSK PHY Table 12-4, since the chip rate of O-QPSK is the same as the data rate of the 2000 kbps MSK PHY.

## LB125 Comments
CID # | Name | Affiliation | Page | Sub-clause | Line # | Comment | Proposed Change | Must Be Satisfied? (enter Yes or No) | Comment Type | Resolution
2001 | Tero Kivinen | INSIDE Secure | 5 | 7.4.4.33 | 23 | This version changed the RS-GFSK Device Capabilities IE to be generic Device Capabilities IE, just to be able to reuse the Link Margin IE field. This left parts of the IE content bit unclear, as they are only relevant for the RS-GFSK PHY. For example the Rate Switch, short PHR and FEC fields are not relevant for other PHYs than RS-GFSK. Their definitions still refer to the RS-GFSK PHY in section 32. On the other hand Frequence Bands supported is something that is supported by other PHYs, but the text refers to the table 10-4c which is only relevant to the TASK and RS-GFSK PHYs. How is this filled in when not using RS-GFSK PHY? Are we still using same table 10-4c, or do we use PHY specific table. Also there are multiple PHYs which support MCS, but the text for PHY MCS Levels supported only refers to the table 32-2 which is only relevant for the RS-GFSK PHY. | If the RS-GFSK Device Capabilities IE is made generic for all PHYs, make it really so. Do not leave it half way and only change the IE names. Make sure it can have relevant information in it, if it supposed to be used in other PHYs. | Yes | T | Revised. All changes to the RS-GFSK Device Capabilities IE will be removed. Add the following text to the second paragraph of 6.17, after the first sentence: "If a device supports more than one data rate, it may use the information contained in the Link Margin IE to determine that the link margin is sufficient to support a higher data rate. " A new Multi-PHY IE will be added (7.4.4.34), indicating device PHY support.

## LB125 Rogue
CID # | Name | Affiliation | Page | Sub-clause | Line # | Comment | Proposed Change | Must Be Satisfied? (enter Yes or No) | Comment Type | Resolution
R2001 | Clint Powell | PWC, LLC. | 13 | 18.2 | 10 | A certain action which is not addressed in the comment resolution should be done by a device which detects a legacy signal. I think that one of the resolutions is that a device which catches preamble signal of legacy mode, 250kbps, will try to change another frequency channel. Another idea is to re-run a backoff counter if the device does not want to change the frequency channel. I would like to ask you to give this kind of comment in SB. | See comment. | Yes | E | Add text following the second sentence in 18.2: "If a device detects that there is a different data rate being used on the channel, a higher layer may decide to change the data rate, or move the receiving device to another channel."

## LB128 Comments
CID # | Name | Affiliation | Page | Sub-clause | Line # | Comment | Proposed Change | Must Be Satisfied? (enter Yes or No) | Comment Type | Resolution
3001 | Tero Kivinen | INSIDE Secure | 5 | 7.4.4.33 | 21 | The change instructions before 7.4.4.33 says that change the title and first paragraph, but the title and first paragraph are now unchanged. Remove the editing instructions on line 21. | This is just editorial change, and can be done during the sponsor ballot. | No | E
3002 | Tero Kivinen | INSIDE Secure | 7 | 8.2.5.4 | 22 | It is bit funny to have enumeration which have exactly one value. Also the enumeration value is funny, as the “2000 kb/s MSK” indicates that PHY has detected 258 kb/s O-QPSK PHY on the link when macLrPhyDetect is true. | Change the enumeration valid range to be useful name. This change is just editorial change, and can be done during the sponsor ballot. | No | E
3003 | Tero Kivinen | INSIDE Secure | 13 | 18.2a | 12 | The following sentence does not make sense: “When operating at 2000 kb/s in the 2450 MHz band, the value of macLrPhyDetect shall be TRUE, and the device shall support the detection of the 250 kb/s O-QPSK PHY.” as it has only conditionals but not what happens if those conditions are true. | Combine with next sentence: “When operating at 2000 kb/s in the 2450 MHz band, and the value of macLrPhyDetect is TRUE, and the device supports the detection of the 250 kb/s O-QPSK PHY, and a device detects that there is a different modulation or data rate being used on the channel, a higher layer may decide, e.g., to change the modulation and/or data rate, or move the receiving device to another channel.” This is also again editorial change and can be done during the sponsor ballot. | No | E