## IEEE_Cover
September 2016 |  | doc. # 15-16-0475-12-0010
IEEE P802.15
Wireless Personal Area Networks
Project | IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Title | 802.15.10 Consolidated Sponsor Ballot Comments
Date Submitted | 2016-09-11
Source | *Clint Powell, +Verotiana Rabarijaona | Voice: 480-586-8457
*PWC, LLC, +NICT
| *Chandler, AZ 85248, + Hikarinooka 3-4 Yokosuka, Kanagawa, Japan | E-mail: *cpowell@ieee.org, + r.h.verotiana@ieee.org
Re: | D6_P802-15-10_Draft_Recommended_Practice
Abstract | 802.15.10 Consolidated Sponsor Ballot Comments
Purpose | [This document represents the consolidated comments submitted for 802.15.10 Sponsor Ballot.]
Notice | This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## SB D06 Comments
Comment # | Name | Affiliation | Category | Page | Subclause | Line | Comment | Must Be Satisfied | Proposed Change | Disposition Status | Disposition Detail | Technical category | Assigned to | Resolution status | Drafting status
i-129 | Bahr, Michael | Siemens AG | Editorial | 0 | 0 | 0 | 802.15.4 in the title should contain IEEE | No | Draft Recommended Practice for Routing Packets in IEEE 802.15.4 Dynamically Changing Wireless Networks | Accept |  |  | Rabarijaona | Resolved | Done
i-19 | Turner, Michelle |  | Editorial | 0 | 0 | 0 | This draft meets all editorial requirements. | No |  | Accept |  |  | Rabarijaona | Resolved | Done
i-109 | Godfrey, Tim | Electric Power Research Institute, Inc. (EPRI) | Technical | 1 | 1.1 | 36 | This document should be a standard, not a recommended practice. Recommended Practice documents are well suited for processes and procedures, but less appropriate for defining a protocol. A protocol requires explicit specification of conformance to enable interoperability. In the future, interoperability certification profiles may be created. They need to reference a standard that defines the protocol. | Yes | Revise the PAR appropriately, and change occurrences of "recommended practice" to "standard" | Reject | The unanimous position of the task group is to continue to proceed forward with a recommended practice. The TG believes that the recommended practice should 1) first be implemented in practice; 2) then identify any issues and opportunities for enhancement; and finally 3) determine the necessary changes and improvements to address the issues identified during this period. Once these three steps have concluded, a new project can be started to turn 15.10 into a standard which incorporates the necessary changes and desired improvements. | PAR | Powell | Resolved | Done
i-126 | Bahr, Michael | Siemens AG | Editorial | 1 | 1.2 | 46 | capabilities not in logical order | No | - Discovery and addition of new nodes - Route establishment - Dynamic Route reconfiguration - re-establishment of broken/lost routes - tear-down of established routes | Accept |  |  | Rabarijaona | Resolved | Done
i-124 | Bahr, Michael | Siemens AG | Editorial | 1 | 1.2 | 50 | "Breaking of established routes" is not a (positive) route related capability. Breaking of routes usually happens without purposeful human intervention. What capability of 15.10 is actually meant (re-establishement of broken routes, tear-down)? | No | Tear down of established routes | Revise | Replace with "Purging of inactive routes". This is a more accurate wording of what the spec does. |  | Rabarijaona | Resolved | Done
i-125 | Bahr, Michael | Siemens AG | Editorial | 1 | 1.2 | 51 | "Loss of routes" is not a (positive) route related capability. Loss of routes usually happens without purposeful human intervention. What capabiltiy of 15.10 is actually meant? | No | re-establishment of lost routes | Accept |  |  | Rabarijaona | Resolved | Done
i-21 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | Editorial | 2 | 2 | 20 | The references to 15.4 and 15.9 are undated. Is there a reason why the reference to 802 isn't? | No | Delete "2014" | Accept |  |  | Rabarijaona | Resolved | Done
i-127 | Bahr, Michael | Siemens AG | Editorial | 3 | 3.1 | 11 | "best US next hop": US is not a common abbreviation for upstream. Using "upstream" is much more fluent for reading. Furthermore, the abbreviation US might be misleading. One would also expect a best Canadian next hop. | No | best upstream next hop | Accept |  |  | Rabarijaona | Resolved | Done
i-128 | Bahr, Michael | Siemens AG | Technical | 3 | 3.1 | 18 | Interestingly, coordinator is not (anymore) defined in IEEE Std 802.15.4 | No | delete "defined in IEEE Std 802.15.4" | Accept |  | Editorial | Rabarijaona | Resolved | Done
i-33 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | Editorial | 3 | 3.1 | 18 | Insert "as" before "defined" | No | See comment | Revise | "defined in IEEE Std 802.15.4" has been deleted |  | Rabarijaona | Resolved | Done
i-1 | Allen, James D | Self Employed | Editorial | 3 | 0 | 55 | Should the footers for all these pages be centered on the page. It looks like the copyright floats left and right depending on even or odd page but the "...unapproved draft...." notice is centered. | No | Center all lines of the foot note. | Reject | This will be corrected by the IEEE editors before publication |  | Rabarijaona | Resolved | Done
i-48 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | Technical | 4 | 4 | 1 | A description of the general architecture somewhere in clause 4 | No | Provide a figure and a description of the general architecture of a device using L2R | Revise | See resolution in the latest version of document 15-16-0483-xx | Overview | Rabarijaona | Resolved | Done
i-130 | Bahr, Michael | Siemens AG | Editorial | 4 | 3.1 | 14 | inconsistent acronym for "small scale", acronym should not be used in term to be defined. | No | small scale layer 2 routing mesh (SSL2R): L2R mesh offering a single service, ... | Revise | Replace the definition with "Small scale layer 2 routing mesh: L2R mesh where the mesh root is located in the same device as the PAN coordinator and operating using short nested information elements." |  | Rabarijaona | Resolved | Done
i-131 | Bahr, Michael | Siemens AG | Editorial | 4 | 3.1 | 17 | acronym should not be introduced as "also called" in definition. | No | small scale PAN (SSPAN): Personal ... | Revise | Replace the name with "small scale personal area network". Delete "Also called SSPAN." |  | Rabarijaona | Resolved | Done
i-132 | Bahr, Michael | Siemens AG | Editorial | 7 | 4.1 | 28 | a device can be part of a network, but not a part of a network | No | Any device wishing to be part of an L2R mesh should be part of a personal area network (PAN). | Accept |  |  | Rabarijaona | Resolved | Done
i-133 | Bahr, Michael | Siemens AG | Technical | 7 | 4.1 | 32 | "should" has a very specific and standardized meaning in IEEE standards (recommended functionality and formats, but not required). It must not be redefined for other things. Furthermore, the standardized functionality and formats enable interoperability, the implementation is completely transparent to interoperability. There is no other requirement on the implementation as that it implements the standardized functionality and format. | No | delete paragraph "The word "should" in this document indicates that the corresponding recommendation for implementation is needed for interoperability." in the whole document, delete text with should where it refers to implementation. | Revise | Delete the paragraph The instances of "should" where it was used to indicate a mandatory requirement will be replaced with "shall" Likewise, those instances of "may" that were meant as a recommendation will be changed to "should" The description of a device behavior or the frame format will use the verb itself (e.g. is, scans...) without an auxiliaries | PAR | Rabarijaona | Resolved | Done
i-136 | Bahr, Michael | Siemens AG | Technical | 8 | 4.3 | 18 | Figure 1: why is the mesh root having 4 hops to ist (southwestern) neighbor instead of just one? | No | provide a more realistic example of PAN links | Reject | The purpose of Figure 1 is to illustrate all possibilities in a PAN construction. E.g. The mesh root is one hop away (on the PAN) to its northeastern neighbor and is 4 hops away to its southwerstern neighbor. Such a case may occur since the topology in the PAN varies depending on the order in which the devices associate, transmit and receive beacons. On the other hand, both the northeastern and the southwestern neighbors are one hop away on the mesh. | Overview | Rabarijaona | Resolved | Done
i-135 | Bahr, Michael | Siemens AG | Technical | 8 | 4.3 | 18 | Figure 1: dashed line connecting PanC DC is not explained in legend | No | add to legend | Revise | Add a legend as follows here and in Figure 2: ---- direct connection to the PAN coordinator | Overview | Rabarijaona | Resolved | Done
i-134 | Bahr, Michael | Siemens AG | Editorial | 8 | 4.3 | 18 | Figure 1 should be black and white, some of the "greyish" nodes are actually greenish in the printout, but not on the screen. | No | make also the printout black and white, check for all figures in document | Reject | The greenish color does not make the figure les clear. Using only black and white would require using patterns to distinguish the nodes, which would make it less easy to understand |  | Rabarijaona | Resolved | Done
i-2 | Allen, James D | Self Employed | Editorial | 9 | 0 | 1 | The Table of contents (I know this front matter stuff is not part of the standard) would be tighter and easier to read if the tab spaces between the clause number and the title were not so large. | No | Consider changing TOC tab spacing. | Reject | This comment will be forwarded to the IEEE editors before publication |  | Rabarijaona | Resolved | Done
i-17 | Thaler, Patricia | Broadcom Limited | General | 12 | 4.4.2 | 20 | IEEE Std 802 defines both globally unique (i.e. EUI-64) and local 64-bit MAC addresses Local addresses are a valid choice and should be included in the addressing. | Yes | Replace "EUI-64" address throughout with "64-bit MAC" address. | Revise | While we recommend the use of EUI-64, we should not preclude the possibility to use local 64-bit MAC addresses. There is a definition for "Short address". For consistency insert a new definition in clause 3.1 as follows: Extended address: a 64-bit extended unique identifier (EUI-64*) or an assigned 64-bit MAC address Move the footnote on EUI-64 on p.8 to the page of the new definition. Replace "EUI-64" with "Extended Address" throughout the document Replace "Routing may use 64-bit extended unique identifiers (EUI-64) or the short addresses allocated by the PAN coordinator to the devices." with "Routing should use extended addresses or short addresses. The mechanism to ensure the uniqueness of 64-bit MAC addresses when they are assigned is out of the scope of this document. Since L2R is to be used above the IEEE Std 802.15.4 that operates with EUI-64s, it is recommended that the implementer also uses EUI-64 for L2R. 16-bit MAC addresses, when used, are allocated and managed by the PAN coordinator." on p.8 l.48 Additionally, state at the end of 4.3 that TMCTP should use EUI-64s to avoid duplication. | Editorial | Rabarijaona | Resolved | Done
i-18 | Thaler, Patricia | Broadcom Limited | General | 13 | 4.4.2 | 18 | The text in the cells for SSPAN and TMCTP Multicast is unclear. Does it mean that only the broadcast addresses are allowed or does it mean that group addresses will be forwarded over the broadcast flooding tree? If the former is intended, that should be changed as there are many protocols that use well-known group addresses. The other cells state the addresses that can be used, not how the addresses will be forwarded. | Yes | Replace "broadcast address flooding and higher layer filtering" with "group address" A table note can be used to indicate that the mechanism that will be used for forwarding these addresses is broadcast address flooding. | Revise | See the latest version of document 15-16-0566-xx | Addressing | Sato | Resolved | Done
i-3 | Allen, James D | Self Employed | Editorial | 13 | 1.1 | 37 | The term "802.15.4" has no antecedent. | No | Change to "IEEE Std 802.15.4" or use a reference number or label (e.g., [802.15.4]") from the references list. | Revise | Insert IEEE Std before 802.15.4 here and in the title |  | Rabarijaona | Resolved | Done
i-4 | Allen, James D | Self Employed | Editorial | 13 | 1.2 | 54 | Foot note missing or is it a section note? | No | The footnote #1 shows up on the next page. Is this what you wanted? | Revise | Make the footnote appear on the same page as the reference |  | Rabarijaona | Resolved | Done
i-116 | Sato, Noriyuki | Oki Electric Industry Co., Ltd. | Technical | 13 | 4.4.1 |  | What the route estabilishment requires and what can be used in the forwarding are different. This table looks to make a confusion. Source routing can be used in any unicast routing including DS in storing mode but only DS in non-store mode depends on it. Furthermore, source routing can be used for US routing if the node knows all of intermediate addresses correctly. | No | Clarify dependency of DS establishment and US Reorder establishment function and forwarding function Use M/O/- instead of Y/O/N, N/A Add P2P establishment There seems to be network type SSPAN, non-SSPAN, TMCTP . Add a table or a list in 4.3. | Revise | See the latest version of document 15-16-0520-xx See revised resolution in the latest version of document 15-16-0573-xx | Overview | Sato | Resolved | Done
i-5 | Allen, James D | Self Employed | Editorial | 14 | 1.1 | 1 | The headers are not the same throughout the Std. Also , this is the first time I've seen the use of "Local and Metropolitan Area Networks - PART 15.10" (on the right-hand header). 15.10 also seems redundant to the fuller citation on the left header. | No | Check the current Style Guide. Make consistent as appropriate. | Reject | This comment will be forwarded to the IEEE editors before publication |  | Rabarijaona | Resolved | Done
i-6 | Allen, James D | Self Employed | Editorial | 14 | 2 | 7 | Should these normative references be numbered or labeled (like "[802.15.4]" to simplify citations like in comment for my first comment? | No | Check the current Style Guide. | Reject | The normative references should not be numbered |  | Rabarijaona | Resolved | Done
i-7 | Allen, James D | Self Employed | Editorial | 14 | 2 | 18 | The Citation for 802.15.9 isn't complete. | No | Change to IEEE Std 802.15.9 | Revise | do so for all the instances |  | Rabarijaona | Resolved | Done
i-22 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | Editorial | 14 | 5.1.1.1 | 26 | "is about" can be improved | No | Use "intends" | Accept |  |  | Rabarijaona | Resolved | Done
i-53 | Kivinen, Tero | INSIDE Secure | Editorial | 14 | 5.1.1.1 | 36 | There is no "Depth" in table 3, there is entry called "My depth". | No | Change "Depth" with "My depth". | Accept |  |  | Rabarijaona | Resolved | Done
i-56 | Kivinen, Tero | INSIDE Secure | Editorial | 14 | 5.1.1.1 | 37 | This text here covers all other Table 3 fields except the P2P path list. Perhaps that should be listed too. | No | Change "The local neighbor table (NT) is initialized as an empty table." to "The local neighbor table (NT) and P2P path list are initialized as an empty tables." | Revise | Insert "If On-demand P2P route discovery is TRUE, the P2P path list is initialized as an empty table." |  | Rabarijaona | Resolved | Done
i-54 | Kivinen, Tero | INSIDE Secure | Editorial | 14 | 5.1.1.1 | 38 | There is no "My PQM" in the table 3, there is entry called "My PQM value". | No | Change "The value of My PQM is initialized to zero" with "The My PQM value is initialized to zero". | Revise | Delete "value" after "My PQM" in the MT |  | Rabarijaona | Resolved | Done
i-55 | Kivinen, Tero | INSIDE Secure | Technical | 14 | 5.1.1.1 | 39 | The text says that other parameters in the MT are set as indicated by the parameters in the primitive, but the parameters in the MT table and in the primitive do not match exactly. Would it be better to make sure that the names matches exactly so there would not be any confusion which value is stored where. It is quite obvious even now, but do we want to be fully exact. | No | Perhaps rename the parameters to the L2RLME-MESH-START so they match exactly with the entries in the MT table (except for spaces). i.e., change the parameters for L2RLME-MESH-START in section 5.1.1.4 as follows: AdressingMode -> MeshAddressMode PqmId -> MetricId OnDemandP2pRouteDiscovery -> OnDemandP2pDiscovery Mpo -> MultiPanOperation And perhaps rename the Link Quality Threshold (LQT) to be LQT in table 3 and spell out the acronym first time it is used in the text, not when it is used in the entry name. | Revise | See proposed change. Additionally : - Replace On-demand P2P Discovery with "On-demand P2P route discovery" in the MT - replace "If the LQM of this ancestor does not satisfy the LQT found in the Threshold field of the TC IEs" with "If the LQM of this ancestor does not satisfy the link quality threshold (LQT) found in LQT in the MT." in 5.2.3, p.40, l.51 | Editorial | Rabarijaona | Resolved | Done
i-120 | Sato, Noriyuki | Oki Electric Industry Co., Ltd. | Technical | 14 |  |  | L2RD IE always need to be placed in the beacon at the scan phase for the device to avoid trying to associate to a device which doesn't talk L2R protocol. And it also avoids racing issue where MAC layer is up but L2R layer is not ready. A mesh root needs to know what PAN type is running before it starts mesh. Putting L2R IE in beacon also tells which PAN type (SSPAN, TMCTP etc.) is used to solve that issue. (0xffff can be used for mesh root ID when no mesh is available.) | No | Add following description after the second paragraph in 5.1.1.1 "Device other than the PAN coordinator needs to know what PAN type is running in the PAN to which it associates before starrting mesh. The PAN type is exchanged by L2R-D IE at discovery phase as described in 5.1.2.1." Add following description after the last paragraph in 5.1.2.1: "If the coordinator that doesn't belong to any L2R mesh yet receives the EBR with the empty L2R-D IE, it replies with an EB with an L2R-D IE containing the information as well but mesh root ID field is filled with 0xffff or 0xffff ffff ffff ffff." | Revise | See the latest version of document 15-16-0520-xx Additionally, insert the following text at the end of 6.1.1.1: "If SSPAN is set to 1, MPO is set to 0 and ignored by the receiver." Move SSPAN before MPO in the L2R-D IE descriptor Instead of the text in the proposed change, insert the following text at the end of 5.1.2.1: When an FFD that can act as a coordinator (including the PAN coordinator) that does not belong to any L2R mesh receives the EBR with the empty L2R-D IE, it replies with an EB with an L2R-D IE where the Mesh Root Address field is set to 0xffff or 0xffff ffff ffff ffff. This is to allow the joining devices to know the type of PAN that is running before association. In a regular PAN, all the flags of the Descriptor field of the L2R-D IE are set to 0. In an SSPAN, the SSPAN field is set to 1. In a TMCTP, the MPO field is set to 1. A device that is to use L2R should associate with a PAN that supports L2R as indicated by L2R-D IEs received from at least one of the existing devices. | Discovery | Sato | Resolved | Done
i-118 | Sato, Noriyuki | Oki Electric Industry Co., Ltd. | Technical | 15 | 5.1.1.1 | 2 | Current specification specifies that a mesh root needs to have PanC DC to start 16-bit mesh. However, a node who joined a mesh which provides PANC DC can start or join to 16-bit mesh. The limitation - Only the node which has PanC DC can start 16-bit mesh - is too strict. | No | Add a description for the condition to establish 16-bit mesh in 5.1.1.1, 5.1.2.2.1 and 5.1.2.2.2 respectively Modify the condition to 16-bit mesh described in 5.1.2.5 | Revise | Replace the following text at the end of section 5.1.1.1. "and the corresponding L2R mesh root should have a PanC DC" with "and the corresponding L2R mesh root should have short address assigend by PanC. If its short address is expired, the mesh root should stop the mesh." Add a folowing sentence in section 5.1.2.2.1 P.19 l.53 and 5.1.2.2.2 P.21. l.54. "A joining device needs to have assigned short address when it select a mesh which opearates with 16 bit address without PanC DC. " Delete "or if there is PanC DC throgh the mesh root," from the sentence on P.25 L.46. | Addressing | Sato | Resolved | Done
i-23 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | Editorial | 16 | 5.1.2.1 | 30 | "a mesh discovery" s/b "the mesh discovery" | No | Make it so | Accept |  |  | Rabarijaona | Resolved | Done
i-115 | Sato, Noriyuki | Oki Electric Industry Co., Ltd. | Editorial | 18 | 5.1.2.1.2 | 10 | "a string with a nonzero length" in 5.1.2.1.1 but "a string with a length of zero" is used in 5.1.2.1.2. If they are same meaning, same wording may be preferred. | No | Consider to correct either. | Revise | Replace "length of zero" with "zero length" |  | Rabarijaona | Resolved | Done
i-34 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | Editorial | 19 | 5.1.2.2.1 | 53 | "to the procedure" s/b "the procedure" | No | Make it so | Accept |  |  | Rabarijaona | Resolved | Done
i-121 | Sato, Noriyuki | Oki Electric Industry Co., Ltd. | Technical | 19 | 5.1.2.2.1 |  | This clause describes that selection of mesh with same mesh ID. However, the device gather mesh ID only at discovery phase. After joined, there is no chance to find new mesh with mesh ID started. | No | Provide some solution for it Ex. Periodical announcement of Mesh ID Light scan when unknown mesh root is found | Revise | See the latest version of document 15-16-0542-xx. See additional instructions in the latest version of document 15-16-0583-xx. | Discovery | Sato | Resolved | WiP
i-74 | Kivinen, Tero | INSIDE Secure | Technical | 20 | 5.1.2.2.1 | 7 | The text says "The device then transmits its own TC IE". In the line 23 the text says that we start periodic transmissions of the TC IE only if we are L2R Router. How does the device know if it is configured to be L2R Router or not? Is the l2rTcIeInterval used for that (it does not look like, as it does not have any special value meaning do not send TC IEs). | Yes | Explain how the device knows whether it is L2R Router, and if it is not does it still send one TC IE when it initially joins, but not the periodic TC IEs or how does it work. If the device is RFD does it still send the initial TC IE? | Revise | As TC IEs need to be sent only if the device is a router, modify the text as follow. Add "if the device is a router as indicated by a non-zero TC IE interval " after "The device then transmits its own TC IE" on p.20 l.7. Additionally change the range of l2rTcIeInterval to 0-63 in Table 51. Reorder Table 51 to have the intervals following each other (TC IE, RA IE and NLM IE intervals) | Discovery | Sato | Resolved | Done
i-73 | Kivinen, Tero | INSIDE Secure | Editorial | 20 | 5.1.2.2.1 | 17 | TC IE does not have the mesh ID, so it is confusing to say that when devices receives a TC IE with the same mesh ID. Change the text so it says that we receive TC IE which is in the list of mesh root addresses which are known to have same Mesh ID. | No | Rewrite the sentence to be more clear. | Revise | Replace "from one of the recorded L2R meshes, with the same mesh ID and" with "from one of the L2R meshes whose mesh root addresses have been recorded in MTs with" |  | Rabarijaona | Resolved | Done
i-8 | Allen, James D | Self Employed | Editorial | 20 | 4.3 | 43 | Figure 1 leads me to ask whether you intended to have a "table of figures" and a "table of tables"? | No | Add tables if appropriate. | Reject | The 802.15 WG Technical Editor does not allow a table of figures or a table of tables. |  | Rabarijaona | Resolved | Done
i-9 | Allen, James D | Self Employed | Editorial | 22 | 4.4.1 | 6 | Does the word "certain" need a better word in "...mesh, in other words the relative distance of a device to a mesh root (which has a depth 0) with respect to a certain metric.". | No | Change as appropriate | Revise | Delete "certain" |  | Rabarijaona | Resolved | Done
i-10 | Allen, James D | Self Employed | Editorial | 23 | 4.4.1 | 10 | Table 1 contains clause numbers. | No | After the table, in the notations list, add: The relevant clauses are enclosed in parenthesis.". | Revise | Insert this sentence at the end of the second paragraph on p.11 |  | Rabarijaona | Resolved | Done
i-35 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | Editorial | 23 | 5.1.2.2.2 | 26 | "Creates" s/b "Create" | No | Make it so | Accept |  |  | Rabarijaona | Resolved | Done
i-24 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | Technical | 24 | 5.1.2.3 | 18 | From the 15.4 MAC sublayer perspective, L2R is the next higher layer. In addition, "Orphan scan" is not necessarily what happens. A device may try to resynchronize with its former coordinator or find a new coordinator | No | Replace "its next higher layer should request an orphan scan process as described in IEEE Std 802.15.4 in order to reestablish" with "it should reestablish " Replace "Orphan scan" with "PAN reconnection" in Figure 9 | Accept |  | Editorial | Rabarijaona | Resolved | Done
i-36 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | Editorial | 25 | 5.1.2.5 | 43 | "by a PanC DC with a value TRUE" s/b "by the PanC DC parameter set to TRUE" | No | Make it so | Accept |  |  | Rabarijaona | Resolved | Done
i-112 | Sato, Noriyuki | Oki Electric Industry Co., Ltd. | Technical | 25 | 5.1.2.5 | 46 | "there is PanC DC" s/b "there is no PanC DC" | No | Correct it. | Accept |  | Editorial | Rabarijaona | Resolved | Done
i-37 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | Editorial | 25 | 5.1.2.5 | 46 | "if there is PanC DC through the mesh root" s/b "if the mesh root does not have a PanC DC" | No | Make it so | Accept |  |  | Rabarijaona | Resolved | Done
i-78 | Kivinen, Tero | INSIDE Secure | Technical | 26 | 5.1.2.5.1 | 4 | This text claims that 0xff means for indefinite duration, but both the L2RLME-AA-RQ.request and the AA-RQ IE uses value of 0x00 for indefinite expiration time. | Yes | Change "0xff" with "0x00" | Accept |  | Addressing | Sato | Resolved | Done
i-11 | Allen, James D | Self Employed | Editorial | 26 | 5.1.1.1 | 35 | Where is Table 3? It's in clause 5.2.1, page 41 (numbered page 29). (Same comment in section 5.1.2.2.1 and perhaps others). | No | When tables and figures are not in the same clause as the citation, it's helpful to add the clause and page number where it can be found. | Revise | Add clause number when the tables and figures are not in the same clause as the citation |  | Rabarijaona | Resolved | Done
i-12 | Allen, James D | Self Employed | Editorial | 27 | 5.1.1.1 | 23 | Figure 3 - the Enhanced Beacon with TC IE is transmitted but it looks like it's sent into space in this chart. Same on several MSCs. | No | Consider changing from "Enhanced Beacon with TC IE" to "Transmission of Enhanced....IE" so the MSC better stands on its own. | Accept |  |  | Rabarijaona | Resolved | Done
i-75 | Kivinen, Tero | INSIDE Secure | Technical | 29 | 5.2.1 | 26 | Here the text says that MT is filled based on the TC IEs but lots of the information the table 3 is not in the TC IE, but are only on the L2R-D IE. i.e., to fill in the Table 3 we need to receive L2R-D not TC IE. The text then says we only store the MT Entries for as many MTs as the number of L2R meshes it has joined, but to be able to join the mesh, it needs to store all the MTs during the discovery phase so that joining phase can use that to find out the MT entries. It seems that Discovery phase returns the information to the higher layer, but how does the higher layer then fill in the MT so that joining process can know that mesh with mesh root address of xxxx has Mesh Id of "Mesh1"? | Yes | I think there is something missing here, i.e. how is the information from the discovery phase (L2R-D IE) passed to the joining phase (TC IE). Where is this explained and how is supposed to work. The joining phase (page 19 line 47, and page 21 line 46) do say we fill in or update the table 3, but information to fill in the table 3 is not available in the TC IE, thus it cannot be filled at that point, it can only be filled during the discovery phase, where we receive L2R-D IE. | Revise | See the latest version of document 15-16-0542-xx | Discovery | Sato | Resolved | Done
i-38 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | Editorial | 29 | 5.2.1 | 42 | "providing" not needed | No | Delete | Accept |  |  | Rabarijaona | Resolved | Done
i-25 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | Editorial | 30 | 5.2.1 | 30 | The range for the metric ID is only from 0 to 15 | No | Replace the valid range with "0x0 - 0xf" | Accept |  |  | Rabarijaona | Resolved | Done
i-51 | Kivinen, Tero | INSIDE Secure | Technical | 30 | 5.2 | 50 | The Dcat Buffering Unit list is inconsistent. In the L2RLME-MESH-START it is 20 MILLISECONDS, in the MT table it is 100 MILLISECONDS, and TC IE it is 20 MILLISECONDS. | Yes | Change the Table 3 valid range for DCat buffering unit to have valid range of "20 MILLISECONDS, SECOND, MINUTE, HOUR" not "100 MILLISECONDS...". | Accept |  | Editorial | Rabarijaona | Resolved | Done
i-113 | Sato, Noriyuki | Oki Electric Industry Co., Ltd. | Editorial | 31 | 5.2.1 | 51 | determines' s/b 'detects' since the condition is directly related to the result without no process to 'determine' | No | Correct it. | Reject | Processing the TC IE to retrieve the MSN itself is the the process to determine whether or not the mesh in initialization mode |  | Rabarijaona | Resolved | Done
i-114 | Sato, Noriyuki | Oki Electric Industry Co., Ltd. | Editorial | 31 | 5.2.1 | 53 | determines' s/b 'detects' since the condition is directly related to the result without no process to 'determine' | No | Correct it. | Reject | See i-113 |  | Rabarijaona | Resolved | Done
i-81 | Kivinen, Tero | INSIDE Secure | Technical | 32 | 5.2.1 | 17 | The Interval unit is common to the TC/RA/NLM IE intervals, but all of those values are received in the different IEs thus the interval might be different for each of them. How is this supposed to be handled. Do we have some requirement somewhere saying that node shall always use same interval unit for TC, RA and NLM IEs, even if the actual interval value is different? | Yes | Perhaps add statement to the page 37 line 22 saying that regardless whether the interval for TC and NLM are same or not, the unit must be same. Similar text for RA and TC somewhere... | Revise | Add statement to the page 20 line 30 and the page 22 line 22 saying ”The intervals for TC IE and RA IE can be adjustable by l2rTcIeInterval and l2rRaIeInterval respectively. Their unit is coommn and set by l2rIntervalUnit." Add statement to the page 37 line 22 saying "Thus, the intervals for TC IE and NLM IE can be adjusted by l2rTcIeInterval and l2rNlmIeInterval respectively. Their unit is common one and is set by l2rIntervalUnit." | Maintenance | Sato | Resolved | Done
i-82 | Kivinen, Tero | INSIDE Secure | Technical | 32 | 5.2.1 | 25 | Why is this valid range starting from 0. Is 0 special value meaning that no RA IEs are sent? If so it should be explained here. The l2rRaIeInterval pib value has range of 1-63 so this is not consistent. Also what value does this have in the beginning, as we only know the remote nodes RA IE Interval after we have received first RA IE from him. Is the value 0 special value meaning we have not received any RA IEs yet, and we do not know the value here yet. | Yes | Explain what is the meaning of value 0. Does the value of 0 mean here same as it means in the l2rRaIeInterval as specified on page 43 line 11, i.e., that same value as l2rTcIeInterval is used? | Revise | Insert "Equal to the TC IE interval if set to 0" at the end of the description Replace the range of the l2rRaIeInterval to 0-63 | Maintenance | Rabarijaona | Resolved | Done
i-13 | Allen, James D | Self Employed | Editorial | 32 | 5.1.2.2.1 | 26 | Missing punctuation | No | Add a period after "...defined in IEEE Std 802.15.4". | Accept |  |  | Rabarijaona | Resolved | Done
i-83 | Kivinen, Tero | INSIDE Secure | Technical | 32 | 5.2.1 | 30 | Why is this valid range starting from 0. Is 0 special value meaning that no NLM IEs are sent? If so it should be explained here. The l2rNlmIeInterval pib value has range of 1-63 so this is not consistent. Also what value does this have in the beginning, as we only know the remote nodes NLM IE Interval after we have received first NLM IE from him. Is the value 0 special value meaning we have not received any NLM IEs yet, and we do not know the value here yet. | Yes | Explain what is the meaning of value 0. | Revise | Value 0 of l2rNlmIeInterval PIB means that no NLM IEs are sent. Value 0 of NLM IE interval in NT means that no NLM IE has received yet. Change "1-63" with "0-63" in the Range column of the attribute l2rNlmIeInterval in the table 51 and add the text "Value 0 means that no NLM IE is sent." in the Description column. Add the text "Value 0 means that no NLM IE has received yet." in the Description cloumn of NLM IE interval in Table 4. Add "NLM IEs may be used by a device." on l.52 p.36 Add "if l2rNlmIeInterval is set to 0, the device does not transmit NLM IEs. If l2rNlmIeAcceptance is set to FALSE, the device discards any received NLM IE and uses the observed link metric as LQM. Otherwise the Announced link metric by the NLM IE is used to calculate the mutual link metric that is used as the LQM." on l.25 p.37 Remove 'NLM operation' from Table 3. Add 'NLM IE acceptance PIB' to Table 51 with the note "Attribute l2rNlmIeAcceptance, Type: Boolean, Range: TRUE, FALSE, Description: If it is TRUE, received NLM IE is used for calculating LQM. | NLM | Sato | Resolved | Done
i-31 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | Technical | 33 | 5.2.1 | 23 | The whole concept of non-storing mode is that no routing information is stored in intermediate devices. Recording an entire path (Intermediate address list) will consume more memory than just recording the next hop in the storing mode (Table 5), which defeats the purpose of the non-storing mode. | No | Delete Table 6. In Table 3, insert "or if storing mode is disabled" at the end of the description of "P2P path list" | Accept |  | NT | Rabarijaona | Resolved | Done
i-62 | Kivinen, Tero | INSIDE Secure | Editorial | 34 | 5.2.1 | 26 | Reference to the table 8-71 to the 802.15.4 is wrong, it should be 8-12. | Yes | Fix the references from 8-71 to 8-12 in Table 7 | Revise | Replace "8-71 in IEEE 802.15.4" with "8-12 in IEEE Std 802.15.4" |  | Rabarijaona | Resolved | Done
i-32 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | Technical | 37 | 5.2.2.1 | 28 | 15.4 allows the MAC sublayer to report the RSSI (received signal strength indicator) to the next higher layer (in this cas L2R) Does the signal strength here refer to the RSSI? | No | Specify if the signal strength can be interpreted as the RSSI from the MAC sublayer. In that case, make sure their respective units match. | Revise | See the latest version of document 15-16-0537-xxx | RSW | Perkins | Resolved | Done
i-84 | Kivinen, Tero | INSIDE Secure | Technical | 38 | 5.2.2.1 | 20 | The text says that value 256 is the maximum possible value for the RSW, but if it is 8-bit value, maximum value that can be represented is 255, not 256 (i.e., range from 0-255), so is the LQM calculated from the RSW metric by substracting MINRSW from there or what? The text later says that if LQM value of the device is 0xff, then it is assumed to be infinity, i.e. 0xffff is stored to the PQM. | Yes | Should the 256 be 255 or what? | Revise | Use 255 See the latest version of document 15-16-0537-xxx | RSW | Perkins | Resolved | Done
i-39 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | Editorial | 39 | 5.2.2.1 | 43 | Extra space in "t he" | No | Delete | Accept |  |  | Rabarijaona | Resolved | Done
i-26 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | Technical | 43 | 5.2.4.2 | 23 | State that the mesh root is the only device recording DS routes | No | Insert "the mesh root is the only device recording DS routes." after "set to 0" Additionally consider creating a method to make the paths known to the NHL. E.g: Use a primitive and insert the address list in the data request primitive when transmitting in non-storing mode. | Revise | See the resolution of i-122 | Routing | Sato | Resolved | Done
i-40 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | Editorial | 50 | 5.2.7.1 | 10 | "P2P-RQ IE" should be plural. See also Figure 23 | No | Make it so | Accept |  |  | Rabarijaona | Resolved | Done
i-110 | Sato, Noriyuki | Oki Electric Industry Co., Ltd. | Editorial | 57 | 5.4.1.1 | 34 | Source routing (non-storing mode) s/b "Source routing". Non-storing mode needs to use source routing for DS but Non-storing mode doesn't equal to Source routing. Just say in the sentence, "If the non-storing used, source routing needs to be used in DS and on-demand P2P routing." Source routing can be used also in storing mode technically. It doesn't to need to prohibit it. | No | Remove "(non-storing mode)" on the title. Add the sentence "If the intermediate address list exists in the L2R Routing IE or the Short L2R Routing IE, source routing is used." at the begining of this clause. Remove from "When source routing is used..." to the end of this clause. Replace "In either case, source routing should be used for DS and P2P routing." with "In either case source routing should be used." | Revise | Delete 'non-storing mode" Replace the text of the clause with "If the L2R mesh is in non-storing mode, devices only store information about their neighbors but do not otherwise store routing information received with RA or SRA IEs. The mesh root stores all information received from the TC IEs and the RA IEs or SRA IEs. If on-demand P2P routing is enabled, only the end to end source and destination devices of a P2P path store routing information. In either case, source routing is used. The path to the destination is included in the Intermediate Addresses List of the L2R Routing IE or the SLR IE and data frames are routed on the path indicated. An L2R mesh working in non-storing mode is indicated by Storing Mode set to FALSE in the MT." |  | Rabarijaona | Resolved | Done
i-111 | Sato, Noriyuki | Oki Electric Industry Co., Ltd. | Editorial | 57 | 5.4.1.2 | 46 | "Hop-by-hop routing (storing mode)" s/b "Hop-by-hop". This routing method is used for US in non-storing mode. | No | Remove "(storing mode)" | Accept |  |  | Rabarijaona | Resolved | Done
i-41 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | Editorial | 60 | 5.4.1.2 | 14 | Arrows are missing on either side of the "Create L2R Routing IE..." block | No | Add it | Accept |  |  | Rabarijaona | Resolved | Done
i-42 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | Editorial | 60 | 5.4.1.3 | 53 | "the" not needed before "PAN coordinator 1" | No | Delete | Accept |  |  | Rabarijaona | Resolved | Done
i-27 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | Editorial | 61 | 5.4.1.3 | 2 | "This results in the path represented by the bold arrows in Figure 18." The bold arrows have been deleted from Figure 18 | No | Delete this sentence | Accept |  |  | Rabarijaona | Resolved | Done
i-43 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | Technical | 62 | 5.4.1.4 | 3 | A frame is not necessarily coming from the next higher layer, it may also be a frame received from the previous hop, in which case, it remains in the L2R sublayer | No | Start the flow chart at "Failed transmission" Rearrange flow chart | Revise | See resolution in the latest version of document 15-16-0484-xx | Routing | Rabarijaona | Resolved | Done
i-117 | Sato, Noriyuki | Oki Electric Industry Co., Ltd. | Technical | 62 | 5.4.1.5 | 46 | If the originator receives E2E ACK with wrong LSN, it shall just ignore it and try to wait to receive the one with correct LSN to avoid unexpected drop when a delayed previous E2E ACK arrives just before correct one. | No | Replace If the E2E ACK IE is not received during the acknowledgment wait time or contains a LSN that does not correspond to the LSN of the original L2R Routing IE, the source device determines that the transmission has failed. With If the E2E ACK IE is not received during the acknowledgment wait time , the source device determines that the transmission has failed. If E2E ACK IE contains a LSN that does not correspond to the LSN of the original L2R Routing IE, the source device drop it and wait the other which contains correct LSN. | Revise | With If the E2E ACK IE is not received during the acknowledgment wait time , the source device determines that the transmission has failed. If E2E ACK IE contains a LSN that does not correspond to the LSN of the original L2R Routing IE, the source device drop it and wait for E2EACK IE with the correct LSN untill acknowledgement wait time expires. | Routing | Sato | Resolved | Done
i-49 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | Technical | 63 | 5.4.1.5 | 10 | Mention that the LSN of the L2R Routing IE is set to the latest SN of the transmitter of the E2E ACK IE | No | See comment | Revise | Insert "The LSN field of the L2R Routing IE is set to the latest value of the sequence number of the device transmitting the E2E ACK IE." at the end of the clause | Routing | Rabarijaona | Resolved | Done
i-85 | Kivinen, Tero | INSIDE Secure | Technical | 63 | 5.4.1.6 | 17 | I assume that if the E2E AR field is set to 1 the DCat feature cannot be used, i.e., both E2E AR and DCat fields in the L2R Routing IE cannot be on at the same time. | Yes | Explicitly forbid setting E2E AR and DCat fields as it is not clear what happens if frame with E2E AR set 1 is concatenated with other frame. | Revise | Insert the following text before the last sentence of the second paragraph of 5.4.1.6: "If the DCat field is set to 1 in the L2R Routing IE or if a frame is already a concatenation of other frames, as indicated by the presence of the DCat IE, the E2E AR field of the L2R Routing IE is set to 0 by the transmitter and ignored by the receiver." | Editorial | Rabarijaona | Resolved | Done
i-20 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | Technical | 68 | 5.4.3.1 | 1 | "The addressing mode used for broadcast routing depends on the addressing mode used in the L2R mesh." This paragraph describes the PAN broadcast change, in which case the mesh root adress in the L2R Routing IE is set to the broadcast address. What happens if different meshes use different addressing modes? On a different issue, is the intention here to broadcast to all the devices of the PAN or all the devices belonging to at least one L2R mesh? a) In the first case, a device that does not belong to a mesh cannot route a frame so what if some devices do not belong to any L2R mesh? b) In the latter case, what if all the meshes do not have at least one common device with another mesh? | No | Describe the behavior in case different meshes operate with different addressing modes. Perhaps mention that the PAN broadcast uses 64 bit addresses or specify another way for broadcast accross different meshes not working with the same addressing mode. As for the second issue, if the intention is a), I don't think it is possible since a non-L2R device cannot route anyway. If the intention is b), e.g. if there are two L2R meshes A and B with no common devices between them, if the PAN broadcast is initiated from a device in mesh A, the frame won't reach the devices in mesh B. In this case, starting a mesh broadcast in both meshes is a better way to ensure that the broadcast frames reach all the devices in all meshes. If the assumption is that all devices part of the PAN should support L2R, say so in the document. | Revise | See latest version of 15-16-0572-xx | Addressing | Sato | Resolved | Done
i-119 | Sato, Noriyuki | Oki Electric Industry Co., Ltd. | Technical | 74 |  |  | Allign to the IEEE802.11 SSID - having a flag to toggle between unspecified character set and UTF-8. Make it longer. Make it longer like 32 bytes since the variable length content can reduce by the length field if unnecessary. | No | Define a flag in MeshID to indicate if UTF-8 is used or it is unspecified. Make it 32 bytes maximum. (from 0-3 to 0-4) Change the primitives -start, scan. Add a flag into MT | Revise | See the latest version of document 15-16-0521-xx | IE | Sato | Resolved | Done
i-57 | Kivinen, Tero | INSIDE Secure | Technical | 75 | 6.1.2 | 3 | The MPO Descriptor field length is set to be 0/10, bu the MPO Descriptor described in the section 6.1.2.9 is 11 octets long. | Yes | Change "0/10" to "0/11". | Accept |  | Editorial | Rabarijaona | Resolved | Done
i-58 | Kivinen, Tero | INSIDE Secure | Technical | 79 | 6.1.2.11 | 12 | The PQM field is not in the end of the TC IE, thus reading the fields after it is impossible if unknown vendor specific PQMs are used. It would be better to move the PQM to the end of the TC IE, so then at least devices could parse and print out the TC IE even when unknown vendor specific PQMs are used. Another option would be to use the reserved bits 5-7 to indicate the the length of the Value and Threshold fields, i.e., change the bits 5-7 to be length of value field which would allow encoding 0-7 octet long PQMs. | No |  | Revise | Move the PQM to the end of the TC IE | IE | Rabarijaona | Resolved | Done
i-44 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | Editorial | 81 | 6.1.5 | 29 | "Route DA" and "Route SA" could be improved. Using P2P instead of "Route" would be more descriptive of the field | No | Replace "Route" with "P2P" here and throughout the document | Accept |  |  | Rabarijaona | Resolved | Done
i-45 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | Technical | 84 | 6.1.8 | 45 | Looking at the E2E ACK IE format, it seems that it can also be used in an SL2R to reply to a data frame containing an SLR IE. In this case, the E2E ACK IE should also be sent with an SLR IE instead of an L2R Routing IE | No | Insert "or an SLR IE in an SL2R mesh." after "L2R Routing IE" on p.84, l.45 and on p.85, l.1. Insert "The SLSN / LSN field is one octet long in an SL2R mesh and two octets long in an L2R mesh." at the end of p.85, l.2 Modify 5.4.1.5 to consider the use of E2E ACK IEs in SL2R meshes. | Revise | In additon to the 6.1.8 modification in the column of Proposed Change, modify 5.4.1.5 as follows. Replace all phrase of "the L2R Rouitng IE" with "the Routing IE or the SLR IE". Replace all phrase of "the original L2R Rouitng IE" with "the Routing IE or the original SLR IE". Replace all phrase of "LSN" with "LSN or SLSN". There is no E2E AR field in the SLR IE. Therefore E2E ACK is not supported in an SL2R mesh. Replace the field of the E2E ACK IE with "LSN" with a size of 1 octet. In the new routing feature table, (E2EA, Unicast US/Unicast DS/P2P) should be PT1, PT3: O PT2: - | Routing | Sato | Resolved | Done
i-50 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | Technical | 85 | 6.1.10.2 | 48 | Insert "This field is set to 0xffff if no specific address is requested." at the end of the paragraph | No | See comment | Accept |  | Editorial | Rabarijaona | Resolved | Done
i-79 | Kivinen, Tero | INSIDE Secure | Technical | 87 | 6.1.11.3 | 8 | This needs text saying when this is present, i.e., how does one know if it is present or not. | Yes | Either say that whether this is present or not, can be seen from the length of the content field, or say that this is omitted if the status is anything else than 0b000. | Revise | Insert "This field is omitted if the value of the Status field is not 0b000," at the end of the subclause | IE | Rabarijaona | Resolved | Done
i-80 | Kivinen, Tero | INSIDE Secure | Technical | 87 | 6.1.11.4 | 13 | This field is also marked as such that it could be omitted (length is 0/1). If it is omitted, when it is omitted (same as when Allocated Address field was omitted?). | Yes | Explain when this field is present and when not. | Revise | Insert "This field is omitted if the value of the Status field is not 0b000," at the end of the subclause | IE | Rabarijaona | Resolved | Done
i-86 | Kivinen, Tero | INSIDE Secure | Technical | 87 | 6.2 | 20 | Is the LLIE normal payload IE, or Nested IE of type long format? i.e., is it allocated from the table 7-17 or table 7-15 from the 802.15.4? Anyways the Element ID is wrong term, as that is only used by the Header IEs in 802.15.4 section 7.4.2. | Yes | If this is Payload IE, then the proper term is Group ID, but then the value 0x00 cannot be used, as it is already reserved for the ESDU IE, so I assume this is supposed to be Payload IE type of MLME IE containing Nested IE of type long format, and then the proper term is still Sub-ID. So change the :"The LLIE is a long nested IE with the Element-ID 0x00" with "The LLIE is a nested IE of type long format with the Sub-ID 0x00." | Revise | Additionally give a reference the nested IE subclause in 802.15.4. Change the ID to 0xa if needed. Check with Pat. | IE | Rabarijaona | Resolved | Done
i-46 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | Technical | 90 | 6.2.2.1 | 4 | The flags in the Descriptor should be rearranged in a more logical manner to illustrate the relationship between them, when applicable | No | Move "Source Address Present" and "Destination Address Present" before "Destination Address Mode" since "DA Present" and "DA mode" are related. Insert "This field is set to 0 and ignored by the receiver if the DA Present field is set to 0." at the end of the 2nd paragraph on p.90. Move "L2R Retransmission" after "MAC AR Management" since the first is dependant upon the other, i.e. if ACK are not requested at the MAC, L2R ReTx is not applicable. | Accept |  | IE | Rabarijaona | Resolved | Done
i-87 | Kivinen, Tero | INSIDE Secure | Technical | 90 | 6.2.2.1 | 44 | If delay critical field needs to drop frames from the queue, it drops the first non-guaranteed frame. If the Guaranteed frame needs to drop frame from the queue, it drops last. Is this asymmetry intentional. | Yes | Change the Delay Critical frame processing to drop the last non-guaranteed frame in the queue. | Accept |  | Delay critical | Sato | Resolved | Done
i-59 | Kivinen, Tero | INSIDE Secure | Editorial | 95 | 7.1.1.1 | 7 | Table 8-87 reference to the 802.15.4 is wrong, it should be 8-28. This same error is for all entries in the Table 20 | Yes | Fix all references from 8-87 to 8-28 in Table 20. | Accept |  |  | Rabarijaona | Resolved | Done
i-60 | Kivinen, Tero | INSIDE Secure | Editorial | 96 | 7.1.1.2 | 5 | Table 8-87 reference to the 802.15.4 is wrong. It should point to the MLME-SCAN.confirm table, i.e., to the table 8-29. | Yes | Fix all references from 8-87 to 8-29 in Table 21. | Accept |  |  | Rabarijaona | Resolved | Done
i-61 | Kivinen, Tero | INSIDE Secure | Editorial | 96 | 7.1.1.2 | 32 | Reference to the table 8-71 to the 802.15.4 is wrong, it should be 8-12. | Yes | Fix all references from 8-71 to 8-12 in Table 22. | Accept |  |  | Rabarijaona | Resolved | Done
i-14 | Allen, James D | Self Employed | Editorial | 99 | 6.2 | 17 | Use of acronyms and over capitalization in title. | No | The title should really be spelled out (no acronyms in titles or at least spell it out in the fist body sentence) but at least, the "L" in Long should be lower case. I know ... it's a nit pick. | Reject | According to the 802.15 WG editors instructions, each word of IE names (inlcuding neste IEs) should be capitalized According to the Style Manual (2014) the acronym should only be spelled out at first use |  | Rabarijaona | Resolved | Done
i-52 | Kivinen, Tero | INSIDE Secure | Editorial | 100 | 7.1.1.4 | 10 | Add reference to the table 14 for the PqmId, so reader will know what those numbers 0x0 - 0xf means. | No | Change "Identifies the metric in use in the L2R mesh." to "Identifies the metric in use in the L2R mesh. Metric identifier values are listed in Table 14." | Accept |  |  | Rabarijaona | Resolved | Done
i-63 | Kivinen, Tero | INSIDE Secure | Editorial | 102 | 7.1.1.8 | 42 | Table 8-87 reference to the 802.15.4 is wrong, it should be 8-28. | Yes | Fix all references from 8-87 to 8-28 in Table 28. | Accept |  |  | Rabarijaona | Resolved | Done
i-64 | Kivinen, Tero | INSIDE Secure | Editorial | 102 | 7.1.1.8 | 45 | Table 8-134 reference to the 802.15.4 is wrong, it should be 8-75. | Yes | Fix all references from 8-134 to 8-75 in Table 28. | Accept |  |  | Rabarijaona | Resolved | Done
i-72 | Kivinen, Tero | INSIDE Secure | Technical | 103 | 7.1.1.9 | 43 | There is no MeshRootAddress in the L2RLME-JOIN-MESH.request primitive, there is MeshRootList. | Yes | Change "If the MeshRootAddress(es) of the discovered L2R mesh(es) do not match the MeshRootAddress indicated by the L2RLME-JOIN-MESH.request primitive, the Status is set to NO_DESIGNATED_MESH." to "If the MeshRootAddress(es) of the discovered L2R mesh(es) do not match any of the addresses in the MeshRootList indicated by the L2RLME-JOIN-MESH.request primitive, the Status is set to NO_DESIGNATED_MESH." | Accept |  | Editorial | Rabarijaona | Resolved | Done
i-65 | Kivinen, Tero | INSIDE Secure | Editorial | 104 | 7.1.1.10 | 18 | Table 8-87 reference to the 802.15.4 is wrong, it should be 8-28. | Yes | Fix all references from 8-87 to 8-28 in Table 30. | Accept |  |  | Rabarijaona | Resolved | Done
i-66 | Kivinen, Tero | INSIDE Secure | Editorial | 104 | 7.1.1.10 | 21 | Table 8-134 reference to the 802.15.4 is wrong, it should be 8-75. | Yes | Fix all references from 8-134 to 8-75 In Table 30. | Accept |  |  | Rabarijaona | Resolved | Done
i-76 | Kivinen, Tero | INSIDE Secure | Technical | 104 | 7.1.1.11 | 50 | This text says that MT has been created or updated from the information retrieved from a TC IE. The TC IE does not have information which can be used to fill in the MT entry. It can only update some pieces of the MT table, i.e., L2R Max Depth, PQM, Dcat buffering time etc, but it cannot filling the MeshID, SSPAN, Storing Mode etc fields. | Yes | Change the text to say that it will only update the MT entries filled in the table during the PAN scan phase, and will not create any new entries. | Revise | See the resolution of i-75 | Discovery | Sato | Resolved | Done
i-77 | Kivinen, Tero | INSIDE Secure | Technical | 106 | 7.1.1.14 | 44 | If the device is part of multiple meshes, there needs to be MeshAddressMode and MeshRootAddress parameters to this primitive, so upper layer can select which of the meshes he wants to leave. | Yes | Add MeshAddressMode and MeshRootAddress. | Accept |  | Discovery | Sato | Resolved | Done
i-88 | Kivinen, Tero | INSIDE Secure | Technical | 108 | 7.1.1.17 | 32 | If device is part of multiple meshes, and one of them has some thing they want to notify (for example BETTER_MESH_DETECT or MISSING_NT_DATA), then when upper layer gets the L2RLME-NOTIFY.indication it has no way of knowing which mesh this notify relates to. | Yes | Add MeshAddressMode and MeshRootAddress to this primitive too. | Revise | Insert the following new parameters MeshAddressMode¦Enumeration ¦ SHORT, EXTENDED ¦ Addressing mode used in the mesh which the notification is about. ------------------------------------- MeshRootAddress ¦ Address ¦ Short address or EUI-64 as specified by MeshAddressMode ¦ Address of the mesh which the notification is about. For consistency, remove "Indicates" in the descriptions of Table 36 and wherever the description does not require a verb in all the primitive tables | Maintenance | Rabarijaona | Resolved | Done
i-28 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | Editorial | 109 | 7.1.2 | 6 | There are quite a few AA-related primitives. A table giving an overview of all of them would be nice. | No | Insert a table summarizing all the AA-related primitives as in 7.1.1 | Accept |  |  | Rabarijaona | Resolved | Done
i-29 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | Technical | 111 | 7.1.2.3 | 23 | The RequestingDevAddress can be confusing. Precisions would be great | No | Insert "i.e, the Source Address field value of the L2R Routing IE" at the end of the description | Accept |  | Editorial | Rabarijaona | Resolved | Done
i-30 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | Technical | 112 | 7.1.2.4 | 34 | "ExtendedAddress" is a bit vague | No | Replace the name with "JoiningDevEui64" and replace the description with "EUI-64 of the device requesting the assignment or the maintenance of the short address." - Additionally, replace "ExtendedAddress" with "JoiningDevEui64" in the AA-RP.confirm primitive. - Replace "ExtendedAddress" with "ReleasingDevEui64" in the ARLS.indication primitive - Replace "Extended Address" with "Releasing Device EUI-64" in the A-RLS IE | Revise | Replace the name with "JoiningDevExtAdr" and replace the description with "Extended address of the device requesting the assignment or the maintenance of the short address." - Additionally, replace "ExtendedAddress" with "JoiningDevExtAdr" in the AA-RP.confirm primitive. - Replace "ExtendedAddress" with "ReleasingDevExtAdr" in the ARLS.indication primitive - Replace "Extended Address" with "Releasing Device Extended Address" in the A-RLS IE | Editorial | Rabarijaona | Resolved | Done
i-90 | Kivinen, Tero | INSIDE Secure | Technical | 115 | 7.1.3.1 | 14 | This would also require handle as there might be multiple subscriptions for different meshes ongoing at the same time, thus there needs to be a way to correlate the request and the confirm. | Yes | Add Handle. | Revise | Insert the following new parameter MulticastSubscriptionHandle ¦ Integer ¦ 0x00-0xff ¦ Handle used by the next higher layer to track the status of the transmission of an RA IE containing the multicast subscription information | Multicast | Rabarijaona | Resolved | Done
i-89 | Kivinen, Tero | INSIDE Secure | Technical | 115 | 7.1.3.1 | 14 | If device is part of multiple meshes they most likely have different multicast groups and device wants to indicate to which of the meshes this subscription applies. So this primitive needs to indicate the mesh where the subscription applies. | Yes | Add MeshAddressMode and MeshRootAddress to this primitive too. | Revise | Insert the following new parameters MeshAddressMode¦Enumeration ¦ SHORT, EXTENDED ¦ Addressing mode used in the mesh where the multicast subscription notification is to be transmitted ------------------------------------- MeshRootAddress ¦ Address ¦ Short address or EUI-64 as specified by MeshAddressMode ¦ Address of the mesh wherethe multicast subscription notification is to be transmitted | Multicast | Rabarijaona | Resolved | Done
i-91 | Kivinen, Tero | INSIDE Secure | Technical | 115 | 7.1.3.2 | 37 | This would also require handle as there might be multiple subscriptions for different meshes ongoing at the same time, thus there needs to be a way to correlate the request and the confirm. | Yes | Add Handle. | Revise | Insert the following parameter in the confirm primitive MulticastSubscriptionHandle ¦ Integer ¦ 0x00-0xff ¦ Handle associated with an L2RLME-MULTICAST-SUBSCRIPTION.request primitive previously invoked | Multicast | Rabarijaona | Resolved | Done
i-47 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | Editorial | 115 | 7.1.3.2 | 53 | Check if the references to 15.4 match the published document | No | See comment | Accept |  |  | Rabarijaona | Resolved | Done
i-67 | Kivinen, Tero | INSIDE Secure | Editorial | 115 | 7.1.3.2 | 54 | Table 8-135 reference to the 802.15.4 is wrong, it should be 8-76. | Yes | Fix all references from 8-135 to 8-76 in Table 47. | Accept |  |  | Rabarijaona | Resolved | Done
i-123 | Sato, Noriyuki | Oki Electric Industry Co., Ltd. | Technical | 117 | 7.2.1 | 6 | Service ID and Sub-service ID are found in Data request primitive but they are not used by any other in this specification | No | Remove them | Accept |  | Editorial | Rabarijaona | Resolved | Done
i-122 | Sato, Noriyuki | Oki Electric Industry Co., Ltd. | Technical | 117 | 7.2.1 | 6 | Data reuqest needs to have intermediate address list for source routing Route Advertise indication is required for the mesh root in non-storing mode to know path information. | No | Update and add following pritimives to enable the next higher layer at mesh root to manage source routing in non-storing mode: Add intermediate address list into L2R-Data.reuqest Add a new primitive to indicate route advertise information to the next higher layer at mesh root. | Revise | See the latest version of document 15-16-0520-xx The primitive is conceptual so the number of intermediate address list is not needed, in the same way as the other lists in the other primitives. Add a MeshAddressMode to the new primitive | Routing | Sato | Resolved | Done
i-94 | Kivinen, Tero | INSIDE Secure | Technical | 117 | 7.2.1 | 22 | There is no longer concept of ServiceId. | Yes | Remove ServiceId | Accept |  | Editorial | Rabarijaona | Resolved | Done
i-96 | Kivinen, Tero | INSIDE Secure | Technical | 117 | 7.2.1 | 23 | There is no longer concept of SubServiceId. | Yes | Remove SubServiceId | Accept |  | Editorial | Rabarijaona | Resolved | Done
i-92 | Kivinen, Tero | INSIDE Secure | Technical | 118 | 7.2.1 | 9 | How does the multicast frame sending work. Musticast frames have short addresses as destination addresses, but here it says the address mode depends on the MeshAddressMode. | Yes | Specify how multicast frame sending works. | Revise | See the latest version of document 15-16-0564-xx | Multicast | Rabarijaona | Resolved | Done
i-68 | Kivinen, Tero | INSIDE Secure | Editorial | 118 | 7.2.1 | 25 | Table 8-134 reference to the 802.15.4 is wrong, it should be 8-75. | Yes | Fix all references from 8-134 to 8-75 in Table 48. | Accept |  |  | Rabarijaona | Resolved | Done
i-95 | Kivinen, Tero | INSIDE Secure | Technical | 118 | 7.2.1 | 38 | There is no longer concept of ServiceId. | Yes | Remove ServiceId | Accept |  | Editorial | Rabarijaona | Resolved | Done
i-97 | Kivinen, Tero | INSIDE Secure | Technical | 118 | 7.2.1 | 41 | There is no longer concept of SubServiceId. | Yes | Remove SubServiceId | Accept |  | Editorial | Rabarijaona | Resolved | Done
i-98 | Kivinen, Tero | INSIDE Secure | Technical | 118 | 7.2.1 | 50 | I do not think this parameter is set to true depending on the RvSUnsupported parameter, I think this parameter is ignored if mesh does not allow RvS. | Yes | Change text to clarify. Same thing with some of the other parameters, i.e. if Dcat is not allowed in the mesh, then Dcat parameter is ignored etc. | Revise | RvS is allowed or prohibited at different levels: the mesh level (in the TC IE), the device level (with RvSUnsupported) and at the frame level (with RvsProhibited) Create a new L2IB as follows to hold the value of RvSUnsupported from the JOIN.request primitive: l2rRvsUnsupported ¦ Boolean ¦ TRUE, FALSE¦ Indicates whether the device supports RvS Replace "Set to TRUE for every data frame if the RvSUnsupported parameter was set to TRUE when the device initially joined the mesh (see clause 7.1.1.8)." with "Set to TRUE if RvS is prohibited in the L2R mesh or if l2rRvsUnsupported is TRUE." in the description of RvsProhibited Insert "Set to FALSE if DCat is prohibited in the L2R mesh." at the end of the DCat description | Features | Rabarijaona | Resolved | Done
i-99 | Kivinen, Tero | INSIDE Secure | Technical | 119 | 7.2.1 | 18 | The Rl parameter is ignored if MacAr is not set to require acks, so better mention it here too. | Yes | Clarify text | Revise | Insert "This parameter is ignored if MacAr is different from 0x01." Move Rl after MacAr | Features | Rabarijaona | Resolved | Done
i-100 | Kivinen, Tero | INSIDE Secure | Technical | 121 | 7.2.3 | 11 | There is no longer concept of ServiceId. | Yes | Remove ServiceId | Accept |  | Editorial | Rabarijaona | Resolved | Done
i-102 | Kivinen, Tero | INSIDE Secure | Technical | 121 | 7.2.3 | 12 | There is no longer concept of SubServiceId. | Yes | Remove SubServiceId | Accept |  | Editorial | Rabarijaona | Resolved | Done
i-104 | Kivinen, Tero | INSIDE Secure | Technical | 121 | 7.2.3 | 39 | I assume that if there is no PAN ID in the L2R Routing IE (i.e., no MPO) then this is the PAN ID from the MHR. | Yes | Explain that. | Revise | If the source and the destination belong to the same PAN then the PAN ID can also be omitted in MHR according to 15.4. Add ", valid when MPO is used, ignored otherwise." at the end of the descrption of OrgnSrcPanId | Routing | Sato | Resolved | Done
i-105 | Kivinen, Tero | INSIDE Secure | Technical | 121 | 7.2.3 | 46 | I assume that if there is no PAN ID in the L2R Routing IE (i.e., no MPO) then this is the PAN ID from the MHR. | Yes | Explain that. | Revise | If the source and the destination belong to the same PAN then the PAN ID can also be omitted in MHR according to 15.4. Add ", valid when MPO is used, ignored otherwise." at the end of the descrption of OrgnSrcPanId | Routing | Sato | Resolved | Done
i-106 | Kivinen, Tero | INSIDE Secure | Technical | 121 | 7.2.3 | 48 | How does the multicast frame receiving work. The FnlDestAddr is in short address format, even if the mesh uses long addresses, so the MeshAddressMode cannot be used to know the format of FnlDestAddr format. | Yes | Explain how multicast receiving works. | Revise | See the latest version of document 15-16-0564-xx | Multicast | Rabarijaona | Resolved | Done
i-101 | Kivinen, Tero | INSIDE Secure | Technical | 121 | 7.2.3 | 53 | There is no longer concept of ServiceId. | Yes | Remove ServiceId | Accept |  | Editorial | Rabarijaona | Resolved | Done
i-103 | Kivinen, Tero | INSIDE Secure | Technical | 122 | 7.2.3 | 5 | There is no longer concept of SubServiceId. | Yes | Remove SubServiceId | Accept |  | Editorial | Rabarijaona | Resolved | Done
i-69 | Kivinen, Tero | INSIDE Secure | Editorial | 122 | 7.2.3 | 12 | Table 8-136 reference to the 802.15.4 is wrong, it should be 8-77. | Yes | Fix all references from 8-136 to 8-77 in table 50. | Accept |  |  | Rabarijaona | Resolved | Done
i-70 | Kivinen, Tero | INSIDE Secure | Editorial | 122 | 7.2.3 | 19 | What does "See Table 48" in the description of the SecurityLevel, KeyIdMode, KeySource, and KeyIndex mean. There is no such entries in the Table 48, so the reference is clearly wrong. | Yes | Fix the reference to the correct table. I am not sure which table would be correct. | Revise | Replace the valid range and the description of KeyIdMode, KeySource and KeyIndex with "As defined in Table 8-77 in IEEE Std 802.15.4." |  | Rabarijaona | Resolved | Done
i-71 | Kivinen, Tero | INSIDE Secure | Editorial | 122 | 7.2.3 | 21 | Table 9-159 reference to the 802.15.4 is wrong, it should be 9-6. | Yes | Fix all references from 9-159 to 9-6 in table 50. | Revise | See i-70 |  | Rabarijaona | Resolved | Done
i-107 | Kivinen, Tero | INSIDE Secure | Technical | 122 | 7.2.3 | 32 | When Dcat frame is received, I assume the L2R layer will split the frame to separate frames and will call this L2R-DATA.indication call multiple times, i.e., once for each concatenated frame. In that case some of the parameters are same for all of them and do not really relate to the only the part we are processing at that time (for example the HeaderIeList etc). | Yes | Explain how the concatenated frame receive works. | Revise | The HeaderIeList, MpduLinkQuality and Rssi were imported from 15.4. The HeaderIeList, MPDULinkQuality, Rssi are only about the last link and not the entire path. They should be deleted here and in the request primitive See the remaining of the resolution in the latest version of document 15-16-0565-xx | DCat | Rabarijaona | Resolved | Done
i-93 | Kivinen, Tero | INSIDE Secure | Technical | 124 | 7.3 | 5 | There is no SAME_SERVICE value for the range, but it is still as the default. | Yes | Change SAME_SERVICE to SAME_MESH_ID. | Accept |  | Editorial | Rabarijaona | Resolved | Done
i-108 | Kivinen, Tero | INSIDE Secure | Editorial | 125 | 7.3 | 50 | KeyIDMode should be written as KeyIdMode. | No | Globally replace this in the document. | Accept |  |  | Rabarijaona | Resolved | Done
i-15 | Allen, James D | Self Employed | Editorial | 130 | 7.2.1 | 38 | Grammar in Table 48, row ServiceID | No | In: "Indicates the service which the current data frame should be transmitted to." do you mean "Indicates the service to which the current data frame should be transmitted." | Revise | The row has been deleted |  | Rabarijaona | Resolved | Done
i-16 | Allen, James D | Self Employed | Editorial | 140 | A | 6 | There is an acronym in the title. | No | Spell out NLM IE in the title, or at least spell Neighbor Link Metric out in the first sentence. | Revise | Expand in the first sentence |  | Rabarijaona | Resolved | Done

## SB D07 Recirc Comments
| Comment # | Name | Affiliation | Category | Page | Subclause | Line | Comment | Must Be Satisfied | Proposed Change | Disposition Status | Disposition Detail | Technical category | Assigned to | Resolution status | Drafting status
16 | r01-16 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | General | 1 | 1 | 1 | The introduction is missing from the document. | No | Include an introduction |  |  | Editorial | Rabarijaona
15 | r01-15 | Thaler, Patricia | Broadcom Limited | General | 3 | 3.1 | 41 | "assigned MAC address" isn't a defined term. The term for MAC addresses that aren't EUIs is "Local MAC address" (See IEEE Std 802-2014 8.4 ) | Yes | Replace all instances of "assigned 64-bit MAC address" with "64-bit Local MAC address" | Accepted |  | Editorial | Rabarijaona | Resolved
17 | r01-17 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | Editorial | 7 | 4.1 | 28 | Same thing as on the previous line: a device is "part" of a PAN, not "a part" | No | Remove "a" | Accepted |  |  | Rabarijaona | Resolved
6 | r01-6 | Sato, Noriyuki | Oki Electric Industry Co., Ltd. | Technical | 7 | 4.1 | 32 | The word 'should' seems to be used not only for interoperability purpose but also for technical feasiblity. IEEE defines usage for 'should'. It looks that there is no reason to make it superceed the original definition. | No | The following sentence should be removed. The word "should" in this document indicates that the corresponding recommendation for implementation is needed for interoperability. | Accepted |  | Editorial | Rabarijaona | Resolved
18 | r01-18 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | Technical | 8 | 4.3 | 4 | The PanC DC when available is also used to deliver a PAN broadcast frame from a mesh root to the PAN coordinator | No | This should also be mentioned in the use of the PanC DC | Revised | Insert "or is used by the mesh root to deliver PAN broadcast frames to the PAN coordinator." | Mesh management | Sato | Resolved
19 | r01-19 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | Editorial | 10 | 4.4 | 7 | "L2R mesh discovery, starting or joining an L2R mesh" s/b "discovering, starting or joining an L2R mesh" | No | Make it so | Accepted |  |  | Rabarijaona | Resolved
20 | r01-20 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | Editorial | 12 | 4.4 | 1 | Use "feature" instead of "function" as in the tables in the dashed list | No | See comment | Accepted |  |  | Rabarijaona | Resolved
21 | r01-21 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | Editorial | 15 | 5.1 | 21 | "may discover" s/b "discovers" | No | Make it so | Accepted |  |  | Rabarijaona | Resolved
4 | r01-4 | Sato, Noriyuki | Oki Electric Industry Co., Ltd. | Technical | 16 | 5.1.1.3 | 50 | "A mesh root should stop its mesh if it has been disconnected from its PAN" - applying ony 2nd if-clause. How does the device know that it has been disconnected? Is that mean that losing connectivity to PAN coordinator or disconnection to any other device in PAN? When it uses 'should' or 'shall' the condition need to be precise. | No | If it is former, the disconnection causes unavaiablability of services (mesh routing service including AA?). The 2nd 'if' clause - "or if it has been disonnected from its PAN" is unnecessary. If it means latter - disconnection to any PAN devices, it should obviosuly stop any functions other than mesh service in that case. Another option is to delete this sentence "A mesh root should stop its mesh if it is no longer able to provide its services or if it has been disconnected from its PAN." since the condition to invoke this primitive is out of scope but purpose and effect to invoke this primitive is in the scope. | Revised | Delete "of if it has been disconnected from its PAN" | Mesh management | Sato | Resolved
7 | r01-7 | Sato, Noriyuki | Oki Electric Industry Co., Ltd. | Editorial | 16 | 5.1.1.3 | 51 | There are duplicates - "To stop an L2R mesh" and "to stop the running L2R mesh". | No | Delete one. | Revised | Delete "to stop the running L2R mesh" |  | Rabarijaona | Resolved
1 | r01-1 | Brama, Riccardo | CMC Labs | Editorial | 17 | 5.1.2.1 | 36 | Label for figure is wrong. Errata: FIgure 5 | No | Corrige: Figure 6 | Accepted |  |  | Rabarijaona | Resolved
8 | r01-8 | Sato, Noriyuki | Oki Electric Industry Co., Ltd. | Editorial | 17 | 5.1.2.1 | 36 | The reference to figure 5 is incorrect. | No | s/b figure 6 | Accepted |  |  | Rabarijaona | Resolved
9 | r01-9 | Sato, Noriyuki | Oki Electric Industry Co., Ltd. | Technical | 18 | 5.1.2.1 | 39 | 'empty L2RD IE' is incorrect. | No | s/b stuffed L2RD IE. | Revised | Delete "empty" | Editorial | Rabarijaona | Resolved
10 | r01-10 | Sato, Noriyuki | Oki Electric Industry Co., Ltd. | Technical | 18 | 5.1.2.1 | 43 | 'empty L2RD IE' is incorrect. | No | s/b stuffed L2RD IE. | Revised | Delete "empty" | Editorial | Rabarijaona | Resolved
11 | r01-11 | Sato, Noriyuki | Oki Electric Industry Co., Ltd. | Technical | 18 | 5.1.2.1.1 | 50 | L2R layer needs to report all of canditdates to NHL so that NHL can select a mesh to join. This section describes that L2R layer reports one mesh that mesh ID matches to the one in the scan primitive. The relationship between mesh ID and mesh is not 'one-to-one'. | No | Change the section so that primitive reports all of meshes to which the condition matches. |  |  | Mesh management | Sato
22 | r01-22 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | Editorial | 19 | 5.1.2.1.1 | 6 | "and the Mesh ID field" s/b ", and sets the Mesh ID field" | No | Make it so | Accepted |  |  | Rabarijaona | Resolved
23 | r01-23 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | Editorial | 19 | 5.1.2.1.1 | 13 | "primitive" missing after "L2RLME-PAN-SCAN.confirm" | No | Add it | Accepted |  |  | Rabarijaona | Resolved
24 | r01-24 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | Editorial | 20 | 5.1.2.2.1 | 51 | Explain how a device knows that a mesh root does not have a PanC DC | No | Insert "as indicated by the PanC DC field of the TC IE set to 0" after "PanC DC" | Accepted |  |  | Rabarijaona | Resolved
2 | r01-2 | Brama, Riccardo | CMC Labs | Technical | 20 | 5.1.2.2.1 | 52 | A device joining a L2R mesh operating on short addresses in which the mesh root does not have a PanC DC may have received a short address from a different PAN coordinator. It is in fact possible to discover L2R mesh deployed within different PANs. Sentence "only if it has already been assigned with a short address" does not guarantee the device short address validity within the PAN in which the L2R mesh network has been deployed. | No | Instead of "only if it has already been assigned with a short address" use the following "only after having associated with the PAN on which the L2R mesh is operating". |  |  | AA | Sato
12 | r01-12 | Sato, Noriyuki | Oki Electric Industry Co., Ltd. | Editorial | 21 | 5.1.2.2.1 | 3 | "At the end of the joining procedure the L2R mesh..."? | No | After this procedure, the next higher layer may set the elements to different values later. | Revised | Replace "At the end of" with "After" |  | Rabarijaona | Resolved
13 | r01-13 | Sato, Noriyuki | Oki Electric Industry Co., Ltd. | Technical | 21 | 5.1.2.2.1 | 19 | It says, "L2R sublayer may optionally disconnect from the current L2R mesh and join the new one." This procedure can be disabled by the 'l2rSwitchMesh' with false. So, the sentence s/b "L2R sublayer disconnects from ...." | No | delete 'may optionally' | Revised | Replace "may optionally disconnect" with "disconnects" | Editorial | Rabarijaona | Resolved
25 | r01-25 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | Editorial | 29 | 5.2.1 | 51 | Uncap "Encoding" | No | See comment | Accepted |  |  | Rabarijaona | Resolved
5 | r01-5 | Sato, Noriyuki | Oki Electric Industry Co., Ltd. | Technical | 29 | 5.2.1 | 54 | Mesh ID 'Identifies the L2R mesh' may mislead 'Mesh ID' is unique for each mesh. | No | Add an explanation that allows Mesh ID can share among the meshes. | Revised | Replace the description with "L2R mesh identifier" | Editorial | Rabarijaona | Resolved
26 | r01-26 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | Technical | 29 | 5.2.1 | 54 | The type and the valid range of the Mesh ID should depend on the value of the Mesh ID Encoding | No | Replace the type and valid range as per comment | Revised | Replace the Type and Valid Range of MeshID with "String" and "any string" respectively in Table 60 | Editorial | Rabarijaona | Resolved
27 | r01-27 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | Editorial | 30 | 5.2.1 | 11 | The description of Mesh root address is still depending on the service | No | Replace with "Address of the mesh root of the L2R mesh" | Accepted |  |  | Rabarijaona | Resolved
28 | r01-28 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | Editorial | 32 | 5.2.1 | 52 | "primitive" missing after "L2RLMENOTIFY. indication" and "L2RLME-PAN-SCAN.request" on the next line | No | Add it | Accepted |  |  | Rabarijaona | Resolved
29 | r01-29 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | Editorial | 38 | 5.2.2.1 | 11 | "to measure" s/b "as" | No | Make it so | Accepted |  |  | Rabarijaona | Resolved
30 | r01-30 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | Technical | 43 | 5.2.4.2 | 28 | The "L2RLME-INTERMEDIATE-ADDRLIST. indication primitive should also be used for source routing in P2P | No | Use the same primitive to report a path when source routing is used with P2P. Add "a P2P RQ IE or a P2P-RP IE" after RA IE on p.110, l.34 in the description of the primitive |  |  | Route establishment | Perkins
31 | r01-31 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | Editorial | 45 | 5.2.6 | 11 | Figure 19 s/b Figure 20 | No | Make it so | Accepted |  |  | Rabarijaona | Resolved
33 | r01-33 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | Editorial | 45 | 5.2.6 | 18 | "is treated as a unicast address and" is not needed anymore | No | Delete | Accepted |  |  | Rabarijaona | Resolved
32 | r01-32 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | Editorial | 45 | 5.2.6 | 38 | "Transmission" missing after "RA IE" | No | Add it | Accepted |  |  | Rabarijaona | Resolved
34 | r01-34 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | Editorial | 63 | 5.4.1.6 | 28 | "and ignored by the receiver." The E2E AR field is not ignored by the receiver, it is used by the receiver to know that it shouldn't send an E2E ACK IE | No | Delete | Accepted |  |  | Rabarijaona | Resolved
35 | r01-35 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | Technical | 68 | 5.4.3.1 | 35 | The device broadcast the frame only if it has neighbor within the appropriate mesh | No | Insert "in the mesh managed by the mesh root identified by the Mesh Root Address field" at the end of the sentence |  |  | Mesh management | Sato
36 | r01-36 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | Editorial | 68 | 5.4.3.1 | 37 | "the" missing before "Mesh Root" | No | Add it | Accepted |  |  | Rabarijaona | Resolved
37 | r01-37 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | Editorial | 86 | 6.1.9.1 | 21 | Uncap the second "Extended Address" | No | See comment | Accepted |  |  | Rabarijaona | Resolved
38 | r01-38 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | Technical | 96 | 7.1.1.1 | 6 | The PAN-SCAN primitive uses the Mesh Root Address, not the Destination Address | No | Remove DestAddrMode and DestAddr from the semantics and from Table 21 | Revised | Replace "DestAddrMode" with "MeshAddrMode" and "DestAddr" with "MeshRootAddr" | Editorial | Rabarijaona | Resolved
39 | r01-39 | Rabarijaona, Verotiana | National Institute of Information and Communications Technology (NICT) | Editorial | 127 | 7.2.2.2 | 54 | "code" missing after "error" | No | Add it | Accepted |  |  | Rabarijaona | Resolved
14 | r01-14 | Sato, Noriyuki | Oki Electric Industry Co., Ltd. | Technical | 132 | 7.3 | 43 | Intervals for TC IE, RA IE and NLME IE are values which related to the following capablity for network change (topology, links etc.). So they can share the same inteval unit. However, for the 'l2rSnSaRecordTimeout', it is related to the network size to avoid duplication of flooding frames. Main factor may be duty cycle, though there would be case that different interval unit need to be used for the record timeout. | No | Add another inteval unit for l2rSnSaRecordTimeout like l2rSnSaRecordTimeUnit. |  |  | Route establishment | Perkins
3 | r01-3 | Thomas, Angela |  | Technical |  |  |  | RAC Comment: Please review the use of EUI-64 in the draft. It appears to the RAC that EUI-64 is incorrectly being used as a synonym for 64-bit individual MAC address. While an EUI-64 may be used as an individual MAC address, not all individual 64-bit MAC addresses are EUI-64. An EUI-64 may be used as a universally/globally unique MAC address; but IEEE 802 networks also allow use of locally administered individual addresses as the source address for communication. The task group should carefully consider if there will be a case where locally administered addresses may be desirable for use. As written the RAC believes the draft standard precludes use of locally administered addresses as a source address. If the option for use of locally administered addresses is to be accommodated in 802.15.10, another term should be used that accommodates both local and universal 64-bit individual addresses (i.e., individual MAC address). There are 78 uses of EUI-64, 1 in the acronyms and 77 in other portions of the draft. To allow use of locally administered addresses, the it appears to RAC reviewers that all of these 77 occurrences would be replaced with another term, eliminating the need for the acronym (unless new text is added properly using the term EUI-64). If all devices shall have an EUI-64 and only use that EUI-64 as a source address, by implication, the protocol for joining a network should include a test that the individual address used is an EUI-64, and not a 64-bit locally administered address. Also, a clear indication of this requirement should be added to the draft, rather than relying on the value specifications spread throughout the draft. Please also take note of P802c, which proposes conventions for higher probability of locally administered addresses being unique than occurs with strictly manually configured local addresses. Though P802c is primarily addressing eliminating use of EUI-48 in virtual and similar ephemeral devices, it is not limited to 48-bit addressing. | Yes |  |  |  | Editorial | Rabarijaona

## Tero Comments
Comment # | Name | Affiliation | Category | Page | Subclause | Line | Comment | Must Be Satisfied | Proposed Change | Disposition Status | Disposition Detail | Technical category | Assigned to | Resolution status | Drafting status
r-01 |  |  |  | 0 |  |  | pdf index is broken, everything is under "Introduction" and there is extra "Participants" entry in index.
r-02 |  |  | T | 16 | 5.1.1.2 |  | there is text saying that if we change parameters we send TC with MSN betwen 0xf0 and 0xff. Then there is text on section 5.2.1 on page 31 saying that if we receive such TC IE, we clear the MT related to the L2R mesh adverticed in the TC IE. This is fine, but what device next need sto do is not specified anywhere. As the device now has lost the L2R-D IE information for the mesh, so it needs to do mesh discovery phase again, i.e. sending the EBR with L2R-D IE to the pan following section 5.1.2.1.3. This text should most likely be added to the 5.2.1, i.e. after it has cleared the MT for the L2R it should rediscover the mesh using 5.1.2.1.3. |  |  | Revised | Replace "clears" with "updates the MT based on the TC IE Descriptor fields" Rename the sublause to "Procedure to update the topology parameters" |  | Rabarijaona | Resolved
r-03 |  |  | T | 18 | 5.1.2.1 |  | there is text saying: "When an FFD that can act as a coordinator (including the PAN coordinator) that does not belong to any L2R mesh receives the EBR with the empty L2R-D IE, it replies with an EB with an L2R-D IE where the Mesh Root Address field is set to 0xffff or 0xffff ffff ffff ffff." This means that all nodes which are not part of any L2R mesh, and does not even want to be part of one, will be sending empty L2R-D IEs every single time they see EBR with empty L2R-D IE. This does not sound right. The text continues sayinging: "This is to allow the joining devices to know the type of PAN that is running before association. In a regular PAN, all the flags of the Descriptor field of the L2RD IE are set to 0. In an SSPAN, the SSPAN field is set to 1. In a TMCTP, the MPO field is set to 1." I do not understand how the node which is NOT part of any L2R mesh can even know what type of PAN there are... |  |  |  | Addressed with r01-9, 10, 11. "empty" is deleted Only devices matching the requested MeshId respond |  | Rabarijaona | Resolved
r-04 |  |  | E |  | 5.1.2.1.1 |  | change "The device sends an L2R-D IE where" to "The device sends an EBR with an L2R-D IE where" |  |  | Accepted |  |  | Rabarijaona | Resolved
r-05 |  |  | E |  | 5.1.2.1.2 |  | change "The device sends an L2R-D IE where" with "The device sends an EBR With an L2R-D IE where" and "All neighbors receiving the IE respond with an L2R-D IE" with "All neighbors receiving the IE respond with an EB with an L2R-D IE" |  |  | Accepted |  |  | Rabarijaona | Resolved
r-06 |  |  | T |  | 5.1.2.1.2 |  | there is text saying that we create "MT corresponding to each distinct MeshId." (this text is ther twice). Is this really for distinct MeshID, or is it distinct mesh root address. I.e., if there is multiple meshes each offering same services (i.e., having MeshId of "Internet") but with different mesh roots, I would assume we create one MT for each of the mesh roots not just one with MeshID of "Internet" having one (which one?) mesh root address. |  |  | Revised | Use "Mesh root address" |  | Rabarijaona | Resolved
r-07 |  |  | T |  | 5.1.2.1.3 |  | should we actually allow also having the destination address of the coordinator? I.e. when the network is being reconfigured and the node transmits TC IE with MSN of 0xf0, then the one who receives that wants to know if the parameters in the L2R-D IE has changed, so it wants to send EBR with empty L2R-D (or one with specific MeshID), and it would be logical to send it to the node who sent the TC IE With MSN of 0xf0. The text in 5.1.2.1.3 forbis this, and says it must be sent to the broadcast address. |  |  |  | The reconfiguration of the parameters does not require discovery |  | Rabarijaona | Resolved
r-08 |  |  | T |  | 5.1.2.2.2 |  | there is text saying "When the joining device receives the response TC IE and if the mesh root address therein corresponds to the mesh root address of a recorded MT, it computes its own depth and PQM as described in 5.2.1. The device creates or updates an MT entry related to the L2R mesh advertised in the TC IE." The node can never create the MT entry based on the TC IE alone, as TC IE does not have enough information. Thus it would be better to just say that "The device updates an MT entry related ...", i.e. remove "creates or" words. The MT entry is already there as device has done discovery phase first, thus received the L2R-D IEs containing enough information to create MT entry. The same error is also in the Figure 9, where it says "Create MT and import appropriate NT". It should say "Update MT and ..." |  |  | Accepted |  |  | Rabarijaona | Resolved
r-09 |  |  | T |  | 5.2.1 |  | table 5, it would make it much easier to understand where things come out if there would be column telling which IE contains the information. Also the spellings are inconsistent with the normal CamelCase, here you have spaces and more uppercase letters: Mesh Id Encoding -> MeshIdEncoding L2R-D IE Mesh Id -> MeshId L2R-D IE Mesh address mode -> MeshAddressMode L2R-D IE, TC IE Mesh root address -> MeshRootAddress L2R-D IE, TC IE MSN -> Msn TC IE SSPAN -> Sspan L2R-D IE Local NT -> LocalNT - PanC DC -> PanCDc L2R-D IE Metric ID -> MetricId TC IE LQT -> Lqt TC IE My PQM -> MyPqm TC IE L2R max depth -> L2rMaxDepth TC IE My depth -> MyDepth TC IE Key exchange mode -> KeyExchangeMode L2R-D IE DCat -> Dcat L2R-D IE DCat buffering unit -> DcatBufferingUnit TC IE DCat buffering time -> DcatBufferingTime TC IE MultiPAN operation -> MultiPanOperation L2R-D IE RA IE Required -> RaIeRequired L2R-D IE Storing mode -> StoringMode L2R-D IE L2R multicast -> L2rMulticast L2R-D IE On-demand P2P route discovery ->OnDemandP2pRouteDiscovery L2R-D IE P2P path list -> P2pPathList - This would also make the entries to have same names as parameteris to the L2RLME-MESH-START.request. |  |  | Revised |  |  | Rabarijaona | WiP
r-10 |  |  | T |  | 5.2.1 |  | there is text saying: "If a device receives a TC IE where the mesh root address does not correspond to that of the recorded MT(s) and if the device is required to record the MT if l2rMeshRecordMode is set to SAME_MESH_ID or ALL_MESH, the L2R sublayer creates a new MT and notifies the next higher layer with the L2RLME-NOTIFY. indication where Notification is set to NEW_MESH_FOUND. " If the l2rMeshRecordMode is se to the SAME_MESH_ID, and node receives TC IE, it does not have any way of knowing whether it is same mesh or not unles the entry is already in the MT. Should it then do EBR with empty L2R-D IE to get the L2R-D IE to know if it is same mesh? I would assume not, so I guess it should only create the new MT if the l2rMeshRecordMode is ALL_MESH. Also the 1st sentence seems to have some grammar error and does not parse that well, the "if l2rMeshRecordMode" part looks funny... |  |  | Revised | Should it then do EBR with empty L2R-D IE to get the L2R-D IE to know if it is same mesh? ==> yes as written in "The device transmits an L2R-D IE in an EBR where the Mesh Root Address Present field is set to 1 and the Mesh Root Address field is set to MeshRootAddress. The devices belonging to the L2R mesh with the requested mesh root respond to the L2R-D IE. The other devices discard the L2R-D IE." The l2rMeshIdMeshRootList should always be uptated with all the mesh IDs and mesh root address regardless of the l2rSwitchMode See additional changes on comment in p.32 |  | Rabarijaona | WiP
r-11 |  |  | T |  | 5.2.7 |  | P2P route establishment, the figure 22 has step that when we receive also the P2P-RP we check if it is already seen or not "Seen (Route, SA/PSN)" part. This step is not in the text for P2P-RP. It is there for P2P-RQ. Should it be in text for both? |  |  | Revised | The P2P-RP IE is processed in the same way as the P2P-RQ IE. Insert "as described abovein 5.2.7.1" after "When a device receives a P2P-RP IE, it processes the information in the IE in the same way as it processes the information in a P2P-RQ IE." at the end of p.47 |  | Rabarijaona | Resolved
r-12 |  |  | T |  | 5.4.1.4 |  | figure 30 has text "Forward frame", which is wrong, as I think this is also done for when the frame is sent out first time (i.e., from the original source). Changing that to "Transmit frame" would be more accurate. |  |  | Accepted |  |  | Rabarijaona | Resolved
r-13 |  |  | T |  |  |  | Table 59 and 61 are global, but there is no references when they are used. Add reference to them in section 5.5.3, i.e., change "For a broadcast transmission, the L2R sublayer refers to l2rBCSecLevel, l2rBCSecKeyIdMode, l2rBCSecKeySource, and l2rBCSecKeyIndex." to "For a broadcast transmission, the L2R sublayer refers to l2rBCSecLevel, l2rBCSecKeyIdMode, l2rBCSecKeySource, and l2rBCSecKeyIndex in Table 59.". And change "When a device transmits a unicast data frame, the L2R sublayer refers to the security L2IB attributes related to the next hop found in the l2rListOfKeySetting." to "When a device transmits a unicast data frame, the L2R sublayer refers to the security L2IB attributes related to the next hop found in the l2rListOfKeySetting in Table 61." |  |  | Accepted |  |  | Rabarijaona | Resolved
r-14 |  |  | T |  | 6.1.1.2 |  | there is now new Mesh ID Encoding telling whether the Mesh ID is encoded in UTF-8 or not. If one Mesh ID has value of "Internet" and is encoded in the UTF-8 and other has same ID, but is encoded in Unspecified encoding, are they cosnidered same? I.e., is the mesh ID octet values just compared directly each other and encoding is ignored, or should both the mesh ID and the encoding be same to make Mesh IDs same? This should be specified here. |  |  | Revised | Mesh ID Encoding is side information and it tells whether UTF-8 is specified as encoding method or not. 'Unspecified' means any ecndoing including UTF-8. The matching strings shall be done regardless Mesh ID Encoding. p.15, l.39, "The mesh ID is set to the value of MeshId from the primitive" shall be changed to "The mesh ID and the mesh ID Encoding are set to the values from the primitive." p.19, l.1, "Mesh ID field is set accoding to MeshId" shall be replaced with "Mesh ID field is set accodring to MeshId and MeshIdEncoding". p.19, l.4, "If it belongs to an L2R mesh with the requested MeshId, it responds with an L2R-D IE in an EB." The matching of MeshIDs between in L2R-D IE and the one to which the device belongs is done regardless Mesh ID encoding" p.75, l.39, figure 37, 'Format of the MeshID' field shall be 'Format of MeshID information' and 'ID' shall be 'Mesh ID'. p.75, l.47, "... length of the ID field..." shall be "...length of the Mesh ID field". p.75, l.52, "The ID field...." shall be 'The Mesh ID field..." |  | Sato | WiP
r-15 |  |  | T |  | 7.1.1.4 |  | L2RLME-MESH-START.request there is NlmOperation parameter, and in the table 9 note, there is reference to the NLMOperation in the MT table, but the MT table does not have such field. I assume NlmOperation in the L2RLME-MESH-START.request will just set the l2rNlmIeInterval L2IB attribute, but why is that set by the L2RLME-MESH-START.request, and not by the higher layer just modifying the L2IB attributes directly? What does the NLMOperatin note on Table 9 mean? |  |  | Revised | "N: When M is satisfied and additionally NLMOperation in the MT is true" in the foot note under the table 9 on the page 9 shall be replaced with "N: When M is satisfied and additionally l2rNlmIeInterval is non-zero value" Remove 'NLMOperation' parameter from 'L2RLME-MESH-START.request' primitive described on p.100. Remove the row for the 'NLMOperation' from table 25. |  | Sato | WiP
r-16 |  |  | T |  | 7.3 |  | table 58, the MeshIdEncoding is missing. If there is MeshId, I assume the encoding needs to be there too. |  |  | Accepted |  |  |  | Resolved
r-17 |  |  | T |  | 7.7 |  | table 60, the MeshIdEncoding is missing. If there is MeshId, I assume the encoding needs to be there too. |  |  | Accepted |  |  |  | Resolved