## comments
Comment ID | Date | Comment # | Name | Style | Vote | Category | Page | Subclause | Line | Comment | File | Must Be Satisfied | Proposed Change | Disposition Status | Disposition Detail
21867600023 | 06-Nov-2016 22:03:57 ET | r02-26 | Rolfe, Benjamin | Individual | Approve | Editorial | 83 | 7.13 | 61 | Insertions should be shown underlined |  | No | As proposed | Accepted
21867300023 | 06-Nov-2016 10:26:34 ET | r02-25 | Lee, Jae Seung | Individual | Approve | Technical | 160 | E.7.3.1a | 45 | Add Non-secure multi-protocol data frame and secure multi-protocol data frame for pairnet. |  | No | As in the comment | Revised | Added two rows to Table E-3a as specified in https://mentor.ieee.org/802.15/dcn/16/15-16-0804-01-003e-sb-comment-resolution-on-security-part-1.docx
21867200023 | 06-Nov-2016 10:26:34 ET | r02-24 | Lee, Jae Seung | Individual | Approve | Technical | 158 | E.7.2 | 52 | "Insertion and detection of pilot symbols" is option for OOK PHY. Change M --> O |  | No | For OOKHPLF6.2, Change FHD4:M to FHD4:O | Revised | Changed the values.
21867100023 | 06-Nov-2016 10:26:34 ET | r02-23 | Lee, Jae Seung | Individual | Approve | Technical | 103 | 9a.4.6 | 41 | Since only the SFC is used for non-Beacon frame, this sentence should be modified. |  | No | As in the comment | Revised | Modified last paragraph of 9a.4.6 according to https://mentor.ieee.org/802.15/dcn/16/15-16-0804-01-003e-sb-comment-resolution-on-security-part-1.docx and changed the word "ensure" to "check".
21867000023 | 06-Nov-2016 10:26:34 ET | r02-22 | Lee, Jae Seung | Individual | Approve | Technical | 95 | 9a.2.1 | 49 | Change "Security interfaces" to "Notational conventions". The baseline is using this as a sub-cluase title. |  | No | Change "Security interfaces" to "Notational conventions". | Accepted
21866900023 | 06-Nov-2016 10:26:34 ET | r02-21 | Lee, Jae Seung | Individual | Approve | Technical | 92 | 8.3.7 | 18 | The last paragraph in 8.3.7 in the baseline should be amended for 15.3e. |  | No | Amend the last paragraph in the baseline | Revised | Modified last paragraph of 8.3.7 according to https://mentor.ieee.org/802.15/dcn/16/15-16-0804-01-003e-sb-comment-resolution-on-security-part-1.docx
21866800023 | 06-Nov-2016 10:26:34 ET | r02-20 | Lee, Jae Seung | Individual | Approve | Technical | 91 | 8.3.7 | 65 | It is better to return an error indication on SFC verification error. |  | No | Specify that the SFC error indication is returned. | Revised | Revised error indication according to https://mentor.ieee.org/802.15/dcn/16/15-16-0804-01-003e-sb-comment-resolution-on-security-part-1.docx
21866700023 | 06-Nov-2016 10:26:34 ET | r02-19 | Lee, Jae Seung | Individual | Approve | Technical | 91 | 8.3.7 | 46 | To distinguish SFC related security error and the time token related error, it is better to use different name other than BAD-TIME-TOKEN |  | No | Add a reason code for SFC related error. | Revised | Added reason code according to https://mentor.ieee.org/802.15/dcn/16/15-16-0804-01-003e-sb-comment-resolution-on-security-part-1.docx
21866600023 | 06-Nov-2016 10:26:34 ET | r02-18 | Lee, Jae Seung | Individual | Approve | Technical | 91 | 8.3.7 | 36 | A reference to the pairnet secure Beacon frame should be added. |  | No | Add reference to the pairnet secure Beacon frame. | Revised | Added reference according to https://mentor.ieee.org/802.15/dcn/16/15-16-0804-01-003e-sb-comment-resolution-on-security-part-1.docx
21866500023 | 06-Nov-2016 10:26:34 ET | r02-17 | Lee, Jae Seung | Individual | Approve | Technical | 91 | 8.3.6 | 11 | mMaxTimeTokenChange is not defined in 15.3e. |  | No | Define mMaxTimeTokenChange in clause 7.16 | Revised | Defined mMaxTimeTokenChange according to https://mentor.ieee.org/802.15/dcn/16/15-16-0809-01-003e-sb-comment-resolution-on-security-part-2.docx
21866400023 | 06-Nov-2016 10:26:34 ET | r02-16 | Lee, Jae Seung | Individual | Approve | Technical | 90 | 8.3.5 | 64 | Change non-PRDEV to piconet DEV for clarity. |  | No | Change non-PRDEV to piconet DEV. | Accepted
21866300023 | 06-Nov-2016 10:26:34 ET | r02-15 | Lee, Jae Seung | Individual | Approve | Technical | 90 | 8.3.5 | 35 | Change non-PRDEV to piconet DEV for clarity. |  | No | Change non-PRDEV to piconet DEV. | Accepted
21866200023 | 06-Nov-2016 10:26:34 ET | r02-14 | Lee, Jae Seung | Individual | Approve | Technical | 90 | 8.3.5 | 17 | Change non-PRDEV to piconet DEV for clarity. |  | No | Change non-PRDEV to piconet DEV. | Accepted
21866100023 | 06-Nov-2016 10:26:34 ET | r02-13 | Lee, Jae Seung | Individual | Approve | Technical | 89 | 8.3.3 | 16 | Change non-PRDEV to piconet DEV for clarity. |  | No | Change non-PRDEV to piconet DEV. | Accepted
21866000023 | 06-Nov-2016 10:26:34 ET | r02-12 | Lee, Jae Seung | Individual | Approve | Technical | 88 | 8.3.2 | 64 | Since the key originator only needs to distribute the key to one DEV in the pairnet, mMaxKeyChangeDuration can be very short. |  | No | Change the behavior on mMaxKeyChangeDuration. | Revised | Modified according to https://mentor.ieee.org/802.15/dcn/16/15-16-0809-01-003e-sb-comment-resolution-on-security-part-2.docx
21865900023 | 06-Nov-2016 10:26:34 ET | r02-11 | Lee, Jae Seung | Individual | Approve | Technical | 88 | 8.3.2 | 57 | This paragraph specifies that a PRC changes the SECID in the beacon after Key Distribution and the DEV can use the new key after receiving the beacon, but it cannot be applied to pairnet since the beacon is not transmitted during the associated phase and the key change is not possible for pairnet during associated phase. |  | No | Modify the key distribution method for pairnet to allow the key change during the associated phase. | Revised | Modified according to https://mentor.ieee.org/802.15/dcn/16/15-16-0809-01-003e-sb-comment-resolution-on-security-part-2.docx
21865800023 | 06-Nov-2016 10:26:34 ET | r02-10 | Lee, Jae Seung | Individual | Approve | Technical | 88 | 8.2.2 | 26 | Table 6-22a should be updated to include the secure membership and it should be referenced from this subclause |  | No | Update Table 6-22a to include the secure membership and make it referenced in this sub-clause. | Revised | In 8.2.2, added the phrase "for piconet" and "Table 6-22a for pairnet" in the second paragraph.
21865700023 | 06-Nov-2016 10:26:34 ET | r02-9 | Lee, Jae Seung | Individual | Approve | Editorial | 84 | 7.13 | 5 | broadcast --> broadcasted |  | No | As in the comment | Rejected | Incorrect grammar
21865600023 | 06-Nov-2016 10:26:34 ET | r02-8 | Lee, Jae Seung | Individual | Approve | Editorial | 80 | 7.8.3 | 10 | shall copy to --> shall be copioed to |  | No | As in the comment | Revised | "shall copy" changed to "shall be copied"
21865500023 | 06-Nov-2016 10:26:34 ET | r02-7 | Lee, Jae Seung | Individual | Approve | Technical | 73 | 7.1 | 11 | "7.1 Introduction" in the baseline has not been amended for 15.3e. |  | No | Consider to amend 7.1 to include 15.3e. | Rejected | Withdrawn by commenter
21865400023 | 06-Nov-2016 10:26:34 ET | r02-6 | Lee, Jae Seung | Individual | Approve | Technical | 69 | 6.5.2.3 | 28 | No-ACK policy can be used for Distributed Key Request command in the baseline, but it may not be useful for 15.3e since the Key is distributed to only one DEV in the pairnet. |  | No | Consider to make the 15.3e always use Stk-ACK as the ack policy for Distributed Key Request command. | Revised | Modified according to https://mentor.ieee.org/802.15/dcn/16/15-16-0809-01-003e-sb-comment-resolution-on-security-part-2.docx
21865300023 | 06-Nov-2016 10:26:34 ET | r02-5 | Lee, Jae Seung | Individual | Approve | Technical | 64 | 6.5 | 40 | Description on the secure membership is missed in the sentence. |  | No | Add description on secure membership for 15.3e and update the Table 6-22a to include the secure membership.. | Revised | Added a column in Table 6-22a according to https://mentor.ieee.org/802.15/dcn/16/15-16-0804-00-003e-sb-comment-resolution-on-security-part-1.docx Changed first paragraph of 6.5.
21865200023 | 06-Nov-2016 10:26:34 ET | r02-4 | Lee, Jae Seung | Individual | Approve | Technical | 35 | 6.2 | 60 | 15.3e is modifying the definition of pMaxFrameBodySize in the baseline. Since the MAC frame format of 15.3e is different from the baseline (MAC subheader, padding, etc.), it is better to split the sentence into two parts, one for the legacy and the other for 15.3e. |  | No | Split the sentence into two parts: (1) pMaxFrameBodySize for the legacy (The sentence in the baseline should be used.) (2) pMaxFrameBodySize for 15.3e (The sentence in the current spec should be used.) | Revised | Modified according to https://mentor.ieee.org/802.15/dcn/16/15-16-0809-01-003e-sb-comment-resolution-on-security-part-2.docx
21864300023 | 05-Nov-2016 06:51:21 ET | r02-3 | Kondou, Keitarou | Individual | Approve | Technical | 112 | 11a.2.2.4 | 4 | Value field of N_PPRE_frame is wrongly defined. |  | No | Should be changed to "CEIL[Nblock_MFB / Nblock_PPRE] - 1" | Accepted
21864200023 | 05-Nov-2016 06:51:21 ET | r02-2 | Kondou, Keitarou | Individual | Approve | Editorial | 38 | 6.2.1.2 | 7 | All the values represented by binary numbers should be prefixed by '0b' as in the baseline document (See Table 6-1 for example). |  | No | Change the notation of the values in Table 6-1a, Table 6-2a, Table 11a-14 and Table 11a-15 | Revised | Corrected the notation in the suggested tables and also in Table 6-21a
21850500023 | 02-Nov-2016 14:16:46 ET | r02-1 | Gibbons, Patrick | Editorial Coordination |  | Editorial |  |  |  | This draft meets all editorial requirements. |  | No |  | Accepted