## Cover
July 2016 |  | 15-16-0485-00-004u-sponsor-ballot-comments.xlsx
IEEE P802.15
Wireless Personal Area Networks
Project | IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Title | 802.15.4v Sponsor Ballot Consolidated Comments
Date Submitted | 2017-02-06
Source | Phil Beecher | Voice:
16, BN3 4LE, UK
E-mail: pbeecher@wi-sun.org
Re: | P802.15.4v Draft Standard Amendment
Abstract | Amendment 802.15.4v Comments for Sponsor Ballot
Purpose | Development and approval of amendment
Notice | This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## 4v_D4-initial
Comment ID | Date | Comment # | Name | Affiliation | Category | Page | Subclause | Line | Comment | File | Must Be Satisfied | Proposed Change | Disposition Status | Disposition Detail | Other1 | Other2 | Other3 | Editor Status
21955800023 | 16-Dec-2016 00:31:30 ET | i-1 | Perry, Lisa |  | General |  |  |  | This draft meets all editorial requirements. |  | No |  | Accepted
21986400023 | 20-Dec-2016 08:25:18 ET | i-2 | Kivinen, Tero | INSIDE Secure | Editorial | 4 | 10.1.2.8 | 7 | The table 10-10 uses "Frequency band (MHz)" instead of "Band designation", and this causes confusion as actual frequencies are not unique, and there are overlapping ranges which needs to be mapped to the band designations through Table 10-1. |  | Yes | Fix the table 10-10 so that includes BOTH frequency band and band designation. Rename the first column to "Frequency band (MHz)" to "Frequency band (MHz) / Band designation". Change entries accordingly, i.e., replace 470-510 863-870 866-869** 870-876 ... In page 4 with 470-510 / 410 MHz 863-870 / 863 MHz 866-869** / 867 MHz (Singapore) 870-876 / 870 MHz (Europe) ... In this table the Band designation can be on its own row, i.e., add forced line break after "/". In addition to that add editor note, that other entries in Table 10-10 not listed here are modified accordingly. | Rejected | All the frequency bands that are used as part of the 15.4v tables use the same format per current 15.4-2015 tables. No changes required.
21986500023 | 20-Dec-2016 08:25:18 ET | i-3 | Kivinen, Tero | INSIDE Secure | Editorial | 7 | 20.1 | 11 | The table 20-1 uses "Frequency band (MHz)" instead of "Band designation", and this causes confusion as actual frequencies are not unique, and there are overlapping ranges which needs to be mapped to the band designations through Table 10-1. |  | Yes | Fix the table 20-1 so that includes BOTH frequency band and band designation. Rename the first column to "Frequency band (MHz)" to "Frequency band (MHz) / Band designation". Change entries accordingly, i.e., replace 866-869 870-876 902-928(v2) 902-907.5 & 915-928 ... with 866-869 / 867 MHz (Singapore) 870-876 / 870 MHz (Europe) 902-928(v2) / 915 MHz (NA/Mexico) 902-907.5 & 915-928 / 915 MHz (Brazil) ... In addition to that add editor note, that other entries in Table 20-1 not listed here are modified accordingly. | Rejected | All the frequency bands that are used as part of the 15.4v tables use the same format per current 15.4-2015 tables. No changes required.
21986600023 | 20-Dec-2016 08:25:18 ET | i-4 | Kivinen, Tero | INSIDE Secure | Editorial | 8 | 20.3 | 6 | The table 20-6 uses "Frequency band (MHz)" instead of "Band designation", and this causes confusion as actual frequencies are not unique, and there are overlapping ranges which needs to be mapped to the band designations through Table 10-1. |  | Yes | Fix the table 20-6 so that includes BOTH frequency band and band designation. Rename the first column to "Frequency band (MHz)" to "Frequency band (MHz) / Band designation". Change entries accordingly, i.e., replace 470-510 863-870 with 470-510 / 470 MHz 863-870 / 863 MHz In addition to that add editor note, that other entries in Table 20-6 not listed here are modified accordingly. | Rejected | All the frequency bands that are used as part of the 15.4v tables use the same format per current 15.4-2015 tables. No changes required.
21986700023 | 20-Dec-2016 08:25:18 ET | i-5 | Kivinen, Tero | INSIDE Secure | Editorial | 9 | 20.3 | 1 | The table 20-7 uses "Frequency band (MHz)" instead of "Band designation", and this causes confusion as actual frequencies are not unique, and there are overlapping ranges which needs to be mapped to the band designations through Table 10-1. |  | Yes | Fix the table 20-7 so that includes BOTH frequency band and band designation. Rename the first column to "Frequency band (MHz)" to "Frequency band (MHz) / Band designation". Change entries accordingly, i.e., replace 920-928 866-869 870-876 902-928(v2) ... with 920-928 / 920 MHz 866-869 / 867 MHz (Singapore) 870-876 / 870 MHz (Europe) 902-928(v2) / 915 MHz (NA/Mexico) ... | Rejected | All the frequency bands that are used as part of the 15.4v tables use the same format per current 15.4-2015 tables. No changes required.
21986800023 | 20-Dec-2016 08:25:18 ET | i-6 | Kivinen, Tero | INSIDE Secure | Editorial | 12 | 22.3.2 | 1 | The table 22-2 uses "Frequency band (MHz)" instead of "Band designation", and this causes confusion as actual frequencies are not unique, and there are overlapping ranges which needs to be mapped to the band designations through Table 10-1. |  | Yes | Fix the table 22-2 so that includes BOTH frequency band and band designation. Rename the first column to "Frequency band (MHz)" to "Frequency band (MHz) / Band designation". Change entries accordingly, i.e., replace 866-869 870-876 902-928(v2) ... with 866-869 / 867 MHz (Singapore) 870-876 / 870 MHz (Europe) 902-928(v2) / 915 MHz (NA/Mexico) ... In addition to that add editor note, that other entries in Table 22-2 not listed here are modified accordingly. | Rejected | All the frequency bands that are used as part of the 15.4v tables use the same format per current 15.4-2015 tables. No changes required.
21986900023 | 20-Dec-2016 08:25:18 ET | i-7 | Kivinen, Tero | INSIDE Secure | Editorial | 12 | 22.3.3 | 1 | The table 22-3 uses "Frequency band (MHz)" instead of "Band designation", and this causes confusion as actual frequencies are not unique, and there are overlapping ranges which needs to be mapped to the band designations through Table 10-1. |  | Yes | Fix the table 22-3 so that includes BOTH frequency band and band designation. Rename the first column to "Frequency band (MHz)" to "Frequency band (MHz) / Band designation". Change entries accordingly, i.e., replace 866-869 870-876 902-928(v2) ... with 866-869 / 867 MHz (Singapore) 870-876 / 870 MHz (Europe) 902-928(v2) / 915 MHz (NA/Mexico) ... In addition to that add editor note, that other entries in Table 22-3 not listed here are modified accordingly. | Rejected | All the frequency bands that are used as part of the 15.4v tables use the same format per current 15.4-2015 tables. No changes required.
21987000023 | 20-Dec-2016 08:25:18 ET | i-8 | Kivinen, Tero | INSIDE Secure | Editorial | 13 | 22.3.4 | 1 | The table 22-4 uses "Frequency band (MHz)" instead of "Band designation", and this causes confusion as actual frequencies are not unique, and there are overlapping ranges which needs to be mapped to the band designations through Table 10-1. |  | Yes | Fix the table 22-4 so that includes BOTH frequency band and band designation. Rename the first column to "Frequency band (MHz)" to "Frequency band (MHz) / Band designation". Change entries accordingly, i.e., replace 866-869 870-876 902-928(v2) ... with 866-869 / 867 MHz (Singapore) 870-876 / 870 MHz (Europe) 902-928(v2) / 915 MHz (NA/Mexico) ... In this table the Band designation can be on its own row, i.e., add forced line break after "/". In addition to that add editor note, that other entries in Table 22-4 not listed here are modified accordingly. | Rejected | All the frequency bands that are used as part of the 15.4v tables use the same format per current 15.4-2015 tables. No changes required.
21987100023 | 20-Dec-2016 08:25:18 ET | i-9 | Kivinen, Tero | INSIDE Secure | Editorial | 14 | 22.3.5 | 1 | The table 22-5 uses "Frequency band (MHz)" instead of "Band designation", and this causes confusion as actual frequencies are not unique, and there are overlapping ranges which needs to be mapped to the band designations through Table 10-1. |  | Yes | Fix the table 22-5 so that includes BOTH frequency band and band designation. Rename the first column to "Frequency band (MHz)" to "Frequency band (MHz) / Band designation". Change entries accordingly, i.e., replace 866-869 870-876 902-928(v2) ... with 866-869 / 867 MHz (Singapore) 870-876 / 870 MHz (Europe) 902-928(v2) / 915 MHz (NA/Mexico) ... In this table the Band designation can be on its own row, i.e., add forced line break after "/". In addition to that add editor note, that other entries in Table 22-5 not listed here are modified accordingly. | Rejected | All the frequency bands that are used as part of the 15.4v tables use the same format per current 15.4-2015 tables. No changes required.
21987200023 | 20-Dec-2016 08:25:18 ET | i-10 | Kivinen, Tero | INSIDE Secure | Editorial | 14 | 22.3.11 | 6 | The table 22-19 uses "Frequency band (MHz)" instead of "Band designation", and this causes confusion as actual frequencies are not unique, and there are overlapping ranges which needs to be mapped to the band designations through Table 10-1. |  | Yes | Fix the table 22-19 so that includes BOTH frequency band and band designation. Rename the first column to "Frequency band (MHz)" to "Frequency band (MHz) / Band designation". Change entries accordingly, i.e., replace 866-869 870-876 902-928(v2) ... with 866-869 / 867 MHz (Singapore) 870-876 / 870 MHz (Europe) 902-928(v2) / 915 MHz (NA/Mexico) ... In addition to that add editor note, that other entries in Table 22-19 not listed here are modified accordingly. | Rejected | All the frequency bands that are used as part of the 15.4v tables use the same format per current 15.4-2015 tables. No changes required.
21987300023 | 20-Dec-2016 08:25:18 ET | i-11 | Kivinen, Tero | INSIDE Secure | Editorial | 15 | 22.3.12 | 1 | The table 22-20 uses "Frequency band (MHz)" instead of "Band designation", and this causes confusion as actual frequencies are not unique, and there are overlapping ranges which needs to be mapped to the band designations through Table 10-1. |  | Yes | Fix the table 22-20 so that includes BOTH frequency band and band designation. Rename the first column to "Frequency band (MHz)" to "Frequency band (MHz) / Band designation". Change entries accordingly, i.e., replace 866-869 870-876 902-928(v2) ... with 866-869 / 867 MHz (Singapore) 870-876 / 870 MHz (Europe) 902-928(v2) / 915 MHz (NA/Mexico) ... In addition to that add editor note, that other entries in Table 22-20 not listed here are modified accordingly. | Rejected | All the frequency bands that are used as part of the 15.4v tables use the same format per current 15.4-2015 tables. No changes required.
21987400023 | 20-Dec-2016 08:25:18 ET | i-12 | Kivinen, Tero | INSIDE Secure | Editorial | 16 | 22.5.3 | 1 | The table 22-21 uses "Frequency band (MHz)" instead of "Band designation", and this causes confusion as actual frequencies are not unique, and there are overlapping ranges which needs to be mapped to the band designations through Table 10-1. |  | Yes | Fix the table 22-21 so that includes BOTH frequency band and band designation. Rename the first column to "Frequency band (MHz)" to "Frequency band (MHz) / Band designation". Change entries accordingly, i.e., replace 866-869 870-876 902-928(v2) ... with 866-869 / 867 MHz (Singapore) 870-876 / 870 MHz (Europe) 902-928(v2) / 915 MHz (NA/Mexico) ... In addition to that add editor note, that other entries in Table 22-21 not listed here are modified accordingly. | Rejected | All the frequency bands that are used as part of the 15.4v tables use the same format per current 15.4-2015 tables. No changes required.
21987500023 | 20-Dec-2016 08:25:18 ET | i-13 | Kivinen, Tero | INSIDE Secure | Editorial | 16 | 22.5.3 | 4 | The table 22-22 uses "Frequency band (MHz)" instead of "Band designation", and this causes confusion as actual frequencies are not unique, and there are overlapping ranges which needs to be mapped to the band designations through Table 10-1. |  | Yes | Fix the table 22-22 so that includes BOTH frequency band and band designation. Rename the first column to "Frequency band (MHz)" to "Frequency band (MHz) / Band designation". Change entries accordingly, i.e., replace 866-869 870-876 902-928(v2) ... with 866-869 / 867 MHz (Singapore) 870-876 / 870 MHz (Europe) 902-928(v2) / 915 MHz (NA/Mexico) ... In addition to that add editor note, that other entries in Table 22-22 not listed here are modified accordingly. | Rejected | All the frequency bands that are used as part of the 15.4v tables use the same format per current 15.4-2015 tables. No changes required.
21987600023 | 20-Dec-2016 08:25:18 ET | i-14 | Kivinen, Tero | INSIDE Secure | Editorial | 17 | 22.5.4 | 1 | Table 22-23 formatting is wrong. There is no header line, and the header for the "Frequency band (MHz)" is repeated on every row. This same formatting error is also in the 802.15.4-2015. |  | No | Add header line to the table 22-23, and move "Frequency band (MHz)" there from the individual lines. Leave the header for last 3 columns empty. | Rejected | The format that was used as part of Table 22-23 is the same format per 15.4-2015 table 22-23. No changes required.
21987700023 | 20-Dec-2016 08:25:18 ET | i-15 | Kivinen, Tero | INSIDE Secure | Editorial | 17 | 22.5.4 | 1 | The table 22-23 uses "Frequency band (MHz)" instead of "Band designation", and this causes confusion as actual frequencies are not unique, and there are overlapping ranges which needs to be mapped to the band designations through Table 10-1. |  | Yes | Fix the table 22-23 so that includes BOTH frequency band and band designation. Rename the first column to "Frequency band (MHz)" to "Frequency band (MHz) / Band designation". Change entries accordingly, i.e., replace 866-869 870-876 902-928(v2) ... with 866-869 / 867 MHz (Singapore) 870-876 / 870 MHz (Europe) 902-928(v2) / 915 MHz (NA/Mexico) ... In addition to that add editor note, that other entries in Table 22-23 not listed here are modified accordingly. | Rejected | All the frequency bands that are used as part of the 15.4v tables use the same format per current 15.4-2015 tables. No changes required.
21987800023 | 20-Dec-2016 08:25:18 ET | i-16 | Kivinen, Tero | INSIDE Secure | Editorial | 17 | 22.5.13 | 5 | The table 22-24 uses "Frequency band (MHz)" instead of "Band designation", and this causes confusion as actual frequencies are not unique, and there are overlapping ranges which needs to be mapped to the band designations through Table 10-1. |  | Yes | Fix the table 22-24 so that includes BOTH frequency band and band designation. Rename the first column to "Frequency band (MHz)" to "Frequency band (MHz) / Band designation". Change entries accordingly, i.e., replace 866-869 870-876 902-928(v2) ... with 866-869 / 867 MHz (Singapore) 870-876 / 870 MHz (Europe) 902-928(v2) / 915 MHz (NA/Mexico) ... In addition to that add editor note, that other entries in Table 22-24 not listed here are modified accordingly. | Rejected | All the frequency bands that are used as part of the 15.4v tables use the same format per current 15.4-2015 tables. No changes required. | Note for Phil to send a comment to SC-maintanance
21992400023 | 05-Jan-2017 05:56:56 ET | i-17 | Shah, Kunal | Silver Spring Networks Inc. | Editorial | 2 | 7.4.4.10 | 6 | The font size for "Mode Switch" field is different than other fields. |  | No | Change the font size for "Mode Switch" field to make it consistent with other fields. | Accepted |  |  |  |  | Done
21992500023 | 05-Jan-2017 05:56:56 ET | i-18 | Shah, Kunal | Silver Spring Networks Inc. | Editorial | 2 | 7.4.4.10 | 18 | Band desgination heading in Table 7-19a, where "d" should be capital to be consistent with the base standard. |  | No | See comment | Revised | Undeline 'd' and strikethrough the D in Table 7-19. | Note for Phil to send a comment to SC-maintanance |  |  | Done
21992600023 | 05-Jan-2017 05:56:56 ET | i-19 | Shah, Kunal | Silver Spring Networks Inc. | Editorial | 2 | 7.4.4.10 | 21 | Band desgination heading in Table 7-19a, where "d" should be capital to be consistent with the base standard. |  | No | See comment | Rejected | Per IEEE style manual 2014 clause 13, only the first letter of the first word in table headings should be capitalized. No change is required.
21992700023 | 05-Jan-2017 05:56:56 ET | i-20 | Shah, Kunal | Silver Spring Networks Inc. | Editorial | 2 | 7.4.4.10 | 21 | NA and ANZ need to be included in the acronym section. |  | No | Include the acronyms in section 3.2 | Revised | All references to countries and geographical areas were removed throughout the draft. No change required.
21995800023 | 07-Jan-2017 16:39:40 ET | i-21 | Nikolich, Paul | None - Self-funded | Technical | 2 | 7 | 17 | The band designations in the Frequency Band Identifier tables call out specific countries and regions, which implies compliance to the relevant local regulatory regimes are necessary to meet the amendment's technical requirements, yet I was unable to find references to the regulations of the particular countries or regions |  | No | In the reference section of the base document add pointers to the relevant country/region regulatory requirements. | Revised | All references to countries and geographical areas were removed throughout the draft. No change required. |  |  |  | Done
21995900023 | 07-Jan-2017 23:36:58 ET | i-22 | Gilb, James | Self | Editorial | ii | 0 | 12 | The use of spaces and the size of the dash between the frequency numbers is not consistent, e.g., it is "863-870" (small dash, no spaces) in the abstract and "863 - 870" (long dash, spaces) in the keywords. |  | Yes | Change the dashes to match the abstract and remove the spaces from "863 - 870 MHz band, 870 - 876 MHz band, 470 - 510 MHz band, 902 - 928 MHz" | Accepted |  |  |  |  | Done
21996000023 | 07-Jan-2017 23:36:58 ET | i-23 | Gilb, James | Self | Editorial | 2 | 7.4.4.10 | 6 | "Mode Switch" is set in the wrong font. |  | Yes | Change the font size and type for "Mode Switch" to match the rest of the figure. | Accepted |  |  |  |  | Done
21996100023 | 07-Jan-2017 23:36:58 ET | i-24 | Gilb, James | Self | Editorial | 2 | 7.4.4.10 | 10 | In correct capitalization of the field name as per the IEEE 802.15 Style guide. |  | Yes | Change "Extended band identifier field" to be "Extended Band Identifier field" | Accepted |  |  |  |  | Done
21996200023 | 07-Jan-2017 23:36:58 ET | i-25 | Gilb, James | Self | Editorial | 2 | 7.4.4.10 | 21 | The acronyms NA and ANZ have not been expanded previously and are not in the acronyms subclause. |  | Yes | Since these acronyms are used in multiple places, in Table 7-19a, change "NA" to be "North America (NA)" and "ANZ" to be "Australia and New Zealand". Add to the draft clause 3, subclause 3.2 and define these acronyms. | Rejected | These acronyms will be removed.
21996300023 | 07-Jan-2017 23:36:58 ET | i-26 | Gilb, James | Self | Technical | 2 | 7.4.4.10 | 18 | The convention in the standard has been to identify frequency bands only, and not countries or geographical regions. This draft adds country designations to some of the bands identified, but not others. If other countries allocate the same band at a later time, the standard would need to be updated. Likewise, if a country removes an allocation, the standard would need to be updated. The policy has been to define the air interface only and leave it to the implementers to verify that they are meeting local regulatory requirements. |  | Yes | Delete all references to countries and/or geographic regions Table 7-19 and Table 7-19a | Revised | All references to countries and geographical areas were removed throughout the draft. No change required. |  |  |  | Done
21996400023 | 07-Jan-2017 23:36:58 ET | i-27 | Gilb, James | Self | Editorial | 2 | 7.4.4.10 | 17 | The editing instructions do not make it clear that the other rows are unmodified. |  | Yes | Add to the editing instructions "The rows that are not shown are unmodified." | Accepted |  |  |  |  | Done
21996500023 | 07-Jan-2017 23:36:58 ET | i-28 | Gilb, James | Self | Editorial | 3 | 7.4.4.10 | 5 | In correct capitalization of the field name as per the IEEE 802.15 Style guide. |  | Yes | Change "SUN device capabilities IE" to be "SUN Device Capabilities IE" (yes, I know it is broken in the published draft, fix it now.) | Accepted |  |  |  |  | Done
21996600023 | 07-Jan-2017 23:36:58 ET | i-29 | Gilb, James | Self | Editorial | 3 | 7.4.4.10 | 6 | In correct capitalization of the field name as per the IEEE 802.15 Style guide. |  | No | Change "Extended band identifier field" to be "Extended Band Identifier field" | Revised | The sentence is removed. |  |  |  | Done
21996700023 | 07-Jan-2017 23:36:58 ET | i-30 | Gilb, James | Self | Technical | 3 | 7.4.4.10 | 6 | Repeated normative language. This is stated earlier on page 2, line 9. |  | Yes | Delete "If Extended band identifier field in Figure 7-62 is set to zero, then the Specific Frequency Bands field is 2 octets long with frequency band identifiers given in Table 7-19. Otherwise the Frequency Band field is 4 octets long with the extended frequency band identifier values given in Table 7-19 and Table 7-19a." on lines 6-9, page 3. | Accepted |  |  |  |  | Done
21996800023 | 07-Jan-2017 23:36:58 ET | i-31 | Gilb, James | Self | Technical | 3 | 7.4.4.10 | 11 | In 802.15.4u, mode IDs 10 is marked as reserved. Hence, the row needs to be modified, not added. |  | Yes | Change line 10 to say "Change Table 7-22 as indicated, all rows not shown are not modified". In Table 7-22, the second row, second column, should be "Reserved" with strikethough followed by and underlined "300 kb/s; 2-FSK; mod. Index = 0.5; channel spacing = 400kHz" | Accepted |  | Phil to send an email to James asking the question regarding editing instructions to Tables. |  |  | Done
21996900023 | 07-Jan-2017 23:36:58 ET | i-32 | Gilb, James | Self | Technical | 3 | 7.4.4.10 | 16 | In the 915 MHz NA/Mexico band row, there is a "(v2)" following 902-928 with no explanation of what this means. |  | Yes | Change "(v2)" to be " (alternate)" | Accepted |  |  |  |  | Done
21997000023 | 07-Jan-2017 23:36:58 ET | i-33 | Gilb, James | Self | Editorial | 4 | 7.4.4.10 | 1 | The last row, first column does not break well. |  | Yes | Change the "/" to be ", " so that the cell contents will break across lines better. Also, expand the column width so that perhaps it will not have to break across lines. | Revised | All references to countries and geographical areas were removed throughout the draft. No change required. |  |  |  | Done
21997100023 | 07-Jan-2017 23:36:58 ET | i-34 | Gilb, James | Self | Editorial | 4 | 7.4.4.10 | 1 | The header row shall be repeated when a table breaks across pages. |  | Yes | If you are using the Word template, then this is in the table properties. In Framemaker it is in the table properties popup. Ask the Working Group Technical Editor for help if the Task Group Technical Editor does not know how to fix this. | Revised | The standard will be professionally edited by IEEE prior to publication. |  |  |  | Done
21997200023 | 07-Jan-2017 23:36:58 ET | i-35 | Gilb, James | Self | Technical | 4 | 7.4.4.10 | 1 | The table footnote is incorrectly specified, a letter is supposed to be used. Notes in a standard are informative, but are formatted in a specific manner, not as shown here. A table footnote is normative according to the style manual. |  | Yes | Your best bet here is to remove the "*" from the table and follow the table with this "NOTE: The 915 MHz (NA/Mexico), 915 MHz (Brazil) and 915 MHz (ANZ) frequency bands provide additional PHY parameter definitions." Refer to the IEEE Style manual for formatting help. | Revised | Removed "* Editors" from the note and changed the band identifier to match up with the changed band desgination per Table 10-1. |  |  |  | Done
21997300023 | 07-Jan-2017 23:36:58 ET | i-36 | Gilb, James | Self | Technical | 4 | 10.1.2.8 | 7 | The changes to the table are incorrectly specified. |  | Yes | In the third row, the strike through for "470.2" should be changed to a strike through of "470.4" because that is what is in the base standard. | Accepted |  |  |  |  | Done
21997400023 | 07-Jan-2017 23:36:58 ET | i-37 | Gilb, James | Self | Technical | 4 | 10.1.2.8 | 7 | The changes to the table are incorrectly specified. |  | Yes | In the rows for 863-870 SUN FSK operating modes, there is underlined text, but no strike through to show the deletion of the existing text. Add the following with strike through to the last three columns: first row "0.2", "34", "863.125" and second row "0.4", "17", "863.225" | Accepted |  |  |  |  | Done
21997500023 | 07-Jan-2017 23:36:58 ET | i-38 | Gilb, James | Self | Technical | 4 | 10.1.2.8 | 7 | The changes to the table are incorrectly specified. |  | Yes | In the rows for 863-870 SUN OFDM Option 4, add the following with strike through to the last two columns "34" and "863.125" | Accepted |  |  |  |  | Done
21997600023 | 07-Jan-2017 23:36:58 ET | i-39 | Gilb, James | Self | Editorial | 4 | 10.1.2.8 | 7 | "CH" is used, but is not defined as an acronym. As an aside, plurals of an acronym do not use an apostrophe in IEEE standards |  | Yes | Change "CH's" to be "channels" in all places in Table 10-10. This occurs on all 3 pages. | Accepted |  |  |  |  | Done
21997700023 | 07-Jan-2017 23:36:58 ET | i-40 | Gilb, James | Self | Editorial | 5 | 10.1.2.8 | 1 | The header row shall be repeated when a table breaks across pages. |  | Yes | If you are using the Word template, then this is in the table properties. In Framemaker it is in the table properties popup. Ask the Working Group Technical Editor for help if the Task Group Technical Editor does not know how to fix this. | Revised | The standard will be professionally edited by IEEE prior to publication. |  |  |  | Done
21997800023 | 07-Jan-2017 23:36:58 ET | i-41 | Gilb, James | Self | Editorial | 5 | 10.1.2.8 | 1 | In the new 902-928 band, there is a "(v2)" with no explanation |  | Yes | If this is supposed to indicate a different 902-928 band, then chose a name and define it, e.g., "902-928 (alternate)" and add text that describe its use. | Revised | 902-928(v2) changes to 902-928 (alternate). Move the description for the band designation to an informative Annex. |  |  |  | Done
21997900023 | 07-Jan-2017 23:36:58 ET | i-42 | Gilb, James | Self | Editorial | 4 | 10.1.2.8 | 7 | The convention (for better or worse) in this table is to use ampersand instead of "and" |  | Yes | Change "#2 and #3" to be "#2 & #3" | Revised | Change "SUN FSK operating modes #1, #2 and #3" in Table 10-10 to "SUN FSK operating modes #1, #2 & #3". |  |  |  | Done
21998000023 | 07-Jan-2017 23:36:58 ET | i-43 | Gilb, James | Self | Editorial | 4 | 10.1.2.8 | 7 | "1st freq" is wrong, it should be first and "freq" is not a word. |  | Yes | Change "1st freq" to be "first frequency" in all locations in the table (approximately 35 places). This occurs on all 3 pages | Accepted |  |  |  |  | Done
21998100023 | 07-Jan-2017 23:36:58 ET | i-44 | Gilb, James | Self | Editorial | 4 | 10.1.2.8 | 7 | The use of spaces and the size of the dash between the channel numbers is not consistent, e.g., it is "0-26" (small dash, no spaces) in the abstract and "15 - 29 (long dash, spaces) in the keywords. |  | Yes | Change the dashes to be a regular dash and remove the spaces around it. This occurs in multiple locations in the table on all 3 pages. | Accepted |  |  |  |  | Done
21998200023 | 07-Jan-2017 23:36:58 ET | i-45 | Gilb, James | Self | Technical | 7 | 10.1.2.8 | 1 | The table footnote is incorrectly specified, a letter is supposed to be used, not * or **. Notes in a standard are informative, but are formatted in a specific manner, not as shown here. A table footnote is normative according to the style manual. |  | Yes | Change to lettered footnotes and remove "Note: " from the footnote text as "Note" is used only for informative notes. The table footnotes are normative. | Revised | Remove "Note:" from the footnote. Change '*' to 'a' and '**' to 'b' in the footnote and associated rows in the table. |  |  |  | Done
21998300023 | 07-Jan-2017 23:36:58 ET | i-46 | Gilb, James | Self | Editorial | 5 | 10.1.2.8 | 7 | The last row in the table breaks across pages. Yes, this is the default in MS Word because it is a silly program. It is rarely correct to break a row across pages and should be the exception. |  | Yes | Modify the row format to remove the check box that says "allow row to break across pages" Do this for all the rows in the table (if you select the table, then select table properties from the right click menu, select the row tab, you can fix all the rows at once.) | Revised | The standard will be professionally edited by IEEE prior to publication. |  |  |  | Done
21998400023 | 07-Jan-2017 23:36:58 ET | i-47 | Gilb, James | Self | Editorial | 7 | 10.2.7 | 6 | "x" (the letter) is never used to indicate multiplication. It is either ampersand or the specific math character that is a times symbol. Also a number less than 15 without a unit is spelled out. |  | Yes | The simple thing here is to change "2 x symbol rate" to be "twice the symbol rate" or "two times the symbol rate" | Revised | Change the current text from "2 x symbol rate" to "twice the symbol rate" |  |  |  | Done
21998500023 | 07-Jan-2017 23:36:58 ET | i-48 | Gilb, James | Self | Technical | 3 | 20.1 | 16 | In the 902-928 row, there is a "(v2)" with no explanation of what this means. |  | Yes | Change "(v2)" to be " (alternate)" | Accepted |  |  |  |  | Done
21998600023 | 07-Jan-2017 23:36:58 ET | i-49 | Gilb, James | Self | Editorial | 7 | 20.3 | 14 | Incorrect editing instructions |  | Yes | Change "paragraph #2 of 20.3" to be "the second paragraph" | Revised | All references to countries and geographical areas were removed throughout the draft. Thus paragraph #2 of 20.3 is unchanged by this amendment. |  |  |  | Done
21998700023 | 07-Jan-2017 23:36:58 ET | i-50 | Gilb, James | Self | Editorial | 7 | 20.3 | 14 | Incorrect editing instructions |  | Yes | Change "paragraph #3 of 20.3" to be "the third paragraph" | Accepted |  |  |  |  | Done
21998800023 | 07-Jan-2017 23:36:58 ET | i-51 | Gilb, James | Self | Technical | 7 | 20.3 | 10 | This paragraph has two major mistakes. The first is the continuation of the mistake of associating countries or geographical regions with a band. The second is that the purpose of defining a band name (e.g., 915 MHz band) is that it is not necessary to provide additional information about the band in every location in which it is referenced. |  | Yes | On line 2, delete "(China)", "(Europe)" and "(NA)", one lines 10-12, delete the country names and parentheses. Even if this information was kept in Table 10-1 (it should be removed), there is no reason to copy in every location in which the band is referenced. | Revised | All references to countries and geographical areas were removed throughout the draft. Thus paragraph #2 of 20.3 is unchanged by this amendment. |  |  |  | Done
21998900023 | 07-Jan-2017 23:36:58 ET | i-52 | Gilb, James | Self | Technical | 3 | 10.1.1 | 16 | The 802.15.4 standard does not reference regulatory information (there is an informative document that has this on http://mentor.ieee.org, referenced in the bibliography of the 2015 standard). Instead, the standard only specifies the over the air interface and regulatory compliance is up to the implementer and user. Furthermore, adding country names dates the standard as countries, independently change their regulations and it is not reasonable to hope that the standard can keep up. |  | Yes | Delete the country and geographical regions from the band designation in Table 10-1. It serves no useful purpose. | Revised | Changed the band designations to remove all references to countries and geographical areas throughout the draft. For frequency ID's used multiple times - adding a "-" and a letter (a,b,c,etc…) to differentiate between the designators. These have been changed in Tables 7-19, 7-19a and 10-1 and are then carried forward in multiple parts of clauses 20, 21 and 22. |  |  |  | Done
21999000023 | 07-Jan-2017 23:56:07 ET | i-53 | Gilb, James | Self | Editorial | 4 | 10.1.2.8 | 7 | The use of spaces and the size of the dash between the channel numbers is not consistent, e.g., it is "0-26" (small dash, no spaces) and "15 - 29 (long dash, spaces) |  | Yes | Change the dashes to be a regular dash and remove the spaces around it. This occurs in multiple locations in the table on all 3 pages. | Accepted
21999100023 | 07-Jan-2017 23:56:07 ET | i-54 | Gilb, James | Self | Editorial | 7 | 20.3 | 14 | Incorrect editing instructions |  | Yes | Change "paragraph #2" to be "the second paragraph" | Accepted
21999200023 | 07-Jan-2017 23:56:07 ET | i-55 | Gilb, James | Self | Editorial | 7 | 20.3 | 14 | Incorrect editing instructions |  | Yes | Change "paragraph #3" to be "the third paragraph" | Accepted
21999300023 | 07-Jan-2017 23:56:07 ET | i-56 | Gilb, James | Self | Technical | 10 | 20.6.6 | 7 | According to SI-10, dBc is an improper unit. In this case, it is also incorrect as it is measured relative to the modulated in-band signal and not the carrier. The base standard has it correct as "dB", not "dBc" |  | Yes | Change "dBc" to be "dB" in 3 locations in lines 7-9 | Revised | Insert new paragraph in subcluase 20.6.6 after the first paragraph as follows: When Operating mode #1 with 100 kHz channel spacing or Operating mode #3 with 200 kHz channel spacing or Operating mode #5 with 400 kHz channel spacing is used as specified in Table 20-6 and Table 20-7, offset frequencies M1 and M2 and the integrated bandwidth (with respect to the M1 and M2 offset frequencies) are defined as follows: The integration bandwidth shall be equal to 5/8 x S, where S is the channel spacing, expressed in units of hertz. M1 = 9/16 × S × (1 + h) M2 = 9/8 × S × (1 + h) where h is the modulation index for 2-level modulation. The transmit spectral content at M1 and M2 for the Operating modes specified above shall be less than -20 dB and -35 dB, respectively. Otherwise for all other Operating modes specified in Table 20-6 and Table 20-7, the offset frequencies M1 and M2 and the integrated bandwidth shall be defined as follows: The proposal is shown on slide 7 of 15-17-0068-02. |  |  |  | Done
21999400023 | 07-Jan-2017 23:56:07 ET | i-57 | Gilb, James | Self | Editorial | 10 | 21.5.1 | 16 | The bands are to be listed individually. |  | Yes | Change "-- 902 - 907.5 MHz & 915 - 928 MHz" to be "-- 902 - 907.5 MHz" and "-- 915 - 928 MHz" (i.e., separate lines in the dashed list). | Rejected | Brazil defines this frequency band as a single non-contiguous band. No changes required.
21999500023 | 07-Jan-2017 23:56:07 ET | i-58 | Gilb, James | Self | Editorial | 7 | 20.1 | 11 | The bands are to be listed individually. |  | Yes | Put "902-907.5 MHz" and "915 - 928 MHz" on separate rows in the table | Rejected | Brazil defines this frequency band as a single non-contiguous band. No changes required.
21999600023 | 07-Jan-2017 23:56:07 ET | i-59 | Gilb, James | Self | Editorial | 7 | 20.1 | 11 | The use of spaces and the size of the dash between the frequency numbers is not consistent |  | Yes | Change "920.5 - 924.5" to be "920.2-924.4" (remove spaces and use a regular size dash). | Accepted |  |  |  |  | Done
21999700023 | 07-Jan-2017 23:56:07 ET | i-60 | Gilb, James | Self | Editorial | 10 | 21.5.1 | 13 | The use of spaces and the size of the dash between the frequency numbers is not consistent |  | Yes | Remove the spaces between the number and the dash and use a regular size dash in the list of frequencies to match the usage in the base standard. | Accepted |  |  |  |  | Done
21999800023 | 07-Jan-2017 23:56:07 ET | i-61 | Gilb, James | Self | Editorial | 11 | 22.1 | 6 | Incorrect editing instructions |  | Yes | Change "paragraph #2" to be "the second paragraph" | Accepted |  |  |  |  | Done
21999900023 | 07-Jan-2017 23:56:07 ET | i-62 | Gilb, James | Self | Editorial | 8 | 22.1 | 8 | Listing the countries with the bands is incorrect according to the editorial and technical convention of 802.15.4 |  | Yes | Delete "(NA, NA/Mexico, Brazil and ANZ)" | Revised | All references to countries and geographical areas were removed throughout the draft.
22000000023 | 07-Jan-2017 23:56:07 ET | i-63 | Gilb, James | Self | Editorial | 13 | 22.2.1.1 | 13 | Listing the countries with the bands is incorrect according to the editorial and technical convention of 802.15.4 |  | Yes | Delete "(NA, NA/Mexico, Brazil and ANZ)", "(China)", "(Singapore)", "(Europe)" (2 places), "(Europe and Philippines)", "(Malaysia)", "(Japan, China, Hong Kong, Singapore, Thailand and Vietnam)" | Revised | All references to countries and geographical areas were removed throughout the draft.
22000100023 | 07-Jan-2017 23:56:07 ET | i-64 | Gilb, James | Self | Editorial | 11 | 22.1 | 6 | Incorrect editing instructions |  | Yes | Change "paragraph #1" to be "the first paragraph" | Revised | Change the "paragraph #1" to "the first paragraph" on line 12. Also change the "paragraph #2" to "the second paragraph" on line 19
22000200023 | 07-Jan-2017 23:56:07 ET | i-65 | Gilb, James | Self | Editorial | 11 | 22.2.2 | 20 | Listing the countries with the bands is incorrect according to the editorial and technical convention of 802.15.4 |  | Yes | Delete the country and geographical regions from the text. | Revised | All references to countries and geographical areas were removed throughout the draft.
22000300023 | 07-Jan-2017 23:56:07 ET | i-66 | Gilb, James | Self | Editorial | 12 | 20.1 | 1 | The bands are to be listed individually. |  | Yes | Put "902-907.5 MHz" and "915 - 928 MHz" on separate rows in the table | Rejected | Brazil defines this frequency band as a single non-contiguous band. No changes required.
22000400023 | 07-Jan-2017 23:58:11 ET | i-67 | Gilb, James | Self | Editorial | 12 | 22.3.2 | 1 | The bands are to be listed individually. |  | Yes | Put "902-907.5 MHz" and "915 - 928 MHz" on separate rows in the table | Rejected | Brazil defines this frequency band as a single non-contiguous band. No changes required.
22000500023 | 07-Jan-2017 23:58:11 ET | i-68 | Gilb, James | Self | Editorial | 12 | 22.3.2 | 1 | In the 902-928 row, there is a "(v2)" with no explanation of what this means. |  | Yes | Change "(v2)" to be " (alternate)" | Accepted |  |  |  |  | Done
22000600023 | 07-Jan-2017 23:58:11 ET | i-69 | Gilb, James | Self | Editorial | 12 | 22.3.3 | 5 | The bands are to be listed individually. |  | Yes | Put "902-907.5 MHz" and "915 - 928 MHz" on separate rows in the table | Rejected | Brazil defines this frequency band as a single non-contiguous band. No changes required.
22000700023 | 07-Jan-2017 23:58:11 ET | i-70 | Gilb, James | Self | Editorial | 12 | 22.3.3 | 5 | In the 902-928 row, there is a "(v2)" with no explanation of what this means. |  | Yes | Change "(v2)" to be " (alternate)" | Accepted |  |  |  |  | Done

## 4v-D4-Rogue-Comment
Comment ID | Date | Comment # | Name | Affiliation | Category | Page | Subclause | Line | Comment | File | Must Be Satisfied | Proposed Change | Disposition Status | Disposition Detail | Other1 | Other2 | Other3 | Editor Status
r-1 |  | r-1 | Kunal Shah | Silver Spring Networks | Technical | 10 | 20.6.6 | 7 | There are new operating modes (#1, #3 and #5) defined in the draft with tighter channel spacing due to the regulatory limitations. For those defined operating modes, the transmit spectral mask will fall after the center of the adjacent channel. |  | No | The spectral mask offset frequencies need to updated for operating modes #1, #3 and #5 | Revised | Insert new paragraph in subcluase 20.6.6 after the first paragraph as follows: When Operating mode #1 with 100 kHz channel spacing or Operating mode #3 with 200 kHz channel spacing or Operating mode #5 with 400 kHz channel spacing is used as specified in Table 20-6 and Table 20-7, offset frequencies M1 and M2 and the integrated bandwidth (with respect to the M1 and M2 offset frequencies) are defined as follows: The integration bandwidth shall be equal to 5/8 x S, where S is the channel spacing, expressed in units of hertz. M1 = 9/16 × S × (1 + h) M2 = 9/8 × S × (1 + h) where h is the modulation index for 2-level modulation. The transmit spectral content at M1 and M2 for the Operating modes specified above shall be less than -20 dB and -35 dB, respectively. Otherwise for all other Operating modes specified in Table 20-6 and Table 20-7, the offset frequencies M1 and M2 and the integrated bandwidth shall be defined as follows: The proposal is shown on slide 7 of 15-17-0068-02. |  |  |  | Done

## 4v_D5-recirc1
Comment ID | Date | Comment # | Name | Affiliation | Category | Page | Subclause | Line | Comment | File | Must Be Satisfied | Proposed Change | Disposition Status | Disposition Detail | Other1 | Other2 | Other3
22046600023 | 03-Feb-2017 13:50:19 ET | r01-2 | Perry, Lisa |  | General |  |  |  | This draft meets all editorial requirements. |  | No |  | Accepted
22042600023 | 31-Jan-2017 18:52:27 ET | r01-1 | Powell, Clinton | Powell Wireless Consulting, LLC | Technical | 11 | 20.6.6 | 6 | Since the Transmit Spectral Mask defined in 802.15.4 2015 was found to be incorrect, please provide an example along with the proposed resolution that illustrates visually that the newly proposed mask does not pose a problem as well. |  | Yes | Add an example in the proposed comment resolution document showing how the new mask fixes the previous error and does not introduce another error. An example for the worst case modulation index and a reasonable Tx filter will suffice. | Revised | The example is shown in doc#802.15-17-0118-00-004v posted on mentor. No change is required.