## Slide 1
Project: IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Submission Title: [TG4s Opening Information for January 2017]
Date Submitted: [16 January 2017]
Source: [Shoichi Kitazawa / Hidetoshi Yokota] Company [Muroran IT / Landis&Gyr]
Address [Muroan Hokkaido, JAPAN / Tokyo JAPAN]
Voice:[+81-143-46-5345 / +81 3-5532-7455], FAX: [], E-Mail:[kitazawa@ieee.org / hidetoshi.yokota@landisgyr.com]
Re: []
Abstract: [Opening information for the TG4s January 2017.]
Purpose: [Opening information.]
Notice: This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Slide 2: TG4s Opening Information for January 2017
Shoichi Kitazawa
Hidetoshi Yokota

## Slide 3: IEEE Patent Policy
IEEE Patent Policy

## Slide 4: TG4s schedule for the week
 | Monday | Tuesday | Wednesday | Thursday
AM1 |  | Highland Ballroom V | Highland Ballroom V | 
AM2 | Highland Ballroom V |  |  | Highland Ballroom VI
PM1 |  |  |  | 
PM2 |  |  |  | 

## Slide 5: Agenda
TG4s meeting call to order
Call for essential patents and policies & procedures reminder
Agenda Setting
Approve SAT and BRC Teleconference meeting minutes
Comment resolution
Timeline
TG Motion for BRC and Teleconference
Plan for next meeting
Report on progress to WG

## Slide 6: Time planning
TG Kickoff November 2014
Editing1st Draft May 2015
Motion for Letter Ballot July 2016
Sponsor Ballot March 2017
Submission to RevCom November 2017
Timeline of TG4s (15-14-0559-r2)

## Slide 7: Timeline
Timeline of TG4s (15-14-0559-r2)
Year |  | 2014 |  |  |  |  |  | 2015 |  |  |  |  |  | 2016 |  |  |  |  |  | 2017 |  |  |  |  | 
Month |  | 1 | 3 | 5 | 7 | 9 | 11 | 1 | 3 | 5 | 7 | 9 | 11 | 1 | 3 | 5 | 7 | 9 | 11 | 1 | 3 | 5 | 7 | 9 | 11
SG | PAR & CSD development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
TG Work Items | Start TG |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Use Cases & TGD |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Editing Draft |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Letter Ballot |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | LB Comment Resolution |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Initial Sponsor Ballot |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | SB Comment Resolution |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Submission to RevCom |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 8: Contributions
TG4s November 2016 Meeting Minutes (15-16-854r0)
802.15.4s Letter Ballot Consolidated Comments (15-16-596-r10)
TG4s BRC Teleconference Minutes for January 2017(15-17-40-r0)