## Slide 1
Project: IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Submission Title: 15.7m Closing Report March 2017
Date Submitted: March 2017
Source: Rick Roberts Company Intel
Address
Voice:, FAX:, E-Mail: richard.d.roberts@intel.com
Re:
Abstract:
Purpose:
Notice: This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Slide 2
Background
TG7m conducted a task group letter ballot review of draft D1
Draft D1 was issued at the end of October.
The comment period closed prior to the January meeting.
There were 826 technical comments submitted and 251 editorial comments.
2/3th of the comments were resolved in January and it was planned to resolve the rest in March.
However, due to travel problems, no delegates from Kookmin or SNUST could attend the March meeting, so the committee decided to skip related comments and carry them over to draft D2.

## Slide 3
Status of OCC comments at the end of March Meeting
At the end of the January meeting we had completed draft D1 comment resolution through Clause 13 (PHY IV specifications) and had just started on Clause 14 (PHY V specification).
During the March meeting we completed the remaining resolvable comments and skipped all unresolvable comments in clauses 14 (PHY V) and 15 (PHY VI) associated with Kookmin and SNUST. These skipped comments will be carried over to draft D2 since the text in clauses 14 and 15 is substantially unchanged.
All other D1 comments that are unresolved or awaiting input are hence “rejected” and will have to be resubmitted against draft D2. This is due to extensive text re-organization.

## Slide 4
Status of LiFi comments/text at the end of the March Meeting
All LiFi draft D1 comments were skipped and all LiFi text remained unedited; that is, the text is as per draft D1.
The LiFi text will remain in draft D2 in its draft D1 form through the May meeting, after which it will be removed.
The LiFi text removal will be via comments submitted against draft D2.

## Slide 5
Plans for May meeting
April 1st : Publish draft D2 for review and comment.
Deadline for comments against draft D2 is May 1st, 2017.
Comments against D2 should include recommendations on which LiFi relevant text should be removed.
Comments against draft D2 will be resolved during the May meeting. The text is maturing so we expect fewer comments and hopefully we can get them all resolved during the May meeting.
The edits for generation of draft D3 will be done after the May meeting.

## Slide 6
Schedule and Timeline Review
Draft D3 will be published near the end of May (say May 31st ).
Committee has two choices to make at the end of May meeting:
  Go to WG letter ballot in June with draft D3 (current schedule baseline)
  Have another round of TG review resulting in a draft D4 that goes to WG letter ballot in August (2 month schedule slip)
Of great influence is the quality of the text and comment resolution related to draft D3; that is, does the committee feel draft D3 is of sufficient consensus quality.