## TG7r1
108th IEEE 802.15 WPAN MEETING
Daejeon Convention Center
Daejeon, Korea
Session Objectives:
– Request conditional approval for Letter Ballot
– Prepare D3
(– 94 technical comments carried over from March meeting (resolve these first)
– 361 new technical comments
– 35 editorial comments)
– Release D3 by June
– Letter Ballot 1 by June
Task Group 7m OWC, Mon. PM1, May 8, 2017
1.1 | MEETING CALLED TO ORDER | Yeong Min Jang | 1
1.2 | Welcome / patent policy | Yeong Min Jang | 5
1.3 | Meeting Objectives and Minutes Approval (17-200-r2) | Yeong Min Jang | 5
1.4 | May Agenda Approval(17-0271-r0) | Yeong Min Jang | 10
1.5 | D2 Combined Comments (17-259-r1) | Rick | 80
1.6 | Recess | Yeong Min Jang | 1
Task Group 7m OWC, Mon. PM2, May 8, 2017
2.1 | MEETING CALLED TO ORDER | Yeong Min Jang | 1
2.2 | D2 Combined Comments (17-259-r0) | Rick | 90
2.3 | ITU-R Issues | Nikola | 20
2.4
2.5 | Recess | Yeong Min Jang | 1
Task Group 7m OWC, Tue. PM1, May 9, 2017
3.1 | MEETING CALLED TO ORDER | Yeong Min Jang | 3
3.2 | D2 Combined Comments (17-259-r2)==comments carried over from March meeting (resolve these first) | Rick | 110
3.3
3.4
3.5 | Recess | Yeong Min Jang | 2
Task Group 7m OWC, Tue. PM2, May 9, 2017
4.1 | MEETING CALLED TO ORDER | Yeong Min Jang | 3
4.2 | D2 Combined Comments (17-259-r2) | Rick | 110
4.3
4.4
4.5 | Recess | Yeong Min Jang | 2
Task Group 7m OWC, Wed. AM1, May 10, 2017
5.1 | MEETING CALLED TO ORDER | Yeong Min Jang | 3
5.2 | D2 Combined Comments (17-259-r2) | Rick | 110
5.3
5.4
5.5 | Recess | Yeong Min Jang | 2
Task Group 7m OWC, Wed. PM1, May 10, 2017
6.1 | MEETING CALLED TO ORDER | Yeong Min Jang | 3
6.2 | D2 Combined Comments (17-259-r2) | Rick | 110
6.3
6.4
6.5 | Recess | Yeong Min Jang | 2
Task Group 7m OWC, Wed. PM2, May 10, 2017
7.1 | MEETING CALLED TO ORDER | Yeong Min Jang | 3
7.2 | D2 Combined Comments (17-259-r2) | Rick | 110
7.3
7.4
7.5 | Recess | Yeong Min Jang | 2
Task Group 7m OWC, Thurs. AM2, May 11, 2017
8.1 | MEETING CALLED TO ORDER | Yeong Min Jang | 3
8.2 | QR code issue (on 11am with Bob) |  | 20
8.3 | OCC dimming (Trang) |  | 20
8.4 | Vinary (Clause 15 part) |  | 60
8.5
8.6 | Recess | Yeong Min Jang | 2
Task Group 7m OWC, Thur. PM1, May 11, 2017
9.1 | MEETING CALLED TO ORDER | Yeong Min Jang | 3
9.2 | Vinary (Clause 15 part) |  | 110
9.3
9.4
9.5 | Recess | Yeong Min Jang | 2
Task Group 7m OWC, Thur. PM2, May 11, 2017
10.1 | MEETING CALLED TO ORDER | Yeong Min Jang | 3
10.2 | Vinary (Clause 15 part) |  | 60
10.3 | Plan for July meeting | Yeong Min Jang | 20
10.4 | Time line & schedule review and modification | Yeong Min Jang | 20
10.5 | Other businesses | Yeong Min Jang | 5
10.6 | Adjourn | Yeong Min Jang | 5