## Slide 1
Date: 2018-03-08
Author(s):
Suggested time lines for SG MG

## Slide 2
Suggested timeline for SPEC generation
March 2017 (Vancouver) - PAR and CSD for TG13 got approved, new contributions discussed | April 2017 Additional comments against 15.7m submission | May 2017 (Daejeon ) - Comments resolution against D1 of TG7r1 | June 2017 Generate D0 of TG13 Comment submission
July 2017 (Berlin) Commen resolution Decision on LC in 802.11  MAC Ad-hoc meeting in Berlin after Plenary | August 2017 Comment submission against D0 | September 2017 (Kona) Finalize comment resolution against D0 | October 2017 Generate D1 of TG13 Comment submission
November 2017 (Orlando) General discussion about PHY and MAC, Work on text | December 2017 - Comment submission against D1 until 1st January 2018 | January 2018 (Irvine) Comment resolution against D1 PM PHY proposals | February 2018 Generate D2 of TG13 Comment submission Initial evaluation of PM PHY

## Slide 3
Suggested timeline for SPEC generation
March 2018 (Rosemont) Resolution of first comments against D2 Discuss on PM PHY Brainstorm on MAC | April 2018 Submit further comments against D2 Finalize evaluation of PM PHY, Submit LB OFDM PHY text | May 2018 (Warsaw) Comment resolution against D2 Present LB PHY Discussion of MAC features, issue CfP | June 2018 Prepare HB OFDM PHY text proposals Submission of comments on MAC against D2 and text proposals
July 2018 Present and discuss HB OFDM PHY text Resolve first comments against D2 incl. MAC Discussion MAC text proposals | August 2018 Create D3 Comment submission against D3 Comment submission against PHY and MAC proposals | September 2018 Comment resolution against D3 Technical Freeze of TG13 Spec | October 2018 Create D4 Submit D4 to WG letter ballot Provide WG ballot comments
November 2018 Resolve WG LB comments | December 2018 Release D5 Submit to SB | January 2019 SB Comment Resolution Start submission to RevCom | February Get on the telco agenda

## Slide 4
Suggested timeline for SPEC generation
March 2019 standard is published Have party |  |  | 

## Slide 5
Thank you！