## Slide 1
Date: 2018-03-08
Author(s):
Suggested time lines for SG MG

## Slide 2
Suggested timeline for SPEC generation
March 2017 (Vancouver) - PAR and CSD for TG13 got approved, new contributions discussed | April 2017 Additional comments against 15.7m submission | May 2017 (Daejeon ) - Comments resolution against D1 of TG7r1 | June 2017 Generate D0 of TG13 Comment submission
July 2017 (Berlin) Commen resolution Decision on LC in 802.11  MAC Ad-hoc meeting in Berlin after Plenary | August 2017 Comment submission against D0 | September 2017 (Kona) Finalize comment resolution against D0 | October 2017 Generate D1 of TG13 Comment submission
November 2017 (Orlando) General discussion about PHY and MAC, Work on text | December 2017 - Comment submission against D1 until 1st January 2018 | January 2018 (Irvine) Comment resolution against D1 PM PHY proposals | February 2018 Generate D2 of TG13 Comment submission Initial evaluation of PM PHY

## Slide 3
Suggested timeline for SPEC generation
March 2018 (Rosemont) Resolution of first comments against D2 Discuss on PM PHY Brainstorm on MAC | April 2018 Submit further comments against D2 Finalize evaluation of PM PHY, Submit LB OFDM PHY text | May 2018 (Warsaw) Comment resolution against D2 Present LB PHY Discussion of MAC features, issue CfP | June 2018 Prepare HB OFDM PHY text proposals Submission of comments against D2 and MAC proposals
July 2018 Present and discuss HB OFDM PHY text Resolve all comments against D2 incl. MAC Discussion MAC text proposals | August 2018 Create D3 Comment submission against D3 Comments against HB PHY | September 2018 Comment resolution against D3 Work on TG13 MAC | October 2018 Create D3.1 Provide technical inputs
November 2018 Resolve comments Hear technical contributions to MAC | December 2018 Release D3 | January 2019 Provide MAC text inputs Resolve comments | February Create D4.0 Collect comments

## Slide 4
Suggested timeline for SPEC generation
March 2019 Resolve comments Include missing text | April 2019 Work on additional new text | May 2019 Resolve comments Include new text in D5.0 | June 2019 - Work on additional new text
July 2019 Include new text in D6.0 Create TBD list and start to work on it | August 2019 Send D6.0 to informal review by WG technical Editor Work on TBD list | September Include new text from TBD Resolve Technical Editor comments D7.0 to WGLB | October Create comments in WGLB Resolve open issues
November WGLB comments resolution Start recirc | December - Review recirc | January 2020 Go to SB | 

## Slide 5
Thank you！