## Slide 1
Project: IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Submission Title: 15.7m OWC TG Closing Report Nov. 2017
Date Submitted: Nov. 8, 2017
Source: Yeong Min Jang Company: Kookmin University
Address
Voice:, FAX:, E-Mail: yjang@kookmin.ac.kr
Re:
Abstract:
Purpose:
Notice: This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.
IEEE 15-17-0634-00-007a

## Slide 2
Background
TG7m conducted a task group letter ballot review of draft D5
Draft D1 was issued at the end of October, 2016.
There were 826 technical comments and 251 editorial comments.
Draft D2 was issued at end of March, 2017.
For D2, there were 362 technical comments and 36 editorial comments.
Draft D3 was issued at the middle of June, 2017.
For D3, there were 407 technical comments and 41 editorial comments. There are 2 postponed technical comments.
Draft D4 was issued at the middle of August, 2017.
For D4, there were 285 technical comments and 26 editorial comments.
Draft D5 was issued at the middle of Oct., 2017.
For D5, there were 150 technical and editorial comments.
IEEE 15-17-0634-00-007a

## Slide 3
Status of comments at the end of Nov. Meeting
Resolved comments resolution for D5 document
IEEE 15-17-0634-00-007a

## Slide 4
Plans for January meeting
D6 comment resolution
Release D6 (Nov. 2017)
Letter Ballot 1 for D6 (Nov. 2017)
LB1 comment resolution (Jan. 2018)
Schedule
- Nov 17 All the supplemental text for the D5 comment
resolution will be uploaded to the Mentor
Nov. 24 Release D6
Teleconference: Discuss via e-mail reflector
Requesting 10 sessions
IEEE 15-17-0634-00-007a

## Slide 5
TG Motion #1:
Move that 802.15 WG start a WG Letter Ballot requesting approval of CA document 15-17-627r0 and document P802-15-7m_D06 (as edited in accordance with the instructions in document 15-17-0597-r3-007a) and to forward document P802-15-7m_D06, as edited in accordance with the instructions in document 15-17-0597-r3-007a, and CA document 15-17-627r0 to Sponsor Ballot pending the completion and inclusion of the edits in the draft.
Moved By: Soo-young Chang
Seconded By: Hideki
Y/A/N = 7 / 0 /0
IEEE 15-17-0634-00-007a

## Slide 6
TG Motion #2:
Motion for TG Approval to Form a TG7m BRC.
TG7m requests that 802.15 WG approve the formation of a Ballot Resolution Committee (BRC) for the WG balloting of the P802.15.7m-D01 with the following membership: Yeong Min Jang, Rick Roberts, Hideki Aoyama, Soo-Young Chang, Jaesang Cha, and Van Trang Nguyen. The 802.15 TG7m BRC is authorized to approve comment resolutions and to approve the start of recirculation ballots of the revised draft on behalf of the 802.15 WG. Comment resolution on recirculation ballots between sessions will be conducted via reflector email and via teleconferences announced to the reflector as per the LMSC 802 WG P&P.
Moved by: Hideki
Seconded by: Soo-Young Chang
Y/N/A: 7 / 0 /0
IEEE 15-17-0634-00-007a

## Slide 7
WG motion #1:
Motion for WG Approval to Start Letter Ballot.
Move that 802.15 WG start a WG Letter Ballot requesting approval to forward document P802-15-7m-D06, and CA document 15-17-627r0 to Sponsor Ballot
Moved By:
Seconded By:
IEEE 15-17-0634-00-007a

## Slide 8
WG motion #2:
Motion for WG Approval to Form a TG4s BRC.
Move that 802.15 WG approve the formation of a Ballot Resolution Committee (BRC) for the WG balloting of the P802.15.7m-D06 with the following membership: Yeong Min Jang, Rick Roberts, Hideki Aoyama, Soo-Young Chang, Jaesang Cha, and Van Trang Nguyen. The 802.15.7m BRC is authorized to approve comment resolutions and to approve the start of recirculation ballots of the revised draft on behalf of the 802.15 WG. Comment resolution on recirculation ballots between sessions will be conducted via reflector email and via teleconferences announced to the reflector as per the LMSC 802 WG P&P
Moved By:
Seconded By:
IEEE 15-17-0634-00-007a

## Slide 9
2017 |  |  | 
Q1 | January | February | March
 | Continue comment resolution against D1 Prepare draft D2 | Comment resolution to delete against unnecessary parts of D1 | Finish comment resolution against D1 Prepare draft D2
Q2 | April | May | June
 | Release Draft D2 | D2 comment resolution Prepare D3 | Release D3
Q3 | July | August | September
 | D3 comment resolution | Release D4 | D4 comment resolution
Q4 | October | November | December
 | Release D5 | D5 comment resolution Request (conditional) approval for Letter Ballot | Release D6 Letter Ballot 1 for D6
Submission
Updated Milestone and Schedule
IEEE 15-17-0634-00-007a

## Slide 10
Updated Milestone and Schedule
2018 |  |  | 
Q1 | January | February | March
 | LB1 comment resolution | Release D7 | Request for Sponsor Ballot 1 for D7
Q2 | April | May | June
 | SB1 | SB1 comment resolution | Release D8 SB2 for D8 ?
Q3 | July | August | September
 | SB2 comment resolution | Release D9 | SA review
Q4 | October | November | December
 |  | Publish the standard IEEE802.15.7-2018 Have a party! | 
IEEE 15-17-0634-00-007a