## Slide 1: IEEE 802.15 TG13 Multi-Gbit/s Optical Wireless Communication January 2019 Closing Plenary Slides
Date: 2019-01-18
Author:
January 2019

## Slide 2
This presentation contains the IEEE 802.15 TG13 Multi- Gbit/s Optical Wireless Communication Closing Plenary Slides for the January 2019 session in St. Louis.
Abstract
January 2019

## Slide 3
TG13 schedule for St. Louis
 | MON | TUE | WED | THU
AM1 |  | TG13 #3 |  | 
AM2 |  |  |  | TG13 #6
PM1 | TG13 #1 |  | TG13 #5 | TG13 #7
PM2 | TG13 #2 | TG13 #4 |  | TG13 #8
PM3 |  |  |  | 
January 2019

## Slide 4
8 time slots this week
New contributions have been added to the draft
  HB PHY : doc. 15-18/0273r4
  Beacon-enabled MAC mode: doc. 15-18/0616r3
Resolved all comments against D3.1 in 15-19/0017r2
Reviewed the current draft
  Remove obsolete text
  Created new comments in 15-19/0052r1
Requested 6 slots plus 1 joint slot for security in March
WGLB will be started in March
TG13 activities in St. Louis
January 2019

## Slide 5
TG13 Plans until March
Prepare D4 and provide comments
Create missing text in the draft
Create list of frame subtypes
TG13 Telcos are scheduled on
Feb. 1 8:00-9:00 EST Review new text
Feb. 15 8:00-9:00 EST Review new text
March 7 8:00-9:00 EST Prepare March meeting
January 2019

## Slide 6
TG13 Plans for March Plenary
6 + 1 additional session requested
Resolve comments from D4.0
Revise draft accordingly
Start WGLB
January 2019

## Slide 7
Updated timeline for TG13
February 2019 Create D4.0 Collect comments | March 2019 Resolve comments Include missing text Start WGLB | April 2019 Receive comments | May 2019 Resolve WGLB comments Start recirc, form BRC
June 2019 Resolve recirc comments | July 2019 Submit to SB |  |