## Slide 1
Project: IEEE P802.15 Working Group for Wireless Specialty Networks (WSNs)
Submission Title: [IEEE 802.15.4y SECN Closing Report]
Date Submitted: [14 March 2019]
Source: [Don Sturek] Company [Itron]
Address [San Jose, CA]
Voice:[], E-Mail:[don.sturek@itron.com]
Re: [IEEE 802.15.4y SECN closing report for March 2019 plenary session.]
Abstract: [IEEE 802.15.4y SECN closing report for March 2019 plenary session]
Purpose: [IEEE 802.15.4y SECN closing report for March 2019 plenary session]
Notice: This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Slide 2: IEEE 802.15.4y SECN Closing report
March 14, 2018
Don Sturek
IEEE 802.15.4y SECN Chair

## Slide 3
Work Plan
Review contribution for Annex B coverage of AES-256-CCM
  15-19-0081
Review 802.15.9a PAR/CSD: 15-19-0082, 15-19-0086
Review IEEE 802.15.4, Section 9 edits needed for 4y
Update timeline
Notes: Jul 12, 2010
Page 3

## Slide 4
Work Plan for 4y
Update key descriptor: Tero (in process)
Update 15.4-2015 Section 9 Security Text (see 15-18-0324-01) for technical comments (Tero)
Create “Annex B” for AES-256-CCM: Don (draft created, to be modified)
Create “Annex C” for AES-256-CCM: Tero (draft created)
Address ANA process for adding in cipher suites (use AES-256-CCM as first example): Don (to be addressed in July)
Notes: Jul 12, 2010
Page 4

## Slide 5
Progress in Vancouver
Timeline
    Key Descriptor and Section 9 changes– May 2019
    Annex B for AES-256 – May 2019
    Annex C for AES-256 – May 2019
    Initial WG Letter Ballot –July 2019
    Recirculation Letter Ballot – September 2019, conditional approval from EC for SA ballot
    SA Ballot – January 2020
Notes: Jul 12, 2010
Page 5

## Slide 6
Progress in Vancouver
PAR/CSD for IEEE 802.15.9 update
    Completed a draft of PAR/CSD (15-19-0082-00 and 15-19-0086-00)
    Tero has volunteered to chair
Notes: Jul 12, 2010
Page 6

## Slide 7
Agenda for May
Review the Section 9, Annex B and Annex C changes
Create draft in private area, perform WG internal review closing before the July meeting
Notes: Jul 12, 2010
Page 7