## Slide 1: IEEE 802.15 TG13 Multi-Gbit/s Optical Wireless Communication May 2019 Closing Report
Date: 2019-05-16
Author:
May 2019

## Slide 2
This presentation contains the IEEE 802.15 TG13 Multi- Gbit/s Optical Wireless Communication closing report for the May 2019 session in Atlanta.
Abstract
May 2019

## Slide 3
TG13 schedule for Atlanta
 | MON | TUE | WED | THU
AM1 | WG opening | TG13 #2 |  | 
AM2 | TGbb#1 |  | WG midweek | TG13#5
PM1 | TG13 #1 | TG13 #3 | TG13#4 | TG13#6
PM2 | TGbb#2 | TGbb#3 | TGbb#4 | 
PM3 |  |  |  | WG closing
May 2019

## Slide 4
6 sessions in Atlanta
Review and discuss status of clauses 4-10
  4: MAC text t.b.d. after clauses 5-10 are complete
  5: new text is stable, details under discussion
  6: new text is stable, details under discussion
  7: create new text, take requ. functionality in D4.1 into account
  8: postponed
  9: to be revised
  10: deleted
Discuss text on MIMO and relaying in the draft
Resolve comments against D4.1
TG13 activities this week
May 2019

## Slide 5: Plan for finalization of TG13 Spec
June telcos - Finalize detailed discussion on clauses 5-7 - Postpone discussion on clause 8 - Draft text for clause 4
July Plenary Review draft again and submit for WGLB
September Interim Resolve comments from WGLB and submit for recirculation
Telcos October Resolve comments from recirc
November Plenary Submit draft to SB
May 2019

## Slide 6
TG13 Plans until July
Finalize detailed discussion on clauses 5-7
Postpone discussion on clause 8
Draft text for clause 4
May 2019

## Slide 7
TG13 Motion #48
TG13 Telcos are scheduled on
  May 21 10:00-11:00 EST on TG13 MAC
  June 4 10:00-11:00 EST on TG13 MAC
  June 25 10:00-11:00 EST on TG13 MAC
  July 2 10:00-11:00 EST on TG13 MAC
Moved by Nikola
Seconded by Tuncer
Motion passed unanimously.
May 2019

## Slide 8
TG13 Plans for July meeting
May 2019
6 sessions requested
Finalize text on Clause 4-7
Discussion on Clause 8
Create draft 6.0 and submit to WGLB

## Slide 9
Suggested timeline for SPEC generation
March 2019 Resolve comments Include missing text Create D4.1 | April 2019 Receive comments | May 2019 Work on MAC Resolve comments Create D5.0 | June 2019 Create missing text and comments
July 2019 Finalize text and complete the draft Submit to WGLB | August - Receive WGLB comments | September Resolve WGLB comments Start receirc | October - Start recirc
November - Go to SB |  |  |