## IEEE_Cover
February 2019 |  | P802.15.13-D1-Comment-Entry-Form.xlsx
IEEE P802.15
Wireless Specialty Networks
Project | IEEE P802.15 Task Group 13 Multi-Gigabit/s Optical Wireless Communications
Title | LB168 - combined comments against d2
Date Submitted | April 06, 2020
Source | Kai Lennert Bober | email: kai.lennert.bober@hhi.fraunhofer.de
Re: | 15-20-0096-04-0013 | Revision 4
Abstract | 802.15.13 D2 Comments
Purpose | This document contains the collected comments on D2 (letter ballot 168)
Notice | This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Comments
CID | Name | Affiliation | Email | Phone # | Page | Sub-clause | Line # | Comment | Proposed Change | E/T | Must Be Satisfied? (enter Yes or No) | Resolution: | TE Status | Notes on comment | Action required by whom
704 | Volker Jungnickel |  |  |  | 1 | title | 2-4 | change title | 802.15.13-2020 – Draft Standard for Local and Metropolitan Area Networks – Part 15.13: High Data Rate Optical Wireless Networks | T | N | revise |  | Once the PAR is successfully changed, update title as follows: P802.15.13 – Draft Standard for Local and Metropolitan Area Networks – Part 15.13: High Data Rate Optical Wireless Networks
718 | Kai Lennert Bober |  |  |  | 1 | 1 | 1 | Check wether all figures, tables and pages are numbered consecutively for MEC. | as proposed | E | No
719 | Kai Lennert Bober |  |  |  | 1 | 1 | 1 | Check wether figures are legible for MEC. Avoid color. | as proposed | E | No
720 | Kai Lennert Bober |  |  |  | 1 | 1 | 1 | Check wether normative references from clause 2 are used and wether all used normative references are in clause 2 for MEC. | as proposed | E | No
721 | Kai Lennert Bober |  |  |  | 1 | 1 | 1 | Check wether all figures, tables, equations and annexes are called out in the text. | as proposed | E | No
722 | Kai Lennert Bober |  |  |  | 1 | 1 | 1 | Check verb usage (shall, should, may) for MEC. Are the verbs appropriately used? | as proposed | E | No
723 | Kai Lennert Bober |  |  |  | 1 | 1 | 1 | Format variables in italics, constants in roman for MEC. Add variable list after all equations for MEC. | as proposed | E | No
576 | Kai Lennert Bober | Fraunhofer HHI |  |  | 2 | 3 | 1 | The clause title is not approproate anymore, since no definitions are given | Change clause title to "Acronyms, and abbreviations" | E | NO | revise |  | Change clause title to "Acronyms and abbreviations"
705 | Volker Jungnickel |  |  |  | 2 | abstract | 3 | add further applications also mentioned in the introduction | i...ndustrial wireless, fixed wireless access, home and office scenarios | T | N | revise |  | Change sentence in PIIL1-3 as follows: This standard defines the protocol and compatible network equipment for optical wireless communications and its operation as an optical wireless personal area network (OWPAN) supporting data rates of multiple Gbit/s for wireless specialty applications.
577 | Sang-Kyu Lim | ETRI |  |  | 4 | 3.1 |  | CAPP | Add "CAPP" to 3.1. | E | No | revise |  | -Add a new acronym "CAPP" - "Contention access polling period" to subclause 3.1 -Add a new acronym "CFPP" - "Contention-free polling period" to subclause 3.1 -Change sentences P29L21-23 as follows: Following the control frame, the contention access polling period (CAPP) starts. During the CAPP, devices compete on the uplink channel sending Poll Request frames to the coordinator to enable the coordinator to poll the device in the following contention-fee polling period (CFPP).
578 | Sang-Kyu Lim | ETRI |  |  | 4 | 3.1 | 10 | CFP = contention free period | Change "contention free period" to "contention-free period" for consistency. | E | No | accept
579 | Sang-Kyu Lim | ETRI |  |  | 4 | 3.1 |  | CFPP | Add "CFPP" to 3.1. | E | No | accept |  | resolved by resolution of CID 577
580 | Sang-Kyu Lim | ETRI |  |  | 5 | 3.1 | 15 | LSFR = Linear feedback shift register | Change "LSFR" to "LFSR". | E | No | accept
581 | Sang-Kyu Lim | ETRI |  |  | 6 | 3.1 |  | TAIFS = turn-around interframe space | Add "TAIFS" to 3.1. | E | No | accept
582 | Kai Lennert Bober | Fraunhofer HHI |  |  | 8 | 4.3.2 | 13 | The term / acronym OFE hinders readability. Furthermore, there is confusion about the use in the compound "multi-OFE". Several other places confused some commentors: -"beacon frame shall be transmitted over all OFEs simultaneously" was not clear to Ben | Find a better term | E | NO | reject |  | use the acronym "OFE" as is has been done until now because it is a specific term for optical communications. The compound term "multi-OFE" is replaced in resolution of CID 627
583 | Kai Lennert Bober | Fraunhofer HHI |  |  | 13 | 4.6.2 | 35 | There is confusion about the term PSDU. In 4.6.2 it says that the PSDU is preficed with the header to yield the PPDU. Should the field in the PPDU be named "PSDU" or "Payload" | Rename PPDU field to "Payload" everywhere. | E | NO | revise |  | Rename "PSDU" field to "Payload" in all PPDUs. Rename "Optional Fields" in HB-PHY to "MIMO PS"
584 | Kai Lennert Bober | Fraunhofer HHI |  |  | 13 | 4.6.2 | 35 | The PHY frame structure is specific to each PHY. The whole point of having interfaces for each PHY is that PHYs can be independent from each other. Thus, the PPDU format does not have to be the same for each PHY. Having a common PPDU format limits the possibilities of the PHYs. | Change paragraph starting in P13L35 to something more generic such as: Furthermore, the PSDU is supplemented with various fields needed by each respecfice PHY such as a preamble or a PHY header. | T | NO | revise |  | Change paragraph starting in P13L35 to something more generic such as: Furthermore, the PSDU is supplemented with various fields needed by each respective PHY such as a preamble or a PHY header.
585 | Sang-Kyu Lim | ETRI |  |  | 14 | 4.6.5 | 25 | According to Table 57, the gross data rates of HB-PHY are from 23 Mb/s to 2192Mb/s, and according to 4.6.1, the data rates of HB-PHY are from 10Mb/s up to multiple Gb/s. | The data rates for HB-PHY in this sentence need to be synchronized with those of Table 57 and 4.6.1. | T | No | revise |  | Change sentence in P13L26 as follows: It allows data rates from 23 Mb/s up to 2.192 Gb/s. Change sentence in P14L25 as follows: The HB-PHY is intended for low latency and very high data rates, between 23 Mb/s and 2.192 Gb/s. Change sentence in P13L22 as follows: It allows data rates from 9.6 Mb/s to 726.6 Mb/s. Change sentence in P14L4 as follows: The PM-PHY is intended for moderate data rates between 9.6 Mb/s and 726.6 Mb/s, low power and low latency.
586 | Kai Lennert Bober | Fraunhofer HHI |  |  | 14 | 4.6.3 | 6 | The term OCR is unnecessarily confusing. | Replace optical clock rate (OCR) and all orrurrences in the document with a simple term. E.g. "sample rate", "baud rate", "bandwidth" where appropriate. | T | NO | revise |  | Replace optical clock rate (OCR) and all orrurrences in the document with the term "clock rate". Do not use an acronym.
587 | Kai Lennert Bober | Fraunhofer HHI |  |  | 14 | 4.6.3 | 14 | PHY support for relaying is not specified | Remove relaying from clause 4 | T | NO | postpone |  |  | Tuncer
588 | Kai Lennert Bober | Fraunhofer HHI |  |  | 14 | 4.6.4 | 21 | It is nowhere defined, what reverse polarity OFDM is. | Remove the references to reverse polarity in multiple locations. | T | NO | revise |  | Delete sentence in P101L20-22 Change sentence in P14L20-21 "Furthermore, the enhanced unipolar OFDM (eU-OFDM) and reverse polarity optical OFDM waveforms are supported." to "Furthermore, enhanced unipolar OFDM (eU-OFDM) is supported."
706 | Volker Jungnickel |  |  |  | 14 |  | 1-4 | change title | 802.15.13-2020 – Draft Standard for Local and Metropolitan Area Networks – Part 15.13: High Data Rate Optical Wireless Networks | T | N | revise |  | Once the PAR is successfully changed, update title as follows: P802.15.13 – Draft Standard for Local and Metropolitan Area Networks – Part 15.13: High Data Rate Optical Wireless Networks
589 | Kai Lennert Bober | Fraunhofer HHI |  |  | 15 | 4.7.3 | 31 | This subclause is not accurate anymore. The use of asymmetric clock rate is only possible in the PM-PHY. Furthermore there is a statement about mandatory clock rates for coordinators which is not normative. This should be removed. | Change the text as follows: The standard supports multiple OCRs in order to accommodate a wide variety of optical sources and receivers. | E | NO | accept
707 | Volker Jungnickel |  |  |  | 15 | 1.1. | 5 | scope should be wider than that | change "at distances in the range of 200 m unrestricted line-of-sight" into "at distances of few meters for mobile indoor applications and up to 200 meters for fixed outdoor scenarios" | T | N | postpone
708 | Volker Jungnickel |  |  |  | 15 | 1.2 | 12-13 | same as previous | change "at distances in the range of 200 m unrestricted line-of-sight" into "at distances of few meters for mobile indoor applications and up to 200 meters for fixed outdoor scenarios" | T | N | postpone
709 | Volker Jungnickel |  |  |  | 15 | 1.2 | 14 | modify | change "...which are non…" into "...which are very robust, have low latency and non ... | T | N | postpone
710 | Volker Jungnickel |  |  |  | 21 | 4.3.1 | 2 | add | change to "...any other 802.15.13 networks …" | T | N | postpone
711 | Volker Jungnickel |  |  |  | 21 | 4.3.2 | 23 | move | move text "The distributed MIMO star topology is illustrated in Figure 2." after the first sentence on line 12. | E | N | postpone
590 | Kai Lennert Bober | Fraunhofer HHI |  |  | 22 | 5.3.4.1 | 28 | Extra space | remove extra space after "procedure" | E | NO | accept
712 | Volker Jungnickel |  |  |  | 22 | 4.3.4. | 9-11 | Figure 4 is not referred to in the text | Add "The coordinated star topology is illustrated in Figure 4." after all text in line 11. | E | N | revise |  | Add "The coordinated star topology is illustrated in Figure 4." after line 10.
591 | Kai Lennert Bober | Fraunhofer HHI |  |  | 23 | 5.3.4.2 | 36 | Separate the channel access in the CAP from the logical association procedure | Reduce 5.3.4 to include the actual channel access only with only one decision diagram. Then move all logical association procedure into 5.5 and describe how the retry, backoff and other variables map from the logical process to the specific channel access mechanism in the CAP. | T | NO | postpone |  |  | Lennert
713 | Volker Jungnickel |  |  |  | 23 | 4.3.4. | 6-10 | This text is related to coexistence and should be merged with 4.4.4. | Discuss the coexistence concept again and adapt the text, accordingly. | T | N | revise |  | Change title of subclause 4.3.4 to Coordinated topology Change "coordinated star topology" in P9L11 to coordinated topology Change caption of figure 4 to Coordinated topology Remove P10L6-10
714 | Volker Jungnickel |  |  |  | 23 | 4.4. | 11 | Coexistence should be improved. One should introduce a simple coexitence protocol (SCP) which is operated at very low speed out-of-band and followed by all OWC standards. | Revise coexistence. | T | N | postpone
715 | Volker Jungnickel |  |  |  | 24 | 4.5.1. | 27 | MLME is not explained at the right place | change into "...invokes MAC layer management entity (MLME) functionality through the MLME service access point (MLME-SAP)." | E | N | accept
592 | Kai Lennert Bober | Fraunhofer HHI |  |  | 25 | 5.3.4.3 | 1 | Separate the channel access in the CAP from the logical resource / GTS request procedure | Reduce 5.3.4 to include the actual channel access only with only one decision diagram. Then move all resource request procedure into 5.3.6 and describe how the parameters for the numbers of retries and the backoff map from the resource request to the CAP medium access. Furthermore, rename "resource request" into "GTS request" | T | NO | postpone |  |  | Lennert
593 | Kai Lennert Bober | Fraunhofer HHI |  |  | 32 | 5.4.3 | 4 | Do not use the term "packet" but use "frame" instead or, if appropriate, the following more specific terms: MSDU MPDU / PSDU PPDU | Replace all occurrences of "packet" with "frame" in clause 5.4 and 6.2.3 with the following exceptions: Replace "PHY packet" in P34L4 with "PPDU" | T | NO | postpone |  | This needs text update | Nikola
594 | Sang-Kyu Lim | ETRI |  |  | 35 | 5.5.1 | 19 | macEdScanThreshold | If "macEdScanThreshold" is a MAC PIB attribute, then add "macEdScanThreshold" to Table 40. | T | No | revise |  | Change sentence in 35L18 as follows: If a device detects at least one non-decodable signal during the scan time, the device shall add an entry with OWPAN ID = ff-ff-ff-ff-ff-ff with the received power level of the strongest received signal to the scan result list.
595 | Sang-Kyu Lim | ETRI |  |  | 39 | 5.7.2 | 31 | phyMaxPsduSize | "aPhyMaxPsduSize" is specified in Table 45 and Table 58 for PM-PHY and HB-PHY, respectively. However, if "phyMaxPsduSize" is a PHY PIB attribute, then it should be shown in Table 43. | T | No | postpone |  |  | Stephan Berner | Agree, See also CID 654. Input from Nikola needed on what the maximum PSDU size is
596 | Sang-Kyu Lim | ETRI |  |  | 43 | 5.9.1 | 22 | capMcsRequest | If "capMcsRequest" is a MAC capability, then add "capMcsRequest" to Table 42. | T | No | accept
597 | Sang-Kyu Lim | ETRI |  |  | 44 | 5.9.3.1 | 3 | capMcsRequest | If "capMcsRequest" is a MAC capability, then add "capMcsRequest" to Table 42. | T | No | accept
598 | Sang-Kyu Lim | ETRI |  |  | 44 | 5.9.3.2 | 13 | capHbPhy | If "capHbPhy" is a MAC capability, then add "capHbPhy" to Table 42. | T | No | revise |  | Change sentence in P44L13 as follows: A receiving device may measure the effective channel at receptions of unicast frames.
599 | Kai Lennert Bober | Fraunhofer HHI |  |  | 46 | 5.9.5 | 2 | Figure 27 and Figure 28 are not vector graphics | Provide the vector graphic source in visio format to the TE. | E | NO | postpone |  | Please provide visio files | Tuncer
600 | Kai Lennert Bober | Fraunhofer HHI |  |  | 47 | 6.1.1 | 3 | Maybe the notational conventions from 802.15.4 can be used. Check wether copying the notational conventions from IEEE 802.15.4-2015 are appropriate and if decided, copy them into draft and remove clause 6.1. Ensure that the actual text update is consistent with the rest of the draft and update. | as proposed | T | NO | reject
601 | Kai Lennert Bober | Fraunhofer HHI |  |  | 47 | 6.1.2 | 19 | Paragraphs about reserved values are redundant. | Change the two pagagraphs in P47L19-24 as follows: Fields that are “reserved” do not carry meaningful information in the current version of the standard. This may be changed in later versions. Values of fields that are “reserved” shall not be used in outgoing frames. Fields that are reserved shall be set to all zeros for transmission and shall be ignored on reception. In addition, certain values for fields are reserved. Reserved values shall not be used in outgoing frames. If a MAC frame is received with one or more fields carrying a reserved value, that MAC frame shall be dropped. | T | NO | accept
602 | Kai Lennert Bober | Fraunhofer HHI |  |  | 48 | 6.1.3 | 6 | Unify the line widths in all figures showing frames, elements or fields in clause 6. | as proposed | E | NO | accept
603 | Sang-Kyu Lim | ETRI |  |  | 49 | 6.2.1 |  | "0/2" for Poll Ack, "2/6" for Receiver Address, "2/6" for Transmitter Address, "0/2/6" for Auxiliary Address, and "0/2" for Sequence Control in Figure 32. What do these numbers say ? | Please specify again the field size for each field in Figure 32 in order that readers get to understand them better. | T | No | Postpone |  | Please create text describing the representation on the basis of 802.15.4-2015 | Lennert
604 | Kai Lennert Bober | Fraunhofer HHI |  |  | 49 | 6.2.1 | 16 | The use of 6-octet MAC addresses and 2-octet short addresses is not well described. In addition, another format would be greatly beneficial for implementation complexity: Having the original MSDU destination and source MAC addresses as part of the MSDU. If the EThernet header is kept, all frame processing boils down to adding headers and tailers. Thus, no data must be moved in memory. | Clarify frame format inclusing use of short addresses (for privacy also), the OWPAN ID and MSDU format. | T | NO | Postpone |  | Please provide text update | Lennert
605 | Sang-Kyu Lim | ETRI |  |  | 53 | 6.3 |  | "0/2" for Poll Ack, "2/6" for Receiver Address, "2/6" for Transmitter Address, and "0/6" for Auxiliary Address in Figure 36. What do these numbers say ? | Please specify again the field size for each field in Figure 36 in order that readers get to understand them better. | T | No | postpone |  | See CID 603
606 | Sang-Kyu Lim | ETRI |  |  | 53 | 6.4.1 |  | "0/2" for Poll Ack, "2/6" for Receiver Address, and "2/6" for Transmitter Address in Figure 37. What do these numbers say ? | Please specify again the field size for each field in Figure 37 in order that readers get to understand them better. | T | No | postpone |  | See CID 603
607 | Sang-Kyu Lim | ETRI |  |  | 54 | 6.4.2 |  | "0/2" for Poll Ack, "2/6" for Receiver Address, and "2/6" for Transmitter Address in Figure 38. What do these numbers say ? | Please specify again the field size for each field in Figure 38 in order that readers get to understand them better. | T | No | postpone |  | See CID 603
608 | Sang-Kyu Lim | ETRI |  |  | 55 | 6.5 |  | "0/2" for Poll Ack, "2/6" for Receiver Address, and "2/6" for Transmitter Address in Figure 39. What do these numbers say ? | Please specify again the field size for each field in Figure 39 in order that readers get to understand them better. | T | No | postpone |  | See CID 603
609 | Kai Lennert Bober | Fraunhofer HHI |  |  | 57 | 6.6.3 | 6 | Table contains status 3 - Require further authentication, which is not applicable anymore after removing security. | Remove status 3 | T | NO | accept
610 | Sang-Kyu Lim | ETRI |  |  | 58 | 6.6.5 |  | Figure 43 | Change "1 octets" for CAP Slot Width in Figure 43 to "1 octet". | E | No | accept
611 | Sang-Kyu Lim | ETRI |  |  | 58 | 6.6.5 |  | Figure 43 | Change "1 octets" for CAP Slots in Figure 43 to "1 octet". | E | No | accept
612 | Sang-Kyu Lim | ETRI |  |  | 58 | 6.6.5 | 11 | Incomplete sentence | Delete "This". Or complete the sentence. | T | No | accept
613 | Sang-Kyu Lim | ETRI |  |  | 60 | 6.6.9 |  | Figure 47 | Change "octet 5-6" for Slot Number in Figure 47 to "octets 5-6". | E | No | accept
614 | Sang-Kyu Lim | ETRI |  |  | 60 | 6.6.9 | 16 | Fractional Noise Floor is not shown in Figure 47. | Delete "Fractional Noise Floor" and its description in the text body. | T | No | revise |  | Ensure that the comment resolution for CID 477 from doc 20-0078-00-0013 is implemented correctly.
615 | Sang-Kyu Lim | ETRI |  |  | 60 | 6.6.9 |  | Noise Floor is shown in Figure 47. | Add "Noise Floor" and its description to the text body. | T | No | revise |  | Resolved by CID 614
616 | Sang-Kyu Lim | ETRI |  |  | 62 | 6.6.13 |  | Figure 53 | Change "4 Bits" for Bitmap Width in Figure 53 to "4 bits" for consistency. | E | No | accept
617 | Sang-Kyu Lim | ETRI |  |  | 62 | 6.6.13 |  | Figure 53 | Change "12 Bits" for First Sequence Number in Figure 53 to "4 bits" for consistency. | E | No | accept
618 | Kai Lennert Bober | Fraunhofer HHI |  |  | 65 | 6.6.18 | 6 | The "Foreign Device Address" field has 6 octets and not 2. | Correct the sentence "If the address is unknown, the field shall be set to the broadcast short address." into: "If the address is unknown, the field shall be set to the broadcast address." | T | NO | accept
619 | Sang-Kyu Lim | ETRI |  |  | 66 | 6.6.19 |  | Table 10 | Add MCS element for LB-PHY to Table 10. | T | No | postpone |  | Stephan provides text
620 | Kai Lennert Bober | Fraunhofer HHI |  |  | 66 | 6.6.19 | 14 | There is no LB-PHY Rates Element. There should be a single element conveying the information about the set of supported MCSs for the LB-PHY. Currently there are 8 "Rates" for the LB-PHY according to table 53. These can be signalled through an 1-octet bitmap. Also, the term "rates" in the LB-PHY should be reworked to "MCS". | Add an LB-PHY MCS element as proposed with an own subclause and place reference to it in row for value 1. | T | NO | postpone |  | See CID 619
621 | Kai Lennert Bober | Fraunhofer HHI |  |  | 66 | 6.6.20 | 17 | Concerns the whole subclause: Currently, the supported MCS Element is the only way to communicate MCS of the PM-PHY between the coordinator and device. The supported MCS Element allows only to specify a certain set of a) Clock rates b) Modulation formats c) Line codings This means, that all possible combinations between the supported modes must be supported. This prevents a fine granular set of supported MCS. Potentially, a huge number of MCS needs to be implemented. | Provide more explicit way of specifying the set of supported MCS. E.g. a list of single octet values. Or even a 256-Bit (32 octets) wide bitmap? | T | NO | Postpone |  | Take discussion offline between Sang-Kyu, Volker, Xu | Volker
622 | Kai Lennert Bober | Fraunhofer HHI |  |  | 66 | 6.6.22 | 5 | Move the protocol description from 6.6.22 into the functional description part. Clause 6 is meant for frame formats only. | Do as proposed. Do not make the devices human (rephrase) | E | NO | postpone |  | Please check that all protocol details in 6.6.22 are also contained in clause 5 (the protocol specification). | Stephan Berner
623 | Sang-Kyu Lim | ETRI |  |  | 67 |  |  | The sub-clauses for PM-PHY MCS element and HB-PHY MCS element are 6.6.20 and 6.6.21, respectively. However, the sub-clause for LB-PHY MCS element is not shown. | Please add the sub-clause for LB-PHY MCS Element. | T | No | postpone |  | Please provide definition of LB-PHY MCS element (8 rates). Please provide text update to possibly remove the Extended Supported Rates field in the Random Access element. | Stephan Berner
624 | Kai Lennert Bober | Fraunhofer HHI |  |  | 75 | 7.3.3.3 | 21 | The DISASSOCIATIE.confirm primitive should have a "status" parameter | Add a new parameter "Status" after P75L24 and as the last row of table 27. Columns in table 27: Type: enumeration Value range: SUCCESS, FAIL_OTHER Indicates whether the preceding MLME-DISASSOCIATE.request primitive was successful or not. | T | NO | Postpone |  | Please provide text update for Status parameter | Lennert
625 | Sang-Kyu Lim | ETRI |  |  | 82 | 7.4 |  | Unit/Range for macDeviceTimeout in Table 40 | [1, 65545] --> Is it correct ? | T | No | revise |  | Change 65545 to 65535
626 | Kai Lennert Bober | Fraunhofer HHI |  |  | 83 | 7.4 | 4 | The MAC address is not a constant but rather a PIB attribute | Remove constant aMac48Address and add new MAC PIB attribute macMac48Address with get and set option. | T | NO | accept
627 | Kai Lennert Bober | Fraunhofer HHI |  |  | 85 | 8.2.3 | 27 | Rename multi-OFE channel estimation to explicit MIMO channel estimation | Do as proposed | E | NO | revise |  | Rename multi-OFE channel estimation to explicit MIMO channel estimation. Rename as follows: capability capMultiOfeEstimation -> capExplicitMimoEstimation multi-OFE pilot -> explicit MIMO pilot Multi-OFE Feedback element -> Explicit MIMO Feedback element Rename clause title "5.9.4 Multi-OFE channel feedback" -> "5.9.4 Explicit MIMO channel feedback"
628 | Kai Lennert Bober | Fraunhofer HHI |  |  | 86 | 8.2.3 | 5 | Fix usage of the term "division" for the Multi-OFE pilots | Alter sentence in L4-5 as follows: For a given PPDU, which is designated by the MAC to contain multi-OFE pilots, the PHY receives an OFE index through the PD-SAP. The PHY is able determine the form of the pilot symbol based on that OFE index. | E | NO | accept
629 | Kai Lennert Bober | Fraunhofer HHI |  |  | 87 | 8.3.2 | 1 | The PHY PIB attributes in table 43 are not needed as the PHY SAP is not specified. Rather, each device implementation should know the PHY's capabilities to send MIMO PS. | Remove the two PHY PIB attributes phyMultiOfeDivisions and phyMultiOfeSymbols. | T | NO | revise |  | Add the following text after P86L23: Each PHY has its own set of PIB attributes. The DME is able to obtain the used PHY type by reading the phyImplementedPhy PIB attribute. Remove the two existing PHY PIB attributes from table 43. Add a new attribute to table 43 as follows: Name: phyImplementedPhy Description: The type of PHY. get/set: get Range: PM-PHY, LB-PHY, HB-PHY Unit: Enumeration
630 | Kai Lennert Bober | Fraunhofer HHI |  |  | 88 | 9.1.1 | 14 | Change table 44 to the same format as the equivalent tables for the LB-PHY and HB-PHY. | As commented. | E | NO | Postpone |  | Please provide text update for table 44 | Lennert
724 | Sang-Kyu Lim |  |  |  | 88 | 9.1.2 | 15 | "Encoding" is not a good term | Change all occurences to "Line Code" | T | N | accept
631 | Kai Lennert Bober | Fraunhofer HHI |  |  | 89 | 9.3.1.1 | 13 | The acronym AGC is only used two times. | Replace acronym with full term in both locations. | E | NO | accept
632 | Kai Lennert Bober | Fraunhofer HHI |  |  | 89 | 9.3 | 8 | Merge "Transmission" subclauses of PHYs with the "PPDU format clause"? | Do as proposed in comment for all three PHYs | E | NO | accept
633 | Kai Lennert Bober | Fraunhofer HHI |  |  | 89 | 9.3.1.1 | 16 | Many variables in the PM-PHY are in bold font. Those should be converted to non-bold italic as prescribed for variables. | Format all variables in the PM-PHY and in the whole document in non-bold italic font. | E | NO | accept
634 | Kai Lennert Bober | Fraunhofer HHI |  |  | 89 | 9.1.3 | 1 | The maximum PSDU size can only be 2047 with 12 bits | Change 2048 to 2047 | T | NO | accept
635 | Sang-Kyu Lim | ETRI |  |  | 90 | 9.3.1.1 |  | Preamble length for Encoding ID = 3 in Table 46 | Change "394" to "384" in Table 46. | T | No | accept
636 | Kai Lennert Bober | Fraunhofer HHI |  |  | 90 | 9.3.2.1 | 13 | The PPDU header field tables of all PHYs should have the same format. | Find a common table structure for all PHY headers | E | NO | withdrawn
637 | Kai Lennert Bober | Fraunhofer HHI |  |  | 90 | 9.3.2.1 | 12 | The SI field in the PM-PHY header has 4 bits | Correct number of bits | T | NO | accept
638 | Kai Lennert Bober | Fraunhofer HHI |  |  | 90 | 9.3.2.1 | 14 | It is not clear, in which bit-order multy-bit-fields in the PM-PHY are transmitted. | Add clause specifying the bit-order used in the PM-PHY for the header and also payload (i.e. PSDU bits). Check Section 4 of 15.4-2015 and add similar conventions to our standard if appropriate. | T | NO | postpone |  | Please provide text to specify the bit and byte order | Volker
639 | Sang-Kyu Lim | ETRI |  |  | 91 | 9.3.3 | 24 | k=5…11 | Change "k = 5…11" to "k = 6…10". | T | No | accept
640 | Kai Lennert Bober | Fraunhofer HHI |  |  | 91 | 9.3.3 | 16 | Subclause 9.3.3. should be subclause 9.3.2.4 | Move clause as proposed | E | NO | accept
641 | Kai Lennert Bober | Fraunhofer HHI |  |  | 91 | 9.3.2.3 | 15 | The MIMO PS shall have a long cyclic prefix. | Alter sentence in L15 as follows: A long cyclic prefix, as described in 9.4.8 is finally inserted. | T | NO | accept
726 | Volker Jungnickel |  |  |  | 91 | 9.3.2.3 | 14 | MIMO PS must be sent in maximum clock rate | Change text as needed | T | n | postpone |  | Please provide text update | Volker
642 | Kai Lennert Bober | Fraunhofer HHI |  |  | 93 | 9.4.2 | 8 | Table 49 does not include the long cyclic prefix. | Include column for the number of samples of the long cyclic prefix in table 49. | T | NO | accept
643 | Kai Lennert Bober | Fraunhofer HHI |  |  | 93 | 9.4.2 | 8 | N_CP is not unambigous anymore if there are multiple cyclic prefix lengths. | Find better variable names for the two cyclic prefix lengths. E.g. N_CPL and N_CPS | E | NO | revise |  | rename N_CP to N_CPShort and introduce a new N_CPLong for the long cyclic prefix.
644 | Kai Lennert Bober | Fraunhofer HHI |  |  | 93 | 9.4.1 | 1 | The spatial precoding is logically handled above the PHY, by selecting a certain set of PHYs for transmission. For consistency, the spatial precoder can be removed here. | Remove Line 26 | T | NO | postpone |  |  | Volker
645 | Kai Lennert Bober | Fraunhofer HHI |  |  | 93 | 11.3.2.2 | 17 | Malte H.: Did we not agree to remove the padding bits after FEC encoding? In that case, prepending zeros (such as the RS Encoder would do) might be a good idea. If the padding sequence is transmitted, using valid 8B10B symbols would be a good idea in order to not break the balance of the line coding. |  | T | NO
646 | Kai Lennert Bober | Fraunhofer HHI |  |  | 93 | 11.3.2.2 | 20 | Malte H.: [...] the primitive polynomial x^10 + x^3 + 1 is used. The base exponent of the root of the generator polynomial is 0. |  | T | NO
647 | Kai Lennert Bober | Fraunhofer HHI |  |  | 94 | 9.4.7 | 23 | The relevant Hadamard matrices should be included in the Standard. | Place the relevant hadamard matrices in the Annex and put a reference in the right place in the PM-PHY clause | E | NO
648 | Kai Lennert Bober | Fraunhofer HHI |  |  | 94 | 9.4.7 | 18 | The text says theat u_0 is set to 0 but figure 70 shows it going into the P/S converter. | For clarity, remove the X:0 going from the FWHT to the P/S component in figure 74. Clarify this in the text. | E | NO
725 | Volker Jungnickel |  |  |  | 94 | 9.4.7 | 23 | Equation is unclear: Why is the "H bar" term needed? | Add text for clarification | T | n | Postpone |  | Request text from VLNComm | Volker
649 | Sang-Kyu Lim | ETRI |  |  | 96 | 10.1.1 | 10 to 11 | According to 4.6.1, LB-PHY uses bit-interleaved coded OFDM modulation, and HB-PHY is based on OFDM modulation with adaptive bitloading. The sentence in line #10 on page 96 say that LB-PHY supports the application of adaptive bit and power loading techniques as well as MIMO. However, the sentence in line #6 on page 101 say that LB-PHY does not support adaptive bit loading. | If LB-PHY supports adaptive bitloading, then delete the sentence in line #6 on page 101. Or, if LB-PHY does not support adaptive bitl oading, then change the the sentence in line #10 on page 96. | T | No | revise |  | Modify sentences on P96L10-11 as follows: LB-PHY supports MIMO and relaying functionality.
650 | Kai Lennert Bober | Fraunhofer HHI |  |  | 96 | 10.1.1 | 14 | This paragraph seems duplicate with the content in P100L2-4. OCR_m is not defined. | Remove one of the occurences of this sentence. | E | NO | revise |  | Remove P96L15: "The data rates for 〖OCR〗_m are 〖OCR〗_m times of the data rates for OCR 1MHz in the above table for each MCS accordingly." Remove P96L14: "The OCR shall be obtained by dividing the available frequency by 8." because this is implementation specific. Remove sentence in P100L3-4: "The data rates..."
651 | Sang-Kyu Lim | ETRI |  |  | 97 |  |  | The PHY constants for PM-PHY and HB-PHY are shown in 9.1.3 and 11.1.3, respectively. However, the PHY constants for LB-PHY are not shown. | Add the sub-clause specifying the PHY constants for LB-PHY to 10.1. | T | No | revise |  | Add section 10.1.3 PHY constants, add a 4x4 table with the following rows. 1st row: Name, Description, Value, Unit 2nd row: aPhyMaxPsduSize, The maximum supported PSDU size. This attribute is PHY-specific., 2047, octets 3rdrow:aPhyTurnaroundTime, Not applicable because full duplex PHY, N/A, N/A 4th row: aPhyClockAccuracy, The minimum accuracy of the PHY reference clock., +/- 20, ppm
652 | Kai Lennert Bober | Fraunhofer HHI |  |  | 97 | 10.1.1 | 2 | Some figures in the LB-PHY are bitmaps | Provide the figure as B/W vector graphics to the TE: Figure 71 Figure 73 Figure 74 Figure 75 Figure 76 Figure 77 Figure 78 Figure 79 Figure 80 Figure 81 Figure 82 Figure 83 Figure 84 Figure 85 | E | NO | accept |  |  | -
653 | Kai Lennert Bober | Fraunhofer HHI |  |  | 97 | 10.3.1.1 | 11 | Do not use the term "packet" but use "frame" instead or, if appropriate, the following more specific terms: MSDU MPDU / PSDU PPDU | Replace "packet" with "PPDU" in: P97L11 P101L7 105L19 P106L1 (Table 56 in "Device to acknowledge" row) P106L9 P107L12 | T | NO | accept
654 | Kai Lennert Bober | Fraunhofer HHI |  |  | 97 | 10.1 | 4 | The LB-PHY lacks a PHY constants table | Insert new PHY constants subclause and table under 10.1. Add the appropriate values for clock accuracy, max tunraround time. | T | NO | duplicate |  | see CID 651
655 | Sang-Kyu Lim | ETRI |  |  | 98 | 10.3.1.2 | 13 | Equation Number (13) | Delete the equation number (13). | E | No | accept
656 | Kai Lennert Bober | Fraunhofer HHI |  |  | 98 | 10.3.1.2 | 5 | Term "Guard Interval" should be unified with CP | Use only cyclic prefix in the whole standard, especially other places in the LB-PHY clause | T | NO | accept
657 | Kai Lennert Bober | Fraunhofer HHI |  |  | 99 | 10.3.2.1 | 16 | It is not clear how setting the bandwidh (OCR) the LB-PHY works. Is is supposedly set to a fixed value by some entity and not dynamically. | Either include a protocol mechanism to set the bandwidth or include a PHY PIB attribute to set the bandwidth from the DME via the MLME get/set primitives. | T | NO | postpone |  |  | Lennert
658 | Kai Lennert Bober | Fraunhofer HHI |  |  | 99 | 10.3.2.1 | 12 | It is not clear, in which bit-order multy-bit-fields in the LB-PHY are transmitted. | Add clause specifying the bit-order used in the LB-PHY. | T | NO | revise |  | Insert a section 10.3.1 "Bit order" Text: The least significant bit (LSB) of multiple bit fields or data octets is transmitted first
659 | Sang-Kyu Lim | ETRI |  |  | 100 | 10.3.2.1 |  | The field for High-reliability control is shown in Table 52, but its description is not shown in text body. | Add the description for High-reliability control field to the text body. | T | No | revise |  | Add "High reliability header" at P100L12 before the colon.
660 | Kai Lennert Bober | Fraunhofer HHI |  |  | 100 | 10.3.2.1 | 25 | (Table 54) The term "reference symbol" has the same meaning as the term "pilot symbols" in the other PHYs | Change usage of the term "reference symbol" to "pilot symbol" in the whole LB-PHY. | E | NO | accept
661 | Sang-Kyu Lim | ETRI |  |  | 102 | 10.3.2.3.3 |  | MIMO Pilot Symbols Format I and MIMO Reference Symbols Format II | Change the naming style for the titles of 10.3.2.3.2 and 10.3.2.3.3. | T | No | accept
662 | Kai Lennert Bober | Fraunhofer HHI |  |  | 102 | 10.3.2.2 | 18 | If HCS is not used in the LB-PHY, there is no necessity to keep the field in the PPDU format or text. | Remove 10.3.2.2 and the HCS field from figure 72 | T | NO | accept
663 | Kai Lennert Bober | Fraunhofer HHI |  |  | 102 | 10.3.2.3.2 | 27 | Term "MIMO transmitter" should be unified with other PHYs / MAC | Replace "MIMO transmitter" with "OFE" | E | NO | revise |  | Define what an optical frontend (OFE) is in the "definitions" clause: An OFE is the interface to the optical wireless channel. It consists of a single optical transmitter and receiver. An OFE corresponds to an antenna in RF. Thereafter replace "MIMO transmitter" with "OFE".
664 | Kai Lennert Bober | Fraunhofer HHI |  |  | 102 | 10.3.2.3.1 | 23 | Check if PS could always be replaced by "pilot symbols" in favor of readability. | Do as proposed | E | NO | accept
665 | Kai Lennert Bober | Fraunhofer HHI |  |  | 103 | 10.3.2.3.3 | 4 | Term "MIMO transmitter" should be unified with other PHYs / MAC | Replace "MIMO transmitter" with "OFE" | E | NO | accept |  | see resolution CID 663
666 | Kai Lennert Bober | Fraunhofer HHI |  |  | 105 | 10.3.3.1 | 13 | "PSDU length" is a more suitable name than "Length of packet" | Rename the "Length of packet" field to "PSDU length" in the table and in the rest of clause 10 | E | NO | accept
667 | Kai Lennert Bober | Fraunhofer HHI |  |  | 106 | 10.3.3.2 | 1 | Do not use the term "packet" but use "frame" instead or, if appropriate, the following more specific terms: MSDU MPDU / PSDU PPDU | Replace "packet" with MPDU in P106L1 (Table 56 in "Sequence number" row) and in P106L12 | T | NO | revise |  | replace "packet" with "PPDU" in both locations in table 56, L9 and L12.
668 | Kai Lennert Bober | Fraunhofer HHI |  |  | 106 | 10.3.3.2 | 1 | It is not clear, which role the "Sequence number" field in the high reliability control header has. How is it related to these other fields: Compressed Sequence Number field of the Poll ACK field? Sequence Number field in the Sequence Control field of the general MAC frame format field? | Please add clarifying text | T | NO
669 | Kai Lennert Bober | Fraunhofer HHI |  |  | 113 | 10.4.4 | 7 | "PLCP" is nowhere defined | It seems, this term comes from 802.11, referring to the preamble. If technically the Preamble part of the SHR is meant, this should be reflected in the text. Add text for PLCP preamble. | T | NO
670 | Kai Lennert Bober | Fraunhofer HHI |  |  | 113 | 10.4.4 | 11 | Figure 82 is not mentioned in the text | Add text referring to Figure 82 or remove figure 82. | E | NO
671 | Sang-Kyu Lim | ETRI |  |  | 118 | 11.1.1 | 4 | According to Table 57, the gross data rates of HB-PHY are from 23 Mb/s to 2192Mb/s, and according to 4.6.1, the data rates of HB-PHY are from 10Mb/s up to multiple Gb/s. | The data rates for HB-PHY in this sentence need to be synchronized with those of Table 57 and 4.6.1. | T | No
716 | Volker Jungnickel |  |  |  | 118 | 11.1.1 | 7 | Update non-normative reference on HB-PHY (so far G.9960-2015) to the latest recommendations. These may be G.9991, G.9963 and more | As proposed | T | No
717 | Volker Jungnickel |  |  |  | 118 | 11 | 1 | Update the text for the HB-PHY and incorporate the latest version, e.g. from 802.11bb | As proposed | T | No
672 | Kai Lennert Bober | Fraunhofer HHI |  |  | 119 | 11.1.4 | 10 | The use of "comb shift" and "comb spacing" is not optimal. First, both should not have acronyms. | Change comb shift to carrier offset. Change comb spacing to carrier spacing | E | NO
673 | Kai Lennert Bober | Fraunhofer HHI |  |  | 119 | 11.3.1.1 | 18 | It is not clear how setting the bandwidh (OCR) the HB-PHY works. Is is supposedly set to a fixed value by some entity and not dynamically. | Either include a protocol mechanism to set the bandwidth or include a PHY PIB attribute to set the bandwidth from the DME via the MLME get/set primitives. | T | NO
674 | Kai Lennert Bober | Fraunhofer HHI |  |  | 120 | 11.3.2.1 | 24 | It is not clear, in which bit-order multy-bit-fields in the HB-PHY are transmitted. | Add clause specifying the bit-order used in the HB-PHY and check for consistency with the ITU-T G.9960 recommendation. | T | NO
675 | Kai Lennert Bober | Fraunhofer HHI |  |  | 121 | 11.3.2.1 | 1 | The HCS in the HB-PHY header does not specify, which bits are included into the checksum. | Specify this. | T | NO
676 | Kai Lennert Bober | Fraunhofer HHI |  |  | 122 | 11.3.2.2 | 18 | The sentence "The value of Δ shall respect the fundamental relation Δ ≤ N / N_CP" Only makes sense, if the number of subcarriers N is variable. Otherwise we should make sure that the maximum comb spacing always satisfies this relation. | Ensure that the relation is always satisfied. | T | NO
677 | Kai Lennert Bober | Fraunhofer HHI |  |  | 122 | 11.3.2.2 | 16 | Malte H.: I think this should be: [index of first usable subcarrier] + [0, delta, 2*delta, ... , N-delta-[index of first usable subcarrier]] (+ CS), instead of starting at delta and cyclically pushing the top pilots around. |  | T | NO
678 | Kai Lennert Bober | Fraunhofer HHI |  |  | 123 | 11.3.2.2 | 1 | The PHY header does not have variables but fields. | Change "variable" to "field". Furthermore, give the field a more expressive name. Rename fields that have such acronyms to readable names in the other PHY header fields. | E | NO
679 | Kai Lennert Bober | Fraunhofer HHI |  |  | 123 | 11.3.2.2 | 1 | The PHY header must include the comb spacing and not the comb shift. This must be clarified. | Clarify as proposed. | T | NO
680 | Kai Lennert Bober | Fraunhofer HHI |  |  | 123 | 11.3.2.2 | 3 | CS_max is not explained. | Remove variable | T | NO
681 | Kai Lennert Bober | Fraunhofer HHI |  |  | 123 | 11.3.2.2 | 1 | Malte H.: Cyclic shift of the comb indices. CS could just be an offset (without cyclic shift), e.g. n_offs, with the indices suggested in the previous comment. | Make the "cyclic shift" an "offset". | E | NO
682 | Kai Lennert Bober | Fraunhofer HHI |  |  | 123 | 11.3.2.2 | 3 | Malte H.: By using a single... is redundant with the formula below. | Remove either of them. | E | NO
683 | Kai Lennert Bober | Fraunhofer HHI |  |  | 123 | 11.3.2.2 | 5 | Malte H.: Why not N_PS * delta? (CS starts at 0). Also, maybe give the number of streams a symbol (i.e. N_ss). | Use N_PS * delta | T | NO
684 | Kai Lennert Bober | Fraunhofer HHI |  |  | 123 | 11.3.2.2 | 6 | Malte H.: This needs to be delta, not delta-1, as it represents the cycle of repetition. |  | T | NO
685 | Kai Lennert Bober | Fraunhofer HHI |  |  | 123 | 11.3.2.2 | 6 | Malte H.: It should say b <= delta -1 | Change to b <= delta -1 | T | NO
686 | Kai Lennert Bober | Fraunhofer HHI |  |  | 123 | 11.3.2.2 | 6 | Malte H.: This is a bit unclear. Assuming: i is the subcarrier index, a identifies the row in the Hadamard matrix, and b is equal to CS? Then the pilot sequence for subcarrier i is RS(i) * [a-th row of H_k], which should be stated more clearly and with consistently named symbols. It might also be useful to solve this equation for a, to give an instruction for which signs to use for pilot generation. Also, a and b seem to be a bit meaningless as symbols...H54 |  | T | NO
687 | Kai Lennert Bober | Fraunhofer HHI |  |  | 123 | 11.3.2.2 | 8 | Malte H.: How are k or M assigned? M >= N / delta? |  | T | NO
688 | Sang-Kyu Lim | ETRI |  |  | 125 | 11.3.4.1 |  | Figure 91 | "Header FEC encoder" in Figure 91. --> Is it correct ? Or "Payload FEC encoder" ? | T | No
689 | Kai Lennert Bober | Fraunhofer HHI |  |  | 127 | 11.4.1 | 22 | "Forward error correction" is not accurate, since the subclause contains also the scrambling. | Rename subclause to "coding and scrambling" or similar. Alternatively, move scrambling out of the clause. | E | NO
690 | Kai Lennert Bober | Fraunhofer HHI |  |  | 133 | 11.4.2.3 | 1 | At the receiver, it must somehow be clear which scrambler initialization the transmitter used to load pseudo random bits onto the ISC. Otherwise the ISC cannot be used as pilot subcarriers. | Add routine to negotiate an initialization during association or define a fixed scrambler seed for the bits to load on ISCs. | T | NO
691 | Sang-Kyu Lim | ETRI |  |  | 138 | Annex A | 29 | ITU-T G.9960 | Change "Unified high-speed wireline-based ~" to "Unified high-speed wire-line based ~". | T | No
692 | Sang-Kyu Lim | ETRI |  |  | 140 | Annex B.2 | 2 | k=1…11 | Change "k = 1…11" to "k = 0…10". | T | No
696 | Tunçer Baykaş | Istanbul Medipol University |  |  |  | general |  | The relaying function is not explained adequately. | Update the Chapters 4,5,6, 7, 9
697 | Tunçer Baykaş | Istanbul Medipol University |  |  |  | 4.5.2 |  | The relaying function could be added in the explanations. | Update the papragraph “Moreover, the 802.15.13 MAC supports the use of advanced MIMO schemes with distributed, networked optical wireless frontends and for multiple mobile devices, as well as relaying operation.” | E | N
698 | Tunçer Baykaş | Istanbul Medipol University |  |  |  | 4.6.1 |  | Relaying allows communication between noncoordinator devices. | Remove sentence “Direct communication between non-coordinator devices is not foreseen. “ | T | Y
699 | Tunçer Baykaş | Istanbul Medipol University |  |  |  | 4.6.1 |  | Relaying should be mentioned in subsections | Refer to relaying in "4.6.1.1 Data transfer from a device to a coordinator and 4.6.1.2 Data transfer from a coordinator to a device "
700 | Tunçer Baykaş | Istanbul Medipol University |  |  |  | 5.2 |  | Update the section of how the realying device associates | Relaying should be explained here
701 | Tunçer Baykaş | Istanbul Medipol University |  |  |  | 6 |  | Elements and capability list for relaying are missing | Update elements and capability list for relaying
702 | Tunçer Baykaş | Istanbul Medipol University |  |  |  | 5.8 |  | How adaptive transmission work with relaying should be explained | Update section 5.8
703 | Tunçer Baykaş | Istanbul Medipol University |  |  |  | 5.7 |  | How the acknowledgment work for the relaying? | Describe the single and block acknowledgement for relaying.
693 | Kai Lennert Bober | Fraunhofer HHI |  |  | 143 | Annex B4 | 5 | Table headers should be kept with tables | Keep all table headers with the table in whole document | E | NO
694 | Sang-Kyu Lim | ETRI |  |  | XIII |  |  | Annex A, B, and C are not shown in Table of Contents. | Please put Annex A, B, and C into the table of contents. | E | No
695 | Sang-Kyu Lim | ETRI |  |  |  | 11 |  | PM-PHY has the sub-clause 9.4.2 and Table 49 for the optical clock rate. However, the sub-clause and a table for HB-PHY optical clock rate are not shown in the clause 11. | Add the sub-clause and a table for HB-PHY optical clock rate to the clause 11. | T | No

## Cell Values
Values for Resolution | Values for TE status | Values for must be satisfied | Values for E/T
Accept | Done | Yes | E
Reject | Ask | No | T
Revise | Not applied
Withdrawn
Duplicate
Postpone