## Slide 1
Project: IEEE P802.15 Working Group for Wireless Specialty Networks (WSNs)
Submission Title: [IEEE 802.15.4y Sept 2020 Closing Report]
Date Submitted: [18 Sept 2020]
Source: [Don Sturek] Company [Itron]
Address [San Jose, CA]
Voice:[], E-Mail:[don.sturek@itron.com]
Re: [IEEE 802.15.4y closing report for Sept 2020 interim session.]
Abstract: [IEEE 802.15.4y closing report for Sept 2020 interim session]
Purpose: [IEEE 802.15.4y closing report for Sept 2020 interim session]
Notice: This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Slide 2: IEEE 802.15.4y SECN Closing report
Sept 18, 2020
Don Sturek
IEEE 802.15.4y SECN Chair

## Slide 3
Work Plan for Sept 2020 interim
Confirm completion of comment resolution for LB167
Create CRG for continued comment resolution
Notes: Jul 12, 2010
Page 3

## Slide 4
Work Plan for 4y to next IEEE 802 meeting
Re-circulate draft to the WG
Continue comment resolution on re-circulation when the ballot closes.
Form sponsor ballot pool
Notes: Jul 12, 2010
Page 4

## Slide 5
Progress at Sept 2020 virtual interim
Updated Timeline
    Work Group Recirculation Ballot – Sept 2020
    SA Ballot – November 2020
    Expect around 2 re-circulations of sponsor ballot (send to REVCOM around early 2021)
Notes: Jul 12, 2010
Page 5

## Slide 6
Agenda for next IEEE 802 meeting
Comment resolution on WG re-circulation or start sponsor ballot
Form CRG
Notes: Jul 12, 2010
Page 6

## Slide 7
TG Motion
TG Motion for TG4y Letter Ballot
Move that TG4y formally request that the 802.15 WG start a WG Recirculation Letter Ballot requesting approval of document P802.15.4y-D1, as edited in accordance with the instructions in document 15-20-0103 to Standards Association ballot pending the completion and inclusion of the edits in the draft.
Moved: Kunal Shah
Second: Ben Rolfe
Motion passed unanimously
Notes: Jul 12, 2010
Page 7

## Slide 8
WG Motion
WG Motion for TG4y Letter Ballot
Move that 802.15 WG start a WG Recirculation Letter Ballot requesting approval of document P802-15-4y_D1 and to forward document P802-15-4y_D1, as edited in accordance with the instructions in document 15-20-0103 to Standards Association ballot pending the completion and inclusion of the edits in the draft.
Moved:
Second:
Motion passes by unanimous consent
Notes: Jul 12, 2010
Page 8

## Slide 9
TG Motion
TG CRG Motion
Move that TG4y requests 802.15 WG approve the formation of a Comment Resolution Group (CRG) for the WG balloting of the P802.15.4y-D1 with the following membership: Don Sturek (As Chair), Tero Kivinen, Peter Yee, Ruben Salazar. The 802.15.4y CRG is authorized to approve comment resolutions and to approve the start of recirculation ballots of the revised draft on behalf of 802.15 WG. Comment resolution on ballots between sessions will be conducted via reflector email and via teleconferences announced to the reflector as per the LMSC 802 WG P&P
    Moved By: Ben Rolfe
    Seconded By: Kunal Shah
    Motion passed unanimously
Notes: Jul 12, 2010
Page 9

## Slide 10
WG Motion
WG CRG Motion
Move that TG4y requests 802.15 WG approve the formation of a Comment Resolution Group (CRG) for the WG balloting of the P802.15.4y-D1 with the following membership: Don Sturek (As Chair), Tero Kivinen, Peter Yee, Ruben Salazar. The 802.15.4y CRG is authorized to approve comment resolutions and to approve the start of recirculation ballots of the revised draft on behalf of 802.15 WG. Comment resolution on ballots between sessions will be conducted via reflector email and via teleconferences announced to the reflector as per the LMSC 802 WG P&P
    Moved By:
    Seconded By:
    Motion passes by unanimous consent
Notes: Jul 12, 2010
Page 10