## Slide 1
Project: IEEE P802.15 Working Group for Wireless Specialty Networks (WSN)
Submission Title: Licensed Narrowband Amendment TG16t November 2020 Plenary Meeting Closing Report
Date Submitted: 2020-11-11
Source: Tim Godfrey, EPRI
Abstract: Closing Report
Purpose: Closing Report
Notice: This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Slide 2: TG16t Agenda Nov 2020
Introductions, Secretary, Review and Approve Agenda
Policy Review
Review of PAR Modification
CFC Update and Presentation of Contributions
Development of System Requirements Document (SRD)
Adjourn
TG16t meetings held on Tuesday November 3rd and Tuesday November 10th

## Slide 3: Call for Contributions – Updated Nov 4, 2020
The IEEE 802.15.16t Task Group is developing an amendment to 802.16-2017. Project 802.16t “Amendment - Fixed and Mobile Wireless Access in Narrowband Channels”
This project specifies operation in licensed spectrum with channel bandwidths greater than or equal to 5 kHz and less than 100 kHz. A new PHY will be specified, with changes to the MAC as necessary. The amendment is frequency independent but focuses on spectrum less than 2 GHz. Aggregated operation in adjacent and non-adjacent channels will be supported.
This Call for Contributions solicits input documentation toward the development the amendment. The approved PAR is available at this link. The approved PAR is also available on Mentor as document IEEE 802.15-20-0196r1
Contributions are sought on the following topics;
  Contributions toward the System Requirements Document (IEEE 802.15-20-182r6 or subsequent)
  Contributions related to security requirements for critical infrastructure use cases as described in IEEE 802.15-20-213r2 (or subsequent)
The Task Group is meeting virtually for the time being. Meetings and teleconferences are announced on the TG16t reflector and the 802.15 calendar.
This call for contributions will remain open until (at least) the March 2021 electronic plenary meeting.
Documents should be uploaded to Mentor, to the TG16t task group.
For further information, contact the following:
  IEEE 802.15.16t Task Group Chair: Tim Godfrey <tim.godfrey@ieee.org>
  IEEE 802.15 Working Group Chair: Pat Kinney <pat.kinney@kinneyconsultingllc.com>
Updated CFC Document Link

## Slide 4: Motion on PAR Modification
Approved in July Plenary, Forwarded to EC for approval in November
PAR Modification on Agenda for 802 EC for November and submitted to NesCom.
Feedback from other WG was reviewed by Task Group in 11/3 meeting, response captured in 15-20-0314-01-0000-comments-on-802-15-pars-during-nov-2020-plenary.

## Slide 5: Reason for PAR Modification
Section 8.1 “Additional Explanatory Notes”
The Task Group started its work by evaluating the candidate use cases and available spectrum suitable for licensed narrowband operation.
The use cases are detailed in 802.15-20-0213r2, and the frequency bands are detailed in 802.15-20-055r4
Based on the analysis of use cases and frequency bands, it was learned that a significant fraction of the bands of interest were allocated and structured for Frequency Division Duplexing (FDD) operation. The PAR scope restriction to Time Division Duplexing (TDD) operation was not appropriate, based on the requirement to operate in those frequency bands.

## Slide 6: WG Motion
Move to request that the PAR and CSD contained in documents [15-20-0196-02-016t-licensed-narrowband-amendment-par] and [ec-19-0222-00-ACSD-p802-16t], respectively, be approved by the IEEE 802.15 WG and that the 802 LMSC EC be requested to forward the PAR to NesCom. The 802.15 working group chair and technical editor are authorized to make additional modifications to the PAR and CSD as needed to reflect EC discussion at its closing meeting.
Moved Tim Godfrey (EPRI)
Second Rick Alfvin (Linespeed)
Results: 27/0/5

## Slide 7: Contributions for November 3rd Telecon
315 | 1 | TG16t | Security Requirements for 802.16t | Yael Luz (Ondas Networks)
Contributions for November 10th Telecon

## Slide 8: Discussion on Security Requirements for 802.16t
The group discusses whether the current 16t scope can include security changes under the umbrella of “required by the physical layer changes.”
Options:
  1) Continue 16t and change PAR to include security changes (driven by use cases) in scope
  2 Create a new PAR and TG for Security changes.
Path forward:
  Ask for contributions on security. Amend Call for Contribution
  Understand the requirements for security – what has to be changed
    Look at post-quantum security architecture
  Can the work be done in this TG, or do we need a new TG in parallel?
  Solicit contributions from stakeholders on what their customers and markets require

## Slide 9: Development of the SRD
Discussion and review of SRD draft
Post 802.15-20-182r7 as output
Continue to review and adopt contributions for SRD at next call

## Slide 10: Preparation for development of SDD
As the SRD is finalized, the Task Group will begin considering contributions for the System Design Document (SDD).
A SDD template for TG16t (based on the P802.16s SDD) has been uploaded as 802.15-20-0351r0
The approved 802.16s SDD is available for reference as 802.16-17-006r3

## Slide 11: Revised Project Timeline
Milestone | Date | Updated Date
Task Group Start | January 2020 | 
SRD Approval | Nov 2020 | March 2021
SDD Approval | May 2021 | Sept 2021
Informal TG review of draft | Sept 2021 | Jan 2022
Working Group Letter Ballot | Nov 2021 | March 2022
Working Group Recirculation Letter Ballot | Mar 2022 | July 2022
SA Ballot | Sept 2022 | Jan 2023
Forward to RevCom | March 2023 | July 2023
Request PAR Extension
Assign Editor

## Slide 12: Teleconference Planning
Plan for rest of 2020
August 13 11am Pacific, 2pm Eastern
Sept 17 11am Pacific, 2pm Eastern (802.15 electronic Interim)
Oct 14 10:30am Pacific, 3:30pm Eastern (1.5 hours)
IEEE 802 Electronic Plenary -- IEEE 802.15 will meet over two weeks
  TG16t Meeting 1 Tuesday Nov 3 PM2 1-3pm Pacific 4-6pm Eastern
  TG16t Meeting 2 Tuesday Nov 10 PM2 1-3pm Pacific 4-6pm Eastern
Dec 3 11am Pacific, 2pm Eastern
January 12 11am Pacific, 2pm Eastern

## Slide 13: Upcoming Sessions
July 12-17, 2020, Sheraton Centre Montreal, Montreal Canada, 802 Plenary Session.
September 13-18, 2020, Grand Hyatt Atlanta in Buckhead, Atlanta, Georgia, 802 Wireless Interim Session.
November 18-13, 2020, Marriott Marquis Queen's Park, Bangkok, Thailand, 802 Plenary Session.
January 12-14, 2021, Hotel Irvine, Irvine, California 802 Wireless Interim Session.
March 16-18, 2021 Hyatt Regency Denver Convention Center, 802 Plenary Session
802.16t meets on Tuesday-Thursday during face to face meeting sessions.
Cancelled
Cancelled
Cancelled
Cancelled