## Slide 1
P802.15.9ma Report to EC on Unconditional Approval to go to SA Ballot
Date: 2020-11-19
November 2020
Pat Kinney (Kinney Consulting)
Slide 1
Author(s):
Name | Affiliations | Address | Phone | Email
Pat Kinney | Kinney Consulting |  |  | pat.kinney@kinneyconsultingllc.com
Tero Kivinen | Self |  |  | kivinen@iki.fi
Notes: doc.: IEEE 802.11-yy/xxxxr0
Month Year
John Doe, Some Company
Page 1

## Slide 2
Introduction
This document contains the report to the IEEE 802 Executive Committee in support of a request for unconditional approval to send IEEE P802.15.9ma D2.0 to SA Ballot
The WG motion to request unconditional approval was approved during the November session of the 802.15 working group on 12 November 2020.
  Passed in the Working Group 29 yes, 0 no, 0 abstain
Slide 2
Pat Kinney (Kinney Consulting)
November 2020
Notes: doc.: IEEE 802.11-yy/xxxxr0
Month Year
John Doe, Some Company
Page 2

## Slide 3
Status Summary
The TG9ma Draft went through two WG Letter Ballots. Draft P802.9ma-D01 achieved > 75% needed for an approved draft
The TG has resolved 91 comments received on drafts P802.15.9-D01, and no comments for D02.
Slide 3
Pat Kinney (Kinney Consulting)
November 2020

## Slide 4
November 2020
Pat Kinney (Kinney Consulting)
Slide 4
802.15 WG Letter Ballot Results – P802.15.9ma
Ballot ID | Ballot Close Date | Title | Ballot Type | Pool | Return | %Return | Abstain | %Abstain | Approve | Disapprove | %Approve
178 | 17-Sep-2020 | Technical Letter Ballot for P802.15.9ma/D01 | Technical | 92 | 47 | 51.1% | 10 | 21.3% | 35 | 2 | 94.6%
180 | 8-Oct-2020 | First recirculation draft, P802.15.9ma/D02 | Recirculation | 92 | 48 | 52.2% | 11 | 22.9% | 37 | 0 | 100%
Notes: doc.: IEEE 802.11-yy/xxxxr0
Month Year
John Doe, Some Company
Page 4

## Slide 5
802.15 WG Letter Ballot Comments – P802.15.9ma
November 2020
Pat Kinney (Kinney Consulting)
Slide 5
Ballot ID | Ballot Close Date | Title | Total Number of Comments received (Yes and No votes)
178 | 17-Sep-2020 | Technical Letter Ballot for P802.15.9ma/D01 | 91 (34 T, 57 E)
180 | 8-Oct-2020 | First recirculation draft, P802.15.9ma/D02 | 0 (0 T, 0 E)
Total |  |  | 91 (34 T, 57 E)
Notes: doc.: IEEE 802.11-yy/xxxxr0
Month Year
John Doe, Some Company
Page 5

## Slide 6
IEEE-SA Mandatory Editorial Coordination
Mandatory Editorial Coordination (MEC) completed in the final report doc.: IEEE 802.15-20/XXX:
Slide 6
Pat Kinney (Kinney Consulting)
November 2020

## Slide 7
Unsatisfied Technical comments by “No” voting commenter (0 must-be-satisfied comments received in LB180) No unsatisfied comments, no No votes in LB180
November 2020
Pat Kinney (Kinney Consulting)
Slide 7
Voter | 178 | 180 |  |  |  | Total
Total |  |  |  |  |  | 
Notes: doc.: IEEE 802.11-yy/xxxxr0
Month Year
John Doe, Some Company
Page 7

## Slide 8
Unsatisfied Technical Comments in Categories (No must-be-satisfied comments received in LB180) No unsatisfied comments, no No votes in LB180
November 2020
Pat Kinney (Kinney Consulting)
Slide 8
Notes: doc.: IEEE 802.11-yy/xxxxr0
Month Year
John Doe, Some Company
Page 8

## Slide 9
Unsatisfied comments (No must-be-satisfied comments received in LB180) No unsatisfied comments, no No votes in LB180
Slide 9
November 2020
Pat Kinney (Kinney Consulting)

## Slide 10
TG9ma Timeline
November 2020
Pat Kinney (Kinney Consulting)
Slide 10
 | Open | Close
First SA Ballot | Dec. 7, 2020 | Jan 11, 2021
Second SA Ballot | Feb 1, 2021 | Feb 16, 2021
Third SA Ballot | Apr 1, 2021 | Apr 16 2021
EC to Revcom | Jun 2021 | 
Revcom to SB | Jul 2021 | 
Notes: doc.: IEEE 802.11-yy/xxxxr0
Month Year
John Doe, Some Company
Page 10