## Slide 1
Project: IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
  Submission Title: NG-UWB Road to PAR and CSD Approval
  Date Submitted: February 22, 2021
  Source: Clint Powell (Facebook)
  Address: []
  Voice: +1 480 586-8457, E-Mail:[cpowell@ieee.org]
  Re: PAR and CSD Approval
  Abstract: PAR and CSD Submission Deadlines for 2021
  Purpose: Opportunities for Submission
  Notice: This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
  Release: The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Slide 2
PAR & CSD APPROVAL WORKING BACKWARDS
NesCom/RevCom Approval at Following Mtgs.
  Mtg. Date Submission Date to Get on Agenda*
  NesCom/RevCom: 4/28 Submission by 3/18
  NesCom/RevCom: 6/15 Submission by 5/6
  SASB Series: 9/21 - 9/23 Submission by 8/13
  NesCom/RevCom: 10/22 Submission by 9/10
  SASB: 12/6 - 12/8 Submission by 10/18
  * To get on the NesCom/RevCom Mtg. agenda submission may be provisional (that it is approved by 802 EC before hear at the mtg.), but NesCom/RevCom will not hear it unless it has been approved by the 802 EC.
EC Approval at Following Mtgs. (Opening 802 EC Plenary)*
  Mtg. Date Submission Date to Get on Agenda
  July 11-16 Submission by 6/11
  November 14-19 Submission by 11/16
  * If the 802 EC suspends their regular rules there may be additional opportunities at the monthly EC calls, which occur on the 1st Tues. of the month., in which case the submission deadline would be 30 days prior to the monthly call.
802.15 WG Approval
  At any meeting or via. ballot

## Slide 3
PAR & CSD APPROVAL WORKING BACKWARDS
In summary:
Without the 802 EC suspending the rules, the earliest scenario is the following:
  802.15 WG Approves PAR & CSD and Submits before 6/11 to be on July 802 EC Mtg Agenda
  802 EC Reviews and then Approves PAR & CSD during July 802 EC Plenary
  PAR & CSD is Submitted before 8/13 to be on RevCom 9/21 - 9/23 Series Agenda
  RevCom Reviews and then Approves PAR & CSD during 9/21 - 9/23 Series
With the 802 EC suspending the rules, the earliest unlikely scenario is the following:
  802.15 WG Approves PAR & CSD and Submits before 3/2 to be on 4/6 802 EC Call Agenda
  (the 802 EC would not have suspended the rules by then, so might not take the submission)
  PAR & CSD is Submitted before 3/18 to Provisionally be on RevCom 4/28 Call Agenda
  802 EC Reviews and then Approves PAR & CSD during 4/6 Call
  RevCom Reviews and then Approves PAR & CSD during 4/28 Call
With the 802 EC suspending the rules, the earliest likely scenario is the following:
  802.15 WG Approves PAR & CSD and Submits before 4/6 to be on 5/4 802 EC Call Agenda
  802 EC Reviews and then Approves PAR & CSD during 5/4 Call
  PAR & CSD is Submitted before 5/6 to be on RevCom 6/15 Call Agenda
  RevCom Reviews and then Approves PAR & CSD during 6/15 Call