## Slide 1
Project: IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Submission Title: SG4ab Timeline Options
Source: Carlos Aldana (Facebook), Chunyu Hu (Facebook), Chitto Ghosh (Facebook)
Address : []
E-Mail: [caldana (at) fb.com, chunyuhu (at) fb.com, chittabrata (at) fb.com]
Re: Study Group 4ab: UWB Next Generation
Abstract: Proposal of 3 possible timelines
Purpose: To receive input from the group
Notice: This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.
Notes: Jul 12, 2010
Page 1

## Slide 2: Timeline Based on .4z
In [1], an accelerated timeline was presented that seemed very aggressive.
We would like to present different options for the group’s considerations.
3 options presented:
  Option 1: 12 months for 1st LB
  Option 2: 16 months for 1st LB
  Option 3: 18 months for 1st LB

## Slide 3: Option 1 [1]
2025
2023
2022
2021
2024
.4ab 1st LB
(5/22)
Study Group
Launch
(3/21)
TGD (3/21 - 7/21)
TGD
.4ab Pre Draft
(1/22)
Task Group
Launch
(9/21)
.4ab LB Rcrc1
(9/22)
.4ab LB Rcrc2*
(1/23)
.4ab 1st SB
(5/23)
.4ab SB Rcrc1
(9/23)
.4ab SB Rcrc2*
(1/24)
.4ab Publish
(~June 24)
Finish Work 3/24
DRAFT DEV
TGD (7/21 - 3/22)
* 3rd recirc might be needed (TBD)
Slide 3

## Slide 4: Option 2
2025
2023
2022
2021
2024
TGD (3/21 - 7/21)
Study Group
Launch
(3/21)
TGD
Task Group
Launch
(9/21)
DRAFT DEV
TGD (7/21 - 7/22)
Finish Work 7/24
.4ab 1st LB
(9/22)
.4ab Pre Draft
(5/22)
.4ab LB Rcrc1
(1/23)
.4ab LB Rcrc2*
(5/23)
.4ab 1st SB
(9/23)
.4ab SB Rcrc1
(1/24)
.4ab SB Rcrc2*
(5/24)
.4ab Publish
(~October 24)
* 3rd recirc might be needed (TBD)
Slide 4

## Slide 5: Option 3
2025
2023
2022
2021
2024
Finish Work 9/24
.4ab 1st LB
(11/22)
.4ab Pre Draft
(7/22)
.4ab LB Rcrc1
(3/23)
.4ab LB Rcrc2*
(7/23)
.4ab 1st SB
(11/23)
.4ab SB Rcrc1
(3/24)
.4ab SB Rcrc2*
(7/24)
.4ab Publish
(~Dec 24)
* 3rd recirc might be needed (TBD)
Study Group
Launch
(3/21)
TGD
Task Group
Launch
(9/21)
DRAFT DEV
TGD (7/21 - 9/22)
TGD (3/21 - 7/21)

## Slide 6: Strawpoll
We support to adopt the timeline labeled as :
Option 1
Option 2
Option 3
Option 1/2/3/Abstain (multiple votes allowed)

## Slide 7: Reference
[1] 15-21-209-00 4ab Timeline

## Slide 8: Questions?