## Slide 1
Project: IEEE P802.15 Working Group for Wireless Specialty Networks (WSN)
Submission Title: Licensed Narrowband Amendment TG16t May 2021 Interim Meeting Closing Report
Date Submitted: 2021-05-18
Source: Tim Godfrey, EPRI
Abstract: Closing Report
Purpose: Closing Report for task group meeting
Notice: This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Slide 2: TG16t Meetings during May Interim
Two Meetings May 12 PM1 and May 18 PM1

## Slide 3: Contributions for May Interim
2-May-2021 ET | 2020 | 213 | 8 | TG16t | IEEE 802.16t Use Cases | Daoud Serang (CML Microcircuits) | 12-May-2021 13:04:58 ET | 
18-May-2021 ET | 2021 | 306 | 0 | TG16t | 16t System Description Document | Menashe Shahar (Ondas) | 18-May-2021 11:58:57 ET | Download
17-May-2021 ET | 2021 | 97 | 8 | TG16t | 16t System Requirements Document | Juha Juntunen (Meteorcomm) | 17-May-2021 15:57:00 ET | Download
May 12
May 18

## Slide 4: Discussion on Use Cases
Updated Use Cases document submitted: Doc 15-20-213r9
  Split throughput into column for PHY layer and Goodput
  The goal is to eventually add “goodput” to all use cases. It drives the technical design.
Update to SRD – Doc 15-21-097r8
  Need the PHY-only use cases to describe their use cases in terms of goodput.
  Daoud will update the use cases document to r9.

## Slide 5: Development of the SDD
Contributions
  Menashe provides initial SDD version for review as document 15-21-306r0 week of 5/18.
Discussion on the term Sector from contribution 21-217r0 on 5/11
Continued discussion on 5/18 (15-21-306r0)
  Menashe’s view on the term “sector” – use it because a base station can have multiple sectors. It is the controlling entity for all remotes. Sector is a smaller building block than base station.

## Slide 6: 5/18 discussion on SDD V1.0 in doc 15-21-306r0
Adopt SDD draft document 15-21-306r0 as baseline SDD for further development.
  Approved with unanimous consent.

## Slide 7: Technical Editor
Volunteers for editor are sought
IEEE 802 has developed a process for providing licenses for Framemaker to editors

## Slide 8: Revised Project Timeline
Milestone | Date | Updated Date
Task Group Start | January 2020 | 
SRD Approval | Nov 2020 | April 2021
SDD Approval | May 2021 | Sept 2021
Informal TG review of draft | Sept 2021 | Jan 2022
Working Group Letter Ballot | Nov 2021 | March 2022
Working Group Recirculation Letter Ballot | Mar 2022 | July 2022
SA Ballot | Sept 2022 | Jan 2023
Forward to RevCom | March 2023 | July 2023
Request PAR Extension
Assign Editor

## Slide 9: Teleconference Planning
June Teleconference
  Thursday, June 10 11am PT, 2pm ET

## Slide 10: Closing
Actions
  Call for Contributions for SDD Remains open
  Daoud will reach out to original suppliers of data to get goodput values.
  Juha will update throughput diagram in SRD with linear scale. Will make further updates as new “goodput” data becomes available.