## Slide 1: IEEE 802.15 TG13 Multi-Gbit/s Optical Wireless Communication July 2021 Closing Report
Date: 2021-07-20
Author:

## Slide 2
This presentation contains the IEEE 802.15 TG13 Multi- Gbit/s Optical Wireless Communication Meeting Slides for the July 2021 virtual meeting.
Abstract

## Slide 3
Agenda in doc. 15-21/0368r3
Wednesday, 14 July, 1-3 p.m., PM1
  Motion on agenda, May minutes and CRG Telcos
  Motion to reconfirm CRG
  Preview on D5.0, discuss main open topics
Thursday 15 July, 1-3 p.m., PM1
  doc. 15-21/0339r3
  comments resolution against D4.0
Tuesday 20 July, 1-3 p.m., PM1
  finish comments resolution against D4.0
  discuss if to start recirculation
  plan the CRG telcos,
  plan one telco as TG to discuss doc. 18-21/0080r0 and invite 802.15 WG
  AoB
TG13 activities this week

## Slide 4: TG13 Draft Status
TG13 draft passed the SA ballot
314 comments in total (112 technical, 193 editorial, 9 general)
most comments have been addressed, except the ones on relaying
changes make it hard to oversee the implications on the draft
Technical Editor will create a new prelimiary draft by August 6
CRG will review the draft and include last changes on relaying
1st SA ballot recirculation will start in mid of August
Comments to be resolved in September

## Slide 5: Plan for finalization of TG13 Spec
New draft D5.0 is planned for Aug. 20
  D5.0 will be a preliminarly draft
  Editorial changes maybe needed by CRG before recirculation  D5.1
  Technical changes will be introduced via recirc and comment resolution
  Lennert will be back on Sept. 6
  Draft will be into recirculation during September meeting
  3 more recircs are expected (3rd w/o changes)
  1st recirc finished in September, resolve comments in October
  2nd recirc in November
  3rd recirc (no more changes) in December (Plenary)
  go to REVCOM out of December

## Slide 6: Plan for finalization of TG13 Spec
TG13 CRG Telco dates
  2 Aug. 2021, 11-13 CET (5-7 ET, 18-20 KT)
  9 Aug. 2021, 11-13 CET (5-7 ET, 18-20 KT)
  16 Aug. 2021, 11-13 CET (5-7 ET, 18-20 KT)
  23 Aug. 2021, 11-13 CET (5-7 ET, 18-20 KT): joint meeting with TG7a on ITU-R request in doc. 18-21/0080r0
  30 Aug. 2021, 11-13 CET (5-7 ET, 18-20 KT)
  06 Sept 2021, 11-13 CET (5-7 ET, 18-20 KT)

## Slide 7: TG Motion to reconfirm CRG
Move to request that 802.15 WG approves the formation of a Comment Resolution Group (CRG) for the Standards Association balloting of the P802.15.13_D5 with the following membership: Volker Jungnickel as Chair, Chong Han, Tuncer Baykas, Sang-Kyu Lim, Tero Kivinen. The 802.15.13 CRG is authorized to approve comment resolutions, edit the draft according to the comment resolutions, and to approve the start of recirculation ballots of the revised draft on behalf of the 802.15 WG. Comment resolution on recirculation ballots between sessions will be conducted via reflector email and via teleconferences announced to the reflector as per the LMSC 802 WG P&P.
  Moved: Tuncer Baykas
  Second: Sang-Kyu Lim
  Result: Motion passed unanimously.

## Slide 8: WG Motion to reconfirm CRG
Move that 802.15 WG approves the formation of a Comment Resolution Group (CRG) for the Standards Association balloting of the P802.15.13_D5 with the following membership: Volker Jungnickel as Chair, Chong Han, Tuncer Baykas, Sang-Kyu Lim, Tero Kivinen. The 802.15.13 CRG is authorized to approve comment resolutions, edit the draft according to the comment resolutions, and to approve the start of recirculation ballots of the revised draft on behalf of the 802.15 WG. Comment resolution on recirculation ballots between sessions will be conducted via reflector email and via teleconferences announced to the reflector as per the LMSC 802 WG P&P.
  Moved: Volker Jungnickel
  Second: Rick Alfvin
  Result:

## Slide 9: WG Motion to extend the PAR
Move that 802.15 WG approves the formation of a Comment Resolution Group (CRG) for the Standards Association balloting of the P802.15.13_D5 with the following membership: Volker Jungnickel as Chair, Chong Han, Tuncer Baykas, Sang-Kyu Lim, Tero Kivinen. The 802.15.13 CRG is authorized to approve comment resolutions, edit the draft according to the comment resolutions, and to approve the start of recirculation ballots of the revised draft on behalf of the 802.15 WG. Comment resolution on recirculation ballots between sessions will be conducted via reflector email and via teleconferences announced to the reflector as per the LMSC 802 WG P&P.
  Moved: Volker Jungnickel
  Second: Rick Alfvin
  Result: