## IEEE_Cover
January 2021 |  | 15-21-0524-09-0013
IEEE P802.15
Wireless Specialty Networks
Project | IEEE P802.15.13
Title | TG13 SA-Recirculation 1 Comments
Date Submitted | January 03 2021
Source | Kai Lennert Bober (Fraunhofer HHI) | E-mail: bober@ieee.org
Re:
Abstract | This document contains the comments from recirculation one.
Purpose | Aid the comment resolution in the SA-Ballot of IEEE P802.15.13
Notice | This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## SA-Ballot Comments
Comment ID | Date | Comment # | Name | Email | Phone | Style | Index # | Classification | Vote | Affiliation | Category | Page | Subclause | Line | Comment | File | Must be Satisfied | Proposed Change | Disposition Status | Disposition Detail | Same resolution | Assignee | Notes | TE Comment | ACCEPTED | REJECTED | REVISED
286481 | 16-Sep-2021 15:46:35 UTC-12 | R1-1 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 1 | General Interest | Disapprove | Self Employed | Editorial | 18 | 2 | 9 | I do not think we need dated version for the normative reference to the 802.15.4. We do need to use date version when we refer to some subclause or similar from the 802.15.4-2020, but I think here the undated version is better. |  | No | Change 802.15.4-2020 to be undated version. | ACCEPTED |  |  |  |  | implemented
286490 | 16-Sep-2021 15:46:35 UTC-12 | R1-10 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 9 | General Interest | Disapprove | Self Employed | Editorial | 34 | 5.7.3 | 6 | There is term clause missing. |  | No | Change "specified in 11" to "specified in clause 11". | REVISED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286652 | 23-Sep-2021 21:24:14 UTC-12 | R1-100 | Lim, Sang-Kyu | sklim@etri.re.kr |  | Ballot | 11 | Research | Approve | Electronics and Telecommunications Research Institute (ETRI) | Editorial | 62 | 6.9.5 | 1 | Figure 27 |  | No | The left-side symbols indicate the light sources, and the right-side symbols indicate the photo-detectors. So, use the dashed arrows between light sources and detectors instead of dashed lines in order to show the signal directions. | REVISED | Add an arrow to the wireless propagation line going from left to right (i.e. from light source to photodiode). This type of spatial multiplexing MIMO is not yet supported in the standard. For now, OFEs need to be spatially separated (i.e. through distance or a wall) in order to transmit and receive multiple data streams correctly. Thus, remove the crossing propagation lines (i.e. from source 1 to pd 2 and from source 2 to pd 1). Possibly indicate some distance or wall between the both paths. |  |  |  | implemented
286653 | 23-Sep-2021 21:24:14 UTC-12 | R1-101 | Lim, Sang-Kyu | sklim@etri.re.kr |  | Ballot | 12 | Research | Approve | Electronics and Telecommunications Research Institute (ETRI) | Editorial | 71 | 7.5 | 1 | "other" in Table 4 |  | No | Change "other" to "others". | ACCEPTED |  |  |  |  | implemented
286654 | 23-Sep-2021 21:24:14 UTC-12 | R1-102 | Lim, Sang-Kyu | sklim@etri.re.kr |  | Ballot | 13 | Research | Approve | Electronics and Telecommunications Research Institute (ETRI) | Technical | 82 | 7.6.20 | 15 | In regard to "optical clock rates (OCRs)", please see my comment #5. |  | No | Change "optical clock rates (OCRs)" to "clock rates". | REVISED | Remove the term "(optical) clock rate" generally. Use "clock rate" in the PM-PHY Use "bandwidth" in the HB-PHY | R1-93 R1-102 R1-103 R1-114 R1-118 |  |  | implemented
286655 | 23-Sep-2021 21:24:14 UTC-12 | R1-103 | Lim, Sang-Kyu | sklim@etri.re.kr |  | Ballot | 14 | Research | Approve | Electronics and Telecommunications Research Institute (ETRI) | Technical | 82 | 7.6.20 | 16 | In regard to "OCR", please see my comment #5. |  | No | Change "OCR" to "clock rate". | REVISED | Remove the term "(optical) clock rate" generally. Use "clock rate" in the PM-PHY Use "bandwidth" in the HB-PHY | R1-93 R1-102 R1-103 R1-114 R1-118 |  |  | implemented
286656 | 23-Sep-2021 21:24:14 UTC-12 | R1-104 | Lim, Sang-Kyu | sklim@etri.re.kr |  | Ballot | 15 | Research | Approve | Electronics and Telecommunications Research Institute (ETRI) | Editorial | 85 | 7.6.23 | 1 | Acknowledged Transmission in Table 12 |  | No | Change "Acknowledged Transmission" in Table 12 to "Acknowledged transmission" for style consistency. | ACCEPTED |  |  |  |  | implemented
286657 | 23-Sep-2021 21:24:14 UTC-12 | R1-105 | Lim, Sang-Kyu | sklim@etri.re.kr |  | Ballot | 16 | Research | Approve | Electronics and Telecommunications Research Institute (ETRI) | Editorial | 87 | 7.6.25 | 1 | "other" in Table 14 |  | No | Change "other" to "others". | ACCEPTED |  |  |  |  | implemented
286658 | 23-Sep-2021 21:24:14 UTC-12 | R1-106 | Lim, Sang-Kyu | sklim@etri.re.kr |  | Ballot | 17 | Research | Approve | Electronics and Telecommunications Research Institute (ETRI) | Editorial | 88 | 7.6.28 | 13 | Style in figure caption of Figure 68 |  | No | "Element" in figure caption of Figure 68 should be changed to "element" for style consistency. | ACCEPTED |  |  |  |  | implemented
286659 | 23-Sep-2021 21:24:14 UTC-12 | R1-107 | Lim, Sang-Kyu | sklim@etri.re.kr |  | Ballot | 18 | Research | Approve | Electronics and Telecommunications Research Institute (ETRI) | Editorial | 89 | 7.6.29 | 1 | Style in figure caption of Figure 69 |  | No | "Element" in figure caption of Figure 69 should be changed to "element" for style consistency. | ACCEPTED |  |  |  |  | implemented
286660 | 23-Sep-2021 21:24:14 UTC-12 | R1-108 | Lim, Sang-Kyu | sklim@etri.re.kr |  | Ballot | 19 | Research | Approve | Electronics and Telecommunications Research Institute (ETRI) | Editorial | 89 | 7.6.29 | 4 | Style in table caption of Table 15 |  | No | I'm not sure, but I think "codes" in table caption of Table 15 should be changed to "Codes" for style consistency. Please check it again. | REVISED | Change P89L2 "Status…"into "Values for the Status Code field are listed in Table 15." Change caption of Table 15 into "Values of the Status Code field of the Relay Device Configuration Response element" |  |  |  | implemented
286661 | 23-Sep-2021 21:24:14 UTC-12 | R1-109 | Lim, Sang-Kyu | sklim@etri.re.kr |  | Ballot | 20 | Research | Approve | Electronics and Telecommunications Research Institute (ETRI) | Editorial | 89 | 7.6.30 | 11 | Style in figure caption of Figure 70 |  | No | "Element" in figure caption of Figure 70 should be changed to "element" for style consistency. | ACCEPTED |  |  |  |  | implemented
286491 | 16-Sep-2021 15:46:35 UTC-12 | R1-11 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 10 | General Interest | Disapprove | Self Employed | Editorial | 34 | 5.7.4 | 15 | There is term clause missing. |  | No | Change "specified in 12" to "specified in clause 12". | ACCEPTED |  |  |  |  | implemented
286662 | 23-Sep-2021 21:24:14 UTC-12 | R1-110 | Lim, Sang-Kyu | sklim@etri.re.kr |  | Ballot | 21 | Research | Approve | Electronics and Telecommunications Research Institute (ETRI) | Editorial | 90 | 7.6.31 | 1 | Style in figure caption of Figure 71 |  | No | "Element" in figure caption of Figure 71 should be changed to "element" for style consistency. | ACCEPTED |  |  |  |  | implemented
286663 | 23-Sep-2021 21:24:14 UTC-12 | R1-111 | Lim, Sang-Kyu | sklim@etri.re.kr |  | Ballot | 22 | Research | Approve | Electronics and Telecommunications Research Institute (ETRI) | Editorial | 90 | 7.6.31 | 4 | Style in table caption of Table 16 |  | No | I'm not sure, but I think "codes" in table caption of Table 16 should be changed to "Codes" for style consistency. Please check it again. | REVISED | Change P90L2 "Status…"into "Values for the Status Code field are listed in Table 16." Change caption of Table 16 into "Values of the Status Code field" |  |  |  | implemented
286664 | 23-Sep-2021 21:24:14 UTC-12 | R1-112 | Lim, Sang-Kyu | sklim@etri.re.kr |  | Ballot | 23 | Research | Approve | Electronics and Telecommunications Research Institute (ETRI) | Technical | 107 | 9.3.2 | 23 | Each PHY has its own set of PIB attributes. So, the PHY PIB attributes for the LB-PHY has been defined in Table 48 of the subclause 11.1.4, and the PHY PIB attributes for the HB-PHY has been defined in Table 52 of the subclause 12.1.4. By the way, PHY PIB attributes for the PM-PHY has not been defined in this draft. |  | No | So, the issue is that there is no need to define PHY PIB attributes for the PM-PHY or not. Please check again this issue. | REVISED | Replace the sentence "Each PHY has its own set of PIB attributes." in P107L23 with the following text: PHYs have their own PHY PIB attributes. | R1-112 R1-115 |  |  | implemented
286665 | 23-Sep-2021 21:24:14 UTC-12 | R1-113 | Lim, Sang-Kyu | sklim@etri.re.kr |  | Ballot | 24 | Research | Approve | Electronics and Telecommunications Research Institute (ETRI) | Technical | 109 | 10.1.1 | 10 | FEC code rates in Table 42 |  | No | According to 10.3.4, PM-PHY use RS(36,24) code for the header and RS(256,248) code for the payload. So, update Table 42 so that this meaning can be shown in this Table for better readability. | REVISED | Replace "RS(36,24), RS(256,248)" in the table with "Header: RS(36,24) Payload: RS(256,248)" |  |  |  | implemented
286666 | 23-Sep-2021 21:24:14 UTC-12 | R1-114 | Lim, Sang-Kyu | sklim@etri.re.kr |  | Ballot | 25 | Research | Approve | Electronics and Telecommunications Research Institute (ETRI) | Technical | 109 | 10.1.1 | 10 | In regard to "OCR", please see my comment #5. |  | No | Change "OCR" in Table 42 to "Clock rate". | REVISED | Remove the term "(optical) clock rate" generally. Use "clock rate" in the PM-PHY Use "bandwidth" in the HB-PHY | R1-93 R1-102 R1-103 R1-114 R1-118 |  |  | implemented
286717 | 24-Sep-2021 20:10:58 UTC-12 | R1-161 | Bober, Lennert | klb@posteo.de |  | Ballot | 10 | Producer - Software | Approve | Fraunhofer Heinrich Hertz Institute,Self | Editorial | 44 | 6.4 | 2 | Non-beacon-enabled is awkward as a name for a polling based MAC. |  | No | Rename NBE access to polling-based access | REVISED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286668 | 23-Sep-2021 21:24:14 UTC-12 | R1-116 | Lim, Sang-Kyu | sklim@etri.re.kr |  | Ballot | 27 | Research | Approve | Electronics and Telecommunications Research Institute (ETRI) | Technical | 111 | 10.2.5 | 21 | "as described in 10.2.7." |  | No | It should be changed to "as described in 10.2.8." because MCS IDs are defined in Table 44 of 10.2.8. | ACCEPTED |  |  |  |  | implemented
286669 | 23-Sep-2021 21:24:14 UTC-12 | R1-117 | Lim, Sang-Kyu | sklim@etri.re.kr |  | Ballot | 28 | Research | Approve | Electronics and Telecommunications Research Institute (ETRI) | Editorial | 111 | 10.2.6 | 28 | "ith OFE" |  | No | "ith" should be written in italic. | ACCEPTED |  |  |  |  | implemented
286670 | 23-Sep-2021 21:24:14 UTC-12 | R1-118 | Lim, Sang-Kyu | sklim@etri.re.kr |  | Ballot | 29 | Research | Approve | Electronics and Telecommunications Research Institute (ETRI) | Technical | 112 | 10.2.7 | 8 | In regard to "OCR", please see my comment #5. |  | No | Change "OCR" on this line to "clock rate". | REVISED | Remove the term "(optical) clock rate" generally. Use "clock rate" in the PM-PHY Use "bandwidth" in the HB-PHY | R1-93 R1-102 R1-103 R1-114 R1-118 |  |  | implemented
286671 | 23-Sep-2021 21:24:14 UTC-12 | R1-119 | Lim, Sang-Kyu | sklim@etri.re.kr |  | Ballot | 30 | Research | Approve | Electronics and Telecommunications Research Institute (ETRI) | Technical | 122 | 11.2.5.2 |  | The Relaying Enabled field is shown in Figure 79. However, the text or description on this field is not shown in text body of 11.2.5.2. |  | No | Add the text or description on this field to the text body of 11.2.5.2. | REVISED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286492 | 16-Sep-2021 15:46:35 UTC-12 | R1-12 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 11 | General Interest | Disapprove | Self Employed | Technical | 36 | 6.2.3 | 15 | I think that for acknowledged transmissions the sequence numbers will be assigned, not just may be assigned. Actually 6.8.1 says that all MPDUs except control frames are assigned sequence number. |  | No | I would simply change the text to refer 6.8, i.e. change text to say "Sequence numbers are assigned to MPDUs as described in 6.8.". | ACCEPTED |  |  |  |  | implemented
286672 | 23-Sep-2021 21:24:14 UTC-12 | R1-120 | Lim, Sang-Kyu | sklim@etri.re.kr |  | Ballot | 31 | Research | Approve | Electronics and Telecommunications Research Institute (ETRI) | Technical | 132 | 11.3.3.1 | 11 | In Figure 88, x-axis and y-aixs lines are too bold. The title of y-axis should be " Light Intensity". The font size of titles for x-axis and y-axis is too big. "Data signal" should be changed to "Data Signal". The text "Operation Point" is overlapped with a line. The things that the preamble and the data signal in Figure 88 mean are not clear. |  | No | Based on this comment, redraw Figure 88. | REVISED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286673 | 23-Sep-2021 21:24:15 UTC-12 | R1-121 | Lim, Sang-Kyu | sklim@etri.re.kr |  | Ballot | 32 | Research | Approve | Electronics and Telecommunications Research Institute (ETRI) | Technical | 134 | 11.3.3.2 | 1 | Figure 90 |  | No | Redraw Figure 90 in the same style as Figure 88. When redrawing this, the difference between Figure 88 and Figure 90 should be clear for better visiblity and understanding. | REVISED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286674 | 23-Sep-2021 21:24:15 UTC-12 | R1-122 | Lim, Sang-Kyu | sklim@etri.re.kr |  | Ballot | 33 | Research | Approve | Electronics and Telecommunications Research Institute (ETRI) | Editorial | 159 | 12.3.2.4 | 22 | Font style of the equation |  | No | Use the Italic font style in the equation. | ACCEPTED |  |  |  |  | implemented
286675 | 23-Sep-2021 21:24:15 UTC-12 | R1-123 | Lim, Sang-Kyu | sklim@etri.re.kr |  | Ballot | 34 | Research | Approve | Electronics and Telecommunications Research Institute (ETRI) | Editorial | 159 | 12.3.2.4 | 23 | Font style of the equation |  | No | Use the Italic font style in the equation. | ACCEPTED |  |  |  |  | implemented
286676 | 23-Sep-2021 21:24:15 UTC-12 | R1-124 | Lim, Sang-Kyu | sklim@etri.re.kr |  | Ballot | 35 | Research | Approve | Electronics and Telecommunications Research Institute (ETRI) | Editorial | 159 | 12.3.2.4 | 28 | Font style of the equation |  | No | Use the Italic font style in the equation. | ACCEPTED |  |  |  |  | implemented
286677 | 23-Sep-2021 21:24:15 UTC-12 | R1-125 | Lim, Sang-Kyu | sklim@etri.re.kr |  | Ballot | 36 | Research | Approve | Electronics and Telecommunications Research Institute (ETRI) | Editorial | 172 |  | 3 | Caption style |  | No | Change "Protocol implementation conformance statement (PICS) proforma" to "Protocol Implementation Conformance Statement (PICS) Proforma" for style consistency. | REVISED | Make sure that all clause titles are not capitalized arbitraily. |  |  |  | implemented
286682 | 24-Sep-2021 09:01:08 UTC-12 | R1-126 | Thomas, Angela | a.n.thomas@ieee.org |  | RAC Coordination | 1 |  | N/a |  | Technical | 20 | 3.2 | 11 | "Organizationally Unique Identifier" and "Company ID" are specified as RA assignments and should be capitalized per RA usage. |  | Yes | capitalize "Company ID" | ACCEPTED |  |  |  |  | implemented
286683 | 24-Sep-2021 09:01:08 UTC-12 | R1-127 | Thomas, Angela | a.n.thomas@ieee.org |  | RAC Coordination | 2 |  | N/a |  | Technical | 21 | 3.2 | 18 | "Organizationally Unique Identifier" and "Company ID" are specified as RA assignments and should be capitalized per RA usage. |  | Yes | capitalize "Organizationally Unique Identifier" | ACCEPTED |  |  |  |  | implemented
286684 | 24-Sep-2021 09:01:08 UTC-12 | R1-128 | Thomas, Angela | a.n.thomas@ieee.org |  | RAC Coordination | 3 |  | N/a |  | Technical | 87 | 7.2.26 | 9 | It seems that "organizationally unique identifier" should be "Vendor Identifier", since tha is the parameter in the figure and the text. |  | No | Change "organizationally unique identifier" to "Vendor Identifier" | ACCEPTED |  |  |  |  | implemented
286685 | 24-Sep-2021 09:01:08 UTC-12 | R1-129 | Thomas, Angela | a.n.thomas@ieee.org |  | RAC Coordination | 4 |  | N/a |  | Technical | 87 | 7.2.26 | 10 | It seems that the title of Figure 66 should be "Vendor Specific element", since that is the title of the subclause and used in the text. |  | No | Change "Figure 66 Variable Element Container element" to "Figure 66 Vendor Specific element" | ACCEPTED |  |  |  |  | implemented
286493 | 16-Sep-2021 15:46:36 UTC-12 | R1-13 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 12 | General Interest | Disapprove | Self Employed | Editorial | 36 | 6.2.3 | 16 | I do not think should is correct term here. |  | No | Change "should be buffered" to "are buffered". | ACCEPTED |  |  |  |  | implemented
286686 | 24-Sep-2021 09:01:08 UTC-12 | R1-130 | Thomas, Angela | a.n.thomas@ieee.org |  | RAC Coordination | 5 |  | N/a |  | Technical | 88 | 7.2.26 | 1 | "Organizationally Unique Identifier" and "Company ID" are specified as RA assignments and should be capitalized per RA usage. |  | Yes | Change sentence to "A 24-bit Organizationally Unique Identifier (OUI) or Company ID (CID) allocated to the vendor.5" | ACCEPTED |  |  |  |  | implemented
286687 | 24-Sep-2021 18:44:18 UTC-12 | R1-131 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 52 | General Interest | Disapprove | Self Employed | Technical | 25 | 5.2 | 26 | In section 6.2.2 there is text which says that OWPAN identifier is the MAC Address of the coordinator, so this is not outside the scope of this standard. |  | No | I suggest removing last sentence here and adding reference to 6.2.2. | REVISED | Replace sentence "The mechanism by…." with "The OWPAN ID is selected as described in X" where X is the relevant subclause. |  |  |  | implemented
286688 | 24-Sep-2021 18:44:19 UTC-12 | R1-132 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 53 | General Interest | Disapprove | Self Employed | Editorial | 50 | 6.4.4 | 8 | How does the receiver know which frames the Poll ACK Field and the High-reliability control header acknowledge? The poll ACK field has compressed sequence number, but high reliability header does not, and the device has no way of knowing which of the frames this ACK acknowledges. I mean if coordinators sends data frames d1_1, d1_2, d1_1, d1_2 (i.e., retransmitting both frames twice), and then finally device manages to get one of them (lets day d1_1, but does not see the frame before last d1_2 so it does not even know it should have responded, so then when coordinator sends next frame to device, the device will acknowledge a frame, and device thinks it is acking d1_1, but coordinator thinks it is d1_2. |  | No | Specify how this is supposed to work. | REVISED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286689 | 24-Sep-2021 18:44:19 UTC-12 | R1-133 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 54 | General Interest | Disapprove | Self Employed | Technical | 42 | 6.3.6 | 8 | When are these gts descriptor unicast frames sent? In the cap or in the cfp? |  | Yes | Add description when the gts signaling is done. | REVISED | Change sentence in P38L26 as follows: The CAP shall only be used for transmissions from devices to the coordinator in the Change the sentence in L42L9 "These control frames shall be unicasts and only be received by the devices for which the GTS allocations are designated." to These control frames shall be unicasts within the CFP and only be received by the devices for which the GTS allocations are designated. |  |  |  | implemented
286690 | 24-Sep-2021 18:44:19 UTC-12 | R1-134 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 55 | General Interest | Disapprove | Self Employed | Editorial | 57 | 6.8.1 | 5 | The text may be assigned sequence number is not needed here and is confusing. |  | No | Remove that part and just say may be acknowledged. | ACCEPTED |  |  |  |  | implemented
286691 | 24-Sep-2021 18:44:19 UTC-12 | R1-135 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 56 | General Interest | Disapprove | Self Employed | Technical | 67 | 7.2.2 | 5 | Relay control field is not defined in this standard. |  | No | Add description of the relay control field | REVISED | Add a new subclause 7.2.4 Relay Control field with the following contents: This field contains the MAC address of the relay device if the data frame is exchanged through a relay link between coordinator and relayed device. It is only present if the Relayed Frame field in of the Frame Control field is one. Otherwise, the field does not exist |  |  |  | implemented
286692 | 24-Sep-2021 18:44:19 UTC-12 | R1-136 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 57 | General Interest | Disapprove | Self Employed | Technical | 68 | 7.2.3 | 1 | Why use compessed addresses? The full aid is just 16 bits and full sequence number is 12 bit, thus sending full size of them does not waste that many bytes. |  | No | Change to send full aid and sequence number. | REVISED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286693 | 24-Sep-2021 18:44:19 UTC-12 | R1-137 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 58 | General Interest | Disapprove | Self Employed | Technical | 84 | 7.6.22 | 4 | What is the time resolution of the interval? Microseconds? |  | Yes | Define the time resolution. | REVISED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286694 | 24-Sep-2021 18:44:19 UTC-12 | R1-138 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 59 | General Interest | Disapprove | Self Employed | Technical | 84 | 7.6.22 | 8 | How is this field encoded? |  | Yes | Define the encoding of the capability information field. | REVISED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286695 | 24-Sep-2021 18:44:19 UTC-12 | R1-139 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 60 | General Interest | Disapprove | Self Employed | Editorial | 91 | 8.1 | 8 | Section number missing. |  | No | Fix the reference | ACCEPTED |  |  |  |  | implemented
286494 | 16-Sep-2021 15:46:36 UTC-12 | R1-14 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 13 | General Interest | Disapprove | Self Employed | Technical | 41 | 6.3.5 | 16 | Duplicate with the text on line 31. Perhaps one of them can be removed. |  | No | Remove this sentence, and keep the one on line 31. | ACCEPTED |  |  |  |  | implemented
286696 | 24-Sep-2021 18:44:19 UTC-12 | R1-140 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 61 | General Interest | Disapprove | Self Employed | Technical | 91 | 8.2.1 | 18 | Should we have .confirm for MPCS-DATA operation which would tell whether the frame was acknowledged or not? |  | No | Add .confirm primitive. | REJECTED | The group decided to follow the basic service definition of 802.1AC and 802.3, where no confirm primitive is present. |  |  |  | implemented
286697 | 24-Sep-2021 18:44:19 UTC-12 | R1-141 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 62 | General Interest | Disapprove | Self Employed | Editorial | 93 | 8.3.3.1 | 9 | Typo change ”are no coordinator” to ”are not a cordinator”. |  | No | As described in comment | ACCEPTED |  |  |  |  | implemented
286698 | 24-Sep-2021 18:44:19 UTC-12 | R1-142 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 63 | General Interest | Disapprove | Self Employed | Technical | 105 | 8.5 | 4 | We do not have any capabilities that require others, so why not remove the sentence stating that can have such, and remove the column from the table 40. |  | No | Remove feature. | ACCEPTED |  |  |  |  | implemented
286699 | 24-Sep-2021 18:44:19 UTC-12 | R1-143 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 64 | General Interest | Disapprove | Self Employed | Technical | 121 | 11.2.5.2 | 8 | I do not think the high reliablity header can be optional, so change this text to say so. |  | No | Remove two sentences talking about if high reliability header and change it to say the field is lenth of PSDU plus 8 is used. | REVISED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286700 | 24-Sep-2021 18:44:19 UTC-12 | R1-144 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 65 | General Interest | Disapprove | Self Employed | Technical | 126 | 11.2.6.4 | 3 | There is no other method of doing polling defined, then high reliability header, so it cannot be optional and the text in the beginning is wrong. |  | Yes | Fix the paragraph to specify that high reliability header is mandatory and is used to do polling. | REVISED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286701 | 24-Sep-2021 18:44:19 UTC-12 | R1-145 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 66 | General Interest | Disapprove | Self Employed | Technical | 126 | 11.2.6.4 | 12 | I assume this is compressed AID. This should be stated. |  | Yes | Specify that polled device is compressed 5 bit aid. | REVISED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286702 | 24-Sep-2021 18:44:19 UTC-12 | R1-146 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 67 | General Interest | Disapprove | Self Employed | Technical | 126 | 11.2.6.4 | 14 | I assume this is compressed AID. This should be stated. |  | Yes | Specify that next device to poll is compressed 5 bit aid. | REVISED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286703 | 24-Sep-2021 18:44:19 UTC-12 | R1-147 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 68 | General Interest | Disapprove | Self Employed | Technical | 126 | 11.2.6.4 | 16 | I assume this is compressed AID. This should be stated. |  | Yes | Specify that device to acknowledg is compressed 5 bit aid. | REVISED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286704 | 24-Sep-2021 18:45:38 UTC-12 | R1-148 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 69 | General Interest | Disapprove | Self Employed | Technical | 173 | D.3 | 1 | In table D.3 most of the entries are mandatory for beacon enabled coordinator. |  | No | Add new pics for beacon enabled and change these to be XXX1:M i.e. Being mandatory for those coordinators supporting beacon enabled mode. Same for the non-beacon enabled mode. | REVISED | Add a new item "DT2.1" with item description "The coordinator is able to maintain a beacon-enabled OWPAN". Reference "6" Status "O" Change Status of BECA1, BECA1.1, BECA2, BECA2.1, BECA2.2, BECA2.3 to "DT2.1:M" |  |  |  | implemented
286705 | 24-Sep-2021 18:45:38 UTC-12 | R1-149 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 70 | General Interest | Disapprove | Self Employed | Technical | 174 | D.3 | 1 | Table D.5 are not optional for coordinators. |  | No | Change O to DT2:M | ACCEPTED |  |  |  |  | implemented
286495 | 16-Sep-2021 15:46:36 UTC-12 | R1-15 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 14 | General Interest | Disapprove | Self Employed | Technical | 42 | 6.3.8 | 29 | Is this requirement that device needs to finish its transmissions at least TAIFS before the end of GTS still needed. We do not have device to device communications, thus all communication is between coordinator and device. As this is used only in half duplex communications and in that case the GTS will always be reserved for device to transmit to the coordinator, thus coordinator is always listening. When coordinator wants to transmit something to the device, it will do that outside all of the GTS inside the CFP. The coordinator do need to waith for at least TAIFS before sending to device whose GTS just ended, but I do not think there are other requirements for waiting. |  | No | Remove requirement that device needs to finish transmissions TAIFS before end of GTS. | REVISED | Replace the content of 6.3.8 with the following text: Devices operating in beacon-enabled channel access mode shall stay silent for a certain time after each frame transmission. That time is called the interframe space. The minimum interframe space (MIFS), depends on the PHY used for transmission. It shall be equal to the aPhyMifsDuration constant of each PHY. A transmitting device shall finish its transmissions at least MIFS before the end of the GTS in order to enable all receiving devices to utilize their GTSs from the beginning. Replace all occurrences of TAIFS with MIFS in 6.3.9. Remove TAIFS from figure 12 as it is included in the GTS Replace the description of BECA8.1 in the PICS with the following text: The entity is able to regard for the MIFS. Update the acronym description of TAIFS to MIFS Add the following PHY constant to table 43: aPhyMifsDuration Description: The duration of the MIFS for transmissions using the PM-PHY Value: 3 Unit: µs Add the following PHY constant to table 51: aPhyMifsDuration Description: The duration of the MIFS for transmissions using the HB-PHY Value: 3 Unit: µs | R1-15 R1-166 R1-167 |  |  | implemented
286706 | 24-Sep-2021 18:45:38 UTC-12 | R1-150 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 71 | General Interest | Disapprove | Self Employed | Technical | 175 | D.3 | 3 | Table D.9 ACP1.1 is only mandatory for coordinators. |  | No | Change from M to DT2:M | ACCEPTED |  |  |  |  | implemented
286519 | 16-Sep-2021 15:46:36 UTC-12 | R1-39 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 38 | General Interest | Disapprove | Self Employed | Editorial | 48 | 6.4.4 | 4 | The text "has to be acknowledged" does not match with the description on next paragraph, which says there is ACK bit in the Frame control field which controls this behavior. |  | No | Change "has to be acknowledged" to "may be acknowledged", and "every frame" to "a frame". | REVISED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286708 | 24-Sep-2021 20:10:58 UTC-12 | R1-152 | Bober, Lennert | klb@posteo.de |  | Ballot | 1 | Producer - Software | Approve | Fraunhofer Heinrich Hertz Institute,Self | Technical | 39 | 6.3.4.2 | 29 | The text for CAP retransmissions does not specify how to actually retransmit. |  | No | Add the following text after "CW shall be less or equal to macMaximumCapCw.": "For the retried transmission, BS shall be newly selected as described in 6.3.4.1." | REVISED | Add the following text after P39L30 "macMaximumCapCw.": The device may retry te failed transmission with BS being newly selected as described in 6.3.4.1. |  |  |  | implemented
286709 | 24-Sep-2021 20:10:58 UTC-12 | R1-153 | Bober, Lennert | klb@posteo.de |  | Ballot | 2 | Producer - Software | Approve | Fraunhofer Heinrich Hertz Institute,Self | Technical | 41 | 6.3.5 | 18 | Adjacent GTS could be merged. This must be allowed explicitly. |  | No | Add the following text after "A device shall only transmit in GTS that were assigned to it.": A device may treat two adjacent GTS that were allocated to it as a single GTS. | REJECTED | If the coordinator allocates two separate GTSs, there may be a reason. Combining is actually more logic and thus more complexity. Do not allow this for simplicity reasons now. |  |  |  | implemented
286710 | 24-Sep-2021 20:10:58 UTC-12 | R1-154 | Bober, Lennert | klb@posteo.de |  | Ballot | 3 | Producer - Software | Approve | Fraunhofer Heinrich Hertz Institute,Self | Technical | 111 | 10.2.6 | 24 | The performance of the current MIMO channel estimation sequences in the PM-PHY is not sufficient to support channel estimation with the required accuracy. |  | No | Replace the PM-PHY MIMO Pilots with a better-performing alternative. | REVISED | Replace the MIMO pilots via the resolutions described in doc. https://mentor.ieee.org/802.15/dcn/21/15-21-0447-01-0013-textproposal-for-new-pm-phy-mimo-pilots.docx Make sure that "clock rate" is used instead of "optical clock rate". Make sure that table numbers and references are correct. |  |  |  | implemented
286711 | 24-Sep-2021 20:10:58 UTC-12 | R1-155 | Bober, Lennert | klb@posteo.de |  | Ballot | 4 | Producer - Software | Approve | Fraunhofer Heinrich Hertz Institute,Self | Technical |  |  |  | While there is a clock accuracy specified, it is not explicitly mentioned for which clocks this is. I suppose it is for the transmit clock, defining the center frequency accuracy? |  | No | Place some hint that that the clock accuracy is for the transmit clock center frequency. Potentially also add a hint about the transmit timing clock, if appropriate. | REVISED | Add the following sentence after P113L25: "The clock used for symbol transmission shall have an accuracy of aPhyClockAccuracy. Add the following sentence after P162L8: "All clocks shall be derived from the PHY reference clock, which shall have an accuracy of aPhyClockAccuracy". |  |  |  | implemented
286712 | 24-Sep-2021 20:10:58 UTC-12 | R1-156 | Bober, Lennert | klb@posteo.de |  | Ballot | 5 | Producer - Software | Approve | Fraunhofer Heinrich Hertz Institute,Self | Technical |  |  |  | No regulatory emission characteristics are defined. E.g. for wavelengths, out of band emissions, total emitted power. If there are none, an appropriate hint for implementers should be included. |  | No | Add specification about the relevant regulatory requirements and documents or a hint that none are required to be followed. | REVISED | Add a new entry under "Normative references": IEC 60825-1 Ed. 3.0 b:2014, Safety Of Laser Products - Part 1: Equipment Classification And Requirements Add a new subclause 9.5 "Regulatory requirements" with the following content: OWPANs implemented in accordance with this standard are subject to equipment certification and operating requirements established by regional and national regulatory administrations. The PHY specification establishes minimum technical requirements for interoperability, based upon established regulations at the time this standard was issued. These regulations are subject to revision or may be superseded. Regulatory requirements that do not affect interoperability are not addressed in this standard. Implementers are referred to the regulatory sources in IEC 60825-1 (or its relevant latest version) for further information. | R1-156 R1-157 |  |  | implemented
286713 | 24-Sep-2021 20:10:58 UTC-12 | R1-157 | Bober, Lennert | klb@posteo.de |  | Ballot | 6 | Producer - Software | Approve | Fraunhofer Heinrich Hertz Institute,Self | Technical |  |  |  | No regulatory specifications about the eye safety are included. |  | No | Add reference(s) to the relevant regulatory documents at the appropriate location. | REVISED | Add a new entry under "Normative references": IEC 60825-1 Ed. 3.0 b:2014, Safety Of Laser Products - Part 1: Equipment Classification And Requirements Add a new subclause 9.5 "Regulatory requirements" with the following content: OWPANs implemented in accordance with this standard are subject to equipment certification and operating requirements established by regional and national regulatory administrations. The PHY specification establishes minimum technical requirements for interoperability, based upon established regulations at the time this standard was issued. These regulations are subject to revision or may be superseded. Regulatory requirements that do not affect interoperability are not addressed in this standard. Implementers are referred to the regulatory sources in IEC 60825-1 (or its relevant latest version) for further information. | R1-156 R1-157 |  |  | implemented
286714 | 24-Sep-2021 20:10:58 UTC-12 | R1-158 | Bober, Lennert | klb@posteo.de |  | Ballot | 7 | Producer - Software | Approve | Fraunhofer Heinrich Hertz Institute,Self | Technical |  |  |  | There should be sequence charts for some MAC routines, such as acknowledged transmission, adaptive transmission / MCS request, OWPAN maintenance such as attribute change, starting, scanning and more |  | No | Place meaningful sequence charts in the appropriate locations. | REVISED | Insert a sequence chart for scanning after P50L20. |  |  |  | implemented
286715 | 24-Sep-2021 20:10:58 UTC-12 | R1-159 | Bober, Lennert | klb@posteo.de |  | Ballot | 8 | Producer - Software | Approve | Fraunhofer Heinrich Hertz Institute,Self | Technical |  |  |  | The MAC address (of the coordinator) should not be changeable. At least not during OWPAN up time. |  | No | Update MAC address PIB attribute so it is not changeable. Describe whether MAC address is selectable / random or whether it is assigned only as an EUI-48. | REVISED | Update the "Access" column of the macMac48Address PIB attribute in table 38 to "get". |  |  |  | implemented
286496 | 16-Sep-2021 15:46:36 UTC-12 | R1-16 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 15 | General Interest | Disapprove | Self Employed | Editorial | 44 | 6.4.1 | 14 | In figure 13, what is the meaning of the box labeled as "Non-Beacon-enabled OWPAN MAC"? I think it can be removed without loosing any information. I also assume that device should also try to listen the Random Access frames from the coordinator, and only go to the Contention access polling period when it sees one of them, and then moves to the Contention-free polling period when it sees Poll frame. |  | No | Change the arrow from the "Contention assess polling period" to go directly to "Poll frame from coordinator?". | REVISED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286716 | 24-Sep-2021 20:10:58 UTC-12 | R1-160 | Bober, Lennert | klb@posteo.de |  | Ballot | 9 | Producer - Software | Approve | Fraunhofer Heinrich Hertz Institute,Self | Technical |  |  |  | There may be cases where the ACK timeout is not long enough to cover all fragments of a MPDU. |  | No | Place hint to implementers that coordinators must select / set a sufficiently long ACK timeout when using fragmentation. Alternatively, make ACK be reset on reception of a single fragment more or similar. | REJECTED | The author withdrew the comment. |  |  |  | implemented
286650 | 23-Sep-2021 21:24:14 UTC-12 | R1-98 | Lim, Sang-Kyu | sklim@etri.re.kr |  | Ballot | 9 | Research | Approve | Electronics and Telecommunications Research Institute (ETRI) | Editorial | 48 | 6.4.4 | 7 | Figure 18 |  | No | Capitalize the first letter in "contention-free polling period process" for consistency with other Figures. | REVISED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286718 | 24-Sep-2021 20:10:58 UTC-12 | R1-162 | Bober, Lennert | klb@posteo.de |  | Ballot | 11 | Producer - Software | Approve | Fraunhofer Heinrich Hertz Institute,Self | Editorial | 35 | 6.2 | 15 | Make clause MAC transmissions into something describing the general device functionalitiy. This should also align with the PICS, so a PICS table for device and coordinator functionality can clearly map to this subclause. |  | No |  | REVISED | Change into "General device functions" |  |  |  | implemented
286739 | 24-Sep-2021 20:10:58 UTC-12 | R1-183 | Bober, Lennert | klb@posteo.de |  | Ballot | 32 | Producer - Software | Approve | Fraunhofer Heinrich Hertz Institute,Self | Technical | 66 | 7.2.2 | 17 | The frame control field mixes protocol information with information about the structure of the MAC frame. |  | No | Make the ACK request bit reserved Remove the description of the ACK request bit Create a new field "Fragmentation control" in the general MAC frame format: two octets, four bits are fragement number. Four bits are last fragment. Remaining eight bits are reserved. Remove "Fragment Number" from figure 33. Set one of the newly unsused bits in figure 33 to be ACK requested. Mark the other three bits as reserved. | REVISED | Make the ACK request bit reserved Remove the description of the ACK request bit Create a new field "Fragmentation control" in the general MAC frame format: two octets, four bits are fragement number. Four bits are last fragment. Remaining eight bits are reserved. Remove "Fragment Number" from figure 33. Set one of the newly unsused bits in figure 33 to be ACK requested. Mark the other three bits as reserved Create a field Fragment control with the fragment number and last fragment. |  |  |  | implemented
286720 | 24-Sep-2021 20:10:58 UTC-12 | R1-164 | Bober, Lennert | klb@posteo.de |  | Ballot | 13 | Producer - Software | Approve | Fraunhofer Heinrich Hertz Institute,Self | Technical | 30 | 5.5.2 | 3 | The description of the MAC and PHY in the architecture clause feel redundant with the next subclauses about the MAC and PHY. |  | No | Split the contents of MAC and PHY overview better between the architecture subclause and the then following PHY and MAC descriptions. | REVISED | Replace P29L3-18 with the following text: Each device has a device management entity (DME), responsible for managing the device and, in case the device is a coordinator, the OWPAN. The DME invokes MAC layer management entity (MLME) functionality through the MLME service access point (MLME-SAP). The MLME-SAP defines a set of essential primitives for network operation. Further functionality may be provided by the MAC sublayer to the DME in an implementation-specific manner. The IEEE Std 802.15.13 MAC sublayer controls access to the medium for all types of transfers. It provides the MCPS-SAP and MLME-SAP to the higher layers. Its MCPS-SAP allows the next higher protocol layer to transmit MAC service data units (MSDUs) between peer IEEE Std 802.15.13 devices by supporting the MAC service defined by IEEE Std 802.1AC. The higher layers are a network layer, which provides network configuration, manipulation, and message routing, and an application layer, which provides the intended function of the device. The definition of these higher layers is outside the scope of this standard. The PHY contains the optical wireless transceiver, which is responsible for turning a PHY service data unit (PSDU) into a PHY protocol data unit (PPDU) for transmission. PSDUs are MAC protocol data units (MPDUs) from the MAC sublayer that are transferred through the PHY data service access point (PD-SAP) of the PHY. To yield the PPDU, a PSDU is supplemented with various fields, needed by each respective PHY for reception. Thereafter. the PPDU is output to one or more OFEs U17as an analog signal. Management functions of the PHY are invoked through the PHY management entity service access point (PLME-SAP). Remove 5.5.2 and 5.5.3 |  |  |  | implemented
286721 | 24-Sep-2021 20:10:58 UTC-12 | R1-165 | Bober, Lennert | klb@posteo.de |  | Ballot | 14 | Producer - Software | Approve | Fraunhofer Heinrich Hertz Institute,Self | Technical | 116 | 11.1.1 | 10 | The LB-PHY cannot support relaying, since it is only specified for the beacon-enabled channel access mode. |  | No | Remove statements about LB-PHY supporting relaying. | REVISED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286740 | 24-Sep-2021 20:10:58 UTC-12 | R1-184 | Bober, Lennert | klb@posteo.de |  | Ballot | 33 | Producer - Software | Approve | Fraunhofer Heinrich Hertz Institute,Self | Technical | 70 | 7 | 11 | It is not necessary that all frames have dedicated frames. |  | No | Remove Association Request, Association Response, Disassociation Notification, Alien Signal, Attribute Change Request, Attribute Change Response frames and rely on the elements being exchanged through the Variable Element Container. | REVISED | Remove control frames other than GTS allocation list Variable element container Beacon Random Access Make sure that no "…" frames are used for frames that are removed. Especially, update use of "ACK frame" throughout the standard. Update text where it says ... frame or ... element to be just ... element. Remove management frames apart from Variable Element Container Poll frames Insert the following sentence after P73L4: The Superframe Descriptor element shall only be transmitted as payload of the Beacon frame and not as part of a Variable Element Container. |  |  |  | implemented
286722 | 24-Sep-2021 20:10:58 UTC-12 | R1-166 | Bober, Lennert | klb@posteo.de |  | Ballot | 15 | Producer - Software | Approve | Fraunhofer Heinrich Hertz Institute,Self | Technical | 109 | 10.1 |  | The PM-PHY may require an additional IFS between successive transmissions in order to prevent baseline wander or at least to reset the wander after each PPDU. |  | No | Add IFS for successive transmissions generally in the MAC. Add them alternatively for the PM-PHY only. | REVISED | Replace the content of 6.3.8 with the following text: Devices operating in beacon-enabled channel access mode shall stay silent for a certain time after each frame transmission. That time is called the interframe space. The minimum interframe space (MIFS), depends on the PHY used for transmission. It shall be equal to the aPhyMifsDuration constant of each PHY. A transmitting device shall finish its transmissions at least MIFS before the end of the GTS in order to enable all receiving devices to utilize their GTSs from the beginning. Replace all occurrences of TAIFS with MIFS in 6.3.9. Remove TAIFS from figure 12 as it is included in the GTS Replace the description of BECA8.1 in the PICS with the following text: The entity is able to regard for the MIFS. Update the acronym description of TAIFS to MIFS Add the following PHY constant to table 43: aPhyMifsDuration Description: The duration of the MIFS for transmissions using the PM-PHY Value: 3 Unit: µs Add the following PHY constant to table 51: aPhyMifsDuration Description: The duration of the MIFS for transmissions using the HB-PHY Value: 3 Unit: µs | R1-15 R1-166 R1-167 |  |  | implemented
286724 | 24-Sep-2021 20:10:58 UTC-12 | R1-168 | Bober, Lennert | klb@posteo.de |  | Ballot | 17 | Producer - Software | Approve | Fraunhofer Heinrich Hertz Institute,Self | Technical | 140 | 12 | 1 | The HB-PHY does not refer to the selected clock rate / phyClockRate / bandwith in the modulation clauses. |  | No | The PHY descriptions should refer to this PHY PIB attribute. | REVISED | Replace the description of the phyBandwidth attribute in 12.1.4 with the following text: This attribute determines the bandwidth to use for transmitted PPDUs. All PPDUs shall be transmitted with the correspondig values, defined in table 52. | R1-168 R1-177 |  |  | implemented
286667 | 23-Sep-2021 21:24:14 UTC-12 | R1-115 | Lim, Sang-Kyu | sklim@etri.re.kr |  | Ballot | 26 | Research | Approve | Electronics and Telecommunications Research Institute (ETRI) | Technical | 110 |  |  | According to 9.3.2, each PHY has its own set of PIB attributes. So, the PHY PIB attributes for the LB-PHY has been defined in Table 48 of the subclause 11.1.4, and the PHY PIB attributes for the HB-PHY has been defined in Table 52 of the subclause 12.1.4. By the way, PHY PIB attributes for the PM-PHY has not been defined in this draft. |  | No | So, the issue is that there is no need to define PHY PIB attributes for the PM-PHY or not. Please check again this issue. | REVISED | Replace the sentence "Each PHY has its own set of PIB attributes." in P107L23 with the following text: PHYs have their own PHY PIB attributes. | R1-112 R1-115 |  |  | implemented
286497 | 16-Sep-2021 15:46:36 UTC-12 | R1-17 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 16 | General Interest | Disapprove | Self Employed | Technical | 44 | 6.4.1 | 14 | What is this Contention assess polling period? |  | No | Perhaps it should be "Contetion access polling period". | REVISED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286528 | 16-Sep-2021 15:46:36 UTC-12 | R1-48 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 46 | General Interest | Disapprove | Self Employed | Editorial | 119 | 11.2.5 | 19 | Hanging paragraph. |  | No | Move this paragraph to new subsection 11.2.5.1 and renumber later subsections accordingly. | REVISED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286727 | 24-Sep-2021 20:10:58 UTC-12 | R1-171 | Bober, Lennert | klb@posteo.de |  | Ballot | 20 | Producer - Software | Approve | Fraunhofer Heinrich Hertz Institute,Self | Technical | 113 | 10.3.1 | 4 | The PM-PHY needs some formula to describe how the data rate is calculated. |  | No | Add such formula. | REJECTED | The author withdrew the comment. |  |  |  | implemented
286728 | 24-Sep-2021 20:10:58 UTC-12 | R1-172 | Bober, Lennert | klb@posteo.de |  | Ballot | 21 | Producer - Software | Approve | Fraunhofer Heinrich Hertz Institute,Self | Technical | 114 | 10.3.6 | 15 | It is not clear, how to initialize the running disparity for each 8b10b encoder. I suppose, header and payload go though different transmit chains. |  | No | Specify which streams are 8b10b coded and where the encoders are initialized for header and payload. | REVISED | Draft: Add the following text after P114L15: The 8B10B encoder for the systematic part of the RS block shall be reset for each PPDU. The 8B10B encoder for the redundant part of the RS block shall be reset for each RS block. Both 8B10B encoders shall be reset for the header and the payload independently. |  |  |  | implemented
286729 | 24-Sep-2021 20:10:58 UTC-12 | R1-173 | Bober, Lennert | klb@posteo.de |  | Ballot | 22 | Producer - Software | Approve | Fraunhofer Heinrich Hertz Institute,Self | General |  |  |  | It is unclear, how the DME is supposed to be implemented and how the DME is able to control additional settings that are not currently part of the MLME SAP. |  | No | Describe that MAC is supposed to handles most decisions internally in section "Architecture" i.e. the DME is expected to be internal to the MAC and implemented by the MAC vendor. Most other configuration should happen throught the PIB attributes. In this model, the MLME should only comprise the mandatory features, or alternatively, the features that are invokey by user interaction. I.e. - Starting ending an OWPAN (coordinator) - Scanning for networks - Associating / disassociating with a network - Providing a configuration (get, set PIB values) Describe that a detailed MLME interface could be outside of the scope of the standard / vendor specific. Make sequence chart graphic describing actors (User, DME, MAC, ...). | REVISED | Add the following text under 8.3.1: MLME primitives specified in this clause are required to support the core management functionality of the standard. The management interfaces for other functions than core functions are currently vendor specific. |  |  |  | implemented
286529 | 16-Sep-2021 15:46:36 UTC-12 | R1-49 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 47 | General Interest | Disapprove | Self Employed | Editorial | 121 | 11.2.5.1 | 16 | The Advanced Modulation Header is one bit field, there is no space for character "1" or "0" in it. Change them to numbers, and as they are small integer numbers spell them out as zero and one. |  | No | Change "1" to one, and "0" to zero. | REVISED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286731 | 24-Sep-2021 20:10:58 UTC-12 | R1-175 | Bober, Lennert | klb@posteo.de |  | Ballot | 24 | Producer - Software | Approve | Fraunhofer Heinrich Hertz Institute,Self | Editorial |  |  |  | Create an extra MAC functional clause for MIMO transmission instead of keeping it in the adaptive transmission subcause. |  | No |  | REVISED | Draft: Move 6.9.4 and 6.9.5 to a new subclause 6.10 "Distributed MIMO transmission" |  |  |  | implemented
286732 | 24-Sep-2021 20:10:58 UTC-12 | R1-176 | Bober, Lennert | klb@posteo.de |  | Ballot | 25 | Producer - Software | Approve | Fraunhofer Heinrich Hertz Institute,Self | Editorial |  |  |  | MCPS is a unintuitive name for the data SAP. |  | No | Rename MCPS-SAP to MD-SAP (MAC Data Service Access Point). | ACCEPTED |  |  |  |  | implemented
286530 | 16-Sep-2021 15:46:36 UTC-12 | R1-50 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 48 | General Interest | Disapprove | Self Employed | Editorial | 121 | 11.2.5.1 | 19 | The High reliablity header is one bit field, there is no space for character "1" or "0" in it. Change them to numbers, and as they are small integer numbers spell them out as zero and one. |  | No | Change "1" to one, and "0" to zero. | REVISED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286734 | 24-Sep-2021 20:10:58 UTC-12 | R1-178 | Bober, Lennert | klb@posteo.de |  | Ballot | 27 | Producer - Software | Approve | Fraunhofer Heinrich Hertz Institute,Self | Technical |  |  |  | The features / capabilities cannot be activated or deactivated in the MAC. |  | No | Add PIB attributes per feature. Describe in additional text that the set of used features / capabilities is negotiated during association as follows: The device sends a capability list in the Association Request element. The coordinator selects the intersection of its capabilities and the capabilities received from the device and transmits the result in the Association response. During membership, the intersecting features are used. | REVISED | Replace the text in P52L29-33 with the following text: The coordinator shall transmit the Association Response element to the requesting device. The Association Response element shall include a set of negotiated capabilities to be used between the device and the coordinator. The set of negotiated capabilities shall include no capabilities that were not indicated by the device in the Association Request element. The precise set of capabilities may be selected by the coordinator based on its supported capabilities. The selected capabilities shall be supported for the time the device is associated with the OWPAN. |  |  |  | implemented
286531 | 16-Sep-2021 15:46:36 UTC-12 | R1-51 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 49 | General Interest | Disapprove | Self Employed | Editorial | 122 | 11.2.5.2 | 9 | This is first use of CQI outside figures, expand it here. |  | No | Expand CQI. | REVISED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286498 | 16-Sep-2021 15:46:36 UTC-12 | R1-18 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 17 | General Interest | Disapprove | Self Employed | Technical | 44 | 6.4.1 | 14 | Figure 13 does not specify whether it is from the coordinator point of view or from the device point of view. |  | No | Perhaps change the title to "Flow chart for device in non-beacon-enabled OWPAN MAC". | REVISED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286532 | 16-Sep-2021 15:46:36 UTC-12 | R1-52 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 50 | General Interest | Disapprove | Self Employed | Editorial | 126 | 11.2.6.4 | 17 | Typo. |  | No | Change "date in queue" to "data in queue". | REVISED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286737 | 24-Sep-2021 20:10:58 UTC-12 | R1-181 | Bober, Lennert | klb@posteo.de |  | Ballot | 30 | Producer - Software | Approve | Fraunhofer Heinrich Hertz Institute,Self | Technical | 104 | 10.2.8 | 18 | In 9.2.5, P107L9 it says that the PSDU shall be padded to a multiple of 4 octets. Thus, |  | No | Make PM-PHY aMaxPsduSize 2044 octets. | ACCEPTED |  |  |  |  | implemented
286738 | 24-Sep-2021 20:10:58 UTC-12 | R1-182 | Bober, Lennert | klb@posteo.de |  | Ballot | 31 | Producer - Software | Approve | Fraunhofer Heinrich Hertz Institute,Self | Editorial | 66 | 7.2.2 | 25 | The To Backhaul and from Backhaul fields could be purely numeric. |  | No | Refactor the two fields as a single number with two bits. For each, list how they describe the further frame format. | REVISED | Merge the "To Backhaul" and "From Backhaul" fields into one field "Direction" and update the corresponding columns in table 1. |  |  |  | implemented
286719 | 24-Sep-2021 20:10:58 UTC-12 | R1-163 | Bober, Lennert | klb@posteo.de |  | Ballot | 12 | Producer - Software | Approve | Fraunhofer Heinrich Hertz Institute,Self | Editorial | 172 | D.3 | 20 | Merge tables D.1 and D.2 into a single table "device types" or "device functions". Make it map to the new clause in 6, describing the general device functions. |  | No |  | REJECTED | The author withdrew the comment. |  |  |  | implemented
286707 | 24-Sep-2021 18:45:38 UTC-12 | R1-151 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 72 | General Interest | Disapprove | Self Employed | Technical | 178 | D.3 | 1 | Lots of entries have O even when they should be conditional to the base capabiloty. I.e. Mimo things should be depending whether device is mimo capable. Management frames should most likely be mandatory for all devices etc. |  | No | Go through the pics and make sure they use O and XXX:M or XXX:O correctly. | ACCEPTED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286741 | 24-Sep-2021 20:10:58 UTC-12 | R1-185 | Bober, Lennert | klb@posteo.de |  | Ballot | 34 | Producer - Software | Approve | Fraunhofer Heinrich Hertz Institute,Self | Technical | 38 | 6.3.3 | 3 | It only makes sense to broadcast the beacon frame. Otherwise, devices would have to drop the beacon since it is not addressed to them. However, this is not stated in the text. |  | No | Add "The beacon frame's receiver address shall be the broadcast address." in the appropriate location | REVISED | Add the following sentence after P38L5: The Beacon frame's receiver address shall be the broadcast address. |  |  |  | implemented
286742 | 24-Sep-2021 20:10:58 UTC-12 | R1-186 | Bober, Lennert | klb@posteo.de |  | Ballot | 35 | Producer - Software | Approve | Fraunhofer Heinrich Hertz Institute,Self | Editorial |  |  |  | Some Bitmap figures are not clear |  | No | Specify all bitmaps with MSB and LSB and define transmission order. | ACCEPTED |  |  |  |  | implemented
286743 | 24-Sep-2021 20:10:58 UTC-12 | R1-187 | Bober, Lennert | klb@posteo.de |  | Ballot | 36 | Producer - Software | Approve | Fraunhofer Heinrich Hertz Institute,Self | Technical |  |  |  | It is not clear, which frames are forwarded by the coordinator. |  | No | Specify that only data frames are forwarded. E.g. that the coordinator functions as a bridge. | REVISED | Insert the following sentence after P31L23: MSDUs originating from a device and destined to another device are delivered by the coordinator to the higher layers. To support communication between devices, coordinators need to implement bridging functionality based on IEEE Std 802.1Q™. Insert the following normative reference: IEEE Std 802.1Q™, IEEE Standard for Local and Metropolitan Area Networks—Bridges and Bridged Networks. |  |  |  | implemented
286744 | 24-Sep-2021 20:10:58 UTC-12 | R1-188 | Bober, Lennert | klb@posteo.de |  | Ballot | 37 | Producer - Software | Approve | Fraunhofer Heinrich Hertz Institute,Self | Technical |  |  |  | Specify whether a frame with broadcast destination can be acknowledged. |  | No |  | REVISED | Add the following paragraph after P57L11: MPDUs with the destination address set to the broadcast address shall have the ACK Request bit set to zero. MPDUs with the destination address set to the broadcast address shall not be acknowledged by a receiving device. |  |  |  | implemented
286745 | 25-Sep-2021 01:13:48 UTC-12 | R1-189 | Baykas, Tuncer | tbaykas@gmail.com |  | Ballot | 1 | Producer - Component | Approve | Hyperion Technologies | Editorial | 27 |  | 24 | 'The current standards in the light spectrum are as follows: ' 802.11bb is a project at the moment. |  | No | Change it it to ''The current standards and standardization projects in the light spectrum are as follows: ' | ACCEPTED |  |  |  |  | implemented
286499 | 16-Sep-2021 15:46:36 UTC-12 | R1-19 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 18 | General Interest | Disapprove | Self Employed | Technical | 44 | 6.4.1 | 14 | Figure 13. If this is from the device point of view, then the device should first wait for the Random access frame from the coordinator, and when that is received it will go to the Contention access polling period. During Contention access polling period it waits for poll frame, and when it receives that it goes to the Contention-free polling period and stays there until it sees next Random Access frame. I think the figure is completely wrong. |  | No | Fix the state machine figure. Also perhaps add separate flow chart for coordinator end. | REVISED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286746 | 25-Sep-2021 01:25:52 UTC-12 | R1-190 | Baykas, Tuncer | tbaykas@gmail.com |  | Ballot | 2 | Producer - Component | Approve | Hyperion Technologies | Editorial | 28 |  |  | 802.15.7a is not listed |  | No | Add current LC standardization project(s) | REJECTED | The "IEEE Std 802.15.7™" item will cover the 802.15.7a project once it is published. We do not foresee that 7a will be different from 802.15.7 in terms of coexistence. |  |  |  | implemented
286482 | 16-Sep-2021 15:46:35 UTC-12 | R1-2 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 2 | General Interest | Disapprove | Self Employed | Editorial | 24 | 4.4 | 13 | The "Values of reserved fields shall not be used in outgoing frames" is not correct. The next sentence do say we send them out as zeros, and next paragraph talks about the reserved values. |  | No | Remove sentence "Values of reserved fields shall not be used in outgoing frames." | ACCEPTED |  |  |  |  | implemented
286500 | 16-Sep-2021 15:46:36 UTC-12 | R1-20 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 19 | General Interest | Disapprove | Self Employed | Editorial | 44 | 6.4.1 | 19 | What is the point of sending ACK for the Random access frame? I mean if device does not see it it will still stay in the Contention-free polling period until it will see next Random access frame. Also are all devices going to send this ack for the Random Access Frame? |  | No | Remove the sentence "Polled devices shall send an acknowledgement for the Random Access frame to the coordinator in High-Reliablity Control header of the LB-PHY PPDU or in the Poll ACK field of the MPDU". | REVISED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286501 | 16-Sep-2021 15:46:36 UTC-12 | R1-21 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 20 | General Interest | Disapprove | Self Employed | Technical | 45 | 6.4.1 | 1 | The Figure 14 is missing some description text what each pieces of the figure are. The first frame from coordinator is RA (which is marked), 2nd is "subsequent control frame" (not marked), and then we have CFPP (marked), but the next two frames are not marked, and first of them is next Control frame (RA), and one after that is subsequent control frame. |  | No | I suggest that change the CFPP in the left to be miniature version of the CFPP in the middle. I.e., have the arrow pointing start and end of CFPP similarly in both cases (and the 3rd CFPP starting at the right end of figure), and then add few example packets like we have in the middle for this too. Also mark the middle RA as is done with other two RAs, and perhaps even add descriptive text for "subsequent control frame". | REVISED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286502 | 16-Sep-2021 15:46:36 UTC-12 | R1-22 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 21 | General Interest | Disapprove | Self Employed | Technical | 45 | 6.4.2 | 10 | The term subsequent control frame is not really defined, and perhaps we should add it to the terminology, or at least add proper definition for it. |  | No | Add definition of subsequent control frame. | REVISED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286503 | 16-Sep-2021 15:46:36 UTC-12 | R1-23 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 22 | General Interest | Disapprove | Self Employed | Editorial | 45 | 6.4.2 | 14 | What is the text saying "The Poll Request frame does not have any field except the common management information" trying to say. Similar text is used in multiple locations, but what is the meaning of it. The text also says that ANY frame can act as a Poll frame, so not sure how that works with this. And what is common management information? |  | No | Replace the sentence with something that makes sense. Also fix other locations. | REVISED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286504 | 16-Sep-2021 15:46:36 UTC-12 | R1-24 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 23 | General Interest | Disapprove | Self Employed | Editorial | 45 | 6.4.1 | 1 | The term CFPP is not defined in the section 3. |  | No | Add CFPP Contention-Free Polling Period to the section 3. | REVISED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286505 | 16-Sep-2021 15:46:36 UTC-12 | R1-25 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 24 | General Interest | Disapprove | Self Employed | Technical | 45 | 6.4.1 | 1 | Figure 14 should have 5 lines, one for the Coordinator on top, and then below the line device 1, device 2, device 3, and device 4. Then each D1, D2, D3, D4 frame should be moved to appropriate line. This would make it easier to understand who is responding and when. |  | No | Redraw the figure. | REVISED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286506 | 16-Sep-2021 15:46:36 UTC-12 | R1-26 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 25 | General Interest | Disapprove | Self Employed | Editorial | 46 | 6.4.2 | 1 | Figure 15. On the right side of the figure there is text "Backoff for N cycles". What does the cycles here mean? And who will back off here? Is this flow chart for coordinator or for device. Looks like it is for coordinator, as it has questions like Any connected device, but is it so that CFPP does not start if the poll request is not decoded by the coordinator? If this is from the device point of view then how does the device know whether coordinator decoded the poll request. Techincal |  | No | Redraw this figure to be from the coordinator point of view and fix the flow chart. | REVISED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286507 | 16-Sep-2021 15:46:36 UTC-12 | R1-27 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 26 | General Interest | Disapprove | Self Employed | Technical | 46 | 6.4.2 | 7 | This is first use of the MAC frame header, add the (MHR) text here. |  | No | Change "MAC frame header" to "MAC frame header (MHR)". | REVISED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286508 | 16-Sep-2021 15:46:36 UTC-12 | R1-28 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 27 | General Interest | Disapprove | Self Employed | Technical | 46 | 6.4.2 | 5 | The sentence "Then, the random backoff is introduced." Does not specify how this random backoff is done. What is the window used to pick the random numbers? Is the window made larger after each try? Does the device time out after some time? |  | No | Specify the random backoff process of the non-beacon enabled access control. | REVISED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286509 | 16-Sep-2021 15:46:36 UTC-12 | R1-29 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 28 | General Interest | Disapprove | Self Employed | Technical | 46 | 6.4.3 | 15 | The sentence "each device is required to be able to respond to a Poll frame received from the coordinator" is bit confusing, as there are cases where device might not be able to respond, for example if it is not able to receive the poll frame. |  | No | Perhaps the text should say that device shall respond to valid Poll frame received from the coordinator". Or just remove this text, as I think we have similar requirements later. | REVISED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286510 | 16-Sep-2021 15:46:36 UTC-12 | R1-30 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 29 | General Interest | Disapprove | Self Employed | Technical | 46 | 6.4.3 | 16 | The text "A device shall also be able to request to be polled by an active coordinator" is not exact. |  | No | Change to "A device shall be able to respond to the Poll requests sent by the coordinator". We do not need word active, as we have only one coordinator. The coordinator polls the device using poll frames. Or most likely this text could also be removed, as I think the requirements are listed later already. | REVISED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286511 | 16-Sep-2021 15:46:36 UTC-12 | R1-31 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 30 | General Interest | Disapprove | Self Employed | Technical | 46 | 6.4.3 | 15 | There should be bit more description of how the polling works, i.e., that the high reliability header contains current and next polled device numbers, and when coordinator sends frames devices will know based on those who the coordinator is polling now and polling next. Also because the device knows that it will be next in polling sequence if it saw its address in the next polled device field, it can start sending poll response immediately when it sees packet, it does not even need to process high reliability header to do that. Also current LB-PHY says high reliability header is optional, but I do not see how it can be if only method LB-PHY can use is non-beacon enabled mode, and non-beacon enabled mode do require high reliability header. Techincal |  | No | Add more description of how polling work. | REVISED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286512 | 16-Sep-2021 15:46:36 UTC-12 | R1-32 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 31 | General Interest | Disapprove | Self Employed | Technical | 47 | 6.4.3 | 14 | I think the reply you send is Poll Response frame, not Poll Request frame. |  | No | Change "Poll Request" to "Poll Response". | REVISED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286513 | 16-Sep-2021 15:46:36 UTC-12 | R1-33 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 32 | General Interest | Disapprove | Self Employed | Technical | 47 | 6.4.3 | 21 | Should this really be Poll Request, or just Poll frame? |  | No | As poll request is used in the contention based access, not during the contention-free polling period, this most likely should be "Poll frame". | REVISED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286514 | 16-Sep-2021 15:46:36 UTC-12 | R1-34 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 33 | General Interest | Disapprove | Self Employed | Technical | 47 | 6.4.3 | 4 | I was under impression that poll frame can actually have data included, at least figure 14 has Pkt1 etc attached to the poll frame, so the text "The Poll frame does not have any field except the common management information." is wrong. Techincal |  | No | Properly describe what the poll frame is. Actually as the next paragraph says that any frames transmitted from the coordinator to the device are treated as polling frames this sentence can be removed. | REVISED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286515 | 16-Sep-2021 15:46:36 UTC-12 | R1-35 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 34 | General Interest | Disapprove | Self Employed | Technical | 47 | 6.4.3 | 16 | There is again this text "The Poll Response frame does not have any field except the common management information", which I think is wrong as it can include data etc. |  | No | Remove the sentence. | REVISED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286516 | 16-Sep-2021 15:46:36 UTC-12 | R1-36 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 35 | General Interest | Disapprove | Self Employed | Technical | 47 | 6.4.3 | 21 | Is there a difference with "not detected by the coordinator" to the "not received by the coordinator". I mean does this mean that if it do receive something but the frame checksum is not valid, the coordinator does not mov to the next device in the queue, but stay on the same device? |  | No | Change to "not received". | REVISED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286517 | 16-Sep-2021 15:46:36 UTC-12 | R1-37 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 36 | General Interest | Disapprove | Self Employed | Technical | 47 | 6.4.3 | 21 | How quickly does the coordinator move to the next device? I.e., is the device required to start sending its poll response frame while coordinator is still sending its poll frame, or can it wait for the poll frame to finish before starting to send poll response? This do require all devices to be able to process the high reliability header before the full frame is received, thus most likely will make software implementations very hard, and will most likely always require hardware support. |  | No | If devices are required to start responding before coordinator finishes sending the frame, this should be stated here, or if they are not required to do that, but coordinator waits for certain time before moving to the next device, the timing should be described. | REVISED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286518 | 16-Sep-2021 15:46:36 UTC-12 | R1-38 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 37 | General Interest | Disapprove | Self Employed | Technical | 47 | 6.4.3 | 27 | Having text saying "device shall send ... after a while" is bit vague. Perhaps better text is to say "device wanting to keep link valid shall make sure that it sends a response at least every aMacPollTimeout". |  | No | Replace the "However a device ... shall not conside the link is invalid" to "A device wanting to keep link valid with coordinator, shall make sure that it sends a response to the Poll frame at least every aMacPollTime seconds." | REVISED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286723 | 24-Sep-2021 20:10:58 UTC-12 | R1-167 | Bober, Lennert | klb@posteo.de |  | Ballot | 16 | Producer - Software | Approve | Fraunhofer Heinrich Hertz Institute,Self | Technical |  |  |  | How can the PHYs estimate noise? If there is a mandatory IFS after each PPDU, it can be done in it. |  | No | Alternatively, specify some time / frequencies / … in the PPDU for noise estimation. | REVISED | Replace the content of 6.3.8 with the following text: Devices operating in beacon-enabled channel access mode shall stay silent for a certain time after each frame transmission. That time is called the interframe space. The minimum interframe space (MIFS), depends on the PHY used for transmission. It shall be equal to the aPhyMifsDuration constant of each PHY. A transmitting device shall finish its transmissions at least MIFS before the end of the GTS in order to enable all receiving devices to utilize their GTSs from the beginning. Replace all occurrences of TAIFS with MIFS in 6.3.9. Remove TAIFS from figure 12 as it is included in the GTS Replace the description of BECA8.1 in the PICS with the following text: The entity is able to regard for the MIFS. Update the acronym description of TAIFS to MIFS Add the following PHY constant to table 43: aPhyMifsDuration Description: The duration of the MIFS for transmissions using the PM-PHY Value: 3 Unit: µs Add the following PHY constant to table 51: aPhyMifsDuration Description: The duration of the MIFS for transmissions using the HB-PHY Value: 3 Unit: µs | R1-15 R1-166 R1-167 |  |  | implemented
286484 | 16-Sep-2021 15:46:35 UTC-12 | R1-4 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 3 | General Interest | Disapprove | Self Employed | Technical | 25 | 5.1 | 11 | Here we defined Beacon enabled as "Scheduled", and non-beacon enabled as "Polled". I think those are better terms and should be used throughout the document. |  | No | Change "Beacon-enabled" to "Scheduled", and "Non-beacon-enabled" to "Polled" throughout the document. | REVISED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286520 | 16-Sep-2021 15:46:36 UTC-12 | R1-40 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 39 | General Interest | Disapprove | Self Employed | Editorial | 48 | 6.4.4 | 17 | Figure 19 should have 3 lines, one for the Coordinator on top, and then below the line device 1 and device 2. Then each D1, D2 frame should be moved to appropriate line. This would make it easier to understand who is responding and when. |  | No | Redraw the figure. | REVISED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286521 | 16-Sep-2021 15:46:36 UTC-12 | R1-41 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 40 | General Interest | Disapprove | Self Employed | Editorial | 49 | 6.4.4 | 5 | Figure 20 should have 3 lines, one for the Coordinator on top, and then below the line device 1 and device 2. Then each D1, D2 frame should be moved to appropriate line. This would make it easier to understand who is responding and when. Also change Dev 1 and Dev 2 to D1, and D2 like in other figures. Also add the next polled device to the frames sent by the coordinator. I.e., something like "Poll: D1, Next:D2". |  | No | Redraw the figure. | REVISED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286522 | 16-Sep-2021 15:46:36 UTC-12 | R1-42 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 41 | General Interest | Disapprove | Self Employed | Editorial | 49 | 6.4.4 | 15 | Change "a) Payload CRC error" to "type 1 error: Payload CRC error". |  | No | As specified in comment. | REVISED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286523 | 16-Sep-2021 15:46:36 UTC-12 | R1-43 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 42 | General Interest | Disapprove | Self Employed | Editorial | 49 | 6.4.4 | 21 | Change "b) Header error" to "type 2 error: Header error". |  | No | As specified in comment. | REVISED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286524 | 16-Sep-2021 15:46:36 UTC-12 | R1-44 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 43 | General Interest | Disapprove | Self Employed | Technical | 49 | 6.4.4 | 27 | Change "c) The ..." to "type 3 error: The ...". |  | No | As specified in comment. | REVISED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286525 | 16-Sep-2021 15:46:36 UTC-12 | R1-45 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 44 | General Interest | Disapprove | Self Employed | Technical | 49 | 6.4.4 | 23 | It should be clarified, that the high reliability header that is used here is the high reliability header of the previous frame which contained the next device to poll. I.e., because device knows it will be next because it parsed the previous frame, it can respond even if it cannot parse this header. |  | No | Add more description of the process. | REVISED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286527 | 16-Sep-2021 15:46:36 UTC-12 | R1-47 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 45 | General Interest | Disapprove | Self Employed | Editorial | 110 | 10.2.2 | 7 | This is not first use of LSB, remove the expansion. |  | No | Change to just "LSB". | ACCEPTED |  |  |  |  | implemented
286725 | 24-Sep-2021 20:10:58 UTC-12 | R1-169 | Bober, Lennert | klb@posteo.de |  | Ballot | 18 | Producer - Software | Approve | Fraunhofer Heinrich Hertz Institute,Self | Technical |  |  |  | It is still not clear, what values the PIB attributes have initially. |  | No | Either specify initial values, or some mechanism that makes initial PIB values disseminated / set. | REJECTED | The author withdrew the comment. | R1-169 R1-174 |  |  | implemented
286726 | 24-Sep-2021 20:10:58 UTC-12 | R1-170 | Bober, Lennert | klb@posteo.de |  | Ballot | 19 | Producer - Software | Approve | Fraunhofer Heinrich Hertz Institute,Self | Technical |  |  |  | The Poll Frames should all be control frames, not managment frames. |  | No | Make these frames control frames. | REVISED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286485 | 16-Sep-2021 15:46:35 UTC-12 | R1-5 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 4 | General Interest | Disapprove | Self Employed | Editorial | 27 | 5.3.2 | 7 | Is there really need for dated reference to the 802.1CM? As there is no section number or similar, I think undated reference is ok. |  | No | Change "802.1CM-2018" to "802.1CM". | REVISED | Change "802.1CM-2018" to "802.1CM" in text and in Annex A. |  |  |  | implemented
286730 | 24-Sep-2021 20:10:58 UTC-12 | R1-174 | Bober, Lennert | klb@posteo.de |  | Ballot | 23 | Producer - Software | Approve | Fraunhofer Heinrich Hertz Institute,Self | Technical |  |  |  | Describe how some PIB attributes are filled from specific frames, e.g. the Beacon frame. |  | No |  | REJECTED | The author withdrew the comment. | R1-169 R1-174 |  |  | implemented
286733 | 24-Sep-2021 20:10:58 UTC-12 | R1-177 | Bober, Lennert | klb@posteo.de |  | Ballot | 26 | Producer - Software | Approve | Fraunhofer Heinrich Hertz Institute,Self | Technical |  |  |  | The HB-PHY cannot detect the bandwidth of an incoming PPDU automatically. |  | No | Propose a mechanism to detect the HB-PHY bandwidth. | REVISED | Replace the description of the phyBandwidth attribute in 12.1.4 with the following text: This attribute determines the bandwidth to use for transmitted PPDUs. All PPDUs shall be transmitted with the correspondig values, defined in table 52. | R1-168 R1-177 |  |  | implemented
286735 | 24-Sep-2021 20:10:58 UTC-12 | R1-179 | Bober, Lennert | klb@posteo.de |  | Ballot | 28 | Producer - Software | Approve | Fraunhofer Heinrich Hertz Institute,Self | Technical |  |  |  | A way for the coordinator to trigger an MCS request is needed, e.g. in case the coordinator updated the MIMO configuration. |  | No | Specify e.g. a control frame "Probe Frame" to trigger a channel estimation at the device. | REJECTED | The author withdrew the comment. |  |  |  | implemented
286533 | 16-Sep-2021 15:46:36 UTC-12 | R1-53 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 51 | General Interest | Disapprove | Self Employed | Editorial | 143 | 12.2.5 | 2 | Hanging paragraph. |  | No | Move this paragraph to separate subsection 12.2.5.1 and renumber other subsections accordingly. | REVISED | Remove segmented header functionality and merge sentence with next subclause. |  |  |  | implemented
286486 | 16-Sep-2021 15:46:35 UTC-12 | R1-6 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 5 | General Interest | Disapprove | Self Employed | Editorial | 29 | 5.5.1 | 4 | This is first use of MCPS-SAP, expand it. |  | No | Expand MCPS-SAP on first use. | REVISED | MCPS-SAP is expanded on P25L33 |  |  |  | implemented
286487 | 16-Sep-2021 15:46:35 UTC-12 | R1-7 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 6 | General Interest | Disapprove | Self Employed | Technical | 29 | 5.5.1 | 1 | In figure 6 there is text "not speified" for the MLME-SAP, which is not correct as we do defined basic MLME-SAP operations (associate, disassociat, get, set, scan, start and stop). |  | No | I think we should say "partially specified", as we only defined minimal set of MLME-SAP here in this document. | ACCEPTED |  |  |  |  | implemented
286488 | 16-Sep-2021 15:46:35 UTC-12 | R1-8 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 7 | General Interest | Disapprove | Self Employed | Editorial | 33 | 5.7.2 | 25 | There is term clause missing. |  | No | Change "specified in 10" to "specified in clause 10". | REVISED | Insert the word "clause" whenever refering to a major clause througout the document. |  |  |  | implemented
286489 | 16-Sep-2021 15:46:35 UTC-12 | R1-9 | Kivinen, Tero | kivinen@iki.fi |  | Ballot | 8 | General Interest | Disapprove | Self Employed | Technical | 33 | 5.7.1 | 22 | As non-beacon enabled access control can only be used with LB-PHY, I think we should mention it here. I.e., change "Pulse modulation PHY (PM-PHY) in beacon-enabled access control introduced in section 5.7.2", and "Low bandwidth PHY (LB-PHY) in non-beacon-enabled channel access introduced ...". |  | No | Add in beacon-enabled access control in a and c, and non-beacon-enabled access control in b. | REVISED | The LB-PHY and Non-beacon-enabled channel access are removed as instructed in https://mentor.ieee.org/802.15/dcn/22/15-22-0001-00-0013-removed-parts-for-d6-0.docx |  |  |  | implemented
286642 | 23-Sep-2021 21:24:14 UTC-12 | R1-90 | Lim, Sang-Kyu | sklim@etri.re.kr |  | Ballot | 1 | Research | Approve | Electronics and Telecommunications Research Institute (ETRI) | Technical | VII |  | 4 | The term "LiFi" is shown and it's a kind of abbreviation. So, it should be added to the subclause 3.2. |  | No | Add "LiFi" to the subclause 3.2 | REVISED | Replace "LiFi" with "OWC" in P8L9 P8L15 P8L17 P8L21 |  |  |  | implemented
286643 | 23-Sep-2021 21:24:14 UTC-12 | R1-91 | Lim, Sang-Kyu | sklim@etri.re.kr |  | Ballot | 2 | Research | Approve | Electronics and Telecommunications Research Institute (ETRI) | Editorial | VII |  | 20 | Expression style of "the HB-PHY" |  | No | Change "the HB-PHY" to "the high-bandwidth (HB) PHY" like "the low-bandwidth(LB) PHY". | REVISED | Change text to "Several inputs were merged into a third, low-power pulsed modulation PHY (PM-PHY). After consolidating the PM-PHY and the high bandwidth PHY (HB-PHY) until July 2018, work focused on the MAC." |  |  |  | implemented
286644 | 23-Sep-2021 21:24:14 UTC-12 | R1-92 | Lim, Sang-Kyu | sklim@etri.re.kr |  | Ballot | 3 | Research | Approve | Electronics and Telecommunications Research Institute (ETRI) | Editorial | VII |  | 28 | IEEE SA sponsor ballot |  | No | Detele "sponsor". | ACCEPTED |  |  |  |  | implemented
286645 | 23-Sep-2021 21:24:14 UTC-12 | R1-93 | Lim, Sang-Kyu | sklim@etri.re.kr |  | Ballot | 4 | Research | Approve | Electronics and Telecommunications Research Institute (ETRI) | Technical | 21 | 3.2 | 15 | This is a comment on the term "OCR". According to my understanding on the discussion in TG13, TG13 had decided not to use the term "OCR" because what it means is not clear. So, in most places, the term "clock rate" is used in this draft, but the term "optical clock rate (OCR)" is still shown on pages 82, 109, and 112. |  | No | Delete "OCR" in 3.2. | REVISED | Remove the term "(optical) clock rate" generally. Use "clock rate" in the PM-PHY Use "bandwidth" in the HB-PHY | R1-93 R1-102 R1-103 R1-114 R1-118 |  |  | implemented
286646 | 23-Sep-2021 21:24:14 UTC-12 | R1-94 | Lim, Sang-Kyu | sklim@etri.re.kr |  | Ballot | 5 | Research | Approve | Electronics and Telecommunications Research Institute (ETRI) | Editorial | 26 | 5.3.2 | 12 | Figure 4 |  | No | The part marked with "external" is shown in Figure 3 and Figure 5, but it's not shown in Figure 4. So, put it into Figure 4 for consistency. | ACCEPTED |  |  |  |  | implemented
286647 | 23-Sep-2021 21:24:14 UTC-12 | R1-95 | Lim, Sang-Kyu | sklim@etri.re.kr |  | Ballot | 6 | Research | Approve | Electronics and Telecommunications Research Institute (ETRI) | Editorial | 28 | 5.4 | 9 | IEEE Std 802.15.7TM |  | No | Change it to "IEEE Std 802.15.7TM--2018" as shown in "IEEE Std 802.15.4TM--2020" on page 18. | REJECTED | As per the resolution for R1-190, we want the reference to cover also 7a in the future. Thus, an undated version is appropriate. The style manual proposes to use as little dated references as possible. |  |  |  | implemented
286648 | 23-Sep-2021 21:24:14 UTC-12 | R1-96 | Lim, Sang-Kyu | sklim@etri.re.kr |  | Ballot | 7 | Research | Approve | Electronics and Telecommunications Research Institute (ETRI) | Technical | 28 | 5.4 | 15 | In regard to "by using different optical wavelengths" |  | No | IEEE 802.15.13 standard uses light wavelengths from 10,000nm to 190nm. By the way, looking at the subclause 6.1.2.2 in G.9991, G.9991 uses visible light(380-780nm) and infrared(800-1675nm) as well. So, this draft need to clearly define how to use different optical wavelengths from ones defined in G.9991 in order to keep the coexistence. | REVISED | Replace "Coexistence..." in P28L14 with the following text: Both standards support multiple optical bands for transmission but do not require use of a specific one. Hence, for a given installation, coexistence can be ensured by chosing the wavelengths of both systems so that they do not overlap. |  |  |  | implemented
286649 | 23-Sep-2021 21:24:14 UTC-12 | R1-97 | Lim, Sang-Kyu | sklim@etri.re.kr |  | Ballot | 8 | Research | Approve | Electronics and Telecommunications Research Institute (ETRI) | Editorial | 33 | 5.6.5 | 8 | ACK frames |  | No | "Beacon" in Beacon frame is expressed in italic style. So, change "ACK" in ACK frames to italic style in order to keep the conventions defined in 4.1. | ACCEPTED |  |  |  |  | implemented
286736 | 24-Sep-2021 20:10:58 UTC-12 | R1-180 | Bober, Lennert | klb@posteo.de |  | Ballot | 29 | Producer - Software | Approve | Fraunhofer Heinrich Hertz Institute,Self | Editorial |  |  |  | It is not clear how to interpret values that have neither a 0x, nor a 0b prefix. They should be interpreted as decimal numbers theoretically, but there are many bit structures in the standard in the same format. One cannot distinguish those. |  | No | Make all bit structs be represented as binary numbers or indicate for each struct that they are structs, in which order the bits are processed. | ACCEPTED |  |  |  |  | implemented
286651 | 23-Sep-2021 21:24:14 UTC-12 | R1-99 | Lim, Sang-Kyu | sklim@etri.re.kr |  | Ballot | 10 | Research | Approve | Electronics and Telecommunications Research Institute (ETRI) | Editorial | 61 | 6.9.5 | 29 | Figure 26 |  | No | The left-side symbols indicate the light sources, and the right-side symbols indicate the photo-detectors. So, use the dashed arrows between light sources and detectors instead of dashed lines in order to show the signal directions. | REVISED | Add an arrow to the wireless propagation line going from left to right (i.e. from light source to photodiode). |  |  |  | implemented

## Additional Comments
Comment ID | Date | Comment # | Name | Email | Phone | Style | Index # | Classification | Vote | Affiliation | Category | Page | Subclause | Line | Comment | File | Must be Satisfied | Proposed Change | Disposition Status | Disposition Detail | Same resolution | Assignee | Notes | TE Comment
|  |  | CRG | [7 empty] | Technical |  |  |  | It should be described how a device handles the AID field upon an unsuccessful association request. |  |  | In page 52L36, add the following sentence: When the Association Response has a status other than Success, the AID field of the Association Response element shall be set to zero and ignored by the device requesting association. | ACCEPTED |  |  |  |  | implemented
|  |  | CRG | [7 empty] | Technical |  |  |  | The MLME-DISASSOCIATE should always be successful, even upon retransmission failure. |  |  | "Add reference to MLME-DISASSOCIATE in P53L7. Move P53L8 - P53L14 into a new subclause ""Disassociation through the device"" Change ""may"" to ""shall"" in P53L11. Move P53L15 - P54L2 into a new subclause ""Disassociation through the device"" Change ""may"" to ""shall"" in P53L19. Remove Status ""FAIL_OTHER"" from Table 26. Change Description of the Status parameter to ""This primitive always returns SUCCESS.""" | ACCEPTED |  |  |  |  | implemented
|  |  | CRG | [7 empty] | Technical |  |  |  | Carrying the scrambler state between the header and payload in the PM PHY is unnecessarily complex. |  |  | Update the text in 10.3.3 as follows: The header and payload bits shall be scrambled as defined in 12.3.1.4, but the second initialization of the scrambler shall always be performed with the value contained in SI. | ACCEPTED |  |  |  |  | implemented
|  |  | CRG | [7 empty] | Technical |  |  |  | In the HB-PHY, the value of D is only contained in the PHY header, while it is needed to demodulate, decode and interpret the header itself. |  |  | Remove segmented header functionality. | ACCEPTED |  |  |  |  | implemented
|  |  | CRG | [7 empty] | Technical |  |  |  | The segmented header of the HB-PHY is never used. |  |  | Remove segmented header functionality. | ACCEPTED |  |  |  |  | implemented
|  |  | CRG | [7 empty] | Technical |  |  |  | Currently, there is no content for the extended header in the HB-PHY. |  |  | Remove possibility to have an extended header in the HB-PHY. Make the EHI in the HB-PHY reserved. | ACCEPTED |  |  |  |  | implemented

## TG comment notes
Comment | Resolution
Signalling the CAP in the Beacon gives no time to process the Beacon frame to obtain the actual start of the CAP early enough. | Make CAP signalling valid only in the next superframe, or flexible.
Make the immediate GTS validity an optional feature and specify the time needed between receiving an GTS allocation and the ability to transmit in it (from the device perspective). Create capability "Fast GTS accept" or similar, which indicates that a device can receive immediate GTS allocations (getting active within the same superframe).
Specify a mechanism in the standard to make reservation types more generically (i.g. GTS, CAP-GTS, …)
The maximum number of received fragmented MSDUs should be specified instead of a reassembly timeout. | Draft resolution: Remove PIB attribute macMaxReassemblyTimeout, …
10 ppm oscillators are expensive, the PM-PHY needs a method to correct for the timing drift. | Introduce "Mid-ambles"

## Statistics
Official comments | [8 empty] | Additional comments
TYPE | unhandled | duplicate | assigned | wait | ACCEPTED | REVISED | REJECTED | TOTAL | TYPE |  | assigned | ACCEPTED | REVISED | REJECTED | TOTAL
Technical | 0 | 0 | 0 | 0 | 14 | 69 | 7 | 90 | Technical | 0 | 0 | 6 | 0 | 0 | 6
Editorial | 0 | 0 | 0 | 0 | 26 | 32 | 3 | 61 | Editorial | 0 | 0 | 0 | 0 | 0 | 0
General | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | General | 0 | 0 | 0 | 0 | 0 | 0
TOTAL | 0 | 0 | 0 | 0 | 40 | 102 | 10 | 152 | TOTAL | 0 | 0 | 6 | 0 | 0 | 6
Initial numbers
Total CIDs | Editorial | General | Technical
152 | 61 | 1 | 90