## Slide 1
Project: IEEE P802.15 Working Group for Wireless Specialty Networks (WSN)
Submission Title: TG 15.4ab Agenda and Meeting Slides
Date Submitted: December 14, 2021
Source: Benjamin A. Rolfe (Blind Creek Associates)
Contact:
Voice: +1 408 395 7207, E-Mail: ben.rolfe @ ieee.org
Re: Task Group 4ab: 802.15.4 UWB Next Generation
Abstract: Teleconference (WebEx) Agenda and Meeting Slides
Purpose: Emulate organization, encourage participation and make further progress
Notice: This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.
Notes: Jul 12, 2010
Page 1

## Slide 2: Task Group 15.4ab Next Generation UWB Amendment
Teleconference / Virtual Meeting
December 14 2021

## Slide 3: Task Group Rules
Discussion: Everyone present is welcome
Straw polls: Everyone present may vote
Formal motions: WG voters
  To make, second and vote
Patent policy for PAR activities applies
All the usual rules of conduct
Please identify yourself on first contact with name and affiliation

## Slide 4: IEEE-SA Patent, Copyright, and Participation Policies
See: https://grouper.ieee.org/groups/802/sapolicies.shtml
IEEE-SA Patent Slides for Standards Development Meetings (.pdf)
https://development.standards.ieee.org/myproject/Public/mytools/mob/slideset.pdf
IEEE-SA Standards Board Patent Committee (PatCom) home page
https://standards.ieee.org/content/ieee-standards/en/about/sasb/patcom/index.html
IEEE-SA Participation Policy meeting slide set - individual method (.pdf)
https://standards.ieee.org/content/dam/ieee-standards/standards/web/documents/other/Participant-Behavior-Individual-Method.pdf
Copyright:
https://standards.ieee.org/content/dam/ieee-standards/stand
https://standards.ieee.org/faqs/copyrights/index.htmlards/web/documents/other/ieee-sa-copyright-policy-2019.pdf
https://standards.ieee.org/ipr/copyright-materials.html

## Slide 5: IEEE 802 Ground Rules
Respect … give it, get it
NO product pitches
NO corporate pitches
NO prices
NO restrictive notices – (no confidentially notices in email)
Presentations must be openly available

## Slide 6: Proposed Agenda
Opening and meeting preamble
Recap
Review Call for Proposals
Continuation of technical discussions
Any other Business

## Slide 7: Recap

## Slide 8: 5.2.b Scope of the project (As approved):
This amendment enhances the Ultra Wideband (UWB) physical layers (PHYs) medium access control (MAC), and associated ranging techniques while retaining backward compatibility with enhanced ranging capable devices (ERDEVs). Areas of enhancement include:
  additional coding, preamble and modulation schemes to additional coding, preamble and modulation schemes to support improved link budget and/or reduced air-time relative to IEEE Std 802.15.4 UWB;
  additional channels and operating frequencies;
  interference mitigation techniques to support greater device density and higher traffic use cases relative to the IEEE Std 802.15.4 UWB;
  improvements to accuracy, precision and reliability and interoperability for high-integrity ranging; schemes to reduce complexity and power consumption;
  definitions for tightly coupled hybrid operation with narrowband signaling to assist UWB;
  enhanced native discovery and connection setup mechanisms;
  sensing capabilities to support presence detection and environment mapping;
  and mechanisms supporting low-power low-latency streaming as well as high data-rate streaming allowing at least 50 Mb/s of throughput.
Support for peer-to-peer, peer-to-multi-peer, and station-to-infrastructure protocols are in scope, as are infrastructure synchronization mechanisms. This amendment includes safeguards so that the high throughput data use cases do not cause significant disruption to low duty-cycle ranging use cases.
https://development.standards.ieee.org/myproject-web/app#viewpar/9081

## Slide 9: Review and Status
November Closing Report:
  https://mentor.ieee.org/802.15/dcn/21/15-21-0621-00-04ab-november-2021-closing-report.pptx
Meeting Slides from November
  https://mentor.ieee.org/802.15/dcn/21/15-21-0565-04-04ab-tg4ab-november-meeting-slides.pptx
Draft November meeting minutes
  https://mentor.ieee.org/802.15/dcn/21/15-21-0628-00-04ab-tg15-4ab-nov-plenary-mtg-mins.docx
Meeting slides from November 30th call
  https://mentor.ieee.org/802.15/dcn/21/15-21-0632-01-04ab-tg-15-4ab-agenda-and-meeting-slides.pptx

## Slide 10: Technical Discussion

## Slide 11: Discussions cut short in Nov.
Out-of-band signaling and narrow band assist
Preamble and Equalization
Coding and related discussion
Wake-up radio
Updating channel models and related topics
Schedule discussion

## Slide 12: Project Schedule
Work in Progress - still under discussion

## Slide 13: Next Steps

## Slide 14: Teleconference Schedule
 |  |  | Nov-21 |  |  |  |  |  |  | Dec-21 |  |  | 
Sun | Mon | Tue | Wed | Thr | Fri | Sat | Sun | Mon | Tue | Wed | Thr | Fri | Sat
 | 1 | 2 | 3 | 4 | 5 | 6 |  |  |  | 1 | 2 | 3 | 4
7 | 8 | 9 | 10 | 11 | 12 | 13 | 5 | 6 | 7 | 8 | 9 | 10 | 11
14 | 15 | 16 | 17 | 18 | 19 | 20 | 12 | 13 | 14 | 15 | 16 | 17 | 18
21 | 22 | 23 | 24 | 25 | 26 | 27 | 19 | 20 | 21 | 22 | 23 | 24 | 25
28 | 29 | 30 |  |  |  |  | 26 | 27 | 28 | 29 | 30 | 31 | 
 |  |  | Jan-22 |  |  | 
Sun | Mon | Tue | Wed | Thr | Fri | Sat
 |  |  |  |  |  | 1
2 | 3 | 4 | 5 | 6 | 7 | 8
9 | 10 | 11 | 12 | 13 | 14 | 15
16 | 17 | 18 | 19 | 20 | 21 | 22
23 | 24 | 25 | 26 | 27 | 28 | 29
30 | 31 | IEEE 802 Wireless Electronic Interim Session January 14-27, 2022 |  |  |  | 
Frequency: Bi-weekly
Phase: Tuesday
Time: 09:00 ET (06:00 PT)
Offset: First call November 30th
  [skip week following the plenary]
Duration: 1 hour.
Week | Time (ET)
November 30 | 09:00 ET
December 14 | 09:00 ET
January 4 | 09:00 ET
January 11 | 09:00 ET
January 14: | Jan Interim
Out of Phase

## Slide 15: Other Business

## Slide 16: Adjourned Thanks