## Slide 1: IEEE 802.15 TG13 Multi-Gbit/s Optical Wireless Communication May 2022 Closing Report
Date: 2022-05-18
Author:

## Slide 2
This presentation contains the IEEE 802.15 TG13 Multi- Gbit/s Optical Wireless Communication Closing Report for the May 2022 virtual meeting.
Abstract

## Slide 3
TG13 Motion
Approve Sang-Kyu Lim and Tuncer Baykas as vice chairs of TG13.
Moved by Rias AL-kadi
Seconded by Kai Lennert Bober
Approved by unanimous consent.

## Slide 4: TG13 SA ballot status
Initial SA letter ballot
  82% return rate, 95% approval rate
  3 NO votes with 21 MBS comments
  314 comments were received (9 general, 112 technical, 193 editorial)
1st Recirculation
  83% return rate, 98% approval rate
  1 NO vote with 10 MBS comments
  158 comments were received (1 general, 96 technical, 61 editorial)
2nd Recirculation
  84% return rate, 97% approval rate
  2 NO votes with 6 MBS comments
  94 comments were received (0 general, 45 technical, 49 editorial)

## Slide 5
Agenda in doc. 15-22/0230r3
  WED May-11 AM0
  WED May-11 AM2 Joint session 802.15/802.1
  THUR May-12 AM0
  MO May-16 AM0
  TUE May-17 AM0
  Major achievements
  93/94 SA ballot comments against D6.0 were resolved
  Consented: Major text updates on MAC (flexible beacon position)
  Mostly consented: TG13 PICS
  TBD: Reinsert removed text (LB PHY, polling MAC)
TG13 achievements this week

## Slide 6: Joint meeting with 802.1
TG 13 slides in doc. 15-22/0271r1
  Questions on
    Ethertype
    Handling of multicast
    TSN support
    What to learn from 802.3 TDMA PON
  Answers were provided and discussed
Meeting Minutes in doc. 15-22/0273r0

## Slide 7: TG 13 Motion to reconfirm CRG
Move to request that 802.15 WG approves the formation of a Comment Resolution Group (CRG) for the Standards Association balloting of the P802.15.13_D7 with the following membership: Volker Jungnickel as Chair, Tuncer Baykas, Sang-Kyu Lim, Tero Kivinen. The 802.15.13 CRG is authorized to approve comment resolutions, edit the draft according to the comment resolutions, and to approve the start of recirculation ballots of the revised draft on behalf of the 802.15 WG. Comment resolution on recirculation ballots between sessions will be conducted via reflector email and via teleconferences announced to the reflector as per the LMSC 802 WG P&P.
  Moved: Sang-Kyu Lim
  Second: Joerg Robert
  Result: Motion passed unanimously.

## Slide 8: WG Motion to reconfirm CRG
Move that 802.15 WG approves the formation of a Comment Resolution Group (CRG) for the Standards Association balloting of the P802.15.13_D7 with the following membership: Volker Jungnickel as Chair, Tuncer Baykas, Sang-Kyu Lim, Tero Kivinen. The 802.15.13 CRG is authorized to approve comment resolutions, edit the draft according to the comment resolutions, and to approve the start of recirculation ballots of the revised draft on behalf of the 802.15 WG. Comment resolution on recirculation ballots between sessions will be conducted via reflector email and via teleconferences announced to the reflector as per the LMSC 802 WG P&P.
  Moved: Volker Jungnickel
  Second: Ben Rolfe
  Result: Y / N / A : 34 / 0 / 3

## Slide 9: Plan for CRG Telcos
TG13 CRG Telco dates
  30 May 2022, 11:00-12.30 CET (5:00-6:30 ET, 18:00-19:30 KT)
  6 June 2022, 11:00-12.30 CET (5:00-6:30 ET, 18:00-19:30 KT)
  13 June 2022, 11:00-12.30 CET (5:00-6:30 ET, 18:00-19:30 KT)
  20 June 2022, 11:00-12.30 CET (5:00-6:30 ET, 18:00-19:30 KT)
  27 June 2022, 11:00-12.30 CET (5:00-6:30 ET, 18:00-19:30 KT)
  4 July 2022, 11:00-12.30 CET (5:00-6:30 ET, 18:00-19:30 KT)
  meetings to be cancelled if not needed

## Slide 10: Plan for finalization of TG13 Spec
D7.0 is created and goes to 3rd recirc after May
    Find consensus about text to be reinserted
    Further changes are expected due to comment resolutions
    After May: Create D7.0, start 3rd recirculation
Plan to submit to RevCom is possibly after July

## Slide 11
Informal straw poll
  # in person attending – 4…5
  # virtually attending – 2
  total # in TG during the poll – 14
TG13 is looking forward to meet in Montreal
  small room might be sufficient
  WG members are always welcome 
4 + 1 slots for TG13 and joint meeting with 802.1
Hybrid meeting in July