## Slide 1
Project: IEEE P802.15 Working Group for Wireless Specialty Networks (WSN)
Submission Title: TG 15.4ab Agenda and Meeting Slides
Date Submitted: July 4, 2022
Source: Benjamin A. Rolfe (Blind Creek Associates)
Contact:
Voice: +1 408 395 7207, E-Mail: ben.rolfe @ ieee.org
Re: Task Group 4ab: 802.15.4 UWB Next Generation
Abstract: Teleconference (WebEx) Agenda and Meeting Slides
Purpose: Emulate organization, encourage participation and make further progress
Notice: This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.
Notes: Jul 12, 2010
Page 1

## Slide 2: Task Group 15.4ab Next Generation UWB Amendment
Teleconference / Virtual Meeting
July 5th, 2022

## Slide 3: Task Group Rules
Discussion: Everyone present is welcome
Straw polls: Everyone present may vote
Formal motions: WG voters
  To make, second and vote
Patent policy for PAR activities applies
All the usual rules of conduct
Please identify yourself on first contact with name and affiliation

## Slide 4: IEEE-SA Patent, Copyright, and Participation Policies
See: https://grouper.ieee.org/groups/802/sapolicies.shtml
IEEE-SA Patent Slides for Standards Development Meetings (.pdf)
https://development.standards.ieee.org/myproject/Public/mytools/mob/slideset.pdf
IEEE-SA Standards Board Patent Committee (PatCom) home page
https://standards.ieee.org/content/ieee-standards/en/about/sasb/patcom/index.html
IEEE-SA Participation Policy meeting slide set - individual method (.pdf)
https://standards.ieee.org/content/dam/ieee-standards/standards/web/documents/other/Participant-Behavior-Individual-Method.pdf
Working Group Copyright Materials
https://standards.ieee.org/ipr/copyright-materials.html
https://standards.ieee.org/content/dam/ieee-standards/standards/web/documents/other/ieee-sa-copyright-policy-2019.pdf

## Slide 5: IEEE 802 Ground Rules
Respect … give it, get it
NO product pitches
NO corporate pitches
NO prices
NO restrictive notices – (no confidentially notices in email)
Presentations must be openly available

## Slide 6: Proposed Agenda
Opening and meeting preamble
Recap and Reminders
Technical discussions
  4ab on channelization (>10.5 GHz)
Progressing to drafting
  Status for convergence
Next steps
  July agenda review
Any other Business

## Slide 7: Recap

## Slide 8: 5.2.b Scope of the project (As approved):
This amendment enhances the Ultra Wideband (UWB) physical layers (PHYs) medium access control (MAC), and associated ranging techniques while retaining backward compatibility with enhanced ranging capable devices (ERDEVs). Areas of enhancement include:
  additional coding, preamble and modulation schemes to additional coding, preamble and modulation schemes to support improved link budget and/or reduced air-time relative to IEEE Std 802.15.4 UWB;
  additional channels and operating frequencies;
  interference mitigation techniques to support greater device density and higher traffic use cases relative to the IEEE Std 802.15.4 UWB;
  improvements to accuracy, precision and reliability and interoperability for high-integrity ranging; schemes to reduce complexity and power consumption;
  definitions for tightly coupled hybrid operation with narrowband signaling to assist UWB;
  enhanced native discovery and connection setup mechanisms;
  sensing capabilities to support presence detection and environment mapping;
  and mechanisms supporting low-power low-latency streaming as well as high data-rate streaming allowing at least 50 Mb/s of throughput.
Support for peer-to-peer, peer-to-multi-peer, and station-to-infrastructure protocols are in scope, as are infrastructure synchronization mechanisms. This amendment includes safeguards so that the high throughput data use cases do not cause significant disruption to low duty-cycle ranging use cases.
https://development.standards.ieee.org/myproject-web/app#viewpar/9081

## Slide 9: Project Schedule (working baseline)
Notes: SASB/RevCom schdule for 2024 a guess
Proposed project schedule | Nov-21 | Dec-21 | Jan-22 | Feb-22 | Mar-22 | Apr-22 | May-22 | Jun-22 | Jul-22 | Aug-22 | Sep-22 | Oct-22 | Nov-22 | Dec-22 | Jan-23 | Feb-23 | Mar-23 | Apr-23 | May-23 | Jun-23 | Jul-23 | Aug-23 | Sep-23 | Oct-23 | Nov-23 | Dec-23 | Jan-24 | Feb-24 | Mar-24 | Apr-24 | May-24 | Jun-24 | Jul-24 | Aug-24 | Sep-24 | Oct-24 | Nov-24 | 
Call for proposals |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Hear and evaluate proposals |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Cut-off for new proposals, PHY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Cut-off for new proposals, MAC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Integrate poposals/contributions into TFD |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Develop draft from TFD |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Draft 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
TG draft review and revision |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Working group pre-ballot review |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Pre-ballot review and comment resolution |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
First letter ballot |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | LB |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
LB Comment Resolution |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
WG Recirculatoin |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | LB-R |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Comment resolution, 1st recirc |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Conditional approval for SA ballot |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
WG Recirculatoin |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | LB-R |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Comment resolution, 2nd recirc and final recirc |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
First SA ballot |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SA |  |  |  |  |  |  |  |  |  |  |  |  | 
Comment resolution, first SA ballot |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
SA Resirculation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SA-R |  |  |  |  |  |  |  |  |  | 
Comment resolution, SA recirculation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
SA Resirculation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SA-R |  |  |  |  |  |  | 
Comment resolution, 2nd SA recirc |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Conditional or unconditional approval to RevCom |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ?? |  |  |  | ?? |  |  |  |  | 
Optional 3rd SA recirc if needed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SA-R |  |  |  |  | 
RevCom meets |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ` |  |  |  | `
You are Here >

## Slide 10: Schedule Major Milestones
Call for proposals | November 2021
Cut-off for new features (high level feature set), PHY | May 2022
Cut-off for new features (high level feature set), MAC | July 2022
Draft 0 | September 2022
TG draft review and revision complete | November 2022
Working group pre-ballot review complete | January 2022 (before meeting)
First letter ballot | March 2023 (following meeting)
… | 
Near Term Working Milestones
Progress as of June 28th:
We have most of the PHY features identified
Multiple proposals in some areas, with collaborative convergence underway
Identified gaps being worked (probably more to be found)
Two more telecons before July (including today)

## Slide 11: Moving Forward

## Slide 12: Technical Discussion

## Slide 13: Topics for Discussion
Notes
Our time in July will be very packed
The interim call time can be very useful to collaborate, discuss and converge
We have 1 calls left before July!
We have many!

## Slide 14: A map of the P802.15.4ab enhancements

## Slide 15: Volunteer List
So Far (more expected):
Narrow band assist and improved ranging:
Xiliang Luo, Jonathan Segev, David B., Boris
Sensing
Xiaohui Peng, Pooria Pakrooh
MAC scheduling
Kangin Yoon, Kuan Wu
DL-TDoA:
Zhenzhen Ye, Jean-Marie
Channel access MAC and PHY:
Alex Krebs, Frederic Nabki
Data com improvements
Bin Qian, Frederic Nabki, Carlos Aldana

## Slide 16: Next Steps

## Slide 17: July Plenary
https://mentor.ieee.org/802.15/dcn/22/15-22-0328-01-04ab-july-2022-tg4ab-agenda.xlsx
 |  |  |  |  |  |  | July 2022 Wireless Plenary |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  | Task Group 15.4ab - Next Generation UWB |  |  |  |  |  |  |  |  |  |  |  |  | 
EDT | PDT | UTC | JST | Local Time | Rm 1 | Rm 2 | Rm 3 | Rm 4 |  |  |  |  |  |  |  |  |  |  |  | 
7:00 | 4:00 | 11:00 | 20:00 | 07:00-07:30 | CONTINENTAL BREAKFAST |  |  |  | CONTINENTAL BREAKFAST |  |  |  | CONTINENTAL BREAKFAST |  |  |  | CONTINENTAL BREAKFAST |  |  | 
7:30 | 4:30 | 11:30 | 20:30 | 07:30-08:00 |  |  |  |  |  |  |  |  | 802.15 AC Meeting Rm 3 |  |  |  |  |  |  | 
8:00 | 5:00 | 12:00 | 21:00 | 08:00-08:30 | OPENING 802 EC MEETING |  |  |  | TG4ab | TG13 OWC | TG3ma | TG6ma |  |  |  |  | TG4ab | TG13 OWC | SC THz | TG6ma
8:30 | 5:30 | 12:30 | 21:30 | 08:30-09:00 |  |  |  |  |  |  |  |  | SC-M/ Rules | TG13 OWC | TG3ma | TG6ma |  |  |  | 
9:00 | 6:00 | 13:00 | 22:00 | 09:00-09:30 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
9:30 | 6:30 | 13:30 | 22:30 | 09:30-10:00 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
10:00 | 7:00 | 14:00 | 23:00 | 10:00-10:30 | Break |  |  |  | Break |  |  |  | Break |  |  |  | Break |  |  | 
10:30 | 7:30 | 14:30 | 23:30 | 10:30-11:00 | 802 Joint Plenary |  |  |  | Joint .6a, .4ab, .14 Rm1 |  |  |  | 802.15 WG Midweek Plenary Rm 1 |  |  |  |  | TG4ab | SC IETF | 
11:00 | 8:00 | 15:00 | 0:00 | 11:00-11:30 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
11:30 | 8:30 | 15:30 | 0:30 | 11:30-12:00 | 802.15 WG Opening Plenary Rm 1 |  |  |  | Joint all TG prep for 802.1 Rm 1 |  |  |  | WNG Rm1 |  |  |  |  |  |  | 
12:00 | 9:00 | 16:00 | 1:00 | 12:00-12:30 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
12:30 | 9:30 | 16:30 | 1:30 | 12:30-13:00 | LUNCH ON YOUR OWN |  |  |  | LUNCH ON YOUR OWN |  |  |  | LUNCH ON YOUR OWN |  |  |  | LUNCH ON YOUR OWN |  |  | 
13:00 | 10:00 | 17:00 | 2:00 | 13:00-13:30 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
13:30 | 10:30 | 17:30 | 2:30 | 13:30-14:00 |  | TG4ab |  | TG7a OCC |  | Joint 14/15 | TG16t | TG7a OCC |  | SC-M/ Rules | TG16t | TG7a OCC |  | TG4ab | TG16t | 
14:00 | 11:00 | 18:00 | 3:00 | 14:00-14:30 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
14:30 | 11:30 | 18:30 | 3:30 | 14:30-15:00 |  |  |  |  |  | TG4 Cor1 |  |  |  |  |  |  |  |  |  | 
15:00 | 12:00 | 19:00 | 4:00 | 15:00-15:30 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
15:30 | 12:30 | 19:30 | 4:30 | 15:30-16:00 | Break |  |  |  | Break |  |  |  | Break |  |  |  | Break |  |  | 
16:00 | 13:00 | 20:00 | 5:00 | 16:00-16:30 |  | TG4ab | TG13 OWC |  | TG4ab | SC-M/ Rules |  |  | TG4ab | SC-M/ Rules |  |  | 802.15 WG Closing Plenary Rm 1 |  |  | 
16:30 | 13:30 | 20:30 | 5:30 | 16:30-17:00 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
17:00 | 14:00 | 21:00 | 6:00 | 17:00-17:30 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
17:30 | 14:30 | 21:30 | 6:30 | 17:30-18:00 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
18:00 | 15:00 | 22:00 | 7:00 | 18:00-18:30 | Break |  |  |  | Break |  |  |  | Break |  |  |  | Break |  |  | 

## Slide 18: Telecon Schedule
July '22 |  |  |  |  |  | 
S | M | T | W | T | F | S
 |  |  |  |  | 1 | 2
3 | 4 | 5 | 6 | 7 | 8 | 9
10 | 11 | 12 | 13 | 14 | 15 | 16
17 | 18 | 19 | 20 | 21 | 22 | 23
24 | 25 | 26 | 27 | 28 | 29 | 30
31 |  |  |  |  |  | 
June '22 |  |  |  |  |  | 
S | M | T | W | T | F | S
 |  |  | 1 | 2 | 3 | 4
5 | 6 | 7 | 8 | 9 | 10 | 11
12 | 13 | 14 | 15 | 16 | 17 | 18
19 | 20 | 21 | 22 | 23 | 24 | 25
26 | 27 | 28 | 29 | 30 |  | 
Plenary

## Slide 19: Other Business

## Slide 20: Adjourned Thanks